CONTENTS

1.	PURPOSE	2

2.	BACKGROUND TO THE CONTRACTING aUTHORITY	2

3.	Background to requirement/OVERVIEW of requirement	2

4.	definitions	3

5.	scope of requirement	3

6.	The requirement	3

7.	key milestones	4

8.	authority’s responsibilities	5

9.	reporting	5

10.	volumes	6

11.	continuous improvement	6

12.	Sustainability	6

13.	quality	6

14.	PRICE	6

15.	STAFF AND CUSTOMER SERVICE	7

16.	service levels and performance	7

17.	Security requirements	8

18.	intellectual property rights (ipr)	8

19.	payment	8

20.	additional information	9

21.	Location	9

22.       ANNEX 1…………………………………………………………………………………….10

# PURPOSE

## To provide an evaluation of the effect on aviation security of Virtual Separation (VS) systems deployed in conjunction with EDS-C (Explosive Detection Systems for Cabin Baggage Screening) or other 3D imaging platforms.

## VS is a software function included as an option in the implementation of a number of EDS-C platforms, and is novel in Cabin Baggage Screening. DfT requires that it is evaluated in order to ascertain if it creates any vulnerabilities in the cabin baggage screening process.

# BACKGROUND TO THE CONTRACTING aUTHORITY

## The Department for Transport (DfT) works with its agencies and partners to support the transport network that helps the UK’s businesses and gets people and goods travelling around the country. DfT plans and invests in transport infrastructure.

## The project will be overseen by the Research, Analysis and Development (RAD) team within DfT, which is a team of scientists responsible for ensuring that aviation security screening equipment is fit for purpose.

## RAD will be responsible for technical oversight, answering specific technical queries, and providing liaison with relevant customers and Government Departments.

## See https://www.gov.uk/government/organisations/department-for-transport for further information on DFT.

## RAD is referred to as the Authority hereafter.

# Background to requirement/OVERVIEW of requirement

## UK airports are expected to increase the number of deployed Computer Tomography CT based X-ray to screen cabin baggage in the next 1-2 years. This results from the inclusion of automated explosive detection standards for cabin baggage screening systems in the European Civil Aviation Conference Common Evaluation Process (ECAC CEP).

## Deployment of EDS-C systems (Explosive Detection Systems for Cabin Baggage Screening) machines will allow the realisation of new modes of screening.

## A number of commercial implementations of EDS-C have included automated segmentation algorithms that will identify an item in 3D voxel space and remove it from the primary image in the Graphical User Interface and display it in a secondary window. This is commonly termed Virtual Separation (VS)

## The idea behind the use of such algorithms is that by subtracting difficult (dense and or complex) parts of an image such as a laptop computer, either:

### The remainder of the image without an obscuring item should be able to be screened sufficiently by a screener visually or,

### The segmented item now viewed without background clutter should be   able to be screened sufficiently by a screener visually.

## DfT has a requirement to ensure that the use of these algorithms does not result in unacceptable vulnerabilities.

## The project shall provide:

### A description of how the various Virtual Separation systems operate and what functionalities they provide

### A description of the security benefits arising from the use of VS systems

### An understanding of any detrimental security effects to screener capability caused by VS.

# definitions

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## DfT | ## Department for Transport |
| ## RAD | ## Research, Analysis and Development team within DfT |
| ## EDS-C | ## Means Explosive Detection Systems for Cabin Baggage Screening) |
| ## VS | ## Means Virtual Separation algorithms |
| ## EDS | ## Means Explosive Detection Systems |

# scope of requirement

## Virtual Separation systems used on approved or candidate EDS-C systems are in scope.

## The study should include between 2 and 5 manufacturers.

## Previous work may include evaluations provided by international partners.

## The work should include trialling VS systems using physical test pieces.

## Evaluations including the automated materials detection functions of Explosives Detection Systems (EDS) systems are out of scope.

# The requirement

## The requirement is to develop an understanding of how the inclusion of VS will affect effectiveness of cabin baggage screening:

### Provide a description of how the various Virtual Separation systems operate and what functionalities they provide

### Provide a description of the benefits arising from the use of these systems

### Assess any existing laboratory trials of VS implementations by EU/ECAC member states, airports or manufacturers.

### Assess any existing national testing methodologies for VS and determine if there are any potential vulnerabilities that are not currently assessed in the tests.

### If existing data is not sufficient, prepare a test plan to test whether VS systems are able to automatically segment a relevant set of items in a reasonable range of operational conditions.

### Assess whether prior knowledge of the VS functionality could allow an individual to reduce the probability of detection of a threat item by utilising a vulnerability of the system.  This should be quantified by testing with a range of prohibited items of realistic difficulty/complexity.

### Assess the accuracy and reliability of the implementations of VS functionality available for testing.

### Develop a testing methodologies for testing vulnerabilities in VS systems if such Vulnerabilities are identified in the previous Work Packages.

### OPTIONAL - Provide a qualitative assessment of the benefit to screeners of VS systems. This information will not be evaluated and will be viewed by the Authority post-evaluation of tenders.

# key milestones

## The Potential Provider should note the following project milestones that the Authority will measure the quality of delivery against:

| ### Milestone | ### Description | ### Timeframe |
| --- | --- | --- |
| ### 1 | ### Detailed project plan including Risks, Technical approach and delivery plan | ### By 2 weeks after project start |
| ### 2 | ### Review report of existing data and studies on VS | ### By 8 weeks after project start |
| ### 3 | ### Testing methodology | ### For review as required |
| ### 4 | ### Trial of COTS VS Systems | ### By 16 weeks after project start |
| ### 5 | ### Final report with testing methodology, test results, and recommendation on any vulnerabilities of existing VS implementations | ### By 31/03/18 |

# authority’s responsibilities

## By agreement with the Successful Contractor and DfT RAD. DfT will aid introductions to relevant Manufacturers, Airports, and EU Member States regulatory authorities.

# reporting

## The Successful Contractor shall ensure that the Project Plan is maintained and updated on a regular basis as may be necessary to reflect the then current state of the implementation of the project.

## The Customer shall have the right to require the Successful Contractor to include any reasonable changes or provisions in each version of the Project Plan.

## The Successful Contractor shall perform its obligations so as to achieve each Milestone by the Milestone date.

## The Successful Contractor will inform the customer of changes to risk which will impact upon delivery to time, cost or quality.

## Changes to the Milestones shall only be made in accordance with the variation procedure and provided that the Successful Contractor shall not attempt to postpone any of the Milestones using the variation procedure or otherwise (except in the event of a Customer default which affects the Successful Contractor's ability to achieve a Milestone by the relevant Milestone Date).

## The Successful Contractor must ensure that the right people are in place to manage all aspects of delivery for the Contract. The Successful Contractor must identify named individuals for each role as required as part of their tender submission.

## Tenders must include full details of relevant experience for all named individuals. It is not expected that key staff should change over the course of the Contract but any change required must be communicated at the earliest opportunity and project members being replaced will be substituted by those of a similar experience/authority. The Authority may also request details of relevant experience for the new project members for verification if required. It is not expected that any personal data will be collected or used in the project.

## The project progress will be monitored through regular review meetings. These will be at least monthly, and may be more frequent during the early stages of the project, in order to ensure that the Successful Contractor has sufficient information from the Authority.

### The Successful Contractor must attend these meetings, which will be held either in DfT offices in London or at the Successful Contractor’s premises, at no additional cost to the Authority.

### During the meetings, the Successful Contractor must update the Authority on all progress using the reports as specified in section 9.1, and highlight any new or changed risks that are likely to affect delivery of the project.

## Any delay or issues may also be tabled during the meetings with resolutions agreed and changes addressed by use of the Contract Variation Form.

# volumes

## This requirement is for a one off piece of work. The Contract duration is 6 months, with an option to extend up to a further month at the request of the DfT, if there is extra work arising from the project. The final report will be delivered by 31/03/18.

# continuous improvement

## The Successful Contractor will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

## The Successful Contractor should present new ways of working to the Authority during monthly Contract review meetings.

## Changes to the way in which the Services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

# Sustainability

## There are no sustainability considerations that Potential Providers need to include in their submissions.

# quality

## Quality standards as referred to within the DfT Terms and Conditions associated with this requirement.

# PRICE

## The Potential Provider shall provide a total price for the work and provide a breakdown of how this was arrived at using their hourly/daily rates.

## The Contracting Authority foresees this work being completed within a budget of no more than £80,000 excluding VAT and inclusive of any expenses (see below). £80,000 represents the maximum allocated budget in relation to this Contract.

## Potential Providers are asked to consider that this is a competitive process and the Contracting Authority is actively seeking to achieve Value for Money. Potential Providers should be reminded that this is an Open Market Competition and are advised to put their best bid forward.

## Bids which are above the value of £80,000 excluding VAT will be deemed non-compliant.

## Potential Providers are requested to provide a cost for Travel and Subsistence, as well as a cost for the requirement.

## The budget of £80,000 excluding VAT is inclusive of the cost of Travel and Subsistence and the cost of the specified requirement.  It is expected that Travel and Subsistence should make up a small fraction of the overall cost.

## Travel and Subsistence costs shall be claimed at Department for Transport T and S Policy Rates.  Please see Annex 1.

## Prices are to be submitted via the e-Sourcing Suite - Appendix E excluding VAT.

# STAFF AND CUSTOMER SERVICE

## The Authority requires the Potential Provider to provide a sufficient level of resource throughout the duration of the EDS-C deployment: Virtual Separation Study Contract in order to consistently deliver a quality service to all Parties.

## Potential Provider’s staff assigned to the EDS-C deployment: Virtual Separation Study Contract shall have the relevant qualifications and experience to deliver the Contract.

## The Potential Provider shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# service levels and performance

## The Authority will measure the quality of the Successful Contractor’s delivery by:

| ## Service Area | ## SLA / KPI | ## SLA Description | ## Target |
| --- | --- | --- | --- |
| ## Progress Report | ## SLA | ## Progress reports will be supplied to the DfT project manager by email. This will include a summary of progress against the delivery. | ## Every two weeks after the Contract award. |
| ## Risk Monitoring | ## SLA | ## The Successful Contractor will raise any concerns about the possibility of failing to meet the overall deadline and lack of relevant information to meet the requirements. | ## Every two weeks as part of the Progress Report. |
| ## Communication | ## SLA | ## The Successful Contractor shall acknowledge any communications from the Contract/project manager within two business days. | ## Two business days. |
| ## Emergencies | ## SLA | ## If there is an urgent issue, the Successful Contractor shall make the Contract manager aware of this within two business days. | ## Two business days. |
| ## Dispute resolution | ## SLA | ## If there is a dispute or complaint raised, the Authority should be able to contact the single point of contact for the Successful Contractor and a resolution plan should be put in place within two business days. | ## Two business days. |

# Security requirements

## The Successful Contractor shall adhere to the Authority’s Security Policy as referred to within the DfT Terms and Conditions associated with this requirement.

## Any information arising from this project (including data, interim or final reports, recommendations, vulnerability assessments and information provided by third parties) must be stored securely and access controlled such that only those with a direct need to know may access it.

## Any information held on an IT system must be encrypted and password protected.

## The Successful Contractor may be given access to sensitive information which must only be shared on a strict need to know basis (i.e. selected members of the project team only). The Successful Contractor will destroy all classified information on completion of the project.

## Data may be held on a corporate IT network, subject to points 17.1, 17.2 and 17.3 above being complied with.

## Information from this project may only be shared with third parties if prior written approval is obtained from the DfT. This includes publication, presentations at conferences and informal discussions with peers not directly involved with the project.

## Staff with open access to the collated information and the final report must have (or have a willingness to obtain), at least a basic security check which meets the Basic Personnel Security Standard defined by the Cabinet Office.

## More information on this topic can be found here:

## https://www.gov.uk/government/publications/government-baseline-personnel-security-standard

# intellectual property rights (ipr)

## Intellectual Property Rights will align with the DfT Terms and Conditions associated with this procurement at Appendix C.

# payment

## A purchase order will be raised and the Successful Contractor should issue invoices in accordance with the milestones as set out in paragraph 7.1 above.

## Invoices must show DfT’s purchase order number. This information will be handed over at the inception meeting

## The Contractor must send the invoice (no accompanying information needs to be included with this invoice) to DfT’s Shared Service Centre at:

DfT Shared Service Centre

5 Sandringham Park,

Lansamlet

Swansea Vale,

Swansea

## SA7 0EA

## The payment mechanism shall be Milestone Payments. Invoices shall be submitted for amounts to be agreed by the parties, indicative of the Provider’s bid submission and the Delivery Plan as set out in section 7.1.

## Payments will be made on satisfactory performance of the services, at the payment points defined as per the payment mechanism. Payment will be made if the criteria are met to the satisfaction of the Authority.

## If the provider is late in meeting a specific milestone, that payment and subsequent milestone payments will not be made until the progress of the work is back on schedule.

# additional information

## N/A

# Location

## The work will be carried out at The Successful Contractor’s premises or at manufacturer’s locations as identified by the Successful Contractor as required.

Travel and Subsistence - Annex 1

1. Travelling and subsistence expenses shall not exceed the upper limit of allowances payable to Departmental staff of equivalent status.

2. Any travel undertaken as a consequence of performance of the Contract must utilise the most cost effective means (taking into account the cost of travel, the cost of meals and accommodation and savings in time) for the whole journey. Claims for travelling and subsistence must be related to the performance of duties for the purposes of this Contract and be certified as such. Visits abroad require the prior approval of the Department.

3. The current Departmental rates are shown below. These rates will apply for the duration of the Contract. Please see note below on rail travel.

Travel by Motor Vehicles

4. Motor mileage allowances for travel by private car and van:

Up to 10000 miles - 40 pence per mile

Over 10000 miles - 25 pence per mile

Travel by Motor Cycle

5. Motor mileage allowances for travel by private motorcycle and motorcycle combinations is 24 pence per mile.

Travel by Pedal Cycle

6. The pedal cycle allowance is 20 pence per mile.

Travel by Train

7. Travel by train should be by standard class (including Eurostar) - irrespective of grade, entitlement or distance - unless there are compelling reasons to travel first class or, exceptionally, a first class discount ticket is cheaper. Any claim for travel other than standard class must be approved in advance by the Department.

Before the higher cost travel is used you must consider the business need and whether the extra expenditure is justified.

Subsistence

8. Each Government Department is required to set its own standard rates for night subsistence. The Department has issued the rates set out in paragraph 8 below. For the purposes of this Contract therefore, these rates will apply although it is recognised that other rates and conditions may be applied by different contracting authorities, over whom the Department has no control.

(a) Night subsistence allowance (irrespective of salary) indicative ceilings:

London	£110.00

Elsewhere	£90.00

(b) Day subsistence allowance (irrespective of salary) indicative ceilings:

5 to 10 hours - £4.50

10 to 12 hours - £9.50

over 12 hours - £14.00

Actuals

9. Where it is not possible to obtain accommodation within the rates set out in 8(a) above, tenderers may estimate actual expenditure within the Firm Price breakdown. Supporting evidence including the reasons for exceeding the limits in paragraph 8 and receipts showing disbursements will be required with each claim for payment.

Notes

Each claim for payment under the Contract must separately identify those elements of the claim which represent travel and subsistence expenses.

A supplement of 5 pence per mile may be claimed for each mile another person employed on the Contract is carried in / on a private motor vehicle.

The Department does not insist on comprehensive insurance cover (where applicable) but will accept no liability in the event of any accident, damage, injury or death.

Where motor mileage allowance is claimed, each claim should state the amount of the current claim and the cumulative mileage claimed to date under the Contract.

A night subsistence allowance is an allowance paid for an overnight absence. It covers an absence of up to 24 hours plus any additional period not reckonable for day allowance (i.e. less than 5 hours), and is payable for a period of up to 30 nights in any one place. Thereafter, a lower lodging allowance is payable.

Day allowances are not admissible for any period already covered by a night allowance and similarly a lesser day allowance is not admissible for any period covered by a greater day allowance (e.g. a 5 to 10 hour allowance may not be claimed where a 10 to 12 hour allowance is appropriate). Subsistence allowances are not admissible if the place visited is 5 miles or less by the most direct route from the claimant's normal place of work.

Travelling and subsistence allowances are not admissible in respect of travelling between home and place of work for the purposes of the contract.

The Department in paying travel and subsistence expects contractors to note any benefits (such as frequent flying schemes etc.) and to offset these against further travel costs associated with the Department's business.

**Please Note

The T&S rate needs to apply to the travel associated with the specification in Appendix B. There is a space on the price table for this cost to be placed. This cost is for information only and will not be included in the evaluation.