## Guidance Notes
Risk Identification, Evaluation & Control Tool Guidance Notes
This tool is to aid Project Managers to identify, evaluate and control risks associated with their Projects
The most important thing to remember in using this tool is that YOU as the Project Manager:
Identify the potential Risks associated with your project
Evaluate the probability of the Risks occurrin and their potential impact
Control and help manage the Risks by identifying mitigations
To calculate a Score & RAG (Red, Amber, Green) rating for each of the Risks click on the 'REIC tool' tab and provide detail any identified risks, you will then be required to indicate the following:
A. How probable it is that the Risk will occur by giving it a rating of 2, 4, 6, 8 or 10 where 2 means that the chance of the risk occurring is very low and 10 means that you consider the chances of the risk occurring are very high
B. Estimate the impact (eg on safety, time, financial) should the Risk occur and give it a rating of 2, 4, 6, 8 or 10 (where 2 is a low impact and 10 would be a very high impact)
The tool will then calculate the Risk score by multiplying the probability score by the financial impact score e.g. 2x4=8.
The resulting score will then be given a RAG rating in accordance with the matrix below e.g. a score of 40 would be given a 'Amber' rating. Project Managers should focus their attention on controlling 'Red' risks as a priority.
The Project will then be given an overall Risk Score and RAG rating which is the average of all of the individual Risk scores.
Scored Risk Matrix
Calculated Risk Score & RAG Rating (=PxI)
Probability of occurrence (P) | Very High 10 | 20 | 40 | 60 | 80 | 100
| High 8 | 16 | 32 | 48 | 64 | 80
| Medium 6 | 12 | 24 | 36 | 48 | 60
| Low 4 | 8 | 16 | 24 | 32 | 40
| Very Low 2 | 4 | 8 | 12 | 16 | 20
|  | Very Low 2 | Low 4 | Medium 6 | High 8 | Very High 10
Impact (I)

## RIEC Tool
Risk Identification, Evaluation & Control
Project Title | New Bridge, Anytown
Project Manager | Joe Bloggs
Date updated
Version Control | 1
Overall Risk Score and RAG Rating | #DIV/0!
Identification |  |  | Evaluation |  |  | Control
Area of Risk | Risk | Impact | Probability of occurrence | Impact | Risk Score and RAG Rating | Mitigations | Notes
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select