# Annex A

| Title of Project | Ocean Country Partnership Programme: Ghana Beyond MPA Designation in Ghana (Research and Development) |
| --- | --- |
| Date and Time for Return of Bids | Monday 19 August 2024 @16:00 hours |
| Contract Reference Number | C24-0604-1921 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO STEPHANIE CLARKSON, SARAH HARRISON OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Proposed Start Date | Monday 16 September 2024 |
| Proposed End Date | Friday 21 March 2025 |

Ocean Country Partnership Programme: Beyond MPA Designation in Ghana (Research and Development)

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	4

4.	Project Objectives	5

5.	Project Objectives: Detailed Tasks	5

6.	Potential Follow-On Work	7

7.	Outputs	8

8.	Product Specification	8

9.	Dissemination	9

10.	Timescale	9

11.	Health and Safety	10

12.	Project Management	10

13.	Instructions for Bid Submission	10

14.	Evaluation Criteria	12

15.	Payment	13

16.	Additional Requirements	13

17.  Procurement Timetable (which may be subject to change)	14

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

Ghana has designated five coastal lagoons as Ramsar sites and are currently aiming to designate the first Marine Protected Area (MPA) in Ghana as part of the implementation of the Sustainable Ocean Plan. However, gaps relating to the next stages of the MPA implementation cycle (see Figure 1) (notably around management, monitoring and assessment) following successful designation have been identified.

This work intends to develop the foundational building blocks to address key gaps in furthering understanding on the longer-term benefit of MPAs and to support Ghana’s stakeholders in taking action to effectively and sustainably manage their marine environment.

This project aims to:

- Review existing documentation on MPA implementation strategies and frameworks in Ghana to support understanding around knowledge and legislative gaps for effective MPA implementation. This should include a number of clear recommendations as a result of the findings of the review that should be focussed upon maximising MPAs in the context of supporting sustainable livelihoods, food security, health and the well-being of the Ghanian people.

- Provide a thorough stakeholder mapping analysis to identify key stakeholders and their association with key post-designation stages in the MPA implementation cycle.

- Provide a review of previous MPA awareness raising activities undertaken and educational resources developed in Ghana to support expansion of community outreach and further education around the value and importance of marine conservation.

- Make recommendations for future MPA awareness raising activities and educational resource production to enhance knowledge and understanding on the value and importance of marine conservation in Ghana within the context of supporting sustainable livelihoods, food security, health and the well-being of the Ghanian people.

- Develop a high-level framework for an MPA roadmap that reflects key activities following the designation of MPAs to ensure that MPAs contribute effectively to the conservation of the marine environment.

Figure 1. The MPA implementation Cycle, illustrating the key stages involved in the process that guides the establishment, management and evaluation of MPAs. For the purpose of this work, the stages focussed on will be post-designation and include: Threats & Impacts, Management, Monitoring and Assessment.

## Project Background

The UK Government’s Ocean Country Partnership Programme (OCPP) is a UK-led programme funded through the UK’s Blue Planet Fund. The OCPP provides demand-led technical assistance in marine science to partner countries, supporting them to overcome challenges that threaten marine environments and the livelihoods that depend on them.

This contract sits under the “Marine Biodiversity” theme of the OCPP, which aims to:

- Increase understanding of the value of Marine Protected Areas (MPAs) in supporting sustainable livelihoods, food security, health and well-being;

- Increase understanding of MPA theory and practice, including evidence gathering, identification, selection, monitoring and assessment of MPAs;

- Increase support and compliance for MPAs with stakeholders; and

- Enhance capability and drive within countries to sustainably manage, monitor and assess conservation activities in the future.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are to:

- Produce a comprehensive review of existing documentation available for MPA implementation strategies and frameworks in Ghana.

- Produce a stakeholder mapping analysis that identifies key stakeholders and their association with key stages of the MPA implementation cycle.

- Produce a comprehensive review of previous MPA awareness raising activities undertaken and marine environmental educational resources developed in Ghana.

- Produce a high-level scoping document containing recommendations for future MPA awareness raising activities and marine environmental educational resource production to enhance knowledge and understanding on the value and importance of marine conservation in Ghana.

- Develop a high-level framework for an MPA roadmap that reflects key activities following the designation of MPAs to ensure that MPAs contribute effectively to the conservation of the marine environment.

## Project Objectives: Detailed Tasks

- Produce a comprehensive review of existing documentation available for MPA implementation strategies and frameworks in Ghana.

- The review should include:

  - An overview of the current standing of MPAs in Ghana and the current legislative frameworks in Ghana to support MPA designation.

  - Detailed information on the existing documentation relating to post-designation MPA implementation strategies and frameworks in Ghana. This should include, but not be limited to, the name, purpose, mechanisms and leading authorities. Focus should be applied in particular to documentation relating to MPA management, monitoring and assessment.

  - Detailed information on key gaps in existing documentation relating to post-designation MPA implementation strategies and frameworks in Ghana. Focus should be applied in particular to documentation relating to MPA management, monitoring and assessment.

  - High-level information on potential challenges in addressing the key gaps identified.

  - Where possible, and following agreement with JNCC, liaise with in-country stakeholders to support development of the review.

- Produce a stakeholder mapping analysis that identifies key stakeholders and their association with key stages of the MPA implementation cycle.

- The stakeholder mapping analysis should include sections on identifying, prioritising and understanding stakeholders and clearly identify differentiation between these for awareness raising activities, educational resources and key stages of the MPA implementation cycle. The stakeholder mapping should be inclusive and range from local communities through to government departments. Where possible, and following agreement with JNCC, liaise with in-country stakeholders to support the analysis.

- Produce a comprehensive review of previous MPA awareness raising activities completed and marine environmental educational resources developed in Ghana.

- The review should include:

  - An overview of the need for MPA awareness raising activities and educational resources in Ghana, and where possible link these to national and international priorities, legislation and frameworks.

  - Detailed information on both MPA awareness raising activities undertaken and educational resources developed throughout Ghana.

    - For MPA awareness raising activities this should include, but not be limited to, the name, date, purpose, location, audience, leading developer/contributors and types of engagement. Notably this should also consider whether previous community engagements have used knowledge obtained to feed community perspectives into MPA considerations.

    - For educational resources this should include, but not be limited to, name, date, purpose, dissemination or delivery location, audience, leading developer/contributors, type of resource and utilisation and sustainability.

  - Detailed information on key gaps for MPA awareness raising activities and educational resources in Ghana. In particular, this would focus on identifying the rationale for those gaps, locations not previously covered/incorporated and gaps in content covered.

  - High-level information on potential challenges in addressing the key gaps identified.

  - Where possible, and following agreement with JNCC, liaise with in-country stakeholders to support development of the review.

- Produce a high-level scoping document containing recommendations for future MPA awareness raising activities and marine environmental educational resource production to enhance knowledge and understanding on the value and importance of marine conservation in Ghana.

- The high-level scoping document should:

  - Use the from the findings from objective 3 to outline a scope for future MPA awareness raising activities and marine environmental educational resources. This should focus on the priorities for future awareness raising activities and educational resources in Ghana and include ideas for types of activities and resources, key considerations and challenges, and if possible, identify key locations to undertake activities.

  - Use the findings from objective 2 to identify key stakeholders that should be involved in future MPA awareness raising activities.

- Develop a high-level framework for an MPA roadmap that reflects key activities following the designation of MPAs to ensure that MPAs contribute effectively to the conservation of the marine environment.

- The high-level scoping document should:

  - Use the findings from objective 1 to outline a scope for a post-designation implementation MPA roadmap. This should focus around the MPA implementation cycles stages (notably management, monitoring and assessment) and include links to associated existing legislation, strategies and/or frameworks, key considerations, challenges and gaps. Useful resources/tools should also be highlighted.

  - Use the findings from objective 2 to identify where community perspectives and priorities can be incorporated into the MPA implementation cycles stages (notably management, monitoring and assessment).

  - Consider visual aids that could be used to support and summarise key processes or steps.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26 as follows:

- Beyond MPA designation (development and implementation). Using the findings and outputs of the Beyond MPA designation (research and development) project, this work aims to:

  - Complete an MPA roadmap that highlights the key next steps, actions and considerations for effective MPA implementation following designation in Ghana.

  - Undertake MPA awareness raising activities in local communities and utilise the findings from these engagements to feed community perspectives and priorities into completing the MPA roadmap.

  - Produce education packs that will expand on community outreach already undertaken in Ghana and deliver further education around the value and importance of marine conservation.

Please note that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

Any products or outputs submitted to JNCC [for publication] should be produced using an OCPP template (to be provided) and should be produced in an accessible format (see product specification for more information).

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.  All reports and other documentation which are to be made publicly available must be produced using an OCPP template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

The contractor will not publish any information, by any means of publication, resulting from this contract without written consent from JNCC/OCPP.

The contractor will ensure that data management and storage requirements are stipulated, taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

Collection of personal data to meet the outputs of this contract should be handled in line with JNCC’s OCPP Privacy Notice.

## Dissemination

The products/outputs produced under this contract will be an OCPP product and shall not be published or disseminated without the written permission of JNCC/OCPP. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (Centre for Environment, Fisheries and Aquaculture Science (CEFAS), the Marine Management Organisation (MMO) and Defra as partners in the OCPP.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability. The final products for this contract must be delivered by 21st March 2024 at the latest

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call using Teams or other appropriate online platform) | 16th September 2024 |
| First draft output for objective 1 | 11th October 2024 |
| Second/final draft out for objective 1 | 25th October 2024 |
| First draft output for objective 2 | 22nd November 2024 |
| Second/final draft out for objective 2 | 6th December 2024 |
| First draft output for objective 3 | 10th January 2025 |
| Second/final draft out for objective 3 | 17th January 2025 |
| First draft output for objective 4 | 31st January 2025 |
| Second/final draft out for objective 4 | 14th February 2025 |
| First draft output for objective 5 | 21st February 2025 |
| Second/final draft out for objective 5 | 7th March 2025 |
| Final products delivered | 14th March 2025 |
| Progress meetings | Once a month (September – March) but note there may be a need for video calls in between these scheduled meetings at the discretion of the successful contractor and JNCC. |
| JNCC/OCPP reviews | Reviews will be undertaken by JNCC following delivery of draft outputs and aim to be returned to contractor within one week of receiving them. |

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Stephanie Clarkson

Email: stephanie.clarkson@jncc.gov.uk

Telephone: +44 (0)1733

Name: Sarah Harrison

Email:  sarah.harrison@jncc.gov.uk

Telephone: +44 (0)1733

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

Details of Quality Control procedures to be followed to best avoid bias, conflicting evidence and uncertainty (see JNCC Evidence Quality Assurance (EQA) Policy: Appendix 1. Bias, conflicting evidence and uncertainty) and ensure quality assurance of expert knowledge and opinion (see JNCC Evidence Quality Assurance (EQA) Policy: Appendix 3. Quality Assurance of Expert Knowledge and Opinion)

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Availability of the Project Team for a start-up meeting via Microsoft Teams virtual meeting.

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached, and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation (to submit in a zip folder separate from the proposal):

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments;

  - Copies of your company's modern slavery and or safeguarding statement or policy and;

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff.  Unless otherwise stated in your bid submission, bids will be forwarded to this agency for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of Marine Protected Area implementation generally but ideally in Ghana. | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC’s project manager, payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

The successful contractor should:

- Have a good understanding of marine conservation and specifically the Marine Protected Area implementation cycle.

- Have a good understanding of marine conservation in Ghana, notably in relation to Marine Protected Areas and underpinning legislative frameworks/strategies.

- Have experience of developing technical outputs that concisely but effectively summarise complex information.

- Have experience of engaging and working closely with stakeholders, and be able to actively listen to the range of views of different stakeholders. Ideally the successful contractor will have experience working or engaging with key marine Ghanaian stakeholders.

- Have experience or knowledge on developing and undertaking awareness raising activities with local stakeholders in Ghana.

- Provide quotes in USD or GBP. The quote should cover all costs to successfully deliver the outputs of the contract.

## 17.  Procurement Timetable (which may be subject to change)

| Activity | Date |  |
| --- | --- | --- |
| Publication of Contract Notice | 24 July 2024 |  |
| Last date for receipt of clarification questions | 12 August 2024 |  |
| Final submission date for bids | 19 August 2024 |  |
| Evaluation of bids | w/c 19 August 2024 |
| Post-tender negotiation/clarification and or presentation if required | w/c 26 August 2024 |
| Successful bidder Notified & Contract Award | w/c 2 September 2024 |
| Unsuccessful bidders notified | w/e 6 September 2024 |
| Start of project | 16 September 2024 |