## Schedule of Work
Annex A
MCA - SCHEDULE OF WORKS
Site Address: |  | Filey
The Beach Filey YO14 9LE
Project Type: |  | Minor Works Improvement
Tenderers for the above contract should complete the tables below, indicating what they would charge for each required element. Prices must: • Be stated in Pounds Sterling; • Include all other charges and overheads associated with the element being priced.
|  | General Works, Site conditions and Prelims : | Tender: £ | Comments
Notes
** | R&D Asbestos Survey to be supplied prior to commencement of any works.
** | Existing main power supply and fuse board to be reviewed. Any improvements must be advised at tender stage and detailed to the client in advance.
1 | General conditions temporary siteworks & Preliminaries
1.01 | No storage will be provided on site all materials and waste are to be removed from site as they occur
1.02 | Allow for all skips and storage containers as necessary, including all licenses for their location the client takes no responsibility for any materials, plant or equipment stored or left on site
1.03 | Toilet facilities will be available on site no canteen facilities will be available which contractors are to make allowances for as necessary
1.04 | All public footpaths, highways and fire routes as part of the site and property are to be kept clear of all obstructions and debris at all time. All access and scaffolding should not obstruct the above at any time
1.05 | Allow for the supply of temporary fire fighting equipment, first aid equipment, hard hats, PPE and signage to comply with HSE regulations
1.06 | Allow for standard insurance during the works
1.07 | All electrical work and installation to be undertaken by an NICEIC Approved contractor to current regulations
1.08 | All work carried out must comply with current building regulations
Main Works
2 | Strip out
2.01 | Allow to remove solid brick wall to first floor between front and back room, install steel beam 305 x 105 to support ceiling joist install block work to support steel beam as per plan, included for cladding beam in 15mm fire line plasterboard, Note door and frame to rear room to be replaced
2.02 | Allow to make good ceiling and walls following removal of wall removed ready for decoration
2.03 | Allow to protect existing floor covering during the works
2.04 | Remove radiator set a side for reconnection in new location
2.05 | Remove electrical sockets on both sides of the wall, central heating thermostat and time to be relocated on to new wall area
2.06 | Remove all existing kitchen units and dispose off site. Retain existing services ready for reconnect to new units
3 | Building work remedial works
3.01 | Allow to cut out and replace Spalding brickwork on the internal face left hand side of the garage
3.02 | Allow to repair and redecorate as existing timber frame around the front entrance of the garage door
3.03 | Allow to replace 3 off timber windows to first floor level and 2 off timber windows on ground floor with DG UPVC windows
3.04 | Allow to make good plasterwork around newley installed windows ready for decoration
3.05 | Allow to repoint brickwork below round window on side of building approx 1.5 sq mts
4 | Refurbishment works
4.01 | Install new new FD30 fire door with double vision panels, allow for new hardware to included handles, lock with thumb turn, door closer, kick plates, and fire signage
4.02 | Allow to Install a new fire frame to above door including for fire & smoke seals and new architraves
4.03 | Install the following kitchen units from the Howden Glendevon gloss white range. 1 x 1000 drawer line sink base unit, 1 x 500 x 4 drawer unit, 1 x 1000 wall unit, 28mm bullnose black laminated worktop with connection bolts, joint compound, included for all end panels, plinths, cornice and brushed steel effect handles
4.04 | Provide space for free standing fridge as per plan include for gloss white end panels to both sided of the opening
4.05 | Install inset sink including mixer lever taps, allow for connecting to the existing under sink water heater and wastes in the toilet
4.06 | Allow for 3 x twin sockets above work surface, 1 x single socket outlet below work surface for fridge connected to a neon fused spur above work surface
4.08 | Allow for 5 x twin socket outlets with USB ports in white trunking as indicated on plan
4.09 | Allow to alter emergency lighting to suit new layout
4.01 | Allow to install Metro bevelled tiles to splash back between the worktop and wall cupboards, included for chrome trims. all tiling to be finished to a good quality. Tile colour white. Grout colour grey.
4.11 | Prepare and decorate all previously painted walls and ceilings. Using 1 mist coat and 2 top coat of Dulux Trade matt Emulsion Paint, walls magnolia ceilings white
4.12 | Prepare and decorate all new and previously painted timber surfaces with 1 coat undercoat and 2 top coats of white gloss decorate all doors Ral 5002 blue
4.13 | Supply and install Milliken carpet tiles Ref; light trails colour Titanium to patch repair carpet areas once wall has been removed and kitchen altered allow for a new door nap
5 | Completion
5.01 | On completion of electrical works, provide NICEIC electrical test cert for all new installations
5.02 | On completion of work allow to undertake an emergency lighting/ fire alarm discharge test in line with NICEIC guidelines and provide certification to demonstrate that all emergency lights / alarms are operational and compliant.
5.03 | On completion Contractor to undertake deep clean of working areas and leave the premises clean and tidy, free from dirt, dust and any builders waste and plant.
6 | Preliminaries & Overheads
6.01 | Prelims
6.02 | Overheads
-180%
| TENDER TOTAL |  | 0
-80%
| VAT |  | 0 | 20%
| TOTAL INCLUSIVE OF VAT |  | 0
The nominated Procurement Manager is:
Kathy Monk
MCA Commercial
Bay 3/19 – Spring Place
105 Commercial Road
Southampton
SO15 1EG
Tel:- 020 381 72328
Email: - Contracts@mcga.gov.uk
Signed:
in the capacity of:
duly authorised to sign tenders for and on behalf of :
Postal Address:
Telephone No:
Email:
Date: