ERDF Summative Assessment Plan Form

ESIF-Form-1-012

Part 1 Project Summary

| 1.1 Applicant Details |  |  |  |
| --- | --- | --- | --- |
| Applicant Organisation | Council of the Isles of Scilly |  |  |
| Project Name | Isles of Scilly Voucher Scheme |  |  |
| Programme Priority Axis | 3: Enhancing the Competitiveness of SMEs |  |  |
| Name of ERDF Investment Priority | PA 3A: Promoting entrepreneurship in particular by facilitating the economic exploitation of new ideas and fostering the creation of new firms, including through business incubators PA 3C: Supporting the creation and the extension of advanced capacities for products, services and development PA 3D: Supporting the capacity of SMEs to grow in regional, national and international markets and to engage in innovation processes |  |  |
| LEP Area (s) covered | Cornwall and the Isles of Scilly (C&IoS) |  |  |
| Total Project Value (£) | £2,156,912 |  |  |
| Total ERDF sought (£) | £1,327,226 |  |  |
| ESIF Category of Region |  | Less Developed |  |
|  |  | More Developed |  |
|  |  | Transition |  |

| 1.2 Project Timetable |  |
| --- | --- |
| Proposed Start Date | 1/01/2019 |
| Proposed Financial Completion Date | 31/12/2021 |
| Proposed Practical Completion Date | 31/12/2021 |

1.3 Project Description (brief summary in max. 500 words)

The Project aims to: - Provide investments to island based SMEs leading to long term, sustainable business growth; - Support businesses to implement and realise their growth ambitions in line with the OP EUSIF and Islands Futures Plan; and, - Grow GVA and create additional jobs in support businesses. The ultimate goal is to aid transformation of the Isles of Scilly economy by offering investments of between £1,000 and £100,000 to SMEs located on the Isles of Scilly through a council led and managed Voucher Scheme. This will support business growth and higher paid jobs on the Islands. With project/asset/capital costs averaging 40% more on the Islands due to freight and limited access to services, many commercial and business ambitions are not acted upon. Vouchers will lead to long term, sustainable business growth including higher value job creation and in increase in GVA by addressing the additional costs that Island businesses face delivering projects on the Island. Investments are made in the following types of activities: - Access to new markets; - Feasibility studies; - Consultancy related to growth ambitions; - Technology and product design; - Environmental measures; - Research and development activities; - Workspace; - Equipment; and, - IT solutions. The Project is delivered and only available to applicants on the Isles of Scilly. It is managed through three members of staff: a voucher scheme manager, an engagement officer and a finance assistant. The scheme expects to secure interest in grants from £1,000 to £100,000 and the original expectation was for them to be distributed approximately as follows: Number of projects; Voucher size; Total Eligible value of projects; Average Voucher Intervention Rate; ERDF Funds; State aid. 10; £20,000-£100,000; £700,000.00; 35%/45%; £315,000.00; GBER2(construction). 4; £20,000-£100,000; £162,481.00; 60%**; £97,488.60; De Minimus* (IFB Plans & innovations). 3; £40,000-£80,000; £450,000.00; 50%; £225,000.00; De Minimus. 8; £10,000-£20,000; £200,000.00; 60%; £120,000.00; De Minimus. 15; £3,500-£10,000; £200,000.00; 70%; £140,000.00; De Minimus. 15; £1,000-£3,500; £50,000.00; 70%; £175,000.00; De Minimus(Fast Track). M&A; £394,431.00; 100%; £932,795.00; ERDF. 55; Total; £2,156,912.00; 61.53%; ERDF IR. The Project is contracted to deliver following outputs: - ER/C/O/01- Number of enterprises receiving support -55 - ER/C/O/02- Number of enterprises receiving grants -55 - ER/C/O/05- Number of new enterprises supported - 10 - ER/C/O/06- Private investment matching public support to enterprises(grants) -£829,686 - ER/C/O/08 – Employment increase in supported enterprises - 22 - ER/C/O/28- Number of enterprises supported to introduce new to the market products -1 - ER/C/O/29- Number of enterprises supported to introduce new to the firm products - 35 - ER/P/O/02- Public or Commercial building build or renovated - 500m2

Part 2 Summative Assessment Plan

2.1 Statement of Objectives (max 500 words) Please provide your objectives (i.e. a clear description of what you are hoping the project will achieve). Objectives should focus on describing what insights the summative assessment will seek to provide in respect of: - The design of the project; - How the project has performed against its targets; - The nature of the project’s outcomes and impacts and the value for money that has been achieved; - The lessons which have emerged through the experience of delivering the project.

In this section of the Monitoring and Evaluation Plan VS sets out the key evaluation objectives and research questions based on both local considerations and the national requirements. The guidance encourages grant recipients to use this as a starting point for developing a series of project specific questions or evaluation objectives whilst also focusing on lessons learned. A series of questions has been developed for the IoS Voucher Scheme evaluation that addresses both local and national requirements and is shown in the table overleaf. Key Areas; Core Evaluation Questions; Local Considerations. Project Design, Relevance and Consistency; - What was the project seeking to do? Is this a good idea? - What was the economic and policy context at the time that the project was designed? - What were the specific market failures that the project was seeking to address? Was there a strong rationale for the project? - Was it appropriately designed to achieve its objectives? Was the delivery model appropriate? - Were the targets set for the project realistic and achievable? - How did the context change as the project was delivered and did this exert any particular pressures on project delivery? - Bearing in mind any changes in context or weaknesses in the project design / logic model, can the programme reasonably be expected to perform well against its targets?; - Project design in the context of an Island economy - Complementarity with Mainland provision (grants and business support). Project Delivery (covering progress and project implementation); Progress - Has the project delivered what it expected to in terms of spend and outputs? - What are the factors which explain this performance? - When the project draws to a close, is it expected to have achieved what it set out to? Delivery and Management - Was the project well managed? Were the right governance and management structures in place and did they operate in the way they were expected to? - Has the project delivered its intended activities to a high standard? - Could the delivery of the project have been improved in any way? - Did the project engage with and select the right beneficiaries? Were the right procedures and criteria in place to ensure the project focused on the right beneficiaries? - How are project activities perceived by stakeholders and beneficiaries? What are their perceptions of the quality of activities / delivery? - To what extent have the horizontal principles (e.g. equality & diversity, sustainability etc. as defined by ESIF) been integrated into and shaped delivery?; Progress - Profile of investments – size of grants and sectors supported Delivery and Management - Voucher application process - Role of the Island Futures Board in decision-making. Impact/Effectiveness; - What progress has the project made towards achieving the outcome and impacts (both qualitative & quantitative)? - To what extent are the changes in relevant impact and outcome indicators attributable to project activities? - What are the additional economic, social and environmental benefits of the project (where relevant and applicable to project activities)? - What are the main sources of Strategic Added Value that the programme has created?; - Sustainability of outcomes, given the seasonality and growth potential of Island businesses - Contribution to other Island objectives such as ‘Smart Islands’. Economy; - Was the scheme good value for money? - How does it compare with other interventions; - VFM of Island based delivery. Conclusions and Lessons Learned; - What are the key conclusions - What are the key learning points in relation to each of the above for: - The grant recipient/funding body - Those designing and implementing similar interventions - Policy makers; - How can the lessons learned feed into future voucher schemes.

| 2.2 Logic Model: |  |  |
| --- | --- | --- |
| Have you completed the project logic model form and submitted it to us (see Appendix A of the summative assessment appendices)? | - Yes ☐ | No ☐ |

2.3 Approach, Methods and Tasks (max 500 words) Referring back to the objectives of the summative assessment, please outline the methods that will be used to deliver the insights. The consideration of methods (see Appendix C of the summative assessment appendices) needs to encompass the progress, process and impact focused elements of the summative assessment.

## It should be noted that the Isles of Scilly Voucher Scheme is a relatively small project, which means that the summative assessment requirements will be somewhat lighter touch than might be the case for other types of intervention whilst still being methodologically rigorous. This chapter of the Monitoring and Evaluation Plan covers our overall approach to measuring impact, the methods that will be used to address evaluation objectives and the specific tasks to be carried out. ## Approach to Measuring Impact A key feature of any evaluation process is to understand the true impact of the project on the economy and wider society. The gold standard and ideal way to measure these effects is through the use of ‘counter-factual’ studies, utilising a ‘control group’ to identify the additional benefit achieved. However, identifying suitable control groups and methods can be challenging and it is not always possible. In this case we are not planning to use a control group. This is because: - The Isles of Scilly is a notoriously difficult environment in which to conduct a control group style evaluation because a) level of business support available within the area (reflecting the more developed area status b) the limited pool of potential control businesses reflecting the Island economy. Arguably it would be necessary to ‘match’ project beneficiaries with businesses outside of the area to avoid this but such an approach could also potentially introduce a bias because of the unique nature of the local economy; and, - Ultimately the project is comparatively small and the cost of such an exercise would outweigh the benefits. Instead, our summative assessment will work within a ‘Theory of Change’ Framework. This effectively utilises the logic model to specify and consider the relationship between actions, outcomes and other factors. Initial outcomes are often expressed in terms of changes to knowledge, skills and abilities, intermediate outcomes are the change in behaviour that is expected to lead to impactful, long-term changes in economic or social performance. Attribution is achieved by evidencing the desired behavioural change, and tracing it to the various actions initiated by the intervention, rather than through the use of a counterfactual. ## Assessing Net Impacts It is also important to understand how attributable the outcomes are to the intervention. As well as setting out the gross impacts, the summative assessment will assess the net impacts, after additionally adjustments such as deadweight, displacement, substitution and leakage effects have been accounted for. These are shown in the following table. Adjustments; Description; How This will be Accounted for. Deadweight; The proportion of outputs/outcomes that would have been secured anyway, without the intervention; Beneficiary feedback interviews will explore options such as: - No investment/change would have occurred - Change/investment would have happened more slowly - A smaller level of change/investment would have occurred. Leakage; The proportion of outputs/outcomes that benefit those outside the area - e.g. an Isles of Scilly business decides to expand premises outside the Islands as a result of the support received; Beneficiary feedback interviews will explore: - Existence of sites outside the area - Plans to grow these sites - Whether support received through the voucher scheme has influenced this growth. Displacement; The proportion of outputs/outcomes that are reduced elsewhere in the area - e.g. an Isles of Scilly business grows at the expense of other businesses on the Islands; Beneficiary feedback interviews will explore displacement by understanding the: - Proportion of sales on the Isles of Scilly - Proportion of competitors on the Isles of Scilly. Multiplier Effects; Additional economic activity arising from economic multiplier effects associated with wage and supply chain spending in the local economy; Using industry benchmarks. The Council of the Isles of Scilly has already put in place a system for collating and recording key project documentation and has designed a series of bespoke forms to capture particular pieces of information from participating businesses. These are all recorded on an excel spreadsheet which is used as the basis for reporting to MHCLG. Our summative assessment will draw heavily on the spreadsheet, but will also include supplementary primary research. Our tools include: - A desk based review of key project documentation - including the original ERDF application and project change request forms, the project logic model, MHCLG quarterly reports, internal documentation such as minutes from Steering Group meetings, publicity campaign material etc.; - A desk based review of project monitoring information – drawn from the Excel spreadsheet and project progress reports, focusing on evidence of (contracted) outputs that have been delivered as well as the financial profiles and spend. N.B this is based on a rigorous audit trail that has already been put in place by the Council of the Isles of Scilly team including paperwork documenting business eligibility; application paperwork; project change requests and output evidence etc.; - A desk based review of softer outcomes – drawn from qualitative sources such as project monitoring visits and site completion visits that have been undertaken by the Voucher Scheme staff which seek to capture softer outcomes such as successes, unexpected outcomes, longer term business plans, cross cutting themes etc. - Primary research with participating businesses – which will be undertaken by the evaluation team in the form of qualitative interviews with businesses and the development of case studies; - Primary research with the delivery team – through interviews with Council of the Isles of Scilly staff and third party delivery partners; and, - Primary research with wider stakeholders – through interviews with an agreed selection of strategic partners from both the Isles of Scilly and the Mainland, as well as the funding body. Multiple tools will be used to address each evaluation objective. The following diagram shows this relationship. Desk based review of key project documentation; Desk based review of project monitoring information; Desk based review of softer outcomes; Primary research with participating businesses; Primary research with the delivery team; Primary research with wider stakeholders. Project Design. Project Delivery. Impact/Effectiveness. Economy. Conclusions & lessons Learned. ## Tasks The Voucher Scheme team will be responsible for ensuring that all monitoring data and information is routinely and robustly collected throughout the lifetime of the Project. This material will form the basis of the summative assessment and further details are provided in Chapter Five. Other tasks, to be undertaken by the external evaluators, will include engaging effectively with key stakeholders including beneficiaries, the Project team and various external partners through carefully targeted primary research in order to add depth and value to the summative assessment findings.

2.4 Data and Monitoring (max 500 words) Please briefly demonstrate that appropriate monitoring arrangements are in place to support strong and insightful summative assessment and confirm your commitment to collecting the minimum / compulsory data set out in Appendix D of the summative assessment appendices and also outline any additional monitoring data.

# The Council of the Isles of Scilly has already developed and is administering a series of data capture tools for use with clients. The following table describes the areas of coverage within each. Document Reference No.; Tool; Covering. 1; Expression of Interest https://www.iosvoucherscheme.co.uk/expression-of-interest-form; Name address, business size, new/existing business, estimated costs, timings and outputs. 2.; Application form; Full details of applicant, funding, business case, outputs, management, cross cutting themes, milestones, costs and match funding, financial management and control, compliance, procurement and publicity. 3.; Match funding proof; Bank statement/letter as evidence that the project can be contracted. 4; Procurement form and evidence; Electronic form with supporting evidence including quotes, tenders, awarding methods etc. 5.; Sustainable development appraisal; Form showing how each project contributes to sustainable development and score for each. 6.; VAT declaration; Self-declaration form if the applicant intends to include VAT amounts within their claim. 7.; Investment and eligibility check; Checklist covering key appraisal issues such as: type of activity, benefits to Isles of Scilly, eligible costs, investment priorities, outputs and deliverables. 8.; State Aid Assessment; State aid tests and exemptions. 9.; Application assessment form; Detailed assessment of application against criteria including: business case, outputs, cross cutting themes, milestones, suitability of funding/match, procurement, publicity and overall score. 10.; Signed project appraisal form; Document to evidence that all checks supplied are approved by independent appraiser and projects are approved for contracting with the CIOS.. 11.; Signed offer letter/funding agreement; Agreement between the applicant and CIOS detailing name of project, date of approval, grant awarded, terms and conditions, special conditions, milestones and targets. Can include conditions. 12.; Project Engagement Visit; Visit to check that all outputs will be evidenced correctly and to run through compliant claim procedures. Documented through team records. 13.; Voucher change request; Form – used if applicable when anything is changing within the project delivery such as underspend/overspend/delay/re-profile (money & outputs). 14.; Claims; A file containing all of the project quarterly claim forms including expenditure, progress report, outputs delivery reports etc along with invoices, bank statements. 15.; Asset register; Used to register any asset purchased with the funding of a value £1,000 and above. All assets are liable for monitoring for three years and applicant should record if /when and value of disposal to VS. 16.; Publicity evidence; Contains any evidence the applicant has given as described in the Publicity Guidance. 17.; Output evidence/project monitoring Visit Form (s) - Output confirmation letters for each output - Annual Project Monitoring Visit Record - On-side completion visit record; Includes: - Signed evidence of output achievement - Progress against planned activities, outputs, cross cutting themes, publicity, contract conditions and forward planning - Reflection on success and unexpected outcomes, maintaining the benefits, publicity, output performance asset register. In addition the summative assessment can draw on output from the mandatory MHCLG reporting documents as follows: Tool; Covering. A; MHCLG Monitoring reports; Outputs achieved Description of evidence Cross cutting themes. B; ERDF claims; Expenditure Outputs Procurement Asset register. C; MHCLG data monitoring template (ESIF-Form-1-013); Information for direct beneficiary businesses Beneficiary outcome indicators. ## When Who and How All of these data capture tools are administered by the Council of the Isles of Scilly team and the output from each is recorded on the team’s excel spreadsheet which will enable key data on all of these aspects to be accessed at the touch of a button. The following table sets out the timing and methods of administration for each component. Tool; When Administered; By Who; How. 1.; Expression of Interest; Pre application; Applicant; On-line. 2.; Application form; Pre application; Applicant; Electronic form with supporting evidence. 3.; Match funding proof; Pre-application; Applicant; Bank statement/letter. 4; Procurement form and evidence including quotes, tenders, awarding methods; Application; Applicant; Electronic form with supporting evidence. 5.; Sustainable development appraisal; Appraisal; Assessor; Electronic form. 6.; VAT declaration; Pre-application, repeated in full application; Applicant; Electronic form. 7.; Investment and eligibility check; Appraisal; Assessor; Electronic form. 8.; State Aid Assessment; Appraisal; State aid assessor; Electronic form. 9.; Application assessment form; Appraisal; Assessor; Electronic form. 10.; Project approval form; Upon project approval; Appraiser; Electronic form. 11.; Signed offer letter/funding agreement; Post appraisal and decision; Voucher Scheme Manager, also signed by client; Hard copy x 2, client keeps one copy and returns one signed to Council. 12.; Project Engagement Visit; First engagement with applicant after contracting; Voucher Scheme Manager or Engagement Officer; Face-to-face visit and team records. 13.; Voucher change request; As an when any changes are needed; Applicant; Electronic form. 14.; Claims; Quarterly; Applicant; Electronic form with supporting evidence, including invoices and bank defrayal, progress report & procurement. 15.; Asset register; At the end of each project; Applicant; Electronic form. 16.; Publicity evidence; Continuous; Applicant; Screenshots of website, facebook, business cards, flyers, posters etc. A; MHCLG Monitoring reports; Quarterly; Voucher Scheme Manager; Electronic. B; ERDF claims; Quarterly; Voucher Scheme Manager and finance assistance; Electronic. C; MHCLG data monitoring template (ESIF-Form-1-013); As and when requested by MHCLG (TBC); Voucher Scheme Manager; Electronic. ## Commitment to Collecting Required Output/Outcome Data The table below outlines the monitoring tools that will be used to collect data required for MHCLG’s Data Monitoring Template. Required SME Data; Data Collection Tool. Contact point within business; - Application form. Business sector (SIC); - Application form. Business start date (DD/MM/YY); 2. Application Form. Business trading age; 2. Application Form. FTE employees at time of receiving support; - Application form. Turnover for the last financial year prior to receiving support; 2. Application Form. Annual R&D spend in last complete financial year; 2. Application Form. Number of products and process innovations in last three financial years (No); 2. Application Form. Duration of Support; Not applicable to this project. Intensity of support (Grant/Loan £); 14. Voucher claim form. Intensity of support (Hours); Not applicable to this project. Adoption of new technologies (No); Not applicable to this project. New investment in capital equipment and facilities (£); 14. Voucher claim form. Unsuccessful applicants for support:. Company details (ref no/name, address, postcode); - Application form. Contact point within company (name, tel/email); 2. Application form. Business sector (SIC); 2. Application form. Business start date (DD/MM/YY); 2. Application Form. Business trading age (Years/Months); 2. Application Form.

2.5 Implementing the Summative Assessment (max 500 words) Please set out the practical steps involved in implementing the summative assessment. This should cover the following. - The assessment route: who will undertake the assessment and whether the assessment will be carried out internally or by external evaluators, explaining the rationale for this decision. If external support will be procured, this section should set out the process for procurement and ensure compliance with ERDF regulations. - Timescale and Outputs: delivery plan identifying key milestones and output dates. - Management and Quality Assurance plans.

## Who will undertake the Assessment The summative assessment will be undertaken by an external independent evaluators. Plans are made to procure the works through 3 Quotation framework as per ERDF procurement guidance for Contracting Authorities: works and services over 2,5K under 25K. The rationale for appointing external consultants is to ensure that the evaluation could be conducted from an independent perspective by consultants with expertise in summative assessments. The Council for the Isles of Scilly will follow its own (ESIF compliant) procurement policy and public procurement guidelines for appointing consultants by sending out an invitation to quote to at least 3 relevant suppliers to appoint a single organisation to undertake the project evaluation. The decision to award the contract will be based on a number of criteria including value for money. ## Timescale and Outputs Key milestones and outputs and for the completion of the summative assessment are shown in the table overleaf. The Evaluation is expected to take place between June & Dec 2021 and exact dates for the milestones will be adapted closer to the time. Activity; Dates; Outputs. Project Inception (face-to-face meeting); June; Inception note. Development of Monitoring & Evaluation framework; June – July; Monitoring and Evaluation Plan updating N.B. this will feed into ESIF-Form-1—012 which will be completed by the Voucher team. Drafting of topic guides for stakeholder, delivery team and beneficiary interviews; July; Set of data collection tools (to be signed off by client). Desk based review of: - Key documentation - Wider policy and economic context - Monitoring data; August; N/A. Individual interviews with Mainland stakeholders (by phone) to include: - C&IoS Growth Hub - Outset for Cornwall - Oxford Innovation (ref: grant writing support) - BIG 2 - MHCLG Case Officer; August; N/A. Beneficiary interviews (aiming to make contact with ALL Voucher Scheme recipients); September; N/A. Final review of outputs and spend; September; N/A. Fieldwork on the Island (to be undertaken across two consecutive days) to include: - Delivery team workshop - Individual interviews with stakeholders, primarily including reps from the Island Partnership, Island Futures, Smart Islands and the Tresco Estate - Business case studies; October; N/A. Analysis of all data including VFM and impact assessments; October; N/A. Report writing; November; N/A. Draft report produced; November; Draft report. Meeting to discuss report; November. Amendments made, final report produced and summative assessment template completed; w/b 10th Dec; Final evaluation report and summative assessment report summary (ESIF-Form-1-014). ## Management and Quality Assurance Plans The table below sets out the management and quality assurance plans for the summative assessment. Key Elements. Project Director; External: TBC. Project Manager; External: TBC. Management and oversight arrangements; Management: Milena Fallows Oversight: Nicola Stinson. Budget; £21,000 +VAT. Quality Assurance approach and procedures; The external evaluation team will quality assure the summative assessment by adopting the following processes: - Work conducted by experienced evaluators - Interview notes/analyses documents retained (anonymised) - Quality review/checks undertaken by experienced personnel - Client will have opportunity to review/comment on drafts.

| 2.6 Dissemination (max 500 words) Please set out how you propose to disseminate and share the findings from the summative assessment. |  |  |
| --- | --- | --- |
| I understand that, as a minimum, the full report needs to be shared with DCLG and the summative assessment summary findings template (ref. ESIF-Form-1-014) must be freely available. | - Yes ☐ | No ☐ |
| The table below sets out the plans for dissemination of summative evaluation report. Output. Managing Authority; - Full report & Executive Summary - ESIF-Form-1-014 ERDF. Council of the Isles of Scilly Strategic Partners; - Executive Summary - ESIF-Form-1-014 ERDF. Publication on Council of the Isles of Scilly website; - Executive Summary. Publication on other websites (e.g. Growth Hub); - Executive Summary. Press releases; - Text to be developed by the Voucher Scheme team with success stories. |