Brief Description of the works

- Brief of Works:

  - Inspection and repair of the existing equipment

  - The erection of all festive lighting

  - Testing of equipment once erected

  - Assistance at the official “Switch On” events (Kettering and Desborough).

  - Removal of all festive lighting and storage.

- Locations: (See scheme plans)

  - Kettering

  - Desborough

  - Rothwell

  - Broughton

- Dates:

  - Erection to be completed no later than:

    - Kettering	Wednesday 25th November 2020

    - Desborough	Thursday 26th November 2020

    - Rothwell	Thursday 3rd December 2020

    - Broughton	Friday 4th December 2020

  - Switch on (dates subject to change)

    - Kettering	Thursday 26th November 2020

    - Desborough	Friday 27th November 2020

    - Rothwell	Friday 4th December 2020

  - Switch off

    - No later than Monday 4th January 2021

  - Lighting Removal

    - No later than Sunday 17th January 2021

- Storage of Equipment:

  - All equipment to be collected, returned and stored neatly to:

Environmental Care Depot

Robinson Way

Telford Way Industrial Estate

Kettering

Northants

NN16 8PP

- Insurances:

  - To have a minimum of £10,000,000 in relation to damage made against any persons or property in respect to any one incident.

- Plant Machinery

  - All suitable equipment and plant to be supplied and insured by the contractor unless otherwise requested.

- Training Required:

  - Operates to provide any certification in relation to operation of plant machinery and electrical qualifications that are valid during the duration of the works.

- Site Visits

  - It is advised that contractors visit the site locations to familiarise themselves to the site constraints and understand the full nature of the works requested.

- Weather Proofing

  - The equipment will be installed in exposed conditions and is liable to be affected by severe weather. Therefore any fixings used to erect the equipment must be capable to safely support its weight and stresses during this period.

  - Every effort must be made to ensure the electrical equipment is weather proofed to prevent ingress of water or moisture.

- Traffic Control measures

  - No arrangements have been made to close any areas of the highway.

  - The contractor to ensure that all relevant signage and equipment is laid out in order to comply with the Highway Regulations and work to Traffic Signs Manual Chapter 8 (Part 2: Operations - Traffic Safety Measures and Signs for Road Works and Temporary Situations).

- Reporting

  - The contractor to make daily reports to confirm what works have been completed and feedback any notes of concern / consideration.

  - Faults, repairs or replacements should be reported immediately.

  - On completion of the works, a review to be undertaken to report any items of consideration or repair etc. for the following year.

  - Photographs of each installation must be provided on completion (where necessary clearly showing the lighting column number).

- Health and Safety

  - RAMS to be submitted prior to the commencement of work.

  - CPP – Contractor to submit Construction Phase Plan for approval prior to the commencement of works.

  - To follow Kettering Borough Council’s ‘Safe System of Work  Street Lighting’ reference SL/01/2019.

- Staff Resources

  - The contractor shall provide details of number of staff to be used for the works.

- Installation of Festive Lighting

  - Inspection

    - Prior to the installation, the contractor shall fully inspect the equipment and electrically test and replace any damaged components.

    - The catenary cables throughout the highway shall be inspected prior to the erection of the lights by a specialist third party contractor.

  - Fixing’s

    - Column Mounted Branch Lights

    - To be secured to the columns with 7mm black cable ties to the top and bottom of each stretch of lights.

    - Column Mounted Frames

    - To be secured with metal band strapping. (30mm Steel minimum) at a minimum of 2 points along the frame.

    - Curtain Lights (Building)

    - To be secured to the columns with 7mm x black cable ties every 300mm

    - Curtain Lights (Ceiling)

    - To be secured to the columns with 7mm x black cable ties every 300mm

    - Stringed Lights (including Canopy)

    - To be secured to the columns with 7mm black cable ties every 300mm.

    - Established Tree Lights

    - Where required, removal of the existing string lights to replace with new (supplied by KBC)

    - String lights to be secured to the tree branches with self-expanding tree ties.

    - Feature Tree

    - String lights to be wrapped around and draped along the entire height of the tree.

*All excess strappings and ties must be cut to prevent any excess ties being on show and clear any debris.

- Highway Restrictions

  - All equipment to be fitted in compliance with the Section 178 of the Highways Act 1980.

  - A minimum height of 5.5m clearance must be maintained over the highway.

  - No drilling into the lighting columns is permitted.

  - The use of ladders against lighting columns is not permitted.

- Switch on

  - Site attendance is required on both the Kettering and Desborough “Switch On” events.

  - The contractor maybe asked to assist with other electrical duties leading up to the event and on the day.

- Repair

  - The contractor shall be responsible for the repair and/or re-fixing of any equipment that becomes damaged/dislodged/loose during the period the lights are erected.

  - Any replacements items shall be like for like replacements unless otherwise agreed with Kettering Borough Council.

- Removal

  - Each item shall be carefully removed from the mounting and cleaned as necessary.

  - Cabling shall be wrapped and taped into coils.

  - Items to be stored in the suitable boxes at the Kettering Borough Council Depot.

  - Any items which are damaged and require repair or replacement shall be reported to Kettering Borough Council.

| PROJECT | Quotation Ref: QUMC153 Christmas Lights |
| --- | --- |
| ITEM | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |
|  |  |  |  |  | £ | p |
| 1 | Light Testing Test the existing lights prior to erection | Item | 1 |  |  |  |
| 2 | Light Installation All lighting connections are via a 240V 16Amp 3pin Commando power supply. Kettering Branch Lights Decorative Frames Curtain Lights (building) Stringed Lights (Canopy Inc. icicles) Established Tree Lights Feature Tree Ceiling of Lights - To cover a stretch 200m allowing for flexibility (not be a total length of 200m) and being 6m in width. Lights to be white flashing LED’s. Desborough Branch Lights Decorative Frames Feature Tree Rothwell Established Tree Lights Feature Tree Broughton Established Tree Lights | no no no no no no no no no no no no no | 21 31 8 (drops) 5 9 1 1 (200m) 16 1 1 17 1 4 |  |  |  |
| 3 | Testing Test the lights once erected | Item | 1 |  |  |  |
| 4 | Switch on Set timers 4:00pm - 11:00pm unless otherwise instructed by Kettering Borough Council. Assist with switch on and other associated works. | Item Item | 1 1 |  |  |  |
| ITEM | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |
|  |  |  |  |  | £ | p |
| 5 | Lighting Removal Removal of all erected lights and reporting of any damaged lighting. |  |  |  |  |  |
| 6 | Plant required: (list to provide costings and duration of hire etc.) |  |  |  |  |  |
| Additional Information (do not include within the total cost) | Day Rate: Estimated number of days to erect Daily Rate per member of staff Daily Rate of Plant and Equipment |  |  |  |  |  |
| TOTAL COST £ |  |  |

Deadlines/Switch on Dates:

Kettering 	- Thursday 26th November 2020

Desborough 	- Friday 27th November 2020

Rothwell 	- Friday 4th December 2020

Signed:	_________________________

Name:		_________________________

Company: 	_________________________

Position:	_________________________

Tel:		_________________________

Date: 		_____/_____/_____