Invitation to Tender

for

Corporate Natural Capital Account Project for Forest Enterprise England and the Public Forest Estate

Contract No:CNCA15

# Introduction

The Forestry Commission’s (FC) mission is to protect and expand Britain's forests and woodlands and increase their value to society and the environment.

We take the lead in the development and promotion of sustainable forest management.  We deliver the distinct forestry policies of England and Scotland through specific objectives drawn from the country forestry strategies.

We the FC will always consider equality when conducting our procurement activities.  We require you to meet your duties under the Equality Act 2010 and may ask for evidence that you are aware of and operate in accordance with those requirements.

More information is available on our website at www.forestry.gov.uk

# Specification of Requirements

We will be awarding a contract for the development of a Corporate Natural Capital Account (CNCA) for FEE that enables us to:

- provide evidence to the public, stakeholders and government as to how well we are achieving our FEE mission of delivering benefits to people, nature and the economy through our management of the Public Forest Estate (PFE); and

- make strategic and business decisions about the future management and development of FEE and the PFE.

Specific objectives are to provide a CNCA that:

- establishes a natural capital asset register for the PFE;

- provides a natural capital balance sheet for FEE;

- provides a statement of changes in net natural assets over a recent time period;

- is consistent with the emerging guidance from the Natural Capital Committee and that therefore has validity with an audience of government, stakeholders and other organisations;

- can be replicated every year by FEE staff to allow future statements of changes in net natural assets.

The main deliverables for this project are in January 2016 and March 2016 (roughly 6 months) however our intention is to award this contract for a period of 9 months to allow for any follow up or clarification of the outputs required.

The total value of this contract over the entire period will be in the region of £40,000 including all expenses and disbursements, but excluding VAT. We require fixed price tenders to be submitted.

## Background Information About Forest Enterprise England

Forest Enterprise England (FEE) is the department of the Forestry Commission (FC) that manages England’s government owned forests (the public forest estate or PFE). Our business is wholly related to the management of the PFE  in England (i.e. not relating to forestry in Scotland or Wales).

FEE is tasked with delivering benefits to people, nature and the economy from our management of the PFE, and we do this through providing public access, through managing the land to deliver environmental benefit and through supporting the rural economy. Our management balances these three different goals in different ways in different locations, i.e. in some places environmental management is given priority, in others economic activity, and in others public use. In most geographic locations all three goals are jointly achieved, but in varying intensity.

### Woodland Type

The PFE is 254,000ha of land located across England, and it is predominantly wooded in character. The PFE includes:

- Plantation woodland;

- Native woodland;

- Non-intervention woodland;

- Wood pasture;

- Open habitats (heathland, fens, mountain tops, mire); and

- Agricultural land (pasture and arable).

### Forest Location & Usage

Some of our forests are ‘community forests’ or other forests that are very close to substantial urban populations and have high numbers of visitors. The rest (majority by geographic area) of our forests are in rural locations with some areas of high visitor use concentrated around provided car parking or at visitor centres / hubs, and much dispersed visitor use throughout the forest. The majority of our land is open access, and those using the PFE can enter it through multiple unmonitored access points. We do not know how many people visit the PFE, although we estimate there may be over 40m day visits per annum.

### Land Designations & Environmental Benefit

- All our woodlands are managed to the UK Woodland Assurance Standard (the gold standard for woodland management);

- We have active programmes to manage different types of habitat; for example development of more open habitat and restoration of plantations on ancient woodland.

- A large % of land is covered by designations (e.g. SAC / SSSI / National Park), in many cases these overlap with each other (detailed information can be provided on this).

Our environmental benefit is delivered through managing this variety of habitats to high environmental and social standards, e.g. more than 99% of our SSSIs are in favourable or unfavourable recovering condition (a higher % than other land management organisations of a similar scale like Woodland Trust, Wildlife Trust, Natural England.).

### Economic Benefit

Our economic benefit is delivered through the contribution we make to the rural (predominantly leisure) economy with over 600 micro and SME businesses operating on the PFE, and the contribution we make to the timber business by selling the majority of English grown timber –in 2014/15 1.4m of the total 2.6m green tonnes of hard and softwood that was brought to market from English woodland came from the PFE. We do not process our own timber, and do not directly run the leisure businesses (shops, cafes, bike hire, tourist activities) that operate on the estate. We grant leases to others to extract resources from our land, for example stone through quarrying, we do not undertake any of these activities ourselves.

### FEE’s Engagement To Date in Natural Capital Accounting

FEE, and the wider FC, have been interested in and informed from the beginning about the Natural Capital Committee’s (NCC) work on Corporate Natural Capital Accounting (CNCA) and is a member of the Natural Capital Coalition.

The FC’s Lead Economist, based in the FC’s corporate and forestry support team, has engaged widely on natural capital across Government, the private sector and NGOs. He has been involved in analysis to support the recent publication of the Natural Capital Committee’s Final Report.

Senior staff in FEE have met with some of the pilot organisations to discuss their engagement in the CNCA pilots.  We have started to think about the possible scope of our CNCA using the template provided in the NCA Guidelines on CNCA , and attach our very initial thinking on this as Appendix A.

We are also interested in contributing our development of CNCA to other NCA initiatives including that being led by NCC on behalf of government, and the Natural Capital Coalition’s work on developing processes that work for a broader range of organisations. We look forward to being able to share both outcomes and practice from our own development of CNCA with external parties from government, commercial partners, 3rd sector and the general public.

### FEE Data Resources

The FC and FE have substantial data resources which will provide an essential resource for this work. Please see Appendix B for a list of the information that we are able to provide.

## Proposed FEE CNCA Work

### Objective

Our overarching aims for this project are to deliver a corporate natural capital account for FEE that enables us to:

- provide evidence to the public, stakeholders and government as to how well we are achieving our FEE mission of delivering benefits to people, nature and the economy through our management of the PFE; and

- make strategic and business decisions about the future management and development of FEE and the PFE.

Specific objectives are to provide a CNCA that:

- establishes a natural capital asset register for the PFE;

- provides a natural capital balance sheet for FEE;

- provides a statement of changes in net natural assets over a recent time period;

- is consistent with the emerging guidance from the Natural Capital Committee and that therefore have validity with an audience of government, stakeholders and other organisations;

- can be replicated every  year by FEE staff to allow future statements of changes in net natural assets.

### Scope of proposed work

- The geographic scope of the work is intended to be all of the PFE.

- The impacts of as many ecosystem services as are material and quantifiable are to be included.

NB: FEE has identified a ‘starter for 10’ assessment of the ecosystem services that are reflected in the financial account and might be identifiable in a natural capital account. See Appendix A. We anticipate the appointed consultants using this as the basis for identifying which ecosystem services it is material and feasible to include in a CNCA, and we hope that the consultant will be able to expand the areas we have identified as quantifiable/valuable.

### Project Outputs

- A CNCA’s as described in the objective above;

- Electronic versions of the draft and final reports, written in a clear and accessible style.  These should identify any data weaknesses that constrain a full expression of CNCA for FEE, and set out specific steps that future work could take to remedy these weaknesses. (Please note: FEE sees this work as the first step, and we expect to commission additional work in future to strengthen the initial CNCA. However there is no guarantee of future work associated with this project and our normal procurement processes will apply for any future commissioning);

- Consultant attendance at a meeting with senior staff to introduce and test the draft CNCA, including a discussion of the risks and opportunities that the work introduces. The timing of this meeting at point of draft output is to allow any risks to be addressed and feedback received at this meeting to inform the final CNCA;

- Engagement with and understanding of the CNCA methodology among relevant FEE/FC staff in order to facilitate replication of the work within FEE/FC  in future years. This will require the consultants to work closely with the FEE/FC staff, including delivering an effective handover. (For clarity we are not asking that a specific training programme is put in place, rather that the work is done with FEE staff fully aware and understanding the process.) Consultants are asked to identify what method they will use to ensure that their handover is effective ( e.g. written guidance), and what level of support they will offer to team members if that handover subsequently proves incomplete and queries emerge from the team in the following year’s exercise.

  IPR of the model used to generate the CNCA must be owned and replicable by the FC/FEE to provide the basis for future replication of the CNCA.

### Methodology

- Section 4.8 asks you to detail your proposed methodology with reference to this specification of requirements.

- The methodology must be suitable for a land management organisation like FEE (i.e. rather than supply chain management).

- The methodology must outline what approach (and why this is theoretically sound) is proposed to use economic valuation data. This aspect of the work must be driven by the practical need for usable outputs, but must also be credible to key audiences including government economists and stakeholders.

- As stated in the section on Scope, the priority in this first CNCA exercise is to deliver a CNCA for the whole PFE, and we are looking for an approach that will deliver this. We would also like consultants to explain whether they see potential within this project for additional analysis at a more local level.

### FEE Inputs

- FEE will oversee the work through a lead contact, supported by a Project Team. The lead contact and members of the Project team will be available to provide information and inputs to the consultants during the work. All contacts and requests for information from FEE will be made through a single point of contact to allow for coordination of requests and returns.

- The Project Team will include Pat Snowdon, FC Lead Economist; Miranda Winram FEE Head of Strategy and Insight; FEE/FC Finance representative; Operational Staff representative(s); Peter Burnett FC GIS manager. The expertise of Jonathan Spencer FEE Head of Planning and Environment and other staff members will be drawn on as appropriate. Simon Hodgson, FEE Chief Executive will retain a close interest in the project, and will Chair any wider meetings (e.g. if any are proposed to test emerging outputs) and may attend some team meetings.

- FEE’s head office is in Bristol (BS16 1EJ: 20minutes walk from Bristol Parkway station) and most team members are based there. Where meetings need to be in person, the location should be assumed to be Bristol. Telephone conferences are widely used within FEE as part of business as usual.

- FEE/FC will want to sign off their satisfaction with the validity of data used and approach employed at relevant points during the project.

- FEE will make available data it has for the work, and will retain any IPR over that data. This includes comprehensive Geographic Information System (GIS) data, and support from Corporate Forestry Service (CFS) economists & Inventory Forecasting and Operational Support (IFOS) staff in providing economic and National Forest Inventory (NFI) data. See Appendix B for a summary of the information we have available.

### Consultancy Team

- A range of skills are required, and Section 4.8 asks you to detail your proposed  team and its technical and professional experience and ability with reference to this specification of requirements.

- FEE is open to tender submissions from a sole contractor or from a lead contractor supported by other identified resource/specialists. For the various requirements attaching to the type of bidding model you propose please see Section 4.1 of this document.

- Tenders must include details of the company’s relevant experience and brief biographies of the team members proposed. They must also include an indication of the level of certainty that the individuals detailed will work on this project;

### Project Timescale

- We aim to use outputs from the project in the 2015-16 Annual Report and Accounts. This requires a draft CNCA output to be available by Jan 6th 2016. The final CNCA must be completed and signed off by FEE by the end of March 2016.

- Tenders should include detail of the timescales proposed for undertaking the work, including clear timescales for each stage of the methodology and any assumptions on response times (including provision of data) from FEE/FC as the client.

### Criteria for Tender Award

The scoring criteria are detailed in the relevant later sections of this document, but for rapid reference they are:

- The team’s technical and professional expertise/ experience - 40%

- The methodology/approach to the work - 40%

- Cost of work – 20%

Note: Tenderers must include details in their bid of any areas where they will not be able to comply with these requirements.  If your Tender does not meet these requirements we reserve the right to reject it completely.

# Notes for Completion and Conditions

## Definitions and purpose

The “authority” or “we” means the Forestry Commission, or anyone acting on behalf of the Forestry Commission, that is seeking to invite suitable Suppliers to participate in this procurement process.

“You”/”Your” or “Supplier” or “Bidder” means the body responding to this Invitation to Tender (ITT) i.e. the legal entity submitting a tender.  The ‘Supplier’ or ‘Bidder’ is intended to cover any economic operator as defined by the Public Contracts Regulations 2015 and could be a registered company; charitable organisation; Voluntary Community and Social Enterprise (VCSE); Special Purpose Vehicle; or other form of entity.

This Invitation to Tender (ITT) has been designed to assess both the suitability of a Supplier to deliver the authority’s contract requirement(s); and to determine of those suitable, which supplier(s) have provided the most economically advantageous tender.

## Timetable

Set out below is the procurement timetable.  While we do not intend to depart from the timetable, we reserve the right to do so and if this is required, we will inform Suppliers in writing of any changes.

| Stages | Dates |
| --- | --- |
| Closing date for submitting questions or queries | 1pm on Monday 24th August 2015 |
| Closing Date and Time for Tender Returns | 1pm on Tuesday 1st September 2015 |
| Possible tender clarification interview date (Tender clarification interviews may or may not be undertaken prior to the award of the contract at our discretion. Bidders are asked to make sure they can attend a meeting on either of these dates if required. Bidders will be invited to attend the interview by Friday 4th September.) | Tuesday 8th or Tuesday 15th September 2015 |
| Expected Notification of Tender | Friday 10th or Wed 15th September 2015 |
| Project Initiation Meeting NB: If selected as the successful contractor bidders are asked to make sure they can attend a meeting in Bristol on this date. | 3pm Thursday 24th September 2015 (Bristol) |

## Enquiries

Please send all enquiries by email, by the deadline stated at Section 3.2 quoting the reference number printed at the front of this document to:

Miranda Winram

Email: miranda.winram@forestry.gsi.gov.uk

If we consider any question or request for clarification is relevant to all interested parties, we will circulate both the query and the response to all prospective bidders, although your identity will remain confidential.

If you want to tender, and have not yet registered interest in the contract, you must do so before the closing date for expressing interest to make sure you are told about any questions and answers.

## Responses and supporting documents

Please ensure that all questions are completed in full, and in the format requested.  Failure to do so may result in your submission being disqualified.  If the question does not apply to you, please state clearly ‘N/A’.

Should you need to provide additional Appendices in response to the questions, these should be numbered clearly and listed as part of you declaration.  A template for providing additional information is provided at the end of this document, which should be used unless, due to formatting, this is not possible.

To make the process straightforward, you do not need to provide supporting documents with your tender unless specifically requested to do so.  However, we may ask you for this later.

Your organisation will only be evaluated based on the information in your tender.  If you do not mention any applicable previous experience of working with us in your reply we cannot take this into account.

Please do not send any information that is general company or promotional literature, as this will not form part of our evaluation. Any additional documents you provide must refer to a question within the ITT and be easily identifiable as the answer.

## Return arrangements

Please return your completed tender submission inclusive of any relevant appendices as:

- One copy on disk or USB type storage device in a read only format;

and

- One paper copy.

Please note that we do not accept fax or email copies because they can be opened before the deadline and this compromises the integrity of the tender.  We must receive your completed tender before the closing date and time shown in the Timetable at section 3.2.  We will keep tenders received before this deadline unopened until after this time.  We reserve the right to not consider any tenders received after the deadline.  Please be aware that tenders may be copied for our use.

Mark your envelopes with the words ‘Tender for Corporate Natural Capital Account Project for Forest Enterprise England and the Public Forest Estate CNCA15 - Not to be opened until 1pm Tues 1st Sept’.

Submissions may be excluded if you do not mark the envelope in this way.

Send completed tender documents to the following address:

Miranda Winram, Forestry Commission, 620 Bristol Business Park, Coldharbour Lane, BS16 1EJ

Any tender returns submitted via any other method will not be considered and we reserve the right not to consider any tenders received after the deadline.  Please be aware that tenders may be copied for our use.

## Clarification

During our evaluation process, we may need to seek clarification on aspects of your tender return.  If required we will contact you using the contact details you have provided.  Clarification may require you to submit, supplement, clarify or complete the relevant information or documentation within an appropriate time limit.  The purpose of any such clarification is to provide us with the information we require to score your submission; it will not be an opportunity for you to improve or substantially change the information you have already submitted.

## Verification of information provided

Whilst reserving the right to request information at any time throughout the procurement process, the authority may enable the Supplier to self-certify that there are no mandatory/discretionary grounds for excluding their organisation.  When requesting evidence that the Supplier can meet the specified requirements (such as the questions within the sub-sections of 4.7 of this ITT relating to Technical and Professional Ability) the authority may only obtain such evidence after the final tender evaluation decision i.e. from the winning Supplier only.

## Sub-contracting arrangements

Where the supplier proposes to use one or more sub-contractors to deliver some or all of the requirements, a separate Appendix should be used to provide details of the proposed bidding model that includes members of the supply chain, the percentage of work being delivered by each sub-contractor and the key deliverables each sub-contractor will be responsible for.

The authority recognises that arrangements in relation to sub-contracting may be subject to future change, and may not be finalised until a later date.  However Suppliers should be aware that where information provided to the authority indicates that sub-contractors are to play a significant role in delivering key requirements, any changes to those sub-contracting arrangements may affect the ability of the Supplier to proceed with the procurement process or to provide the supplies and/or services required.  Suppliers should therefore notify the authority immediately of any change in the proposed sub-contractor arrangements.  The authority reserves the right to deselect the Supplier prior to any award, based on an assessment of the updated information.

## Consortia arrangements

If the Supplier completing this ITT is doing so as part of a proposed consortium, the following information must be provided:-

- Names of all consortium members;

- The lead member of the consortium who will be contractually responsible for delivery of the contract (if a separate legal entity is not being created); and

- If the consortium is not proposing to form a legal entity, full details of proposed arrangements within a separate Appendix.

Please note that the authority may require the consortium to assume a specific legal form if awarded the work, to the extent that a specific legal form is deemed by the authority as being necessary for the satisfactory performance of the contract.

All members of the consortium will be required to provide the information required in all sections of the ITT as part of a single composite response to the authority i.e. each member of the consortium is required to complete the form.

Where you are proposing to create a separate legal entity, such as a Special Purpose Vehicle (SPV), you should provide details of the actual or proposed percentage shareholding of the constituent members within the new legal entity in a separate Appendix.

The authority recognises that arrangements in relation to a consortium bid may be subject to future change.  Suppliers should therefore respond on the basis of the arrangements as currently envisaged.  Suppliers are reminded that the authority must be immediately notified of any changes, or proposed changes, in relation to the bidding model so that a further assessment can be carried out by applying the selection criteria to the new information provided.  The authority reserves the right to deselect the Supplier prior to any award of contract, based on an assessment of the updated information.

## Confidentiality

When providing details of contracts in answering section 4.6 of this ITT (Technical and Professional Ability), the Supplier agrees to waive any contractual or other confidentiality rights and obligations associated with these contracts.

The authority reserves the right to contact the named customer contact in section 4.6 regarding the contracts included in section 4.6.  The named customer contact does not owe the authority any duty of care or have any legal liability, except for any deceitful or maliciously false statements of fact.

The authority confirms that it will keep confidential and will not disclose to any third parties any information obtained from a named customer contact, other than to the Cabinet Office and/or contracting authorities defined by the Public Contracts Regulations.

The Supplier must treat all information supplied to it by the authority in confidence and must not disclose it to third parties other than to obtain sureties or quotations for submitting its response.

As part of the tendering process, the Supplier must identify any parts of its tender submission which it designates as confidential and would not want published; such information may include technical or trade secrets or other confidential information.  The authority will then assess this information (along with the rest of the contract), taking account of Regulation 21 of the Public Contracts Regulations, when considering which contractual information should or should not be published or released on request.

## Tender validity

All details of the tender, including prices and rates, must be valid for 90 days from receipt of tender.

## Language

The completed tender and all accompanying documents must be in English.

## Applicable Law

Any contract concluded as a result of this ITT will be governed by English law.

## Pricing

Our maximum budget for this work is £40,000 exclusive of VAT but including all expenses and any disbursements.

All prices will be in sterling and exclusive of VAT.

Consultants are asked to submit fixed fee proposals for the work.

The fee proposed must take into account any likely additional costs that could reasonably be foreseen as part of the project, e.g. if there are any data requirements or software licences that FEE or the consultant may not have in house.

## Additional costs

Once we have awarded the contract we will not pay any additional costs incurred which are not reflected in your tender submission.

## Evaluation

A Tender Panel will evaluate responses to the tender objectively using the criteria and evaluation matrix’ defined within Section 4.

## Gateways

Some questions in the tender are known as gateways and are fundamental requirements of the contract. These are marked on a ‘pass/fail’ basis and if you do not answer these sections appropriately, we may reject your submission in full and cease to evaluate any more questions.

## Weighted questions

Some sections of this ITT include questions that are weighted.  The weightings applied to each question ensure the relative importance of each is correctly reflected in the overall scores applied.

For these questions, the marks out of 4 that are achieved for each question will be subsequently weighted to provide a total number of marks out of 100.

## Award

Once we have carried out the evaluation and identified the successful tenderer(s), we will tell all tenderers in writing by email of our ’award decision’.

### Debriefing

We will give all bidders the opportunity of a debriefing.  Please tell us in writing as soon as possible if you want a debriefing.

## Contract management

If we award a contract you will have to co-operate in managing it and comply with the contract management requirements, as detailed in the Specification of Requirements at Section 2.

## Costs

Unless otherwise stated in this ITT, all costs associated with taking part in this process remain your responsibility and we will not return any part of your completed tender to you.

## Right to cancel or vary the process

We reserve the right to cancel or withdraw from the tendering process at any stage.

## Inducements

Offering an inducement of any kind in relation to obtaining this or any other contract with us will disqualify you from being considered and may constitute a criminal offence.

## Disclaimer

While the information in this ITT and supporting documents has been prepared in good faith by us, it may not be comprehensive nor has it been independently verified.

Neither the FC, nor their advisors, nor their respective directors, officers, members, partners, employees, other staff or agents:

- makes any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of this ITT; or

- accepts any responsibility for the information contained in the ITT or for the fairness, accuracy or completeness of that information nor shall any of them be liable for any loss or damage (other than in respect of fraudulent misrepresentation) arising as a result of relying on such information or any subsequent communication.

# Your response

In order to submit a tender for this requirement you must complete and return the relevant sections, detailed in the table below, in compliance with Section 3 above.  If we have decided that certain sections are not relevant for this particular ITT, we have indicated this by stating ‘N/A’ next to the title heading at the relevant section and by indicating ‘Not Applicable’ within the table below.  Unless otherwise indicated in this way, all sections must be completed and returned.

The table below provides a summary of the evaluation method for each section, however full details of how we will evaluate your submission can be found in the individual Evaluation Matrix’ within each section.

| Section | Title | Evaluation Method |
| --- | --- | --- |
| 4.1 | Supplier Information | For information only but must be completed |
| 4.2 | Grounds for mandatory exclusion | Pass / Fail |
| 4.3 | Grounds for discretionary exclusion – Part 1 | Pass / Fail |
| 4.4 | Grounds for discretionary exclusion – Part 2 | Not Applicable |
| Selection Criteria |  |  |
| 4.5 | Economic and Financial Standing | Not Applicable |
| 4.6 | Technical and Professional Ability | Pass / Fail |
| 4.7 | Additional Selection Modules |  |
| 4.7.1 | Project Specific Questions to assess Technical and Professional Ability | Not Applicable |
| 4.7.2 | Insurance | Not Applicable |
| 4.7.3 | Compliance with equality legislation | Not Applicable |
| 4.7.4 | Environmental Management | Not Applicable |
| 4.7.5 | Health and Safety | Not Applicable |
| Award Criteria |  |  |
| 4.8 | Requirement Specific Questions | Scored and Weighted |
| 4.9 | Pricing Schedule | Scored and Weighted |
| 4.10 | ITT Appendices | Instructions for format |
| 4.11 | Terms and Conditions of Contract | Pass/Fail |
| 4.12 | Declaration | Pass/Fail |

## Supplier Information

| Supplier details |  | Answer |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Full name of the Supplier completing the ITT |  |  |  |  |  |
| Registered company address |  |  |  |  |  |
| Registered company number |  |  |  |  |  |
| Registered charity number |  |  |  |  |  |
| Registered VAT number |  |  |  |  |  |
| Name of immediate parent company |  |  |  |  |  |
| Name of ultimate parent company |  |  |  |  |  |
| Please mark ‘X’ in the relevant box to indicate your trading status |  | i) a public limited company |  |  |  |
|  |  | ii) a limited company |  |  |  |
|  |  | iii) a limited liability partnership |  |  |  |
|  |  | iv) other partnership |  |  |  |
|  |  | v) sole trader |  |  |  |
|  |  | vi) other (please specify) |  |  |  |
| Please mark ‘X’ in the relevant boxes to indicate whether any of the following classifications apply to you |  | i)Voluntary, Community and Social Enterprise (VCSE) |  |  |  |
|  |  | ii) Small or Medium Enterprise (SME) |  |  |  |
|  |  | iii) Sheltered workshop |  |  |  |
|  |  | iv) Public service mutual |  |  |  |
| Bidding model Please mark ‘X’ in the relevant box to indicate whether you are: |  |  |  |  |  |
| a) Bidding as a Prime Contractor and will deliver 100% of the key contract deliverables yourself |  |  |  |  |  |
| b) Bidding as a Prime Contractor and will use third parties to deliver some of the services If yes, please provide details of your proposed bidding model that includes members of the supply chain, the percentage of work being delivered by each sub-contractor and the key contract deliverables each sub-contractor will be responsible for. |  |  |  |  |  |
| c) Bidding as Prime Contractor but will operate as a Managing Agent and will use third parties to deliver all of the services If yes, please provide details of your proposed bidding model that includes members of the supply chain, the percentage of work being delivered by each sub-contractor and the key contract deliverables each sub-contractor will be responsible for. |  |  |  |  |  |
| d) Bidding as a consortium but not proposing to create a new legal entity. If yes, please include details of your consortium in the next column and use a separate Appendix to explain the alternative arrangements i.e. why a new legal entity is not being created. Please note that the authority may require the consortium to assume a specific legal form if awarded the contract to the extent that it is necessary for the satisfactory performance of the contract. |  |  | Consortium members: Lead member: |  |  |
| e) Bidding as a consortium and intend to create a Special Purpose Vehicle (SPV). If yes, please include details of your consortium, current lead member and intended SPV in the next column and provide full details of the bidding model using a separate Appendix. |  |  | Consortium members: Current lead member: Name of Special Purpose Vehicle: |  |  |
| Contact details |  |  |  |  |  |
| Supplier contact details for enquiries about this ITT |  |  |  |  |  |
| Name |  |  |  |  |  |
| Postal address |  |  |  |  |  |
| Country |  |  |  |  |  |
| Phone |  |  |  |  |  |
| Mobile |  |  |  |  |  |
| E-mail |  |  |  |  |  |

| Licensing and registration (please delete the option which doesn’t apply) |  |
| --- | --- |
| Registration with a professional body If applicable, is your business registered with the appropriate trade or professional register(s) in the EU member state where it is established (as set out in Annex XI of directive 2014/24/EU) under the conditions laid down by that member state). | Yes / No If Yes, please provide the registration number in this box. |
| Is it a legal requirement in the state where you are established for you to be licensed or a member of a relevant organisation in order to provide the requirement in this procurement? | Yes / No If Yes, please provide additional details within this box of what is required and confirmation that you have complied with this. |

## Grounds for mandatory exclusion

You will be excluded from the procurement process if there is evidence of convictions relating to specific criminal offences including, but not limited to, bribery, corruption, conspiracy, terrorism, fraud and money laundering, or if you have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security obligations (except where this is disproportionate e.g. only minor amounts involved).

If you have answered “yes” to question 4.2.2 on the non-payment of taxes or social security contributions, and have not paid or entered into a binding arrangement to pay the full amount, you may still avoid exclusion if only minor tax or social security contributions are unpaid or if you have not yet had time to fulfil your obligations since learning of the exact amount due.  If your organisation is in that position please provide details using a separate Appendix. You may contact the authority for advice before completing this form.

| 4.2.1 Within the past five years, has your organisation (or any member of your proposed consortium, if applicable), Directors or partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? | Please indicate your answer by marking ‘X’ in the relevant box. |  |
| --- | --- | --- |
|  | Yes | No |
| - conspiracy within the meaning of section 1 or 1A of the Criminal Law Act 1977 or article 9 or 9A of the Criminal Attempts and Conspiracy (Northern Ireland) Order 1983 where that conspiracy relates to participation in a criminal organisation as defined in Article 2 of Council Framework Decision 2008/841/JHA on the fight against organised crime; |  |  |
| - corruption within the meaning of section 1(2) of the Public Bodies Corrupt Practices Act 1889 or section 1 of the Prevention of Corruption Act 1906; |  |  |
| - the common law offence of bribery; |  |  |
| - bribery within the meaning of sections 1, 2 or 6 of the Bribery Act 2010; or section 113 of the Representation of the People Act 1983; |  |  |
| - any of the following offences, where the offence relates to fraud affecting the European Communities’ financial interests as defined by Article 1 of the Convention on the protection of the financial interests of the European Communities: |  |  |
| (i) the offence of cheating the Revenue; |  |  |
| (ii) the offence of conspiracy to defraud; |  |  |
| (iii) fraud or theft within the meaning of the Theft Act 1968, the Theft Act (Northern Ireland) 1969, the Theft Act 1978 or the Theft (Northern Ireland) Order 1978; |  |  |
| (iv) fraudulent trading within the meaning of section 458 of the Companies Act 1985, article 451 of the Companies (Northern Ireland) Order 1986 or section 993 of the Companies Act 2006; |  |  |
| (v) fraudulent evasion within the meaning of section 170 of the Customs and Excise Management Act 1979 or section 72 of the Value Added Tax Act 1994; |  |  |
| (vi) an offence in connection with taxation in the European Union within the meaning of section 71 of the Criminal Justice Act 1993; |  |  |
| (vii) destroying, defacing or concealing of documents or procuring the execution of a valuable security within the meaning of section 20 of the Theft Act 1968 or section 19 of the Theft Act (Northern Ireland) 1969; |  |  |
| (viii) fraud within the meaning of section 2, 3 or 4 of the Fraud Act 2006; or |  |  |
| (ix) the possession of articles for use in frauds within the meaning of section 6 of the Fraud Act 2006, or the making, adapting, supplying or offering to supply articles for use in frauds within the meaning of section 7 of that Act; |  |  |
| - any offence listed— |  |  |
| (i) in section 41 of the Counter Terrorism Act 2008; or |  |  |
| (ii) in Schedule 2 to that Act where the court has determined that there is a terrorist connection; |  |  |
| - any offence under sections 44 to 46 of the Serious Crime Act 2007 which relates to an offence covered by subparagraph (f); |  |  |
| - money laundering within the meaning of sections 340(11) and 415 of the Proceeds of Crime Act 2002; |  |  |
| - an offence in connection with the proceeds of criminal conduct within the meaning of section 93A, 93B or 93C of the Criminal Justice Act 1988 or article 45, 46 or 47 of the Proceeds of Crime (Northern Ireland) Order 1996; |  |  |
| - an offence under section 4 of the Asylum and Immigration (Treatment of Claimants etc.) Act 2004; |  |  |
| - an offence under section 59A of the Sexual Offences Act 2003; |  |  |
| - an offence under section 71 of the Coroners and Justice Act 2009 |  |  |
| - an offence in connection with the proceeds of drug trafficking within the meaning of section 49, 50 or 51 of the Drug Trafficking Act 1994; or |  |  |
| - any other offence within the meaning of Article 57(1) of the Public Contracts Directive— |  |  |
| (i) as defined by the law of any jurisdiction outside England and Wales and Northern Ireland; or |  |  |
| (ii) created, after the day on which these Regulations were made, in the law of England and Wales or Northern Ireland. |  |  |
| Non-payment of taxes 4.2.2 Has it been established by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which your organisation is established (if outside the UK), that your organisation is in breach of obligations related to the payment of tax or social security contributions? If you have answered Yes to this question, please use a separate Appendix to provide further details. Please also use this Appendix to confirm whether you have paid, or have entered into a binding arrangement with a view to paying, including, where applicable, any accrued interest and/or fines? |  |  |

## Grounds for discretionary exclusion – Part 1

The authority may exclude any Supplier who answers ‘Yes’ in any of the following situations set out in paragraphs (a) to (i);

| 4.3.1 Within the past three years, please indicate if any of the following situations have applied, or currently apply, to your organisation. | Please indicate your answer by marking ‘X’ in the relevant box. |  |
| --- | --- | --- |
|  | Yes | No |
| - your organisation has violated applicable obligations referred to in regulation 56 (2) of the Public Contracts Regulations 2015 in the fields of environmental, social and labour law established by EU law, national law, collective agreements or by the international environmental, social and labour law provisions listed in Annex X to the Public Contracts Directive as amended from time to time; |  |  |
| - your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - *your organisation has a conflict of interest within the meaning of regulation 24 of the Public Contracts Regulations 2015 that cannot be effectively remedied by other, less intrusive, measures; |  |  |
| - the prior involvement of your organisation in the preparation of the procurement procedure has resulted in a distortion of competition, as referred to in regulation 41, that cannot be remedied by other, less intrusive, measures; |  |  |
| - **your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions; |  |  |
| - Your organisation – - has been guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria; or - has withheld such information or is not able to submit supporting documents required under regulation 59 of the Public Contracts Regulations 2015; or |  |  |
| - your organisation has undertaken to |  |  |
| (aa) unduly influence the decision-making process of the contracting authority, or |  |  |
| (bb) obtain confidential information that may confer upon your organisation undue advantages in the procurement procedure; or |  |  |
| - your organisation has negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award. |  |  |

* Conflicts of interest

In accordance with question 4.3.1 (e), the authority may exclude the Supplier if there is a conflict of interest which cannot be effectively remedied. The concept of a conflict of interest includes any situation where relevant staff members have, directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure.

Where there is any indication that a conflict of interest exists or may arise then it is the responsibility of the Supplier to inform the authority, detailing the conflict in a separate Appendix. Provided that it has been carried out in a transparent manner, routine pre-market engagement carried out by the authority should not represent a conflict of interest for the Supplier.

** Taking Account of Bidders’ Past Performance

In accordance with question (g), the authority may assess the past performance of a Supplier (through a Certificate of Performance provided by a Customer or other means of evidence). The authority may take into account any failure to discharge obligations under the previous principal relevant contracts of the Supplier completing this ITT. The authority may also assess whether specified minimum standards for reliability for such contracts are met.

In addition, the authority may re-assess reliability based on past performance at key stages in the procurement process (i.e. Supplier selection, tender evaluation, contract award stage etc.). Suppliers may also be asked to update the evidence they provide in this section to reflect more recent performance on new or existing contracts (or to confirm that nothing has changed).

‘Self-cleaning’

Any Supplier that answers ‘Yes’ to questions 4.2.1, 4.2.2 and 4.3.1 should provide sufficient evidence, in a separate Appendix, that provides a summary of the circumstances and any remedial action that has taken place subsequently and effectively “self cleans” the situation referred to in that question. The Supplier has to demonstrate it has taken such remedial action, to the satisfaction of the authority in each case.

If such evidence is considered by the authority (whose decision will be final) as sufficient, the economic operator concerned shall be allowed to continue in the procurement process.

In order for the evidence referred to above to be sufficient, the Supplier shall, as a minimum, prove that it has;

- paid or undertaken to pay compensation in respect of any damage caused by the criminal offence or misconduct;

- clarified the facts and circumstances in a comprehensive manner by actively collaborating with the investigating authorities; and

- taken concrete technical, organisational and personnel measures that are appropriate to prevent further criminal offences or misconduct.

The measures taken by the Supplier shall be evaluated taking into account the gravity and particular circumstances of the criminal offence or misconduct. Where the measures are considered by the authority to be insufficient, the Supplier shall be given a statement of the reasons for that decision.

## Grounds for discretionary exclusion – Part 2 (N/A)

# Selection Criteria

## Economic and Financial Standing (N/A)

## Technical and Professional Ability

The Government has developed an approach to ensuring that previous poor performance by suppliers can be taken into account and robustly assessed prior to entering into certain new contracts (as described in “Procurement Policy Note 04/15 Taking Account of Suppliers’ Past Performance”.  This will give the Government confidence, based on past performance, in the reliability of suppliers.

The policy is that, as part of any assessment of a supplier’s Technical and Professional ability, contracting authorities should ensure that any failure by the supplier to provide satisfactory performance of previous principal contracts is taken into account in the assessment of whether specified minimum standards for reliability for such contracts are met.

Evidence will be collected from suppliers to enable this assessment to be made (and a random sample of the evidence collected may be verified).

In addition, under the policy, authorities will re-assess reliability based on past performance before key points in the procurement process (i.e. short listing, preferred bidder status, conclusion of contract etc). Suppliers will accordingly be asked to update the evidence they provide in relation to past performance to reflect more recent performance on new or existing contracts (or to confirm that nothing has changed).

| 4.6 | Relevant experience and contract examples |  |  |  |
| --- | --- | --- | --- | --- |
|  | Please provide details of up to three contracts, in any combination from either the public or private sector, that are relevant to the authority’s requirement. Contracts for supplies or services should have been performed during the past three years, and VCSEs may include samples of grant funded work. The named customer contact provided should be prepared to provide written evidence to the authority to confirm the accuracy of the information provided below. Consortia bids should provide relevant examples of where the consortium has delivered similar requirements; if this is not possible (e.g. the consortium is newly formed or a Special Purpose Vehicle will be created for this contract) then three separate examples should be provided between the principal member(s) of the proposed consortium or Special Purpose Vehicle (three examples are not required from each member). Where the Supplier is a Special Purpose Vehicle, or a managing agent not intending to be the main provider of the supplies or services, the information requested should be provided in respect of the principal intended provider(s) or sub-contractor(s) who will deliver the supplies and services. (If required you may provide this information in the form of a referenced Appendix). |  |  |  |
|  |  | Contract 1 | Contract 2 | Contract 3 |
| 4.6.1 | Name of customer organisation |  |  |  |
| 4.6.2 | Point of contact in customer organisation Position in the organisation E-mail address |  |  |  |
| 4.6.3 | Contract start date Contract completion date Estimated Contract Value |  |  |  |
| 4.6.4 | In no more than 500 words, please provide a brief description of the contract delivered including evidence as to your technical capability in this market. |  |  |  |
| 4.6.5 If you cannot provide at least one example for questions 4.6.1 to 4.6.4, in no more than 500 words please provide an explanation for this e.g. your organisation is a new start-up. |  |  |  |  |

- Evaluation Matrix for Section 4.6

Responses to the questions in this section will be scored on the basis of the marking criteria detailed in the table below.

| Weight | Agreed Marking Criteria |
| --- | --- |
| Pass/Fail | Pass – Three references relevant to the subject matter of this ITT have been provided and the authority is content that the minimum standards for reliability have been met. We will consider accepting a lower number of references depending on how long you have been in business. Fail – References are not relevant OR a satisfactory number of references have not been provided OR the authority has evidence of the suppliers’ failure to discharge their obligations under previous principal relevant contract(s) which may include minimum standards for reliability in performing such contracts having not been met. |

## Additional Selection modules

### Project specific questions to assess Technical and Professional Ability (N/A)

### Insurance (N/A)

### Compliance with Equality Legislation (N/A)

### Environmental Management (N/A)

### Health and Safety (N/A)

### Award Criteria

## Requirement Specific Questions

| No. | Question | Weight % |
| --- | --- | --- |
| 1. | With specific reference to the CNCA project work detailed in the specification of requirements (Section 2) please identify what skills you assess that you need in your project team, and how your teams’ technical and professional expertise and experience meets these needs. Please identify this for: - the team as a whole; - any separate entities (e.g. sub-contractors) within the team; and - for the individuals proposed for the team (including brief biographies for each team member). Please give an assurance that the individuals named will be assigned to work on this project from the proposed start date (in Sept 2015) through to the delivery of the main outputs (March 2016). | 40% |
| Answer: |  |  |

| No. | Question | Weight % |
| --- | --- | --- |
| 2. | With specific reference to the CNCA project work detailed in the specification of requirements (Section 2) please set out in detail the methodology/approach that you propose to deliver this work. Please ensure that your methodology includes identification of specific stages of work; proposed client meetings / workshops and locations; and proposed deliverables (including any interim deliverables proposed). | 40 |
| Answer: |  |  |

## Evaluation Matrix for Section 4.8

Responses to the questions in this section will be scored on the basis of the marking criteria detailed in the table below. The information provided on allocation of resources to the project work in Section 4.9 will be taken into account in our assessment of your answers to this section.

| No. | Weighting | Marking Criteria |
| --- | --- | --- |
| 1. & 2. | 40% each | The following evaluation system will be applied to this section: 0 – No response or totally inadequate No response or an inadequate response. 1 – Major Reservations / Constraints The response simply states that the supplier can meet some of the requirements set out in the question or Specification of Requirements, but have not given information or detail on how they will do this. 2 – Some Reservations/Constraints Bidder has provided some information about how they propose to meet most of the requirements as set out in the question or Specification of Requirements. There is some doubt in their ability to consistently meet the full range of requirements. 3 – Fully Compliant Bidder has provided detailed information covering all elements of the question, detailing how they propose to meet all the requirements as set out in the question or Specification of Requirements. This gives full confidence in their ability to meet the full range of our requirements. 4 – Exceeds Requirements Bidder meets the required standard in all respects and exceeds some or all of the major requirements, which in turn leads to added value within the contract. |

## Pricing Schedule

Our maximum budget for this work is £40,000 exclusive of VAT but including all expenses and any disbursements. The scoring and weighting apply to the total fixed price quoted. You are also asked to break down the total cost into stages of methodology for our information only.

All prices will be in sterling.

Consultants are asked to submit fixed fee proposals for the work.

The fee proposed must include any likely additional costs that could reasonably be foreseen as part of the project, e.g. if there are any data requirements or software licences that FEE or the consultant may not have in house. This must also include any licencing costs that may apply to FEE to enable us to replicate the production of a CNCA in-house in subsequent years, or these must be clearly identified as a future additional cost.

|  | Weight % |
| --- | --- |
| Please provide details of your pricing in the schedule provided below | 20 |

| Stage of Work / Key Meetings as set out in your methodology | Total No. of Days | Cost |
| --- | --- | --- |
| Add / delete rows as necessary |  |  |
| Sub-Total Cost |  |  |
| Expenses |  |  |
| Other disbursements (add/delete rows as necessary) |  |  |
| Total Cost excl VAT |  |  |

Please also provide a schedule of days allocated to each team member proposed for the project. Please use the same stages of work as in the table above. This information will help us assess the information provided in response to the questions in Section 4.8.

| Stage of Work / Key Meetings | Name | Name | Name | Name (add columns as required) |
| --- | --- | --- | --- | --- |
|  | No of days | No of days | No of days | No of days |
| Total days: |  |  |  |  |

If this is a bid that involves more than one organisation / company / institution in any format (lead contractor/consortium etc) please also provide a schedule of days allocated to each company/organisation proposed for the project. Please use the same stages of work as in the table above. This information will help us assess the information provided in response to the questions in Section 4.8

| Stage of Work / Key Meetings | Organisation | Organisation | Organisation | Organisation (add columns as required) |
| --- | --- | --- | --- | --- |
|  | No of days | No of days | No of days | No of days |
| Total days: |  |  |  |  |

## Evaluation Matrix for Section 4.9

Responses to this section will be scored on the basis of the marking criteria detailed in the table below.

| Weight | Agreed Marking Criteria |
| --- | --- |
| 20% | Price will be evaluated using the ‘standard differential method’ – each bidder receives 100% of the available marks less the percentage by which their tender is more expensive than the lowest; with 4 being the maximum score achievable. |

## Payment Schedule

It is proposed that the payment schedule for the contract is:

- 50% on delivery of the draft CNCA;

- 40% on final CNCA; and

- 10% on satisfactory completion of all outputs including handover.

If bidders wish to propose an alternative payment schedule they must explain how the alternative proposed prudently ensures that public funds will not be expended prior to the delivery of agreed outputs.

## ITT –Appendices

Please ensure you clearly number appendices along with the section and question it relates to.

Terms and Conditions

This ITT, and any contract arising from it, will be subject to the latest version our terms and conditions for consultancy.

The successful Tenderer’s usual terms and conditions are not, and will not, become terms and conditions of any contract that we may award as a result of this ITT.

| a) | Do you accept the FC’s Terms and Conditions of Contract as detailed above? (delete the option that doesn’t apply) | Yes / No |
| --- | --- | --- |
| b) | If no, please provide details of any specific areas that you have an issue with. Please note that failure to agree to our Terms and Conditions of Contract may invalidate your tender submission. |  |

- Evaluation Matrix for Section 4.11

Responses to the questions in this section will be scored on the basis of the marking criteria detailed in the table below.

| Weight | Agreed Marking Criteria |
| --- | --- |
| Pass/Fail | Pass: Terms and Conditions have been accepted without any exceptions, or exceptions are minor and can be accommodated. Fail: Exceptions noted have been discussed and are unable to be accommodated. |

## Declaration

I declare that to the best of my knowledge the answers submitted to these questions are correct.  I understand that the information will be used in the selection and evaluation process to assess my organisation’s suitability to participate in this procurement, and to determine which supplier(s) provide the most economically advantageous tender in accordance with the criteria set out in this ITT.  I am signing on behalf of ………………………………………………………………… (insert name of supplier).

I understand that the authority may reject my submission if there is a failure to answer all relevant questions fully or if I provide false/misleading information.  I have provided a full list of any Appendices used to provide additional information in response to questions.

The essence of selective tendering is that the authority will receive bona fide competitive tenders from all those tendering.  In recognition of this principle, I certify that this is a bona fide tender, intended to be competitive, and that ‘we’ (I or any other person acting for on behalf of my organisation) have not fixed or adjusted the amount of the tender by or under or in accordance with any agreement or arrangement with any other person.  I also certify that we have not done and we undertake that we will not do so at any time before the hour and date specified for the return of this tender any of the following acts:

- communicate to a person other than the person calling for those tenders the amount or approximate amount of the proposed tender, except where the disclosure, in confidence, of the approximate amount of the tender was necessary to obtain premium insurance quotations required for preparing the tender;

- enter any agreement with any other person whereby they will refrain from tendering or as to the amount of any tender to be submitted;

- offer or pay or give or agree to pay any sum of money or valuable consideration directly or indirectly to any person for doing or having done or causing or having caused to be done in relation to any other tender or proposed tender for this work any act or thing of the sort described above.

In this certificate, the word “’person” includes any individual, partnership, association, or body either corporate or unincorporated; and “’any agreement or arrangement” includes any such transaction, formal or informal, and whether legally binding or not.

I also declare that there is no conflict of interest in relation to the authority’s requirement.

The following appendices form part of our submission;

| Section of ITT | Appendix Number |
| --- | --- |

ITT COMPLETED BY

Name:

Role in Organisation:

Date:

Signature:

- Evaluation Matrix for Section 4.12

Responses to this section will be evaluated on the basis of the marking criteria detailed in the table below.

| Weight | Agreed Marking Criteria |
| --- | --- |
| Pass/Fail | Pass: Completed, signed declaration has been provided with all relevant appendices listed. Fail: Declaration has not been signed or provided, or exceptions have been noted which cannot be accepted. |

Appendix A: First Draft Potential Scope of FEE CNCA

|  | Ecosystem Service |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aesthetics |  | Clean Air | Clean Water | Energy | Cultural | Climate Regulation | Fibre (timber) | Food | Hazard Protection (flooding) | Recreation | Wildlife | Biodiversity (Supporting Service) | ?? |
| Scope of Financial Account Yes(Y)/No(N)/Partial or potential (P) = there are income or expenditure impacts of the ecosystem service. Dark Green = net income shown in national accounts, Light green = some income but net loss from activity. Income from people visiting because they appreciate one or more of the PFE’s ecosystem benefits is wholly allocated to recreation, Y(x) identifies where there is a cost to maintaining e.g. the aesthetic contribution, but where there is no income stream directly associated with that ecosystem service. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Plantation Woodland |  | P | N | P (x) | Y | Y (x) | N | Y | P (venison) | N | Y | Y (x) | Y (x) |  |
| Native Woodland |  | Y (x) | N | P (x) | Y | Y (x) | N | Y | P (venison) | N | Y | Y (x) | Y (x) |  |
| Non-Intervention Woodland (Old Growth Stands) |  | P | N | P (x) | N | Y (x) | N | N | P (venison) | N | Y | Y (x) | Y (x) |  |
| Wood Pasture (grazed) |  | Y (x) | N | P (x) | N | Y (x) | N | N | P (venison) | N | Y | Y (x) | Y (x) |  |
| Open Habitats (heath, moor, mire, mountain top, fens) |  | Y (x) | N | P (x) | P | Y (x) | N | N | P (venison) | N | Y | Y (x) | N |  |
| Agriculture (arable, grazing, meadows) |  | N | N | P (x) | P | P | N | N | P | N | P | P (MS) | N |  |
| Additional scope of Natural Capital Account Light green indicates areas where we think it might be possible to a) quantify the contribution and b) value that quantified contribution. A first step of the work we’re about to commission would elucidate this. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Plantation Woodland |  | P | Y | Y | Y | P | Y | Y(reflect future volume) | P (venison) | Y | Y | Y | Y |  |
| Native Woodland |  | Y | Y | Y | Y | Y | Y | Y(reflect future volume) | P (venison) | Y | Y | Y | Y |  |
| Non-Intervention Woodland (Old Growth Stands) |  | Y | Y | Y | N | N | Y | N | P (venison) | Y | N | Y | Y |  |
| Wood Pasture (grazed) |  | Y | Y | Y | N | Y | Y | N | P (venison) | Y | Y | Y | Y |  |
| Open Habitats (heath, moor, mire, mountain top, fens) |  | Y | N | Y | P | Y | P | N | P | Y | Y | Y | Y |  |
| Agriculture (arable, grazing, meadows) |  | N | N | N | N | N | P |  | P | N | P | p | P |  |

Appendix B: Information / Data FEE are able to make available for this work

Information / data we are able to make available for this work includes:

- National Forest Inventory (see www.forestry.gov.uk). This rolling programme of work is providing  up-to-date information about the size, distribution, composition and condition of our forests and woodlands.  Data and reports on different themes are being released periodically, including for the Public Forest Estate.  To date, these include a woodland map, and 25-year forecasts on stocked area, standing volume, numbers of trees, increment and softwood availability.  Shape files on the NFI spatial data and associated metadata are available on request.  Further reports and data (e.g. on biodiversity) will be published over the next 18 months.  Published data can be used by the consultants and NFI staff can advise further where needed.  The data downloads area of the FC website provides more detail (see http://www.forestry.gov.uk/datadownload).

- Sub-compartment database data. This provides detailed physical information (including through a GIS system “Forester GIS”) on the Public Forest Estate.  Data cover the extent and nature (e.g. woodland, farmland, mountain-top, heathland, riparian areas) of land, habitats, forest management, stocking, wayleaves, roads and windthrow hazard.  Each stand of trees is represented spatially, together with information on individual stand characteristics (for example species, planting year, spacing and yield class) which is periodically updated. As new surveys of stands are conducted (e.g. for operational purposes), survey results are also recorded against the stands. In addition, the SCDB contains details of how stands are being managed – in particular, the planned frequency and type of thinning operations and a ‘due date’ for felling. Data are also provided on a wide range of other features, e.g. badger sets, cycle tracks, with varying data coverage.  The data downloads area of the FC website provides more detail (see http://www.forestry.gov.uk/datadownload).

- Economic data. FC economists can advise on the availability and interpretation of economic values for different services provided by woodlands, including recreation, landscape and biodiversity. The FC’s Forestry Statistics website (see www.forestry.gov.uk/statistics) provides much information, and further advise will be available from FC statisticians;

- Visitor numbers. Forest Enterprise England can provide data on visitor numbers to about 20 of our main visitor centres/car parks, and also some detailed work on understanding discrete geographical parts of our environment, for example Thetford Forest is a large part of Breckland in East Anglia, where a 2014 Biodiversity Audit in East Anglia identified 12,845 species, 2,149 priority species and 72 regional endemics.

- Expenditure. Forest Enterprise England’s internal accounting division of income and expenditure into ‘market’ and ‘non-market’ identifies ecosystem service activities that government pays for, and attributes costs and income to these activities. This is referred to within FEE as our Payment for Ecosystem Services (PES) model and is contained in an Excel spreadsheet.

- Carbon. Forest Research (FR) carbon models can assess sequestration for different species, management regimes and soil types.  Data and analysis can be provided by FC/FR to enable carbon stocks and sequestration on the PFE to be modelled.

See EU definition of SME: http://ec.europa.eu/enterprise/policies/sme/facts-figures-analysis/sme-definition/