## Summary Price schedule
SCHEDULE 1 - PRICE
NOTES:
Please include costs for:
A | Additional research such as, consultation and engagement, significance, history of the sites, use, wider context analysis etc.
B | Consultation: engagement with statutory and non-statutory agencies.
C | The fee must cover the cost of the Professional Services team developing the design proposals in sufficient detail to meet the requirements set out in the Brief and to include the submission of the completed Final documents for sign off.
D | The Fee Proposals should include all outgoings, travel, other expenses and disbursements in connection with the performance of the Consultant’s obligations, save for any exceptional expenses (such as the provision of professional architectural models and computer generated visualisations) as agreed by the Client. Any areas of doubt should be highlighted and any fees that are excluded from the Fee Proposal should be identified.
E | The appointment will be confirmed progressively by work stage, with the commission only progressing beyond each work stage with the selected consultant team subject to the availability of funding and the performance of the team on the previous phase of the commission. If the commission has to be terminated no further payment will be due to the selected consultant other than the fees due to the completion of that work stage.
F | Payments to be made on statisfactory completion and sign off on Milestones
G | If time-charged fees are proposed for any element of the appointment, the tenderer shall state both its best–estimate of a budget and separately a not-to-be-exceeded ceiling for the item.
H | VAT is not to be included.
I | Totals to be inserted in yellow cells below
|  | FIXED SUM | STAGE | PRODUCT | Percentage payment | TOTAL
|  | Milestone 1 | Draft updates to Milestone | Draft updates to milestone presented to client and approved by client | 15% | 0
|  | Milestone 2 | Final Draft documents | Presentation of final draft documents to client | 25% | 0
|  | Milestone 3 | Sign off | Final presentation and sign off on all final documents by client | 60% | 0
FIXED PRICE TOTAL
For information purposes: Time charge for non-specified additional work
Daywork rates should be indicted or elemental costs for potential additional work.
|  |  |  | Consultant (please specify) | Day Rate (£)