Department of Digital, Culture, Media and Sport (DCMS)

Evaluation of the Covid-19 Loneliness Fund

1. Introduction

DCMS is seeking a supplier to evaluate the Covid-19 Loneliness Fund grant delivery programme.  A lead organisation or partnership of organisations is needed to conduct a mixed method process evaluation to understand how the fund was delivered and experienced, with a focus on exploring what worked well and less well in addressing loneliness and how loneliness was experienced during the pandemic. This will help inform future policy development inside and outside government.

The scope of this procurement will cover the following objectives and will be undertaken by the lead or in collaboration with members of a consortium. These objectives represent an overview of the methodology sequence proposed for this project, with the dissemination of evidence & learning being our key output.

2. Activity

2.1 Mixed method process evaluation

2.1.1 Management and analysis of quantitative monitoring data

The supplier will work with the nine grantees to support them in collecting pre-agreed data on outcomes, activities and demographics. They will also be responsible for cleaning, managing and analysing data collected.

2.1.2 Qualitative case studies

The purpose of the qualitative case studies is to provide an in-depth account of how the Fund was delivered and experienced, complementing the quantitative monitoring information and outcomes data, and, to explore  perceived impact of the Fund amongst grantees and their service-users. The supplier will be required to conduct case studies with a sub-sample of grantees, including staff, volunteers and their service-users to explore the evaluation questions (as outlined below).

2.2 Qualitative exploration of the effect of Covid-19 on Loneliness

The supplier will also be expected to conduct qualitative research with staff, volunteers and service-users to explore the effects of Covid-19 on loneliness. DCMS envisages this being done as part of the qualitative case studies, or as standalone encounters.

3. Outputs & Deliverables

The supplier will be expected to:

3.1 Support the quantitative data collection of the 9 grantees, cleaning and managing the data and producing a dataset that can be analysed provide a descriptive account of how the Fund was delivered and experienced

3.2 Produce a final evaluation report which draws on the insights from the quantitative and qualitative data the supplier collects to answer the research questions. These research questions will be outlined in the ITT.

4. Key Dates & Tendering

It is anticipated that a procurement may start in late September with the contract awarded in early October, and then to commence in mid October. These indicative dates are for information purposes only.

The contract is expected to finish in March 2021.

6. VfM will be achieved through competitive tendering. The budget is likely to be between £90,000 - £122,000 (excluding VAT).  The Contract will contain performance measures (KPI’s) to ensure contractor performance and achievement of value for money over the life of the contract.

Delivery of the services could be through a range of methods;

- A single contractor

- A single contractor operating as a lead supplier with a supply chain with different sub-contractors supplying different specialist components of the requirement

- A consortium including a mix of suppliers with the required skill sets

8. Response

We would be interested in your responses to the following questions - go into as much detail as you have time for.

Q1 Would you be interested in bidding for this project?

Q2 What is your recommended timeframe to deliver this project?

Q3 Are the project requirements clear? Do you have any ideas about how DCMS output requirements could be effectively delivered ?

Q4 What, if anything, has the Department missed or overlooked in setting out their requirements?

Q5 What would the indicative cost be for each of the requirements above?

9. Contact Details

Please e-mail Andrew Sternberg (Commercial Business Partner) on andrew.sternberg@dcms.gov.uk with your response to the questions above by Monday 14th September..

Please provide a named point of contact in your organisation, with phone number and email address, who can answer questions in relation to your response..

Depending on the volume of responses DCMS may;

- circulate further pre-tender market engagement material,

- set up phone conference sessions either individually or as a group call

As a minimum respondents will receive access to the OJEU/ Contract Opportunity Notice once the procurement route has been decided.