# HMRC DRS Implementation Plan - Assumes an Effective Date of Monday 10th January & Service Start Date of Monday 12th September.

| Milestone | Buyer Constraints | Delay Payments |
| --- | --- | --- |
| - The Supplier and their DCA Panel to attended and completed the Buyer’s Onboarding events and passed the physical security checks. |  |  |
| - Detailed IT requirements signed off by HMRC and Supplier IT Build/configuration, and connection to HMRCs secure Data Exchange Service for file exchange completed. |  |  |
| - DCA Sub-Contracts Signed to enable sufficient capacity for live service |  |  |
| - Delegations granted by HMRC Commissioners in respect of The Supplier and all sub-contractors who will be carrying out Specified Functions at the Service Start Date | - 6 weeks required following receipt of the information to prepare the submissions and present these to the Commissioners’ and for the Commissioners to grant delegation. - The delegation submissions will not be sent to the Commissioners until the financial accreditation testing has been completed successfully and the financial accreditation bid is ready for submission. - HMRC can submit both the Delegations requests and Financial Accreditation bids concurrently. |  |
| - Supplier and DCA Financial Accreditation testing completed and FA has been granted by HMRC Chief Finance Officer | - The end to end process for Financial Accreditation is approximately 4 months. - Within the 4-month period, 7 weeks is required following successful testing for HMRC to prepare the bids (1 week) which includes the successful test evidence and submit the bids and 6 weeks for the approvals for each DCA plus the supplier. |  |
| - Each DCA subcontractor’s Collection & Contact Strategies & Letters signed off ready for service by HMRC |  |  |
| - Operations Manual baselined and signed off by HMRC |  |  |
| - Data flow diagrams, CRA footprint information and DCA portal security approved by HMRC and all required contractual standards evidenced ready for service. |  |  |
| - The Supplier will have set up all Reporting, Management Information and Invoicing ready for live service |  |  |
| - HMRC is connected to the Supplier’s Portal and HMRC User Set Up’s have been completed. |  |  |
| - Supplier to have provided HMRC User Training & Guidance for use of the Buyer Portal |  |  |
| - Milestones 1 to 11 are complete and Managed Collections Service Controlled Go Live can commencement: Authority to Proceed | - 1 week prior to Controlled Go Live Milestones 1 to 11 have been achieved by the supplier and HMRC can confirm Authority to Proceed into a controlled go live. | Yes |
| 12th September |  |  |
| - Managed Collections Service commencement: Controlled Go Live completed |  | Yes |
| - Completion of the Buyers Post Go Live Stabilisation Period |  |  |

# Delayed Payments Milestones:

As per Call Off Schedule 13 the supplier shall pay to the Buyer such Delay Payments for the following Milestones:

# Milestones 12: 1 to 11 are complete and Managed Collections Service Controlled Go Live can commencement: Authority to Proceed and

Milestone 13: Managed Collections Service commencement: Controlled Go Live completed

(a)  for the first 20 Working Days £1,500 per Working Day of delay (to start after 10th Working Day (day 11))

(b)  for the following 20 Working Days £2,500 per Working Day of delay

(c)  for the following 20 Working Days £3,500 per Working Day of delay.