BFC LOGISTIC MOVEMENT SUPPORT CONTRACT (BFCCB/1354) IMPLEMENTATION PLAN

Introduction

1.	The Innovative bid of CPPC Logistic Group of Companies Ltd. (CPPC) for the BFC Logistic Movement Support Contract (LMSC) BFCCB/1354 requires a phased implementation plan.

Aim

2.	The aim of this brief is to advise the Comd Gp of the phased implementation plan required in order to achieve LMSC Full Operating Capability (FOC) by 1 Sep 16; a detailed timeline is at Annex A.

Background

3.	The introduction of an innovative bid by CPPC and the changes to current operations which will be experienced by the Authority have required a comprehensive approach to integrating CPPC into defence processes.  This has been achieved through stakeholder engagement between; the Authority, subject matter experts, the J4 contract sponsor, DO, commercial teams within HQ BFC and CPPC.  This has led to the production of the integrated timeline detailed within this brief and comprehensive implementation plan.  This has been produced with the aim of achieving a sustainable and effective partnership between CPPC and the Authority.

Concept of Ops

4.	Scheme of Manoeuvre.  Implementation of the new LMSC will be achieved in 4 phases.  There will be a preliminary (preparation) phase, an implementation phase, an evaluation phase, and a phase to confirm BFC new ways of working.

Preliminary Phase (9 – 30 June 16)

5.	Prior to contract award, the Authority in conjunction with the contractor will be required to:

a.	By 1 Jul 16, HQ BFC is to ratify the nomination of an embedded DO and dedicated contract assurance team.

b.	The Contractor is to undertake area visits of units and sub-units to ratify phase 2 processes and to introduce the CPPC Logistics Ops Centre process.

c.	HQ BFC J2/4/6 and DIO to visit Limassol New Port facilities in order to ratify contractor access to DII(F), letting of facilities and review of security processes.

d.	All BFC units (as directed by HQ BFC J4) are to draft initial SOPs and work instructions for the Contractor and Authority stakeholders to form the basis of an agreed set of Operating Procedures. These are to be added to the LMSC BFCCB/1354 in conjunction with the requirements of the agreed innovative bid SOR by AORs as detailed below:

- P&C Tp – Diplomatic and Routine Mail SOP.

- OC SOF – Internal freight movements schedule and forward delivery tasking RAF Akrotiri.

- OC SOF – ATT from ports of entry (Military and Civilian air and sea ports).

- OC SOF – Inter-unit freight deliveries.

- DO – Unit demand process via FMT 1000.

- DO – Port Task Group, assurance, governance, continuous improvement and KPI management processes iaw contract requirements.

- Commander Medical and J4 Logs – Medical provisioning point delivery schedule and process.

- Unit and RIB QM departments – Internal freight movements schedule.

Implementation Phase (1-31 July 16)

6.	Post contract award and prior to 1 Aug 16 the Authority and Contractor will instigate the following in order to achieve contract Initial Operating Capability (IOC):

- Establishment of CPPC’s Op Centre within LNP facility (Op Centre FOC 1 Jul 16).

b.	Immediate commencement of logistics deliveries in full for:

- Medical provisioning point.

- Diplomatic mail (with courier travelling in vehicle).

c.	Contractor shadowing of BFC logistics functions, transferring to BFC shadowing of Contractor by 1 Aug 16.

d.	Refinement of SOPs and work instructions during shadowing process.

Evaluation Phase (1-31 Aug 16)

7.	Evaluation of working practices and handover of tasks from the Authority and Contractor are to be undertaken during the period 1-15 Aug 16.  From 15 Aug – 1 Sep 16, a formal review will be undertaken under the direction of HQ BFC J4 to:

- Ensure the Authority and Contractor is able to maintain full support to BFC and Op SHADER and comply with military and civilian regulations.

- Confirm the SOPs and work instructions are robust, sustainable and fit for purpose.

- Confirm that predicted costs are matched by actual expenditure.

- Produce a confirmation report that FOC has been achieved and that the contractor solution has been implemented.

Confirm Phase (1-30 Sep 16)

7.	Post FOC, HQ BFC J4 in conjunction with the DO and COSU will undertake a review of BFC logistic functions and resources to evaluate any new ways of working for BFC.   A report of the findings is to be submitted to HQ BFC ACOS Spt by 1 Oct 16.

Annex:

A.	LMSC BFCCB/1354 Integration timeline.

Appendix 1 to ANNEX F to Contract BFCCB/1354

BFC EPI WIP 03 04 07 J4

Dated 13 Jun 16

LMSC BFCCB/1354 Integration Timeline

LMSC FOC

LMSC IOC

Ops Centre IOC

Phase 4: Confirm BFC new ways of working

Phase 3: Evaluate and adjust

Phase 1: Prepare

Phase 2: Implement

8 Jun16

1 Oct 16

1 Sep 16

1 Aug 16

1Jul 16

Contract Start Date