INVITATION TO TENDER

&

STATEMENT OF REQUIREMENT

Developing a new Diversity and Inclusion strategy for ORR

CPV Code: 72221000

Tender Reference: ORR/CT/19-45

Purpose of document

- The purpose of this document is to invite proposals for a supplier to develop a new Diversity and Inclusion (D&I) strategy for the Office of Rail and Road.

- This document contains the following sections:

- 1. 	Introduction to the Office of Rail and Road

- 2.  	Statement of Requirement

- 3.	Tender Proposal & Evaluation Criteria

- 4.	Procurement Procedures

- 1. Introduction to the Office of Rail and Road (ORR)

- The Office of Rail and Road is the independent safety and economic regulator for Britain’s railways. We also hold Highways England to account for its day-to-day efficiency and performance in running the strategic road network, and for delivering the five year road investment strategy set by the Department for Transport (DfT).

- ORR currently employs approximately 300 personnel and operates from 6 locations nationwide. The majority of personnel are located at ORR’s headquarters, One Kemble Street, London, which is moving to Canary Wharf from October 2019.

- Our strategic objectives

- 1. Drive for a safer railway: Enforce the law and ensure that the industry delivers continuous improvement in the health and safety of passengers, the workforce and public, by achieving excellence in health and safety culture, management and risk control.

- 2. Support a better service for customers: Use our powers to hold the industry to account for performance and standards of service across the railway network, for passengers and freight. Promote fair competition and the on-going improvement in the experience of users, including through the provision of accurate and timely information.

- 3. Secure value for money from the railway, for users and funders: Strengthen incentives for the whole industry, including through competition and contestability in the supply chain, to drive greater efficiency from the use and maintenance of existing railway capacity and more cost-effective investment in the network.

- 4. Secure improved performance and value for money from the strategic road network: Secure improved performance, including efficiency, safety and sustainability, from the strategic road network, for the benefit of road users and the public, through proportionate, risk-based monitoring, increased transparency, enforcement and robust advice on future performance requirements.

- Supplying ORR

- The ORR procurement unit is responsible for purchasing the goods and services necessary for ORR to achieve its role as the economic and health & safety regulator of the rail industry.

- The ORR procurement unit subscribes to the following values:

- to provide a modern, efficient, transparent and responsible procurement service;

- to achieve value for money by balancing quality and cost;

- to ensure contracts are managed effectively and outputs are delivered;

- to ensure that processes have regard for equality and diversity; and

- to ensure that procurement is undertaken with regard to Law and best practice.

- For further information on ORR please visit our website: www.orr.gov.uk

- Small and Medium Enterprises

ORR considers that this contract may be suitable for economic operators that are small or medium enterprises (SMEs) and voluntary organisations. However, any selection of tenderers will be based on the criteria set out for the procurement, and the contract will be awarded on the basis of the most economically advantageous tender.

Small and Medium Enterprises and Voluntary Organisations:

| Enterprise Category | Headcount | Turnover | Or |  | Balance Sheet Total |
| --- | --- | --- | --- | --- | --- |
| Micro | <10 | ≤ € 2 million |  | ≤ € 2 million |  |
| Small | <50 | ≤ € 10 million |  | ≤ € 10 million |  |
| Medium | <250 | ≤ € 50 million |  | ≤ € 43 million |  |
| Large | >251 | > € 50 million |  | > € 43 million |  |

Please ensure that you indicate how your organisation is categorised on the Form of Tender document which should be submitted along with your proposal.

2. Statement of Requirement

2.1 Background to the project

Introduction The Office of Rail and Road (ORR) has decided to establish an overall strategy, for diversity and Inclusion, drawing on a review of current and planned work and best practice against which the different work streams can be prioritised and monitored. ORR requires independent guidance, expertise, challenge and implementation support in establishing the strategy and carrying out the review. Background ORR has a positive working environment and, in workshops carried out in 2018 on ‘The way we work together’, people told us that they valued ORR as a place to work where they could ‘make a difference’. Staff particularly value their colleagues and the strong working relationships that are developed across the organisation. Although we have not historically had a strategy, we have been able to deliver a range of diversity initiatives including: - ORR D&I statement of intent - Name-blind recruitment - Trained Mental Health First aiders - Director level Health and wellbeing Champion - A development programme for under-represented groups - Workplace adjustment passport - Disability Confident Employer Level 2 - Anti-bullying and harassment volunteer network - A colleague-led Diversity and Inclusion Network We aim to reflect the people and communities we serve. We embrace diversity, meaning that we recognise and value the wide range of backgrounds, culture, views and values of all those who work for us. We recognise and value the contribution that everyone at ORR has to make, and continuously work to maintain an environment which provides everyone with the support and confidence to express their views and contribute to our work in a positive and respectful way. However, from a diversity and inclusion perspective, there are some areas that indicate scope for improvement: - Improving diversity representation across ORR and senior grades. Overall, 60% of colleagues at ORR are male, whilst 40% are female. The majority of colleagues are white (69%), whilst 17% are non-white, and 14% undeclared. Over 68% of colleague are aged 40 years and above; and - Our gender pay gap is wider than we want it to be. There is also the civil service agenda on diversity and inclusion, which is picking up pace and breadth and which is setting higher expectations for individual government departments and other regulators. We therefore want to inject some focus into our approach to diversity and inclusion which is appropriate for our size and resource levels, but is also appropriately ambitious and relevant to emerging initiatives across the civil service.

2.2 Project Objectives & Scope

The aim is to provide ORR with a coherent strategy that will deliver change, have measurable impact in the organisation and which is understood and bought into by its colleagues. We are seeking an experienced Diversity and Inclusion consultant to complete a short-term assignment, to review work carried out to date, to assess progress and gaps / opportunities, and provide strategic direction for ORR to take forward its diversity and inclusion agenda. This is to ensure we have appropriate levels of ambition for the size of our organisation and to meet our statutory responsibilities under the Equality Act. As part of this we would like the consultant to conduct a detailed review of our existing plans and strategy, referencing our current policies and procedures as context; review and gather internal data relating to D&I and conduct conversations with stakeholders (individuals and groups), and understand what best practice is being implemented in other similar organisations. Research and diagnostics - Working with HR, management, ORR Diversity & Inclusion Network, our Staff Representatives Group and other key internal stakeholders, identify the key values, concerns and issues that will need to be taken into account in developing a new ORR D&I strategy; - Provide examples of D&I strategies, including benchmarking approaches to D&I, adopted by other comparable organisations (possibly including private sector) to enable ORR to understand, compare and contrast their approaches; - Conduct a detailed research and review of - the existing policy, workplan, procedures and data relating to D&I - conduct conversations with stakeholders (individuals and groups) to make recommendations on issues identified - all ORR D&I initiatives within HR processes such as recruitment, absence management, workplace adjustment; - risks and opportunities. - Develop a 3 year Diversity and Inclusion strategy including options and prioritised recommendations to deliver a strategy within resources available. This is to be presented to ORR’s Executive Committee setting out the findings of the above research and proposing an overall phased plan. Implementation - Provide advice and support to ORR on communication and implementation of the strategy.

2.3 Project Outputs, Deliverables and Contract Management

Outputs and Deliverables The main deliverable from the project will be a D&I strategy document (in pdf and to a publishable standard) and final report covering the objectives and scope outlined above. The selected consultant will deliver: - Progress reports against agreed plan (by email) on at least a fortnightly basis; - Progress meetings (face to face) with the Associate HR Director (and/or their nominees) and the ORR D&I project team on a monthly basis; - An interim presentation of emerging findings; - A draft strategy and report; - A strategy document including a report on your research, diagnostics, options and prioritised recommendations to deliver the strategy within resources available and with sufficient evidence to support the proposals. - Attendance at relevant Board (e.g Executive Committee) meetings to provide updates. Desired outcomes ORR has identified the following desired outcomes from the reform of its D&I strategy and programme of work: - To ensure that we maintain a positive, engaging and respectful working environment so that no one at ORR experiences behaviour that they reasonably regard as bullying, intimidation or harassment; - To increase the inclusiveness of our recruitment arrangements to attract people from widest diverse backgrounds; - To provide fair and open access to development and encourage all our people to participate fully in the opportunities we offer. - To improve the colleague awareness of and satisfaction levels with ORR’s diversity and inclusion activities Contract Management Requirements During delivery of the work, the selected contractor will keep the HR stakeholders including the D&I project team, Director of Corporate Operations and the SRO updated on progress.

2.4 Project Timescales

The provisional timetable is as follows: - Start up meeting and commencement w/c 28 October 2019. - Monthly updates on progress and any issues - Presentation of interim findings on (To be agreed) - Draft D&I strategy and report by 17 December 2019. - Final D&I strategy and report by the 31 January 2020

2.5 Budget and Payment Schedule

The maximum budget for this piece of work is £40,000 (inc. of expenses, exc. of VAT), however ORR expects bids to be significantly below this threshold. - Payment of the total fee will be on the delivery and acceptance by ORR of all required outputs and/or deliverables.

2.6 Further project related information for bidders

- Intellectual Property Rights - ORR will own the Intellectual Property Rights for all project related documentation and artefacts, unless these are independently copyrighted third party products. - ORR reserves the right to publish the documents, either in full or in part. As such, all documents should be drafted in such a manner that allows publication without the need for input from the chosen supplier. - Transparency requirements - Please note ORR is required to ensure that any new procurement opportunity above £10,000 (excluding VAT) is published on Contracts Finder, unless the ORR is satisfied it is lawful not to. Once a contract has been awarded as a result of a procurement process, ORR is required to publish details of who won the contract, the contract value and indicate whether the winning supplier is a SME or voluntary sector organisation. - Confidentiality - All consultants working on the project may be required to sign a confidentiality agreement and abide by the Cabinet Office’s protective marking guidelines, which ORR uses to protectively mark a proportion of its information. In addition, the consultant may be required to sign additional confidentiality agreements as required by external stakeholders. - Sub-Contractors - Contractors may use sub-contractors subject to the following: - That the Contractor assumes unconditional responsibility for the overall work and its quality; - That individual sub-contractors are clearly identified, with fee rates and grades made explicit to the same level of detail as for the members of the lead consulting team. Internal relationships between the Contractor and its sub-contractors shall be the entire responsibility of the Contractor. Failure to meet deadlines or to deliver work packages by a subcontractor will be attributed by ORR entirely to the Contractor.

3. Tender Response & Evaluation criteria

3.1 The Tender Response

Your proposal should include an outline of how you will meet the requirements outlined in section (2) “Statement of Requirement”. The following information should be included: a) Understanding of our requirements - You should demonstrate a clear understanding of the requirement and overall aims of the project. b) Approach to our requirements - An explanation of your proposed approach to undertaking the phases as detailed above and any methodologies you propose to use, including the research methodology you propose to utilise, including your use of any specialist tools and/or data; - Your views on the deliverability of our outline project plan against timelines and within the broad constraints detailed above. - Details of how you will present your findings, how you will ensure they are sufficiently robust and rigorous so as to withstand scrutiny; - Details of your project management methodology and a project plan to show how deliverables will be produced within the required timescales, detailing the resources that will be allocated, methods for consulting and engaging stakeholders and methods for ensuring sensitive data is stored and used in line with the provisions of the General Data Protection Regulations (GDPR); - Your understanding of the risks, and explain how they would be mitigated to ensure delivery as well as key opportunities that you believe could be realised as part of project delivery; - What support and resources you will require from us and any additional stakeholders that you believe will be engaged. - What are the anticipated timeframes for delivery of the project? Having reviewed the background and requirement please advise of a high level (by month) timeline of the anticipated activity. - c) Proposed delivery team and Experience of the Organisation - CVs of the key personnel including details of how their key skills, experience and qualifications align to the delivery of the project; - Project roles and responsibilities; and - Up to two relevant examples of previous projects of a similar nature that you have successfully delivered out (e.g. case studies, including outcomes) d) Pricing A fixed fee for the project inclusive of all expense. This should include a breakdown of the personnel who will be involved with the project, along with associated charge rates and anticipated time inputs that can be reconciled to the fixed fee.

3.2 Evaluation Criteria

Tenders will be assessed for compliance with procurement and contractual requirements which will include: - Completeness of the tender information - Completed Declaration Form of Tender and Disclaimer - Tender submitted in accordance with the conditions and instructions for tendering - Tender submitted by the closing date and time Tenders that are not compliant may be disqualified from the process. We reserve the right to clarify any issues regarding a Bidder’s compliance. It will be at our sole discretion whether to include the relevant Bidder’s response in the next stage of the process. - The contract will be awarded to the Bidder(s) submitting the ‘most economically advantageous tender’. Tenders will be evaluated according to weighted criteria as follows: - Methodology (20%) - The proposal should set out the methodology by which the project requirement will be initiated, delivered and concluded. In particular, it must: - a) Explain the methodology and delivery mechanisms to ensure that the requirements of this specification are met in terms of quality, highlighting how well your organisation understands public sector equality duty, research and benchmarking, stakeholder engagement and experience of developing D&I strategy with recommendations; - b) Explain how your organisation will work with the ORR, and other stakeholders; including ORR’s HR representatives and your approach to knowledge transfer; - Explanation of how risks will be managed and mitigated - Delivery (20%) - The proposal should set out how and when the project requirement will be delivered. In particular, it must: - a) Explain how this project will be delivered to timescale, (including the delivery of regular reports and updates), and how milestone will be met, detailing the resources that will be allocated to each stage; - b) Demonstrate your understanding of the risks, and project dependencies and explain how they would be mitigated to ensure project delivery; - c) Explain the resources that will be allocated to delivering the required outcomes/output, and what other resources can be called upon if required. - Experience (30%) - The proposal should set out the organisation’s and the delivery team’s experience relevant to the project requirements. In particular, it must: - a) Provide CVs of the consultants who will be delivering the project; - b) Highlight relevant experience of the proposed team for this project, submitting examples of similar projects – see above. - c) up to two case studies - Cost / Value for money (30%) - A fixed fee for delivery of the project requirement (inclusive of all expenses), including a full price breakdown for each stage of the project and details of the day rates that will apply for the lifetime of this project. Marking Scheme Score 0; Unanswered or totally inadequate response to the requirement. Complete failure to grasp/reflect the core issues. 1; Minimal or poor response to meeting the requirement. Limited understanding, misses some aspects. 3; Good understanding and interpretation of requirements, providing clear evidence of how the criterion has been met. 5; Excellent response fully addressing the requirement and providing significant additional evidence of how the criterion has been met and how value would be added.

- 4. Procurement procedures

- Tendering Timetable

- The timescales for the procurement process are as follows:

| - Element | - Timescale |
| --- | --- |
| - Invitation to tender issued | - 25 September 2019 |
| - Deadline for the submission of clarification questions | - 02 October 2019 10:00 |
| - Deadline for submission of proposals | - 09 October 2019 10:00 |
| Shortlisted suppliers notified | - 15 October 2019 |
| Interviews and presentations | - 18 October 2019 |
| - Award contract | - 24 October 2019 |
| - Project Inception Meeting | - 28 October 2019 |

Tendering Instructions and Guidance

Amendments to ITT document

- Any modification to the Invitation to Tender will be issued as soon as possible before the Tender submission date and shall be issued as an addendum to, and shall be deemed to constitute part of, the Invitation to Tender. If necessary, ORR shall revise the Tender Date in order to comply with this requirement.

Clarifications & Queries

- Please note that, for audit purposes, any query in connection with the tender should be submitted via the ORR eTendering portal. The response, as well as the nature of the query, will be notified to all suppliers without disclosing the name of the Supplier who initiated the query.

Submission Process

- Tenders must be uploaded to the ORR eTendering portal no later than the submission date and time shown above. Tenders uploaded after the closing date and time may not be accepted. Bidders have the facility to upload later versions of tenders until the closing date/time.

- Please submit the Form of Tender and Disclaimer certificate along with your proposal. If you are already registered on our eTendering portal but have forgotten your login details, please contact the portal administrator.

- An evaluation team will evaluate all tenders correctly submitted against the stated evaluation criteria.

- By issuing this Invitation to Tender ORR does not undertake to accept the lowest tender, or part or all of any tender. No part of the tender submitted will be returned to the supplier

Cost & Pricing Information

- Tender costs remain the responsibility of those tendering. This includes any costs or expenses incurred by the supplier in connection with the preparation or delivery or in the evaluation of the tender. All details of the tender, including prices and rates, are to remain valid for acceptance for a period of 90 days from the tender closing date.

- Tender prices must be in Sterling.

- Once the contract has been awarded, any additional costs incurred which are not reflected in the tender submission will not be accepted for payment.

- References

- References provided as part of the tender may be approached during the tender stage

- Contractual Information

Following the evaluation of submitted tenders, in accordance with the evaluation criteria stated in this document, a contractor may be selected to perform the services and subsequently issued with an order.

Any contract awarded, as a result of this procurement will be placed with a prime contractor who will take full contractual responsibility for the performance of all obligations under the contract. Any sub-contractors you intend to use to fulfil any aspect of the services must be identified in the tender along with details of their relationship, responsibilities and proposed management arrangements.

The proposal should be submitted in the form of an unconditional offer that is capable of being accepted by the ORR without the need for further negotiation. Any contract arising from this procurement will be based upon ORR’s standard Terms & Conditions (see Form of Agreement attached). You should state in your proposal that you are willing to accept these Terms & Conditions.

The ORR does not expect to negotiate individual terms and expects to contract on the basis of those terms alone. If you do not agree to the Conditions of Contract then your tender may be deselected on that basis alone and not considered further.

- The ORR may be prepared to consider non-fundamental changes to the standard terms and conditions in exceptional circumstances.  If there are any areas where you feel you are not able to comply with the standard ORR terms and conditions, then details should be submitted as a separate annex to the proposal using the following format:

| - Clause Number | - Existing Wording | - Proposed Wording | - Rational for amendment |
| --- | --- | --- | --- |

Any services arising from this ITT will be carried out pursuant to the contract which comprises of:

- ORR Terms & Conditions;

- Service Schedules;

- this Invite to Tender & Statement of Requirement document; and

- the chosen supplier’s successful tender.

## ORR’s Transparency Obligations and the Freedom of Information Act 2000 (the Act)

- The ORR is a central Government department and as such complies with the Government’s transparency agenda.  As a result, there is a presumption that contract documentation will be made available to the public via electronic means.  The ORR will work with the chosen supplier to establish if any information within the contract should be withheld and the reasons for withholding it from publication.

- Typically the following information will be published:

- contract price and any incentivisation mechanisms

- performance metrics and management of them

- plans for management of underperformance and its financial impact

- governance arrangements including through supply chains where significant contract value rests with subcontractors

- resource plans

- service improvement plans

- Where appropriate to do so information will be updated as required during the life of the contract so it remains current;

- In addition, as a public authority, ORR is subject to the provisions of the Freedom of Information Act 2000.  All information submitted to a public authority may need to be disclosed by the public authority in response to a request under the Act.  ORR may also decide to include certain information in the publication scheme which it maintains under the Act. If a bidder considers that any of the information included in its proposal is commercially sensitive, it should identify it and explain (in broad terms) what harm may result from disclosure if a request is received and the time period applicable to that sensitivity.  Bidders should be aware that even where they have indicated that information is commercially sensitive ORR may be required to disclose it under the Act if a request is received.  Bidders should also note that the receipt of any material marked “confidential” or equivalent by the public authority should not be taken to mean that the public authority accepts any duty of confidence by virtue of that marking.   If a request is received ORR may also be required to disclose details of unsuccessful bids

- Please use the following matrix: to list such information:

| - Para. No. | - Description | - Applicable exemption under FOIA 2000 |
| --- | --- | --- |