Year of the Young People Programme Evaluation

Organisation	Heritage Lottery Fund

Department	Strategy & Business Development

Title of procurement	Year of Young People National Lottery Fund

Brief description of supply	Evaluation Service

Estimated value of tender	£20,000 including expenses, venue hire and VAT

Estimated duration  	June 2018 to January 2020

Name of HLF Contact

Anna James

Grants Development Officer

Year of Young People National Lottery Fund

Anna.James@hlf.org.uk

Timetable	Response deadline:
11.00 am on 11th June 2018	

Clarification questions deadline:
25th May 2018

Clarification meetings:
Monday 25th June

Confirmation of contract:
Week commencing 25th June 2018

Completion of evaluation:
January 2020

# 1.	Overview

  - The Heritage Lottery Fund (HLF) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). Since April 2013 we have been operating under our current Strategic Framework: ‘A lasting difference for heritage and people’. See the HLF website for more details.

  - HLF invests in the full breadth of the UK’s heritage and, through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

  - The Year of Young People National Lottery Fund has been launched in Scotland to mark the 2018 Year of Young People in Scotland – a year that aims to inspire Scotland through our young people: celebrating their achievements; valuing their contribution to communities; and creating new opportunities for young people to shine locally, nationally and globally.

  - The Heritage Lottery Fund, Big Lottery Fund and Sport Scotland, along with Spirit of 2012 Trust have created the Year of Young People National Lottery Fund to award grants for heritage, community and sports projects, that will support young people in Scotland to improve their health and wellbeing.

  - The focus on health and wellbeing covers many different aspects from supporting young people to lead active lives to providing opportunities to learn about and improve mental and physical health.

  - The Year of Young People National Lottery Fund intends to support projects that:

  - Encourage positive mental health for young people

  - Inspire young people to lead active lives

  - Ensure young people are involved in developing, delivering and evaluating these projects to meet their needs, informed by the Year of Young People Codesign Blueprint

  - Celebrate and share young people’s achievements

  - Funded projects are expected to deliver the following outcomes:

  - Young people will have been integral to the design, delivery and evaluation of heritage, sport or community activities and

  - Young people will learn about and improve their mental health and become more resilient and/or

  - Young people will lead healthier more active lives

  - The Year of Young People National Lottery Fund was launched in March 2018. The programme is offering grants of between £3,000 and £10,000 for projects focusing on young people aged between 8 and 26, and there are two deadlines for application – 30 April and 18 June 2018. Decisions will be made in June 2018 and August 2018 respectively. The first batch of grantees is expected to start their projects by July 2018 and the second batch by August 2018. With a total budget of £550,000 the programme is estimated to fund between 40-70 projects. Numbers of projects funded may increase if levels of demand lead to additional budget.

  - Young people have helped develop this programme will be involved in the decision-making process, and should be involved in the evaluation of the programme such as through testing evaluation tools.

  - This brief regards the evaluation of the Year of Young People National Lottery Fund in Scotland.

  - We would like to understand the impact of the programme the outcomes for young people, to what extend this size of project can contribute to young people’s wellbeing, and the opportunities they offer for young people to be integral in the whole project cycle (design/ development, delivery, and evaluation). We are interested in what the programme has enabled organisations to achieve, documenting the benefits of the projects, and how these contribute to achieving the Scottish Government outcomes for the Year of Young People 2018.

  - The primary audiences for the report(s) are organisations involved in heritage, sports and community activities for young people, the Scottish Government and other organisations engaged in the Year of Young People 2018.  We want to identify what works well in engaging young people and why, and develop and pilot evaluation tools for measuring wellbeing which could be used in the future by others in the heritage, sports, and community sectors. Reports will be made available on the HLF website and circulated amongst all participating grantees, the programme funders and the Scottish Government. We would like the evaluation to contribute to the wider body of knowledge related to engaging young people and improving their wellbeing, and welcome plans for contributing to this.

# Purpose of the evaluation

  - The aim of the evaluation is to assess how integral young people were in all phases of the projects and the impact this had on their wellbeing.

More specifically the evaluation will answer the following questions:

- To what extent were young people involved in planning, delivering, managing and evaluating the projects and what has been the impact of their involvement on the young people, the projects and the organisations?

- What have been the most effective ways of involving young people in all aspects of the projects e.g. from the inception of the project to its delivery and evaluation?

- What have the benefits been for young people’s wellbeing in terms of mental health, resilience, and physical health?

# Evaluation approach and methodology

  - A methodology for the work is open for consultants to propose. However, we anticipate that it will include the following:

- Development and piloting of an evaluation tool(s) to be used by grantees to get feedback from young people on the impact of the project. Data should be collected in the beginning, mid and end of the project so that the evaluation process will track progress and measure difference. Collecting data from the young people is regarded as the most important aspect of this evaluation.

- The evaluator to involve young people in the development or at least testing of the evaluation tool e.g. through the involvement of young groups such as the Year of Young people 2018 Ambassadors.

- Development of a flexible tool to get feedback from participants which can be tailored to collect feedback from special groups such as young people for who English is their second language, participants with disabilities etc.

- The provision of training, support and guidance to grantees on how to use the evaluation tool(s) to collect data from young people for analysis at programme level. We expect that the first year of the work will focus on the development of tools and capacity building of the grantees so that they will collect reliable data to feed into the programme evaluation. Grantees are also expected to use this data in their final self-evaluation reports, so grantees will need to understand the relevance of data they are asked to collect to their individual projects.

- Some primary data collection through fieldwork by evaluators (interviews, surveys etc.).

  - We expect detailed information and data to be collected from projects and their participants to develop a framework showing impact of involving young people in all stages of the project and impact on their wellbeing. The types of indicators this framework could include, but not be limited to, are:

  - Visitor numbers

  - Audience profile

  - Measures of increase in wellbeing

  - Measures of enjoyment, inspiration and creativity

  - Development of personal skills and capabilities

  - Volunteers

  - We expect the evaluator to deliver two online workshops e.g. webinar, one for each batch of grantees to present the evaluation framework and provide training on the data collection tool(s). This could be part of the projects start-up meetings.

  - The Bidder will also organise a learning event (at a physical location and online facility) at the end of the programme to share successes and challenges, get feedback/validate the evaluation findings and refine and finalise the evaluation tools so that they could be used in future by other projects.

  - We expect the successful Bidder to be able to align with the Scottish Government Evaluation plan of the Year of Young People 2018 so that the Scottish Government can use the evaluation information in demonstrating how the YoYP has met its overall outcomes. These can be made available to the potential Bidders, on request.

  - The Bidder should use and build/adapt existing methods of measuring wellbeing, taking into consideration those tested in the Scottish context. We do not expect this piece of work to create entirely new methods but to tailor methods for young audiences.

# Outputs

  - The following outputs will be required:

A project plan with specific deliverables* and timetable will be agreed with the successful consultant/ies. However, HLF expects the following deliverables in accordance with the following timetable as a minimum:

| Deliverable/Key Milestones* | Due date |
| --- | --- |
| Inception Meeting to agree plans, including reporting structures, learning events and a communication and dissemination strategy. | TBC |
| Make arrangements to contact all grantees from both batches | Within 10 working days of contract start date to contact first batch of grantees and at the beginning of their project to contact second batch of grantees |
| Develop and pilot evaluation tool(s) | June-July 2018 |
| Organise and run workshops for grantees to present evaluation framework and deliver training on data collection tools. | July/ August and September 2018 |
| Organise and facilitate one learning event at the end of the programme | December 2019 |
| A short interim report including update of the evaluation process and a draft evaluation toolkit on measuring wellbeing with structure agreed with HLF. | May 2019 |
| A final report, of 40 pages maximum including the analysis and findings of the overall evaluation, top tips on how to make young people integral to your project and final evaluation toolkit on measuring wellbeing (in the Appendix). The structure to be agreed with HLF. | January 2020 |

The above represents our minimum requirements.

* HLF reserves the right to amend this timetable where required.

  - All reports must adhere to HLF’s accessibility and formatting guidance (appended).

  - The initial findings will be confidential to HLF. HLF may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

  - All reports to include appendices as agreed between HLF and the contractor. The contents and structure of the report to be agreed in advance of writing. All reports to be supplied in electronic format and hard copy if requested.

  - All Bidders are required to adhere to all appropriate regulations and guidelines on the collection, storage, transmission and destruction of personal data (MRS/SRA, Data Protection Act 1998: Guidelines for Social Research, April 2013).

  - The successful Bidder will be expected to discuss and present findings at appropriate times, to internal and external audiences, including HLF, Big Lottery Fund, Sport Scotland, Spirit of 2012 Trust, Scottish Government, Grantees, policy makers and other external stakeholders. The purpose of these presentations is to enable lessons to be learned and demonstrate the impact and value of the YoYP National Lottery Fund.

  - We expect all projects we fund to adhere to the Social Research Association (SRA) ethical guidelines.  If your proposal raises particular ethical issues, you must indicate what they are and what your strategy for addressing them is.

# Contract management

  - We expect the evaluation to begin June 2018 and be completed by January 2020. The final report shall be submitted to HLF by the end of January 2020.

  - The anticipated budget is up to £20,000 to include all expenses and VAT. HLF will not fund travel expenses for grantees and we expect the contractor to budget for venue hire, refreshments and facilitation. Value for money when choosing venues should be a consideration. The contract will be let by the National Heritage Memorial Fund.  Payments will be made in three equal instalments.  The first payment will be made upon signing of the contract and inception meeting. The second one upon receipt of the 2019 interim report, and the final payment upon HLF’s receipt of an approved final copy of the report in January 2020.

  - The contract will be based on the HLF standard terms and conditions.

  - The research will be managed on a day-to-day basis for HLF by Anna James.

# Award Criteria

  - A proposal for undertaking the work should be a maximum of 15 pages and include:

- a detailed methodology for undertaking the study;

- details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects. The project manager / lead contact should be identified;

- the allocation of days between members of the team;

- the daily charging rate of individual staff involved;

- a timescale for carrying out the project;

- an overall cost for the work.

  - Your Bid will be scored out of 100%.

- 70% of the marks will be awarded to Quality

Each question will be scored using the methodology in the table below.

Tender responses submitted will be assessed by HLF against the following Quality Questions:

| Demonstration/Quality questions | Weighting |
| --- | --- |
| - Demonstrated a clear understanding of the aims, objectives and main concerns of the evaluation. | Weighing 10% |
| - Demonstrated an awareness of the different policy contexts, evaluation and issues relating to wellbeing and involving young people. | Weighting 5% |
| - Demonstrated experience of hosting capacity building workshops and learning events. | Weighting 5% |
| - Demonstrate the Bidder has experience and capacity of evaluating projects that involve young people, and measuring wellbeing | Weighting 30% |
| - Demonstrated the Bidder has the capacity and resources to carry out the evaluation within the timescale, or if working in partnership, each organisation has the capacity to fulfil its role and roles of each partner is clear. | Weighting 30% |
| - Demonstrated a clear and realistic project plan, showing phases of the evaluation, tasks for each phase and roles and responsibilities for each member of the team. Within this plan consideration should be given to plans to keep grantees engaged with the evaluation, for its duration. | Weighting 15% |
| - Demonstrated well considered plans for dissemination of evaluation findings. | Weighting 5% |

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the HLF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the HLF confidence in the ability of the Bidder to deliver the contract. Meets the HLF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the HLF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the HLF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in most respects. |

30% of marks will be awarded for Price.

Price: The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A

## Price Criterion at 30%

- 30 marks will be awarded to the lowest priced bid and the remaining Bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced Bidder gets 30% (full marks) for price and the second placed Bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30-2.4 = 27.6 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Lottery Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £500 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£300 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £200 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the HLF | e.g. 0.5 | 1 | 1.5 | 3 | 850 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Notes: 	HLF reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. HLF also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition

# Procurement Process

  - HLF reserves the right to reject abnormally low tenders. HLF reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be:

Deadline for clarification questions*: 25 May 2018

Tender return deadline: completed proposal to be returned to HLF by 11.00 am on 11 June 2018.

Clarification meetings** may be held with shortlisted consultants and would take place on week commencing 18 June 2018

HLF will notify Bidders of our procurement decision week commencing: 25 June 2018.

*HLF will upload responses to clarification on our website, here.  Please note that we will make the anonymised questions, and our responses to them, available to everyone on the HLF website.

**We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting Bidders to attend a clarification meeting.  In order to ensure that both HLF’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring Bidders to attend a clarification meeting.  Scores will be moderated based on any clarifications provided during this meeting.  You are responsible for all your expenses when attending such meetings.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 11.00 am on 11 June 2018 to the following contact:

Anna James

Grants Development Officer

Year of Young People National Lottery Fund

Anna.James@hlf.org.uk

  - Please visit the HLF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

HLF is committed to providing a website that is accessible to the widest possible audience. Our website is annually tested by accessibility auditors and we must meet the WCAG 2.0 AA compliance level. Our accessibility testing covers all of our content, including downloadable documents, as well as the design and functionality of the site.

Reports and other documents created for HLF (including the tender submissions) need to be clear, straightforward to use, and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Tips for creating accessible documents can be found below. However, we strongly recommend referring to the RNIB, Gov.uk and WebAIM for more detailed information.

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

### Formatting

Headings and content in your document should be clearly identified and consistently formatted, to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content.

### Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

### Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

### Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

### Tables

These should be for used for presenting data and not for layout or design. They should also be simple, and include a descriptive title.

### Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

### Acknowledgement

All reports should acknowledge HLF. Our logo can be found on the HLF website.

## Further resources

Please refer to the WCAG 2.0 article on PDF techniques for further information.

Submitting your report to HLF

Please check the accessibility of your document using the Word accessibility checker before submitting: File – Info – Check for Issues – Check Accessibility.

Please submit your document as a Word file.

HLF retains the right to amend documents in order to create accessible versions for publishing.