| Work Package | Requirement | Contract Deliverable | Date Required | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 1.0 Fade Brake Testing |  |  |  |  |
| 1.1 Develop Test Plan | Test plan required to document fade brake testing to be conducted on qty 9 FUCHS vehicles against requirements of Construction & Use Regulations 1986 and all associated EC directives, schedules, references and legislation applicable to an N3 vehicle as at the In Service Date of 1991 as per the recommendation in FUCHS Legislative Compliance Assessment. Test plan should document as a minimum: - Background and objective of testing being conducted; - Applicable legislation, directives and references; - Test standards being adhered to; - Quality management plan; - Testing risk register; - Test equipment; - Test conditions; - Test schedule. | Fade Braking Test Plan | No later than 2 weeks (14 days) from contract award. | Test plan delivered which meets requirement set out in this document and formal written approval provided by the Authority within 10 working days. |
| 1.2 Conduct Testing | Testing to be conducted at premises provided by the Contractor on qty 9 FUCHS Area Survey & Reconnaissance vehicles on a rolling basis based on a schedule to be delivered by the Contractor and agreed by the Authority. Vehicles will be provided fully fit and with driver (and commander if required). Testing to be carried out as per test plan at line item 1.1. | Completion of fade brake testing | Testing to commence no later than 5 working days after receipt of written approval of test plan from the Authority and should be complete within 10 working days. | Testing performed in accordance with test plan at 1.1. |
| 1.3 Deliver Test Report | Test report to be provided no later than 2 weeks from the last day of testing being conducted. Test report will include as a minimum: - Full report of testing conducted; - Test results; - Interpretation of test results against applicable legislation; - Statement of pass or failure; - In the instance of test failure, explanation of likely causes and suggested remedies; - Length of validity of results; - Recommendations (if applicable). | Fade Braking Test Report | 2 weeks from last day of testing. | Test report delivered which meets requirement set out in this document and formal written approval provided by the Authority within 10 working days. |
| 1.4 Deliver Test Findings | Option to request presentation of test findings to Authority by contractor on mutually convenient date at location to be decided by Authority. |  | No later than 10 working days from written acceptance of Test Report from the Authority. |  |
| 1.5 Re-test | Option to re-test any vehicles that fails initial brake fade test subsequent to implementation of recommendations in Test Report (1.4 (e)). Re-test to be followed by production of Test Report as at 1.3. |  | Re-test to be completed no later than 20 working days after implementation of any recommendations/engineering works by the Authority. | Testing performed in accordance with test plan at 1.1 and Test Report delivered as at 1.3. Test report delivered which meets requirement set out in this document and formal written approval provided by the Authority within 10 working days. |