## DEFCON Obligations (Authority)
ANNEX R TO CONTRACT ARTYSYS/00286
Official Sensitive - Commercial
Elective and Candidate Change Register (ECCR)
Contract Title: FC BISA MLU
Contract Number: ARTSYS/00286
DEFCON NUMBER | DEFCON NAME | EDITION | CLAUSE NUMBER | RESPONSIBILITY | OBLIGATION OR ACTION | ADDITIONAL COMMENTS | DATE REQUIRED | PERSON RESPONSIBLE FOR DELIVERY | PERSON RESPONSIBLE FOR RECEIPT | DATE DELIVERED/CONFIRMED | EVIDENCE AT [FILE REF & ENCL]
14 | Inventions And Designs Crown Rights And Ownership Of Patents And Registered Designs | 11/05 | 10 | Authority & Contractor | If between Authority and Contractor, contention arises over Contractor or Crown employee (whether partial or not) invention or design under this condition, it shall fall to a mutually agreed decider or at default of such agreement as appointed by the President of CIPA and shall be final and conclusive | - | If required | Mutually agreed decider or President of CIPA | Contractor & Authority
15 | Design Rights And Rights To Use Design Information. Note: This Condition is applicable to Authorityifications only | 02/98 | 11 | Authority | In the event that the Contract does not cover initial production the Authority will give consideration to placing any first production order for Articles with the Contractor provided that he can offer satisfactory price, delivery and other terms | - | Consideration for initial production | Authority Commercial or Project | Contractor Commercial or Project
15 | Design Rights And Rights To Use Design Information. Note: This Condition is applicable to Authorityifications only | 02/98 | 12 | Authority | Upon request of Contractor, ensure they are provided with a copy of all Information in relation to any Authorityification. The Authority shall grant or procure for the Contractor the right to be granted a licence to use, have used and sub-license in any part of the world any Intellectual Property covering such Information for the purposes of manufacturing, selling and supporting any Article on fair and reasonable terms | - | If Authorityification required and not undertaken by contractor | Authority Commercial or Project | Contractor Commercial or Project
15 | Design Rights And Rights To Use Design Information. Note: This Condition is applicable to Authorityifications only | 02/98 | 14 | Authority | Ensure that Information released to any third party under is limited to that necessary for the task the third party is engaged. | - | Upon release of information | Authority Commercial or Project | N/A
15 | Design Rights And Rights To Use Design Information. Note: This Condition is applicable to Authorityifications only | 02/98 | 15 | Authority | Ensure all disclosures of Information to third parties shall be under express conditions of confidentiality, and shall procure, at the request of the Contractor, a direct confidentiality agreement in the form of DEFFORM 94. | - | At the request of the Contractor upon release of information | Authority Commercial or Project | Contractor Commercial or Project
15 | Design Rights And Rights To Use Design Information. Note: This Condition is applicable to Authorityifications only | 02/98 | 16 | Contractor & Authority (any government department) | At any time whilst under contract the contractor is required to retain information, the contractor shall provide assistance. Such assistance shall be limited to that required to enable a third party to interpret any Information supplied. The Contractor shall be entitled to payment on fair and reasonable terms for assistance | - | At the request of the Authority | Contractor Commercial or Project | Authority Commercial or Project (other government department)
15 | Design Rights And Rights To Use Design Information. Note: This Condition is applicable to Authorityifications only | 02/98 | 17 | Contractor & Authority (any government department) | Any information marked with copyright and/or other restrictive legend provided that the legend acknowledges the Authority's rights under this Condition including Authority made copies | - | As Required | Contractor Commercial or Project | Authority Commercial or Project (other government department)
16 | Repair And Maintenance Information | 10/04 | 9 | Authority | The Contractor shall be entitled to claim payment under the provisions of S55-59 of the PA 1977 or the First Schedule to the RDA 1949 in respect of any patented invention or registered design owned by the Contractor and used in the exercise of the rights granted under Clauses 4 and 5 of this Condition. (monitoring and evaluation, ISS, JTTE, Disposal, Operation and Sales) | - | If Required | Authority Commercial or Project | Contractor Commercial or Project
16 | Repair And Maintenance Information | 10/04 | 11 | Authority | Where an order is to be placed for repair, reworking or reconditioning outside the Authority, the Authority undertakes to invite the Contractor to tender provided that he is still eligible to perform such work | - | In the event that the Contract does not provide for repair, reworking or reconditioning of Articles | Authority Commercial or Project | Contractor Commercial or Project
16 | Repair And Maintenance Information | 10/04 | 13 | Authority | The Authority shall ensure Information released to any third party is limited to that necessary for the task on which the third party is engaged. | - | upon release of information | Authority Commercial or Project | Third Party
16 | Repair And Maintenance Information | 10/04 | 14 | Authority | Ensure all disclosures of Information to third parties shall be under express conditions of confidentiality, and shall procure, at the request of the Contractor, a direct confidentiality agreement in the form of DEFFORM 94. | - | at the request of the Contractor upon release of information | Authority Commercial or Project | Contractor Commercial or Project
16 | Repair And Maintenance Information | 10/04 | 15 | Contractor & Authority (any government department) | At any time whilst under contract the contractor is required to retain information, the contractor shall provide assistance. Such assistance shall be limited to that required to enable a third party to interpret any Information supplied. The Contractor shall be entitled to payment on fair and reasonable terms for assistance | - | At the request of Authority | Contractor Commercial or Project | Authority Commercial or Project
16 | Repair And Maintenance Information | 10/04 | 16 | Contractor & Authority (any government department) | Any information marked with copyright and/or other restrictive legend provided that the legend acknowledges the Authority's rights under this Condition including Authority made copies | - | As Required | Authority & Contractor | Authority & Contractor
23 | Special Jigs, Tooling and Test Equipment | 08/09 | 15 | Authority | Give disposal instructions from receipt of Contractor's notification that the Special Jigs, Tools etc. cease to be required | - | Within 3 months of receipt | Authority Commercial or Project | Contractor Commercial or Project
68 | Supply Of Data For Hazardous Articles, Materials and Substances | 02/17 | 2 | Authority | Report new information regarding hazardous properties of the substance or any information that might call into question the appropriateness of the risk management measures in writing to the Contractor | - | When he becomes aware | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 2 a-b | Authority | Provision of facilities, including land | - | As per GFA Register | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 5a | Authority | The Authority shall accept liability where any such loss or damage was caused or contributed to by any act, neglect or default of any Government Servant. | - | On occurrence of such damage | Authority Commercial or Project | N/A
76 | Contractor's Personnel at Government Establishments | 12/06 | 5b | Authority | Receipting of Contractor property taken on charge | - | On occurrence of such damage | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 7 | Authority | Approval of Contractor Representatives and issue of passes for Representatives for admission to Government Establishment | Representatives are subject to approval as per Clause 6 to DEFCON 76 | On the day of arrival to the Government Establishment | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 10b | Authority | Provision of security related information to Contractor | - | On request | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 10e | Authority | Provision of on-ship rules and regulations | - | On request | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 11 | Authority | Where applicable transport for overseas work from the United Kingdom to the place of duty and local transport overseas whenever possible provided free of charge | - | As required | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 12 | Authority | Provide out-patient medical treatment given to the Contractor's Representatives by a Service Medical Officer or other Government Medical Officer at a Government Establishment overseas free of charge | - | As required | Wider Ministry of Defence | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 16b | Authority | Notification of Health and Safety Hazardous Issues | - | As required | Authority Commercial or Project | Contractor Commercial or Project
76 | Contractor's Personnel at Government Establishments | 12/06 | 16e | Authority | Provision of Health and Safety policies, risk assessments, notices and instructions | - | When a Contractor enters a Government Establishment | Authority Commercial or Project | Contractor Commercial or Project
90 | Copyright | 11/06 | 3 | Authority & Contractor | The Contractor agrees not to publish any copyright work generated under the Contract without Authority consent. The Authority will not object unless delay is considered necessary in the national interest (reviewed on request). | - | On Request | Both Commercial or Project Teams | Both Commercial or Project Teams
90 | Copyright | 11/06 | 4 | Authority | The Authority cannot give copy of work to third party unless permission given by Contractor for the purpose of b) to a supplier or potential supplier (providing under disclosure restriction) or c) to governments and nations for the exchange of information for information only, contained in contract for defence information exchange agreements (providing under a non disclosure agreement) | Unless as in Clause 5 of this Condition | In relation to sharing any copyright work | Both Commercial or Project Teams | Both Commercial or Project Teams
90 | Copyright | 11/06 | 6 | Authority & Contractor | In making copies of copyrighted works must acknowledge Authority rights | - | When making copies of copyrighted works | Contractor Commercial or Project | Authority Commercial or Project
91 | Intellectual Property Rights In Software | 11/06 | 6a | Authority | Hold Deliverable Software in confidence, enforce regulations to preserve its confidential nature and not disclose outside of UK Government entities unless expressly agreed | - | Upon Software delivery | Both Commercial or Project Teams | Both Commercial or Project Teams
91 | Intellectual Property Rights In Software | 11/06 | 6b | Authority | Ensure recipient enters into a confidentiality agreement and only be for the purpose of UK government services. Consult Contractor and consider Contractor proposals for protection of trade secrets | - | Before disclosing any Deliverable Software outside United Kingdom Government Departments | Authority Commercial or Project | Contractor Commercial or Project
91 | Intellectual Property Rights In Software | 11/06 | 6d | Authority | Must ensure recipient is under obligation of confidence and a limitation of use | - | If disclosing software for national interest | Authority Commercial or Project | Contractor Commercial or Project
91 | Intellectual Property Rights In Software | 11/06 | 8 | Authority | Copies of Software shall perpetuate any contract notice relating to the Authority included by the contractor in the software | - | Making copies of deliverable software | Authority Commercial or Project | Contractor Commercial or Project
91 | Intellectual Property Rights In Software | 11/06 | 11b | Authority | Authority shall promptly notify Contractor of cost and provide information as required. Authority shall not make any statement that may prejudice the result of the claim without contractor consent (unless statutorily obliged) | - | In event of claim against Authority as described in 11a | Authority Commercial or Project | Contractor Commercial or Project
91 | Intellectual Property Rights In Software | 11/06 | 11b | Authority & Contractor | Allow at Contractor expense Contractor to negotiate and litigate with Authority assistance. PROVIDING: unconditional admission of liability to indemnify by Contractor. Contractor must keep Authority informed regarding proceedings | - | At the Contractor's request | Both Commercial or Project Teams | Both Commercial or Project Teams
91 | Intellectual Property Rights In Software | 11/06 | 11f | Authority | Authority shall indemnify the Contractor in respect of costs incurred as a result of direct or indirect proposed or actual infringement for Authorityification, copying, possession or use of Authorityified deliverable software not under direction or control of the contractor | - | In event of claim against Contractor for Authority or third party Authorityification | Authority Commercial or Project | Contractor Commercial or Project
91 | Intellectual Property Rights In Software | 11/06 | 11g | Authority | Authority shall indemnify the contractor in respect of costs incurred as a result of direct or indirect proposed or actual infringement as a result of the copying, Authorityification, use or possession for the purposes of the contract, Software that was not originally given to the Authority by the Contractor | - | In event of claim against Contractor | Authority Commercial or Project | Contractor Commercial or Project
126 | International Collaboration | 11/06 | 2 | Authority & Contractor | Under an International Collaboration Agreement the Contractor must provide the Authority with assistance and information as reasonably require for promotion and technical oversight. A reasonable charge for this service, will be borne by the Authority | The period refered to in this clause shall e seven years or until OSD, whichever is longer | If requested by Authority | Contractor Commercial or Project | Authority Commercial or Project
126 | International Collaboration | 11/06 | 7 | Authority | The Authority will consult with Contractor early and frequently regarding potential ICA's he may want to enter | - | Before entering into an International Collaboration Agreement | Authority Commercial or Project | Contractor Commercial or Project
129 | Packaging (For Articles Other Than Munitions) | 11/16 | 5b | Authority | Indicate in the Contract the standard or level of Packaging required for each Article | - | Before Delivery | Authority Commercial or Project | Contractor Commercial or Project
502 | Specification Changes | 05/17 | 6 | Authority | Provide changes in writing and provide an updated Specification to the Contractor | These alterations shall not constitute a formal amendment | When change is identified | Authority Commercial or Project | Contractor Commercial or Project
502 | Specification Changes | 05/17 | 8 | Authority & Contractor | Notify the other party in writing if either party considers there may be a conflict within the Specification | - | Immediately, upon identification | Authority & Contractor | Authority & Contractor
503 | Formal Amendments to Contract | 12/14 | 1 | Authority & Contractor | Provide written agreement to changes | - | Once Formal Amendment to Contract has been proposed | Authority & Contractor | Authority & Contractor
513 | Value Added Tax | 11/16 | 4 | Authority & Contractor | Authority must assess and pay HMRC for UK output VAT for deliverables. Contractor must monitor legal requirement to register for VAT | - | Where Contractor not required to register for UK VAT | Authority & Contractor Commercial | Authority Commercial
513 | Value Added Tax | 11/16 | 5 | Authority | Where Contractor liable to pay non UK VAT, Authority must pay the sum within 30 days of Contractor written request | - | When deliverables supplied outside UK | Authority Commercial or Project | Contractor Commercial
513 | Value Added Tax | 11/16 | 7 | Authority & Contractor | Authority to pay VAT as assessed by HMRC. Contractor shall pay any interest charged or penalties directly to HMRC and are non recoverable from the Authority. | - | In event of Contractor VAT miscalculation | Authority Commercial | HMRC
515 | Bankruptcy and Insolvency | 02/17 | 1 | Authority | Provide written notice of summary determination of the Contract | - | At any time upon occurrence of events outlined in Clause 1 to Condition | Authority Commercial | Contractor Commercial
518 | Transfer | 02/17 | 1 | Authority & Contractor | Provide prior written consent to transfer of all or part of the Contract | - | Upon request to Transfer Contract | Authority & Contractor Commercial | N/A
520 | Corrupt Gifts and Payments of Commission | 02/17 | 3 | Authority | In exercising its rights or remedies under this Condition, the Authority shall act in a reasonable and proportionate manner | - | Upon date at which the Contract becomes effective, for the duration of the performance period of the Contract | Authority & Contractor Commercial | N/A
522 | Payment and Recovery of Sums Due | 11/17 | 2 | Authority | Where the Contractor submits an invoice to the Authority in accordance with clause 1, the Authority will consider and verify that invoice in a timely fashion | DEFCON 522 Clause 1 requires the Contractor to submit invoices through CP&F | Upon receipt of Contractor's invoice, in accordance with DEFCON 522, Clause 1 | Authority Commercial | Contractor Commercial
522 | Payment and Recovery of Sums Due | 11/17 | 3 | Authority | Authority to pay all sums due within 30 days from the date the Authority has determined an invoice is valid and undisputed | - | Upon Valid & undisputed Request | Authority Commercial | Contractor Commercial
525 | Acceptance | 10/98 | 1a | Authority | To inform the Contractor of their rejection of any item within 10 business days |  | Within 10 business days of delivery | Authority Project | Contractor Project
526 | Notices | 08/02 | 1 | Authority & Contractor | Notices shall conform as specified in the Clause | - | For the duration of the Contract | Authority Commercial or Project | Contractor Commercial or Project
526 | Notices | 08/02 | 2 | Authority & Contractor | Notices to be delivered as specified in the Clause | - | For the duration of the Contract | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
528 | Import and Export Licences | 05/17 | 1 | Authority & Contractor | Contractor shall apply for import/export licence. Authority shall provide information, documentation and assistance as necessary | - | When importing or exporting on behalf of Authority (within uk) | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
528 | Import and Export Licences | 07/17 | 7 | Authority & Contractor | The Authority will pay the Contractor a fair and reasonable charge | - | When the Authority evokes Clause 5 or 6 | Authority Commercial or Project | Contractor Commercial or Project
528 | Import and Export Licences | 07/17 | 9 | Authority | The Authority shall provide the Contrator with sufficient information and reasonable asssitance to facilitate the granting of export or import licences by a Foreign Government |  | During performance of the contract | Authority Commercial/ Project | Contractor Commercial or Project
528 | Import and Export Licences | 07/17 | 10 | Authority | The Authority shall provide the Contractor assistance in obtaining UK export licences where necessary for the performance of the contract |  | During performance of the contract | Authority Commercial/ Project | Contractor Commercial or Project
528 | Import and Export Licences | 07/17 | 16 | Authority & Contractor | Contractor shall immediately inform the Authority by issuing an updated DEFFORM 528. Within 20 working days of such notification, the Contractor shall propose to the Authority actions to mitigate the impact of such restrictions. Such proposals may include, where appropriate, mutually supported attempts to obtain removal or Authorityification to the restrictions or to obtain appropriate authorisations from the relevant foreign government. The Authority shall notify the contractor within 20 working days of receipt of a proposal whether it is acceptable and where appropriate the Contract shall be Authorityified in accordance with its terms to implement the proposal. | - | Where Change identified by subcontractor, supplier or third party or the contractor themselves | Contractor Commercial or Project | Authority Commercial or Project
528 | Import and Export Licences | 07/17 | 19 & 20 | Authority | The Authority shall use reasonable endeavours to identify any export control restrictions applying to materiel to be provided to the Contractor as GFA. the Authority shall provide a completed DEFFORM 528 or will provide a new or updated DEFFORM 528 to the Contractor within 30 working days of the date of knowledge and in any case not later than 30 working days prior to the delivery of such materiel to the Contractor. | - | Where Authority is to provide materiel necessary to enable the Contractor to perform the Contract, and that materiel is subject to a non-UK export licence, authorisation, exemption or other related transfer or export control (repeat process where disclosure incomplete or inaccurate) | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
528 | Import and Export Licences | 07/17 | 21 | Authority & Contractor | The Authority and the Contractor shall act promptly to mitigate the impact of such restrictions or incorrect or inaccurate information. Including, where appropriate, mutually supported attempts to obtain removal or Authorityification to the restrictions or to obtain appropriate authorisations from the relevant foreign government. | - | Where: a. restrictions are advised by the Authority to the Contractor in a DEFFORM 528 provided pursuant to Clause 19 or 20 or both; or b. any of the information provided by the Authority in any DEFFORM 528 proves to be incorrect or inaccurate, | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
530 | Dispute Resolution (English Law) | 12/14 | 2 & 3 | Authority & Contractor | Mustgive other party written notice staing that the dispute is referred to arbitration and the particulars of the Contract out of which/in relation to which the dispute has arisen | Must state that dispute is referred to arbitration and the particulars of the Contract out of which/in relation to which the dispute has arisen | When a dispute arises and cannot be resolved by negotiations and parties have ageed to escalate to arbitration | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
531 | Disclosure of Information | 11/14 | 2a-d | Authority & Contractor | Treat information in confidence, shall not disclosure information to third party without written consent, shall not use information otherwise than the purpose of the contract and shall not copy any of the information except to the extent necessary for the purpose of exercising its rights of use and disclosure | Obligation does not apply to any Information as outlined in Clause 5a-c of this DEFCON Information includes oral disclosures where they are confirmed in writing within 10 business days | For the duration of the Contract and applicable during in the tender or negotiations prior to contract award | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
531 | Disclosure of Information | 11/14 | 9 | Authority | Consult the Contractor where the Authority is considering disclosure of Information under the FOI Act or EIR Regulations and provide prior notification to the Contractor of any decision to disclosure Information | To the extent permitted by the time for compliance under the FOI or EIR Act or Regulations Information includes oral disclosures where they are confirmed in writing within 10 business days | As required | Authority Commercial or Project | Contractor Commercial or Project
532A | Protection of Personal Data (Where Personal Data is not being processed on behalf of the Authority) | 06/10 | 2 | Authority & Contractor | Comply with obligations as a Data Controller under the Data Protection Act 1998, andsubsequent legislation and regulations, including but not limited to General Data Protection Regulation (GDPR) | The expression "Data Controller" shall have the same meaning as in the Act | For the duration of the Contract | Authority & Contractor Commercial or Project | Authority & Contractor Commercial or Project
538 | Severability | 06/02 | 1b | Authority & Contractor | Use all reasonable endeavours to replace the invalid, illegal or unenforceable provision by a valid, legal and enforceable substitute provision | Where any provision of the Contract is held to be invalid, illegal or unenforceable | As required | Authority & Contractor Commercial /Project | Authority & Contractor Commercial /Project
539 | Transparency | 08/13 | 3 | Authority | Redact any information that would be exempt from disclosure, including the Contractor Commercially Sensitive Information | If subject to request under FOI Act or EIR Regulations | Where applicable for FOI or EIR requests | Authority Commercial & Project | General Public
566 | Change Of Control Of Contractor | 10/16 | 4 | Authority | Consider notice of change of control and advise of any concerns | - | If Required | Authority Representatives | Contractor Commercial
566 | Change Of Control Of Contractor | 10/16 | 5 | Authority | Give written notice of termination of Contract | - | Within six months of being notified of change of control, as per Clause 1 to this DEFCON | Authority Commercial | Contractor Commercial
595 | General Purpose Automatic Test Equipment Data Requirements | 02/16 | 2 | Authority | Pay a fair and reasonable price based on the actual work involved for the supply of test data | - | As required | Authority Commercial/Project | Contractor Commercial/Project
611 | Issued Property | 02/16 | 5 | Authority | Replace, re-issue or authorise repair of Issued Property and, if appropriate, revise the Contract Price, delivery schedule or both | Where Issued Property is agreed to be defective, or deficient | Within a reasonable time of receipt of any notice under Clause 3 of this Condition | Authority Commercial /Project/Supply Chain Manager | Contractor Project
611 | Issued Property | 02/16 | 5 | Authority | Issue written instructions for the return or disposal of the defective or deficient Issued Property | If appropriate, where Issued Property is agreed to be defective or deficient | As appropriate | Authority Commercial /Project/Supply Chain Manager | Contractor Project
611 | Issued Property | 02/16 | 10 | Authority | Notify the Contractor of the value of the Issued Property | Where practicable, before delivery of the Issued Property | Within a reasonable time of request | Authority Commercial | Contractor Commercial
611 | Issued Property | 02/16 | 14 | Authority | Provide disposal instructions | If no disposal instructions are specified in the Contract | Within two months of Contractor's written request | Authority Commercial /Project | Contractor Commercial /Project
620 | Contract Change Control Procedure | 06/14 | 2a-b | Authority | Serve a Notice on the Contractor | Set out the change required to the Contractor Deliverables in sufficient detail | Upon identification of the Change | Authority Commercial /Project | Contractor Commercial /Project
620 | Contract Change Control Procedure | 06/14 | 4a(1) | Authority | Evaluate the Contractor Change Proposal | - | As soon as practicable, after receipt of Contractor Change Proposal | Authority Commercial /Project | Contractor Commercial /Project
620 | Contract Change Control Procedure | 06/14 | 4b | Authority | Indicate acceptance of Contractor Change Proposal by issuing a numbered amendment letter or serve a notice rejecting the Contractor Change Proposal | - | As soon as practicable | Authority Commercial | Contractor Commercial /Project
621A | Transport (If The Authority Is Responsible For Transport) | 06/97 | 2 & 3 | Authority | All Customs clearance shall be the responsibility of the Transport Officer | (for overseas consignments only) Articles rmust be accompanied byTransit Documentatispecified by the Transport Officer | When the Articles required under the Contract are ready for delivery | Authority Transport officer | Contractor Project or Commercial
624 | Use of Asbestos | 11/13 | 5 | Authority | Determine whether the substance would be suitable for incorporate into any Articles or material which have yet to be supplied | - | Where applicable | Authority Project | Contractor Commercial /Project
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 3 | Authority & Contractor | Upon allegation of infringement of usual COTS item under contract Authority (subject to third party agreement) shall give exclusive conductors of negotiation, settlement and litigation. The Contractor shall indemnify the Authority against any costs (contains caveats) | - | Upon identification of allegation of COTS item infringing 3rd party rights | Contractor Commercial and Authority Commercial | N/A
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 8 | Authority | The Authority shall indemnify the Contractor for costs, as a result of infringement of Patent, Utility Authorityel or Registered Design by the Contractor in the performance of the Contract when infringement arises by reason of following any specification, SOW or instruction in the Contract or using, keeping or disposing of any item given by the Authority for the purpose of the Contract | - | If Contractor infringes Third Party right as a result of Authority mistake | Authority Commercial/Project | Contractor Commercial /Project
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 13 | Authority | The Authority shall assume all liability and indemnify the Contractor against liability, including costs as a result of: a) infringement or alleged infringement by the Contractor of any copyright, database right, design right in respect of any item provided by the Authority for the purpose of the Contract b) alleged misuse of any confidential information, trade secret or the like by the Contractor as a result of use of information provided by the Authority for the purposes of the Contract, but only to the extent that Contractor’s use of that information is for the purposes intended when it was disclosed by the Authority | - | If Contractor infringes Third Party rights at the fault of the Authority | Authority Commercial/Project | Contractor Commercial /Project
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 14c | Authority & Contractor | The affected party shall notify promptly notify the other if a claim is brought relating to an infringement subject to an indemnity | Including details of claim | If an action is brought against either party | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 14d | Authority & Contractor | The party benefiting from the indemnity or authorisation shall allow the other party, at its own expense, to conduct any negotiations for the settlement of the litigation that may arise therefrom and shall provide such information as the other party may reasonably require. | - | If an action is brought against either party | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 14e | Authority & Contractor | Following a notification under sub-Clause 14.c., the party notified shall advise the other party in writing within 30 days whether or not it is assuming conduct of the negotiations or litigation. In that case the party against whom a claim is made or action brought shall not make any statement which might be prejudicial to the settlement or defence of such a claim without the written consent of the other party. | - | If an action is brought against either party | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 14f | Authority & Contractor | The party conducting negotiations for the settlement of a claim shall, if requested, keep the other party fully informed on the negotiations | - | As requested | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
632 | Third Party Intellectual Property – Rights and Restrictions | 08/12 | 15 | Authority & Contractor | As a result of the provision of any item by the Contractor to the Authority, the Contractor may at its own expense replace the item with an item of equivalent functionality and performance so as to avoid infringement or breach; b) The parties will co-operate with one another to mitigate any claim or damage which may arise from use of third party intellectual property rights. | - | Any time a claim or allegation of infringement arises in respect of copyright, database right, design right or breach of confidence | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
642 | Progress Meetings | 06/97 | 1 | Authority & Contractor | Attend progress meetings | - | As specified in Condition 9 to the Contract | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
649 | Vesting | 12/16 | 8 | Authority | Shall pay a fair and reasonable price for any Article or materiel in which it has elected to retain the property under Clause 5 of this Condition | - | When Re-vesting Articles or Materiel under Clause 5 | Authority Commercial/Project | Contractor Commercial /Project
658 | Cyber | 10/17 | 2.1.1 | Authority | Determine Cyber Risk Level appropriate to this Contract | - | Prior to Contract Award and for the duration of the Contract | Authority Commercial/Project | Contractor Commercial /Project
658 | Cyber | 10/17 | 2.1.2 | Authority | Notify the Contractor where the Authority reassesses the Cyber Risk Level of the Contract | - | As soon as reasonably practicable | Authority Commercial/Project | Contractor Commercial /Project
658 | Cyber | 10/17 | 5 | Authority | Use reasonable endeavours to ensure that the conduct of each audit does not unreasonably disrupt the Contractor or delay the provision of Contractor Deliverables | Information received in connection with the audit shall be treated confidentially | During any audits directed by the Authority | Authority Commercial/Project | Contractor Commercial /Project
658 | Cyber | 10/17 | 5 | Authority | Provide 15 calendar days notice of its intention to conduct an audit | - | As required | Authority Commercial/Project | Contractor Commercial /Project
658 | Cyber | 10/17 | 5 | Authority & Contractor | Bear own respective costs and expenses incurred in respect of compliance with obligations under this Condition for audits | If the audit identifies a material breach of the terms of this condition, in which case the Contractor shall reimburse the Authority for all reasonable costs incurred | As required | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
658 | Cyber | 10/17 | 6 | Authority | Act in a reasonable and proportionate manner in exercising its rights or remedies under this Condition and given all due consideration to action other than termination where appropriate | - | For the duration of the Contract | Authority Commercial/Project | Contractor Commercial /Project
670 | Tax Compliance | 02/17 | 8 | Authority | In exercising its rights or remedies under this Condition, the Authority shall act in a reasonable and proportionate manner | Taking into account: gravity and duration of OOTNC and sanctions imposed by court or tribunal and any remedial action taken by the Contractor to prevent reoccurrence of the OOTNC | Upon identification of an OOTNC | Authority Commercial/Project | Contractor Commercial /Project
801 | Amendments to Qualifying Defence Contracts - Consolidated Versions | 12/14 | 2 | Authority | Issue a consolidated version of the Contract to the Contractor | Where the Contract is amended in accordance with DEFCON 503 - on five occasions since consolidated date, to change by more than 5% of Contract Price or in a way considered to be a significant change | Within 28 calendar days of agreeing the relevant amendment | Authority Commercial/Project | Contractor Commercial /Project
801 | Amendments to Qualifying Defence Contracts - Consolidated Versions | 12/14 | 5 | Authority & Contractor | Reach agreement on content of consolidated version | Where notification has been given by the Contractor in accordance with Clause 4b | Upon notification | Contractor Commercial/Authority Commercial | Contractor Commercial/Authority Commercial
801 | Amendments to Qualifying Defence Contracts - Consolidated Versions | 12/14 | 6 | Authority | Re-issue a signed consolidated version which accords with agreement or determination as per Clause 5 | - | Within 14 calendar days of reaching agreement (as per Clause 5) | Authority Commercial/Project | Contractor Commercial /Project
804 | QDC: Confidentiality of Single Source Contract Regulations Information | 03/15 | 2 | Authority | Keep SSCR Information confidential and shall not disclose or make available SSCR Information to any person | Except with prior written consent of Contractor and except as expressly permitted by the Condition | For the duration of the Contract | Authority Commercial/Project | Contractor Commercial /Project
804 | QDC: Confidentiality of Single Source Contract Regulations Information | 03/15 | 4 | Authority | Ensure that the recipient of SSCR Information is made aware of and asked to respect is confidentiality | Where SSCR Information is disclosed to any Central Government Body | As applicable | Authority Commercial/Project | Contractor Commercial /Project
804 | QDC: Confidentiality of Single Source Contract Regulations Information | 03/15 | 5 | Authority | Inform the recipient of the confidential nature of the SSCR Information before disclosure and obtain enforceable obligations to keep the SSCR Information confidential | Where SSCR Information is disclosed to the Authority's professional advisors or consultants | As applicable | Authority Commercial/Project | Contractor Commercial /Project
Note on H22: loganr103: Update with Annex details once known

## Narrative Clause Obligations
ANNEX R TO CONTRACT ARTYSYS/00286
Official Sensitive - Commercial
Authority's Obligations
Contract Title: FC BISA MLU
Contract Number: ARTSYS/00286
SECTION OF T&Cs | NARRATIVE CONDITION TITLE | CLAUSE NUMBER | RESPONSIBILITY | OBLIGATION OR ACTION | ADDITIONAL COMMENTS | DATE REQUIRED | PERSON RESPONSIBLE FOR DELIVERY | PERSON RESPONSIBLE FOR RECEIPT | DATE DELIVERED/CONFIRMED | EVIDENCE AT [FILE REF & ENCL]
General Conditions | Interpretation & Precedence | 2.2 | Authority | Consultation and agreement with the Contractor regarding the order of precedence in contractual documentation, in the event of internal conflict | - | As required | Authority Commercial Or Project | Contractor Commercial or Project
General Conditions | Gainshare | 2.5 | Authority & Contractor | Both parties to work together to ealise potenetial opportunities fr efficiencies in accordance with the Framework agreement at Annex D and in accordance with 2.5 |  | For the duration of the Contract, on a case by case basis | Authority and Contractor Commercial and Project | Authority and Contractor Commercial and Project
General Conditions | Indemnity for Safety Failure Loss | 2.7 | Authority | Accept liability and indemnify Contractor for any Safety Failure Loss relating from all third party claims, where the Authority is responsible for the failure | - | For the duration of the Contract, when applicable | Authority Commercial Or Project | Contractor Commercial or Project
General Conditions | Indemnity for Safety Failure Loss | 2.7 | Authority | Notify the Contractor of decision where the Authority decides not to take control of the conduct of the claim | - | Promptly | Authority Commercial Or Project | Contractor Commercial and Project
General Conditions | Authority Obligations | 2.8 | Authority | The Authority shall perform its actions as laid out in in Annex Q |  |  | Authority Project | Contractor Project
General Conditions | Authority Obligations | 2.8 | Authority | The Authority shall not unreasonably refuse a Relief Request arrising from the Authority failing to perform its obligations as laid out in Annex Q |  |  | Authority Commercial Or Project | Contractor Commercial or Project
Contract Administration | Earned Value Management | 9.5 | Authority & Contractor | The Contractor and the Authority agree to monitor progress against delivery of Line Items 1 and 2 to the Schedule of Requirements to the Contract utilising an Earned Value Management (EVM) system, to be established by 2nd July 2018 | - | Throughout the life of the Contract | Authority and Contractor Commercial and Project | Authority and Contractor Commercial and Project