## Sheet1
PUBLISHED CLARIFICATION SPREADSHEET
Clarifications related to all 4 play area opporunities (Roydon Way, Foots Farm, Burrs Road, Halstead Road) - Published Clarification register
| 2022-07-01 |  |  | Closed Clarifications
Message ref number | Date received | Commercially Sensitive | Message Subject | Clarification message detail | Response sent to all suppliers | Date response published
CQ1 | 2022-07-01 | No | Play Area Tenders | Can you let me know if you have a preference for timber or metal based play equipment on these sites please. | Timber if possible but will consider metal if it fits with the area. | 2022-07-01
CQ2 | 2022-07-04 | No | RfQ Play Areas - Burrs Rd, Roydon Wy, Halstead Rd & Foots Farm | Can you please confirm if there is any flexibility on the proposed contract start date 1st Sept 2022 and if so what is the latest these works could start? | We can delay this until October but I don’t want work delayed over winter because of frozen ground etc | 2022-07-04
CQ3 | 2022-07-04 | No | Clarifications | Can we request an extension for the return date. Preferably four weeks after closing date for the questions responses by the council. Which is currently the 13th July. | Yes we will extend the RFQ to end on the 10th August | 2022-07-05
CQ4 | 2022-07-04 | No | Clarifications | Would it be possible to carry out the site surveys accompanied by a member of the councils parks team. If so please supply contact details. | Depending on dates. Please contact: anepean@tendringdc.gov.uk | 2022-07-06
CQ5 | 2022-07-04 | No | Clarifications | Will the sites be awarded separately or is the council looking for one contractor to carry out all four sites. | Yes all 4 sites will be awarded seperately. | 2022-07-07
CQ6 | 2022-07-04 | No | Clarifications | What is the councils preference for safer surfacing under any new play equipment being proposed to be installed. | No preference as long as it conforms to current safety legislation for the piece of equipment. | 2022-07-08
CQ7 | 2022-07-04 | No | Clarifications | Will the council be supplying any site utilities and services maps prior to 13th July | No | 2022-07-09
CQ8 | 2022-07-13 |  | Contracts Finder Error | Roydon Way value to confirm is £5,000-£9,000. (An extra zero was added in error on contracts finder. The specification is correct in stating £9k).