T5 APMS Practice Information

Prospective Bidders are requested to note the requirement to commence services on 01st July, for contracts within phase 1 of the procurement, and 01st October 2017, for contracts within phase 2 of the procurement. Dates in brackets indicate amended service commencement date within each phase):

| Phase 1 | - Bedfont Practice, TW14 - The Great West Surgery/Heston Practice, TW4/TW5 - Isleworth Practice/Grove Medical Centre, TW7 - Orient Community Practice, E10 - The Rowans Surgery, SW16 - Somers Town Medical Centre, NW1 (01 August 2017) - Chestnuts Park Surgery/The Laurels Medical Practice, N15 (01 August 2017) |
| --- | --- |
| Phase 2 | - Acton Lane/Harness Harlesden, NW10 - Central Colindale Practice, NW9 - Edridge Road Health Centre, CR9 - Featherstone Road Health Centre, UB2 - Half Penny Steps Health Centre, W10 - Hayes Town/Orchard Practice, UB3 - Sandringham Practice, E8 - Springfield Health Centre/Tollgate Lodge Health Centre, N16 - Kings Park Surgery, RM3 (01 January 2018) - Woodbridge Medical Centre, UB1 (01 January 2018) |

T5 APMS Indicative Procurement Timeline

The indicative timeline for The Procurement is set out below.

Bidders are to note that the dates are expected dates at the time of issuing this ITT and are therefore subject to change at the sole discretion of the Authority.

| Milestones | Date |
| --- | --- |
| Advertisement published and ITT documents available | 06th January 2017 |
| Bidder information event | 11th January 2017 |
| Deadline for receipt of Bidder clarification questions | 31st January 2017 |
| Deadline for receipt of ITT submissions | 10th February 2017 |
| Phase 1 Evaluation and Award |  |
| Procurement and Finance Due Diligence | 13th – 17th February 2017 |
| ITT evaluation (Generic and Lot specific) | 20th February – 10th March 2017 |
| Presentations and Interviews | 27th – 31st March 2017 |
| Recommendations to Board | w/c 10th April 2017 |
| Notification of outcome/Initiation of Standstill period | 02nd May 2017 |
| Conclusion of Standstill period | 12th May 2017 |
| Mobilisation | w/c 15th May 2017 |
| Service commencement | 01st July 2017 |
| Phase 2 Evaluation and Award |  |
| ITT evaluation (Lot specific) | 10th April – 05th May 2017 |
| Presentations and Interviews | 22nd – 26th May 2017 |
| Recommendations to Board | w/c 05th June 2017 |
| Notification of outcome/Initiation of Standstill period | 03rd July 2017 |
| Conclusion of Standstill period | 13th July 2017 |
| Mobilisation | w/c 17th July 2017 |
| Service commencement | 01st October 2017 |

Bidders are requested to note that The Authority reserves the right to adjust the timetable as required to meet the needs of the procurement process, and will endeavour to provide adequate notice to Bidders of any necessary adjustment where possible.