# Annex A

| Title of project: | 1517S Survey Benthic Infaunal Sample Analysis |
| --- | --- |
| Date and time for return of tenders: | 14 February 2018 @12:00 hours |
| Contract Reference No: | C17-0256-1199 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO JESSICA TAYLOR, OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Jessica Taylor Joint Nature Conservation Committee Email: jessica.taylor@jncc.gov.uk Tel: 01733 866906 OR Ana Jesus Joint Nature Conservation Committee Email: ana.jesus@jncc.gov.uk Tel: 01733 866923 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca or Gordon Green Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 or 01733 866806 |
| Proposed start-date: | Week beginning 19 February 2018 |
| Proposed end-date: | 20 March 2018 (Phase 1), Phase 2: date negotiable |

1517S Survey Benthic Infaunal Sample Analysis

Contents

01.	Joint Nature Conservation Committee	3

02.	Project Aims	3

03.	Project Background	3

04.	Project Objectives	5

05.	External Quality Assurance	7

06.	JNCC Evidence Quality Assurance Policy	7

07.	Data Provision	8

08.	Outputs	8

09.	Intellectual Property Rights and Dissemination	9

10.	Timescale	10

11.	Health and safety	10

12.	Product specification	10

13.	Project management	10

14.	Instructions for tender submission	10

15.	Evaluation Criteria	12

16.	Payment	13

17.	Additional Contractor requirements	13

Appendix A: Summary Metadata	14

Appendix B: Sample Reference Collection Requirements	17

Appendix C: Quality Assurance	18

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC website: http://jncc.defra.gov.uk/page-1729

## Project Aims

The aim of this project is to undertake the taxonomic analysis of benthic infaunal samples collected on a recent offshore seabed survey of North-east Faroe Shetland Channel and West Shetland Shelf Scottish Nature Conservation Marine Protected Areas (NCMPAs).

## Project Background

The Joint Nature Conservation Committee (JNCC) and Marine Scotland Science (MSS) have recently undertaken an offshore seabed survey visiting the North-east Faroe Shetland Channel Scottish Nature Conservation Marine Protected Area (NCMPA) and the West Shetland Shelf Scottish Nature Conservation Marine Protected Area (NCMPA) onboard the Marine Research Vessel (MRV) Scotia (survey code 1517S).

The North-east Faroe Shetland Channel (hereafter NEF) NCMPA follows the descent of the Faroe Shetland Channel from depths of 330m to 2420m. The site has been designated to protect deep-sea sponge aggregations, which were the focus of the recent survey, as well as offshore deep-sea muds and offshore subtidal sands and gravels.

West Shetland Shelf (hereafter WSS) NCMPA is located to the north of Scotland and overlaps with the Windsock fisheries areas which are managed to encourage the recovery of local cod stocks. The NCMPA is designated to protect the wide variety of sand and gravel within its boundaries which are found at depths from 70m – 150m.

The 1517S survey departed from Aberdeen on 20th October 2017 and returned to Aberdeen on 9th November 2017.

Benthic sediments and biological communities were sampled using a 0.1m2 Hamon Grab (Figure 1). Samples have been collected from within the NEFSC and WSS NCMPAs site boundary, from water depths of 100m to 600m.

Particle Size (PS) sediment samples were extracted to be representative of the whole the sample. The remaining sample was sieved in the field using a 0.5mm mesh diameter sieve for the WSS NCMPA and stacked sieves of 0.5mm and 0.25mm mesh diameter sieves for NEF NCMPA. Both of the fractions, where applicable, were retained separately and preserved in 5% formaldehyde solution buffered with borax.

Faunal samples were held in a variety of plastic buckets with sizes ranging from 5 litres to 25 litres (see Appendix A). Table 1 shows the number of samples collected from each of the two sites.

Table 1. Sediment and infaunal samples collected on 1517S survey

| Survey Code | Vessel | Location | Technique | No. of infaunal samples (0.5mm fraction) | No. of infaunal samples (0.25mm fraction) |
| --- | --- | --- | --- | --- | --- |
| 1517S | MRV Scotia | North-east Faroe Shetland Channel NCMPA | 0.1m2 Hamon Grab | 8 | 8 |
| 1517S | MRV Scotia | West Shetland Shelf NCMPA | 0.1m2 Hamon Grab | 44 | 0 |

For background information regarding the sites sampled and detailed information on the survey design and methodology please refer to the Cruise Report (Taylor. J et al. in press, available from JNCC/MSS on request).

Figure 1. 1517S survey location and boundary of NEFSC and WSS NCMPAs

Figure 2. 0.1m2 sampling surface area Hamon Grab

## Project Objectives

JNCC wishes to commission a contract to undertake the taxonomic analysis of benthic infaunal samples collected on the 1517S cruise. Picking and taxonomic analysis of benthic infaunal samples (i.e. identification and enumeration of all fauna present) are required.

Biomass of samples should also be determined. The contract will be run over two financial years (FY17/18 and FY18/19), with Phase I to be undertaken in FY 17/18 and Phase II to be undertaken at the start of FY18/19.

Prospective contractors should note that while funding is available to commence Phase I, funding for Phase II is awaiting confirmation, and there is no guarantee that Phase II will progress next year.

Tenderers should provide quotes for Phase I and Phase II, and details of how they would undertake the following:

Complete infaunal analysis for all samples (please provide quotes on a per sample basis)

Arrange for 5% of processed samples to be submitted to another contractor for Quality Assurance in line with the NMBAQC own sample scheme guidelines (http://www.nmbaqcs.org/scheme-components/invertebrates/).

Entry of infaunal analysis results (and Particle Size data which will be supplied by JNCC) into Marine Recorder should be considered as a costed option.

### Phase I – Commence infaunal sample analysis

The contract will begin following a start-up meeting to be arranged between the successful contractor, MSS and JNCC upon contract award. Phase I will commence on 19th February 2018 and delivery of outputs should be made by Tuesday 20th March.

Tenderers are invited to state how many samples they could analyse in this approximate 4 week period.

### Phase II – Remainder of infaunal sample analysis

Phase II would commence after Phase I has been signed off.

The detailed contract requirements for both Phases and required contract outputs are detailed below.

### Collection of Samples (Costed Option)

For both contract phases, transport of the samples from Marine Scotland Science (Aberdeen) to the successful laboratory should be included as a costed option in the tender document.

If undertaking this task, the contractor should ensure safe passage of the samples to their laboratory, as the faunal samples are preserved in formaldehyde. The samples will be stored by the contractor until they are processed and analysed. Costs should be provided for continued storage of processed samples by the contractor for 3 years following completion of the contract.

### Analysis of Faunal Samples

This invitation to tender is for the processing of sediment samples to extract and identify all biota retained following sieving on 0.25 mm and 0.5mm capture meshes, as per the NMBAQC guidelines detailing extraction and identification protocols. Sub sampling is permissible following consultation and agreement with the contract manager. However, it is not envisaged that this will be required.

Enumeration, identification and biomass should be carried out following the NMBAQC Processing Requirement Protocol and Taxonomic Discrimination Protocol.

Biomass per recorded taxon (wet weight in grams to at least 4 decimal points) is required for all countable taxa.

The abundance and biomass data matrices should be sent via email to the project manager following completion. Please include an additional column to include the Aphia ID for each species in the taxon list, where appropriate, and order the species list by major taxonomic group.  Where data matrices span multiple tabs in Excel, identical species lists should be used in each tab to facilitate merging at a later date.

All species names must be run through the WoRMS ‘Match Taxa’ tool so that all naming is current.

Identification of MPA Priority Marine Features

For every sample, the presence of NCMPA Priority Marine Features should be noted and should be added as an attribute to the relevant GIS shapefiles (see Section 8).

## External Quality Assurance

5% of samples are to be subject to an external QA process following the requirements of the NMBAQC ‘own sample’ scheme assessment criteria through the NMBAQC component administrator (http://www.nmbaqcs.org/scheme-components/invertebrates/). It is the responsibility of the winning bidder to ensure this process is completed before the delivery of each dataset. Any remedial action required following the QA process must be completed within an agreed timeframe at no extra cost to the project.

If the NMBAQC component administrator is not available to undertake the external QA process an agreed alternative supplier should be found, and will require approval by the project manager.

The project manager is to be notified of the results of the comparison of the results of the external analysis and the primary analysis once this has been completed.

All remedial action taken, and associated rationale, are to be recorded and provided as outputs of this contract.

The contract shall not be deemed complete until this external Quality Assurance step has been completed successfully.

- Prospective contractors should note the following:

- Adherence with the NMBAQC guidelines is not an end in itself but contractors Standard Operating Procedure must be sufficiently rigorous in practise to achieve the required QA standards.

- The objectives of the QA is to ensure the sample analysis meets the QA standards set out in the NMBAQC scheme Own Sample Protocol.

- The Remedial Action process may be iterative until the QA standards are achieved.

- Samples may be withdrawn and refunds requested if samples fail to achieve satisfactory QA within a set number of rounds or within a specified time schedule.

- Contractors should alert the project manager if any samples they receive are deemed to be atypical, such that they require, or would benefit from, some method variation of their Standard Operating Procedure.

## JNCC Evidence Quality Assurance Policy

In January 2014, JNCC implemented a single policy on Evidence Quality Assurance, which is based on a number of existing policies from different work programmes. The policy (EQA Policy) and the associated set of Evidence Quality Guidance Notes provide the standard to follow to help ensure that the quality of JNCC scientific advice and evidence is fit for purpose.

We require that the successful contractor complies with our EQA Policy. The policy can be found here: http://jncc.defra.gov.uk/default.aspx?page=6675

Work under this contract will be subject to the provisions within the EQA policy.

The outputs from this project may be peer reviewed by an independent external expert.

The purpose of this review would be to ensure:

- Methods used are appropriately designed and fit for purpose;

- Interpretation of evidence is based on best scientific practice, analytical methods are sound, sources of other evidence are used appropriately and clearly referenced, and conclusions follow logically there from;

- Evidence quality and the uncertainty associated with its interpretation are clearly communicated;

- Other stakeholders are able to understand our outputs, and other scientists would be able to use the same data to obtain the same results.

Please see Appendix C for further details of quality assurance requirements.

## Data Provision

The following products will be supplied to the successful contractor:

Survey programme

Associated metadata

Draft Cruise Report

Results of Particle Size (PS) Analysis from PS subsamples (expected by end of March 2017)

### Additional Requirements

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The successful contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

Contractors are to provide weekly progress updates via email summarising the stage of each sample in the process including estimated completion dates.

## Outputs

Analysis products should be provided in MS Excel proforma spreadsheets and as ArcGIS shapefiles.

Shapefiles should be complete with imbedded INSPIRE compliant metadata and be fully georeferenced in a defined coordinate system (WGS84 UTM29N preferred).

Point shapefiles required include:

- Sample locations and presence of NCMPA Priority Marine Features

A taxonomic sample reference collection is required (see Appendix B).

The deliverables of this project will include a brief Final Report. The Final Report must adhere to the JNCC report template and house style guidance http://jncc.defra.gov.uk/pdf/JNCC_DesignID_v1.3.pdf.	The report should be provided electronically via email as a Microsoft Word document, and will include the following sections:

- Methodology

- Results

- Overview of conservation importance of site, including any species of particular interest (e.g. Priority Marine Features)

- Details of all QA work undertaken and any remedial action deemed necessary.

| - Output/Deliverable | Format |
| --- | --- |
| Biological analysis of infaunal samples full taxon and biomass as per NMBAQC Standards (in a species matrix format) | MS Excel spreadsheet |
| Infaunal sample taxonomic reference collection and associated metadata | Reference collection (Reference Collection holder to be confirmed) |
| ArcGIS shapefiles for area surveyed as outlined above Shapefile should be imbedded with INSPIRE compliant metadata (INSPIRE metadata template available in ArcGIS) | ArcGIS point shapefiles |
| Final report | MS Word DOC |

For final electronic products, material can be accepted on HDD or DVD whose labels should include details of virus scanning. The date, name and version of the virus scanner used must be stated.

## Intellectual Property Rights and Dissemination

Data collected by JNCC and MSS during the 1517S survey (©JNCC/MSS 2017/2018).

Rights to all knowledge (including but not limited to data, information, know-how, designs, drawings and specifications) brought to the project by either party will remain with that party, and such knowledge is to be used solely for the purposes of conducting this project. Rights to knowledge jointly generated within the project will be owned by the JNCC and MSS.

There is no need for the JNCC or MSS to obtain a licence for data or to pay any fees in perpetuity to enable distribution to third parties of material generated within the project.

The successful contractor will require permission of the JNCC and MSS to publish material; the JNCC and MSS will not unreasonably withhold its permission for the contractor to publish such material in science journals, articles etc. in order to publicise the research to a wider audience.

Although the project is public, it is acknowledged that in certain circumstances confidential information may be used in the implementation of the research project.  The use of confidential information should be minimal and where it is necessary its use should be identified, and discussed with the nominated project manager.

The report produced under this contract will be a JNCC and MSS product and shall not be published or disseminated without the written permission of JNCC and MSS.

It may at some point be published on the JNCC website. The findings from this contract will also be made available to Marine Scotland, the UK Conservation Agencies (Scottish Natural Heritage, Natural England, Natural Resources Wales, and Northern Ireland Environment Agency) and Defra.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | 19/02/2018 |
| Completion of Phase I | 20/03/2018 |
| Completion of Phase II | To be negotiated |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2018/2019 is subject to availability of funds, continuing need and satisfactory contractor performance.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house style guidance http://jncc.defra.gov.uk/pdf/JNCC_DesignID_v1.3.pdf.	 unless stated otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

(Note for author. If research project/contract See Evidence Quality Guidance Note #4 (Communicating Evidence Quality).  Ensure that data management and storage requirements are stipulated, taking into account relevant policy for data access; see Evidence Quality Assurance Policy document).

Copies of documentation associated with the case studies should be provided in electronic format, with an associated reference catalogue.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be: Jessica Taylor

Email: Jessica.taylor@jncc.gov.uk

Tel: +44 (0)1733 866906

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract. For the See Evidence Quality Guidance Note #1 (Bias, Conflicting Evidence and uncertainty) and Evidence Quality Guidance Note #3 (Quality Assurance of Expert Knowledge and Opinion).

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough on 19th February 2018.

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements of the project. | 10 |  |
|  | Soundness and logicality of methods | 7 |  |
|  | Realism and measurability of milestones | 6 |  |
|  | Identification and proposed solutions to potential problems/risks | 6 |  |
|  | Serious weaknesses which threaten success | 6 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (25 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 9 |  |
|  | Risks if important team members drop out | 7 |  |
|  | Adequacy of subcontractors (if any) | 9 |  |
|  | Sub Totals | 25 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 6 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 7 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

Payment for Phase I of the contract will be made upon receipt of species matrix detailing work completed to 20th March 2017 and accompanying invoice.

Payment for Phase II of the contract will be made upon receipt of all agreed, quality assured deliverables for Phase II and accompanying invoice.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

Contractors are to provide weekly progress updates via email summarising the stage of each sample in the process including estimated completion dates.

## Appendix A: Summary Metadata

Table 1: Summary Metadata for North-east Faroe Shetland Channel NCMPA grab samples

| Station Name | Water depth (m) | Date/time | 0.25mm faunal container volume | 0.5mm faunal container volume |
| --- | --- | --- | --- | --- |
| 1517S_NEF_D12_S13 | 520 | 22/10/2017 18:34:16 | 5 L | 10 L |
| 1517S_NEF_D20_S14 | 583 | 22/10/2017 21:09:30 | 5 L | 5 L |
| 1517S_NEF_D11_S15 | 572 | 22/10/2017 23:16:52 | 5 L | 5 L |
| 1517S_NEF_D10_S16 | 585 | 23/10/2017 00:43:10 | 5 L | 5 L |
| 1517S_NEF_D02_S17 | 543 | 23/10/2017 02:09:00 | 5 L | 5 L |
| 1517s_NEF_D32_S27 | 589 | 24/10/2017 21:34:08 | Not known | Not known |
| 1517s_NEF_D31_S28 | 596 | 24/10/2017 22:39:00 | 10 L | 10 L |
| 1517s_NEF_D30_S29 | 600 | 24/10/2017 23:54:12 | 10 L | 10 L |

Table 2: Summary Metadata for West Shetland Shelf NCMPA grab samples

| Station Name | Water depth (m) | Date/time | 0.5mm faunal container volume |
| --- | --- | --- | --- |
| 1517S_WSS_14_S89 | 130 | 01/11/2017 17:25:15 | 5L & 10L |
| 1517S_WSS_10_S91 | 132 | 02/11/2017 06:45:51 | 5L & 10L |
| 1517S_WSS_01_S95 | 132 | 02/11/2017 10:01:50 | 10L |
| 1517S_WSS_04_S96 | 132 | 02/11/2017 10:29:45 | 10L |
| 1517S_WSS_06_S97 | 130 | 02/11/2017 11:09:43 | 10L |
| 1517S_WSS_09_S98 | 128 | 02/11/2017 11:47:33 | 25L |
| 1517S_WSS_12_S99 | 122 | 02/11/2017 12:20:50 | 25L |
| 1517S_WSS_08_S100 | 113 | 02/11/2017 12:50:02 | 10L |
| 1507S_WSS_17_S102 | 131 | 02/11/2017 14:02:41 | 25L |
| 1507S_WSS_13_S103 | 130 | 02/11/2017 14:30:30 | 25L |
| 1507S_WSS_19_S104 | 128.7 | 02/11/2017 15:12:30 | 10L |
| 1517S_WSS_15_S106 | 138 | 02/11/2017 16:27:05 | n/a |
| 1517S_WSS_20_S107 | 130 | 02/11/2017 17:20:25 | 10L |
| 1517S_WSS_22_S111 | 130.5 | 02/11/2017 20:21:05 | 25L |
| 1517S_WSS_25_S112 | 125 | 02/11/2017 20:49:27 | 25L |
| 1517S_WSS_29_S113 | 124 | 02/11/2017 21:13:20 | 2 X 10L |
| 1517S_WSS_34_S114 | 122 | 02/11/2017 21:42:15 | 2 X 10L |
| 1517S_WSS_30_S115 | 123 | 02/11/2017 22:16:16 | 2 X 10L |
| 1517S_WSS_35_S116 | 121 | 02/11/2017 22:53:17 | 2 X 10L |
| 1517S_WSS_31_S117 | 125 | 02/11/2017 23:25:04 | 2 X 10L |
| 1517S_WSS_24_S119 | 126 | 03/11/2017 00:57:35 | 25L |
| 1517S_WSS_28_S120 | 125 | 03/11/2017 01:33:05 | 10L |
| 1517S_WSS_36_S124 | 127 | 03/11/2017 03:50:45 | 25L |
| 1517S_WSS_40_S125 | 124 | 03/11/2017 04:26:45 | 10L |
| 1517S_WSS_45_S126 | 120 | 03/11/2017 04:53:03 | 10L |
| 1517S_WSS_44_S128 | 120 | 03/11/2017 08:40:05 | 5L |
| 1517S_WSS_38_S129 | 120 | 03/11/2017 09:23:57 | 5L |
| 1517S_WSS_43_S130 | 114 | 03/11/2017 09:49:41 | 25L |
| 1517S_WSS_53_S131 | 107 | 03/11/2017 10:15:19 | 10L |
| 1517S_WSS_48_S132 | 114 | 03/11/2017 10:51:05 | 10L |
| 1517S_WSS_49_S134 | 117 | 03/11/2017 12:01:10 | 10L |
| 1517S_WSS_55_S135 | 118 | 03/11/2017 12:29:33 | 10L & 5L |
| 1517S_WSS_50_S136 | 119 | 03/11/2017 12:56:53 | 10L |
| 1517S_WSS_46_S137 | 122.7 | 03/11/2017 13:33:05 | 10L & 5L |
| 1517S_WSS_41_S138 | 121 | 03/11/2017 14:00:30 | 1 X 5L & 1 X10L |
| 1517S_WSS_47_S139 | 114 | 03/11/2017 14:26:30 | 1 X 10L |
| 1517S_WSS_57_S145 | 113 | 03/11/2017 19:28:00 | 10L |
| 1517S_WSS_56_S147 | 120 | 03/11/2017 20:30:15 | 25L |
| 1517S_WSS_64_S152 | 102 | 03/11/2017 23:44:51 | n/a |
| 1517S_WSS_71_S154 | 106 | 04/11/2017 01:11:23 | 10L |
| 1517S_WSS_66_S155 | 113 | 04/11/2017 01:53:23 | 10L |
| 1517S_WSS_72_S156 | 114 | 04/11/2017 02:28:58 | 2X5L |
| 1517S_WSS_67_S157 | 114 | 04/11/2017 03:07:02 | 10L |
| 1517S_WSS_62_S158 | 114 | 04/11/2017 03:35:45 | 5L |

## Appendix B: Sample Reference Collection Requirements

JNCC makes biological samples collected on survey available to museums and other researchers once they’ve been analysed. Survey data are expensive to collect and it is important to ensure these data are used to their full potential. JNCC and MSS currently collaborate with the National Museums of Scotland (NMS) to allow ongoing use, and to secure long-term management, of seabed sample data.

To facilitate the incorporation of invertebrate specimens collected on behalf of JNCC into museum collections, specimens should be:

- Separated by species and by station/sample

- Preserved in 70 – 75% Industrial Methylated Spirit or similar (not formaldehyde)

- Placed in glass sample vials with polyethylene closures. The external diameter of the vials should be less than or equal to 15 mm and the height should be less than or equal to 55 mm. ‘Oversized’ specimens may be placed in any suitable container and will be transferred to glassware by the NMS.

- Each specimen vial should contain a visible internal label which includes (in pencil or alcohol-proof ink):

  - Species/Taxon name (in full)

  - Station/Sample Code

  - Number of specimens contained

A Sample Reference Collection Metadata spreadsheet should be provided detailing:

- Project/survey title and relevant project codes

- Client details (including nominated officer)

- Contractor details (including a nominated contact)

- Survey Vessel and Cruise number

- Generalised Description of Survey Area/Site

- Sampling Date (dd/mm/yyyy)

- Sampling Gear

- Position (Lat/Long including Datum e.g. WGS84)

- Depth (m)

- Species name and authority

- Station/sample code and replicate number– the original project coding is preferred so that the specimen data can be linked to physical and chemical data which may come from other sources/contractors (e.g. latitude/longitude, sediment characteristics)

- Sample substrate (should be entered as Folk)

- Biotope Classification (should be entered as MNCR 04.05)

- Biotope name (exact copy of MNCR 04.05 descriptor)

- Biotope code (exact copy of MNCR 04.05 code)

- Number of specimens per vial

- Details of preservative used

- Initials of identifier/taxonomist

A Species Matrix should also be included.

## Appendix C: Quality Assurance

Internal Quality Assurance

MSS and JNCC will require contractors to provide quality assured products under this contract.  Contractors should also supply a quality plan as part of the contract.  All products supplied will be subject to quality checks by the JNCC to ensure they meet the agreed standards. Contractors should clearly describe their data management facilities and procedures in proposals related to this work.

Documentation

The following documents must be provided by the contractor upon the request of the nominated project manager.  Contractors must also ensure they have a document control system in place to manage these documents (i.e. documents are kept electronically live and there is version control of hard copies to prevent the inadvertent use of obsolete documents).

Standard Operating Procedure

The contractor must provide copies of all relevant Standard Operating Procedures (SOPs) for the contracted work.  An SOP should include:

A clear statement of the qualitative and quantitative goals of the contract work, which demonstrates that the specified methods are fit for purpose.

Methodological details of all steps performed.

Details of the procedures related to the analysis of data.

Details of the quality assurance system in place.

Quality Manual

The contractor should be able to provide on request a quality manual which details an organisation’s quality assurance system/policy (i.e. all aspects of quality assurance described in this document), which allows systematic audits of a monitoring programme to ensure that all aspects of quality assurance are being met.  This should include details of the contractor’s Quality Manager, who is deemed responsible for overseeing the entire QA within the contracted organisation.

Quality Management System

It is recommended that the contractor should have the following Quality Management System (QMS) documentation (or alternative documentation proposed by the contractor which is demonstrated to be equivalent) to demonstrate there is a working QA system in place:

Quality Control Audit

Examination of in-house QC data, check of appropriate control limits, and corrective action is documented where QC data has breached control limits.

Method Witnessing

Comparison of written procedure to observed procedure under real conditions.  Any differences must be resolved through corrective action where needed.

Training Manual

Criteria stating the minimum competency (education, training, work experience and/or other demonstrated skills) necessary for staff to undertake different types of marine monitoring work must be defined in the Training Manual.  The competency of each staff member must be signed off initially against all criteria and evidence of ongoing competency must be maintained on a regular basis in a document such as a Training Log (or individual staff member’s Curriculum Vitae’s).

Adherence to standardised methods

The contractor must adhere to relevant national, European or international standardised methods. The NMBAQC website gives the current list of all British Standards (BSi), International Organization for Standardisation (ISO) standards and European Committee for Standardisation (CEN) standards which currently exist for marine biological monitoring.

The contractor must provide details of any additional standard methods which they adhere to if these are not explicitly stated in the SOP (e.g. UK government agencies protocols and standards for marine monitoring programmes, ICES or NMBAQC standard methods).

Documentary evidence must be provided if the contractor is certified or accredited to a standard method (or their own method) through an accreditation scheme such as Good Laboratory Practice (GLP) or United Kingdom Accreditation Service (UKAS).

Adherence to data standards and guidelines

The contractor must adhere to the relevant data standards and guidelines.

Species lists which are compliant with current taxonomic names and synonyms (e.g. World Register of Marine Species (WoRMS), which is now endorsed by the Healthy and Biologically Diverse Seas Evidence Group (HBDSEG)).

Data and metadata guidelines relevant to the contracted work, which define data and metadata formats (e.g. Marine Environmental Data and Information Network (MEDIN) data guidelines and Mapping European Seabed Habitats (MESH) standards).

Taxonomic resources

The contractor must use the current species dictionary supplied within Marine Recorder to aid in the identification of marine biological taxa. However, contractors who already have Marine Recorder installed should check they have the latest species dictionary update by visiting http://esdm.co.uk/MarineRecorder/index.html and downloading if necessary.

Staff competency

Staff involved in identifying marine biotopes should have a relevant degree level qualification (or equivalent) in a relevant discipline, plus 3 years relevant work experience.  If less experienced staff are proposed to conduct biotope identification, this must be under the direct supervision of a fully trained staff member.

The up-to-date competency of each contracted staff member must be demonstrated via a list of the most up to date and relevant contracted marine work (along with client contact details) and proof of continual professional development of staff through:

Participation in workshops (run internally or externally through universities, museums or marine organisations/associations)

Participation in proficiency tests (Interlaboratory Comparisons or Ring Tests) and/or external quality control tests run through external quality assurance scheme (e.g. the Clean Seas Environmental Monitoring Programme AQC (NMBAQC) scheme or equivalent),

Proof of tertiary qualifications and other qualifications (e.g. Identification Qualification awarded by a professionally recognised institute).

Stated project personnel

The names of proposed project personnel and their role in the contracted work must be specified. Only those staff proposed in the tender submission will be expected to undertake the work.  Changes to contracted staff (including subcontractors) will only be accepted following written approval from the contract manager.

Internal Quality Control

The contractors must demonstrate their internal Quality Control (QC) system (which is outlined in a Quality Control Audit), which includes routine checks of data and analysis.

QC of data and analysis is where samples are re-checked and compared against the original and compared to an expected standard/limit of error/deviation from the original.  It is also where electronic records (in spreadsheets or databases) are checked against the data on the original field/laboratory datasheets.  This measures the repeatability of the method of analysis and data entry, and highlights factors such as inter-worker variability.  QC must also include details of remedial action in cases where expected standards/limits are not met.

Internal QC must be undertaken by a staff member other than the staff member who conducted the original sample analysis.

### External Quality Assurance

External Training, Qualifications and Proficiency Tests

The contractor should provide evidence (Certificates or Statement of Performance) of their up-to-date expertise through active participation in:

- External training (e.g. workshops run through universities, museums, marine organisations/associations),

- Qualification schemes (e.g. Identification Qualification awarded by a professionally recognised institute), and

- Proficiency tests, e.g. Interlaboratory Comparisons or Ring Tests run through an external quality assurance scheme (e.g. the NE Atlantic Marine Biological Analytical Quality Control (NMBAQC) scheme or equivalent).

External Quality Control

Ideally contractors (or their sub-contractors) should follow NMBAQC guidelines for video and stills analysis. Contractors will be required to provide documentary evidence of their compliance with their own QA/QC procedures. The contractor shall facilitate the completion of these QA/QC checks.  In all cases, if the products do not meet the required quality standard the contractor will have to undertake appropriate remedial action and then re-supply the product. All costs associated with such remedial action will be borne by the contractor and will not be charged to the MSS or JNCC.

Note a teleconference should suffice for the start-up meeting

http://www.nmbaqcs.org/media/1175/nmbaqc-inv-prp-v10-june2010.pdf

http://www.marinespecies.org/aphia.php?p=match

http://jncc.defra.gov.uk/pdf/Priority%20Marine%20Features%20in%20Scotlands%20seas.%2024%20July%202014.pdf

http://www.nmbaqcs.org/media/1643/nmbaqc_epibiota_interpretation_guidelines_final.pdf