## Sheet1
Plymouth Marjon University Campus Development Plan
Clarification Log
Clarification No | Date Received | Clarification | Clarification Response | Date Issued
1 | 23rd May 2019 | Updates to Selection Questionniare Question 6.5 - OLD QUESTION - Weighting 20% Candidates are required to set out the processes that your organisation has deployed to previous projects to ensure consideration and application of current construction methods and best practise products and technologies that delivered a sustainably designed and constructed building that delivered low carbon emissions. Please provide details to demonstrate how you have used and considered current and proposed building construction methods, products and technologies to deliver a well-designed, usable and sustainable building with low carbon emissions. | The orignial Selection Questionnaire has been removed from Contracts Finder and replaced with the updated version. 6.5 - Now asks:- Weighting 20% Candidates are required to set out the processes that your organisation has deployed to previous projects to ensure consideration and application of current design and construction methods and best practise products and technologies that delivered a sustainably designed and constructed building that delivered low carbon emissions. Please provide details to demonstrate how you have used and considered current and proposed building design and construction methods, products and technologies to deliver a well-designed, usable and sustainable building with low carbon emissions. | 23rd May 2019
2 | 23rd May 2019 | Updates to Selection Questionniare Question 6.6 - OLD QUESTION - Weighting 5%. Candidates are required to provide details on how you have been proactive in raising awareness of relevant industry standards and best practise that during the delivery of the contact/project to reduce energy and water consumption. Please provide details of your approach together with the outcomes and effects you were able to influence and achieve. | The orignial Selection Questionnaire has been removed from Contracts Finder and replaced with the updated version. 6.6 - Now asks:- Weighting 5%. Candidates are required to provide details on how you have been proactive in ensuring relevant industry standards and best practise have been implemented during the delivery of the contact/project to reduce energy and water consumption and the results at post-occupancy stage. Please provide details of your approach together with the outcomes and effects you were able to influence and achieve. | 23rd May 2019
3 | 23rd May 2019 | Updates to Selection Questionniare Question 6.8 - OLD QUESTION - Weighting 5% Plymouth Marjon University are fortunate enough to have a deer herd on Campus; Please provide details of the measures that you have put in place to ensure that protected wildlife is not damaged or disturbed. Please provide details to explain how you have put appropriate measures in place that have been effective in ensuring that protected wildlife in not damages or disturbed throughout this project. | The orignial Selection Questionnaire has been removed from Contracts Finder and replaced with the updated version. 6.8 - Now asks:- Weighting 5% Plymouth Marjon University are fortunate enough to have a biodiverse campus of flora and fauna, including a deer herd which roams through the Campus; Please provide details of the measures that you have put in place to ensure that the biodiversity is enhanced rather than damaged or disturbed. Please provide details to explain how you have put appropriate measures in place that have been effective in ensuring that the biodiversity is enhanced rather than damaged or disturbed throughout this project. | 23rd May 2019
4 | 23rd May 2019 | We have acquired the information related to the above masterplan process but cannot see an indication of which specific disciplines the OJEU relates to. Are you only after an architect at this stage or a wider team? If you are after a wider team, can you clarify which disciplines need to be included within each bid?
5 | 23rd May 2019 | Please can we clarify if the site visits stated below are for June or July? Plymouth Marjon University wishes to invite interested suppliers to attend a Site Visit on either: - (please note these will be allocated on a first come first serve basis) • 10th July 2019 @ 10:30 to 12:30 or 14:00 to 16:00 • 11th July @ 10:30 to 12:30 or 14:00 to 16:00 • 12th July @ 10:30 to 12:30 or 14:00 to 16:00 • 16th July 2019 @ 10:30 to 12:30 or 14:00 to 16:00 • 17th July 2019 @ 10:30 to 12:30 or 14:00 to 16:00 | Plymouth Marjon University are applying the Restricted Procedure; this is a two stage process. The first stage is the completion and return of the Selection Questionnaire only; This aspect of the procedure assesses supplier experiences, knowledge and skills, and is essentially backward looking. For those suppliers who are shortlisted – the 2nd stage of the process will involves the completion of the Statement of Requirements and pricing information; which is the quality and forward looking requirements, accordingly the site visits are part of this part of the process. The Public Contracts Regulations 2015; require procurers to make a full suite of tender documents available at the beginning of the process; Should you feel that a site visit would benefit you in completing and submitting your Selection Questionnaire please let me know and I will look to make the necessary arrangements. | 24th May 2019
6 | 24th May 2019 | In relation to section 4.3 of the Selection Questionnaire, please could you clarify what is the required annual turnover for candidates? | The estimated contract value is £200,000.00 which is the required turnover; As you know the 2015 Procurement Regulations allow contracting authorities to apply a turnover of up to twice the estimated contract value (£400,000.00); but we believe a more realistic and sensible value is the £200,000.00 contract value. | 4th June 2019
7 | 28th May 2019 | We would like to submit for the above-named tender and just wanted to clarify if the submission is to be made directly by email to this address (ie not to a portal), and that it should consist of simply the selection questionnaire (plus attachments) in the first instance? (We are assuming that the tender documents are provided for information at this stage.) | Yes the Selection Questionnaire are attachments are the only aspect that needs to be submitted at this stage. These are to be sent to the procurement@marjon.ac.uk email address as opposed to a portal. The Public Contract Regulations 2015 require a full suite of tender documents to be made available to all suppliers from day one and so yes these are for your information at this time. | 4th June 2019
8 | 28th May 2019 | Could you please confirm if the deadline is 17/06 as per the notice or 24/06 as per the selection Questionnaire? Also can you confirm that that Final Invitation to Tender word document is for information only at this stage? | The submission date and time for the Selection Questonnaire is midday on 24th June - an amendement to the OJEU Notice has been requested. | 4th June 2019
9 | 28th May 2019 | Please can you advise the FTP address to upload our SQ response onto | The Selection Questionnaire and associated attachments are to be submitted electronically to procurement@marjon.ac.uk email account as opposed to a portal. | 4th June 2019
10 | 28th May 2019 | Following the release of clarification questions with the tender documents, I am still unclear as to whether you would like us to submit a full design team, or if you are looking for architects only? | At this stage – Plymouth Marjon University only require the completion and submission of the Selection Questionnaire; however, noting that your clarification is fundamental to the next stage of the process. We can confirm that the delivery team will require the following disciplines and specialisms:- Project Management, Architectural and Design, Cost Consultancy, Civil and Structural Engineering etc | 4th June 2019
11 | 28th May 2019 | Please can you advise on the design services required for the Development Plan. | Please refer to clarification 4 for response information | 4th June 2019
12 | 28th May 2019 | Must we use the template provided or is ok to use our own in house template keeping in line with the page counts/font sizes as requested by you? | As we have received extensive interest in this opportunity we require responses to be returned on our templates as these will be familiar to our evaluations teams. | 4th June 2019
13 | 29th May 2019 | 1. For the avoidance of doubt, could you please confirm that it is only the Selection Questionnaire document to be answered and returned at this stage? i.e. The Commercial Pricing Schedule & the questions contained within the Specification document are just for reference at this stage and to be answered at ITT stage if shortlisted? 2. Is the University looking for a Project Manager led team? 3. Are we able to submit our responses to Section 6.0 of the SQ in a separate document that is clearly referenced? | 1. The Public Contracts Regulations 2015 have made it a compulsory requirement to issue a complete tender pack at day one of The Restricted Procedure; Stage one of this procedure requires the completion and submission of the Selection Questionnaire and associated attachments only – with the remaining documents being applied to those who are shortlisted. 2. In recognition of the required disciplines and specialisms – a project management and ethos will be required to support and manage a multi-disciplinary team. 3. Our preference is that the tables are used wherever possible as this is easier for the evaluations team. | 4th June 2019
14 | 31st May 2019 | Regarding this Tender opportunity. Please confirm whether the questions within the specification document need to be answered in addition to the Selection questionnaire? | The Public Contracts Regulations 2015 have made it a compulsory requirement to issue a complete tender pack at day one of The Restricted Procedure; Stage one of this procedure requires the completion and submission of the Selection Questionnaire and any associated attachments only – with the remaining documents – ITT, Specification & Pricing Schedule etc., being applied to only those who are shortlisted. | 4th June 2019
15 | 1st June 2019 | I note in the ITT document, that as regards terms and conditions, the following is included:- “By submitting a Tender, Tenderers are agreeing to be bound by the JCT Design and Build 2016 Terms and Conditions of this ITT and the form of Contract without further negotiation or amendment. PLYMOUTH MARJON UNIVERSITY CANNOT NEGOTIATE WITH ANY TENDERER ABOUT THE TERMS AND CONDITIONS OF THE CONTRACT.” Can you please confirm that this is the form of contract, and that there are no other terms and conditions, other than those contained within the ITT document. | I can confirm that no other terms and conditions will apply to this procurement and resultant project from those identified in the documents issued. | 4th June 2019
16 | 3rd June 2019 | If we are acting as a Lead Consultant with sub-consultants delivering, for example, landscape design are we required to provide a completed Standard Selection Questionnaire for each sub-consultant? If so, should this include a completed Part 3 for each sub-consultancy? Do you have page or word limits are set for the answers to questions 6.1 to 6.8 in Section 6 | No – only the ‘lead’ organisation is required to complete the Selection Questionnaire as any ultimate contract will be between Plymouth Marjon University and the lead organisation, and it is understood that the Lead Organisation will perform their own due diligence checks of their sub-contractors. – That said there are sections within the Selection Questionnaire that require completion when utilising the services of sub-contracts – namely:- Question Number 1.2(a) - (i) up to and including 1.2(b) - (ii). We haven’t included a word limit – but please ensure that your response targets/addresses the salient points of each question. | 4th June 2019
17 | 3rd June 2019 | Clarification 1 - In section 4.2 of the, Selection Questionnaire: ‘Where we have specified a minimum level of economic and financial standing and/ or a minimum financial threshold within the evaluation criteria for this procurement, please self-certify by answering ‘Yes’ or ‘No’ that you meet the requirements set out.’ Please confirm if there is a minimum level of economic and financial standing required? Clarification 2 - In section 6.1 of the Selection Questionnaire: Candidates are required to provide details of up to three relevant examples of contracts, that demonstrate your organisation’s experience in delivering similar services….. Where consultants will be a sub-consultants to a lead consultant, are sub consultant’s contract case studies able to be included or do these have to be only from the lead consultant? | Clarification 1 The estimated contract value is £200,000.00 which is the required turnover; As you know the 2015 Procurement Regulations allow contracting authorities to apply a turnover of up to twice the estimated contract value (£400,000.00); but we believe a more realistic and sensible value is the £200,000.00 contract value. Clarification 2 Our preference would be that the reference sites are linked to the lead organisation – as any resultant contract will be between Plymouth Marjon University and the lead organisation. (The lead organisation is essentially responsible for undertaking due diligence checks on their sub-contractors). As I am sure you have noted this section allows a statement to be submitted should it be difficult to provide 3 examples. | 4th June 2019
18 | 3rd June 2019 | Could you advise if there is a page count / limit for the responses to 6.5, 6.6, 6.7 and 6.8? Also should the responses to these questions be entered straight into MS Word document? Can we provide the response to 6.4 as a separate pdf attachment? | We haven’t included a word limit – but please ensure that your response targets/addresses the salient points of each question. Our preference would be that the template provided is used for all responses as the evaluators are familiar with this format – embedded documents are permitted – but please ensure that you don’t PDF the final version as to do so means that we will be unable to open/access the embedded documents. | 4th June 2019
19 | 3rd June 2019 | Please can you provide clarification on the following items 1. Address of the site we can upload information to (ref, p17) 2. Word limit and page limit for questions 6.1, 6.3 – 6.8 3. Can we submit our response using our own document format with the questions clearly identified. Or 4. Should we complete the word document and provide images, diagrams and certificates as appendices | 1. The Selection Questionnaire is to be submitted electronically at procurement@marjon.ac.uk by midday on Monday 24th June 2019 2. We have purposely not included a page limit to these questions – that said tenderers are encouraged to address the salient points of the questions 3 & 4. Our preference would be that the template provided is used for all responses as the evaluators are familiar with this format – embedded documents are permitted – but please ensure that you don’t PDF the final version as to do so means that we will be unable to open/access the embedded documents. | 4th June 2019
Plymouth Marjon University have applied the 71000000 as the main CPV code - but this drill's down in to following:-
In addition to the above - our Specification Includes the following 'Acknowledging that the achievement of a detailed and meaningful analysis, will come to fruition from the scrutiny and exploration of several specialist disciplines, for example, Architects, Designers, Planners, Quantity Surveyors, Engineers, Landscapers, Business Strategists, Feasibility Consultants, Investment Specialists'.