## Price Schedule
Schedule of Works - Mechanical System at Penhill Changing Rooms
|  | £ |  | £
PRELIMINARIES |  |  | £
1.1 | Site Management: Allow for all necessary site management including a designated site manager.
1.2 | Health and Safety: Provide written risk assessments (RAMS) before commencing any work. Allow for carrying out all the work in accordance with current health and safety regulations.
1.3 | Drawings: Allow for CAD drawing.
1.4 | Fencing and access: Form a secure works site area using the existing perimeter fencing to prevent unauthorised access to the site whilst carrying out of the works. Allow for maintaining access to the site during the carrying out of the works.
1.5 | Signage: Allow for all site health and safety signage for both the public and the workforce to be in accordance with current health & safety regulations.
1.6 | Goods & Materials: Allow for all goods and materials to be supplied new, in good condition and brought to site as and when needed. Allow for protection and security of all goods and materials until the completion of the works.
1.7 | Workmanship: Allow for all workmanship to be to approved construction industry standards and codes of practice.
1.8 | Plant, tools and equipment: Allow for all necessary small plant, tools and equipment for the carrying out of the works including arranging for power as required. Note the site may be used for power provision during the carrying out of the works.
1.9 | Welfare facilities: Allow for all necessary temporary welfare facilities to be in accordance with current health and safety regulations including arranging for power, water and sanitation as required. Note the site may be used for welfare provision during the carrying out of the works.
1. 10 | Waste and Cleaning: Allow for removing all waste from site to approved tips as the work proceeds including the use of covered skips as required. Leave the site clean and tidy on completion of the works.
INTERNAL PLANT ROOM WORKS |  |  | £
2.1 | Remove and dispose of 2 No. existing 500L hot water vessels, strip out pipework to enable relocation of the plant room to the opposite end of the building. Quality Proposals - Manufacturer / Supplier / Grade / Standard / Reference: Boss unvented cylinders
2.2 | To run new cold main from incoming supply across roof space to new designated plant room.
2.3 | To install boosted cold water pump with floor mounted storage tanks
2.4 | To supply and install 3 x 500L hot water cylinders with capacity for 3 immersions on each
2.5 | To supply and install new thermostatic blending valves to serve hot water for showers.
2.6 | To supply and install water softener.
2.7 | Modify pipework in roof space to suit new location of cylinders
2.8 | Upon completion, all systems must be tested and commissioned to ensure functionality. To include booster pump, blending valves and immersion heaters
INTERNAL -CHANGING ROOMS 1-6 (INCLUSIVE) |  |  | £
3.1 | To remove all existing shower heads and push buttons, and make good any existing holes in cladding boards.
3.2 | To supply and install new hygienic PVC wall cladding (grey or similar) all shower enclosures.
3.3 | To supply and install new exposed (surface mounted) chrome concussive showers, 3 per room (x18), with new exposed (surface mounted) chrome pipework to suit.
3.4 | To replace shower waste & grate to all rooms
3.5 | To replace basin taps, acrylic mirror & new toilet seat pads in all rooms
3.6 | To setup the water softener and complete pipework insulation.
3.7 | To conduct a handover and supply all necessary documentation to the Council
ELECTRICAL & MECHANICAL INSTALLATIONS |  |  | £
4.1 | To install wiring system for 3 x dual element storage heaters thermostatically controlled and utilising existing RCCB main switch distribution board in accordance with current electrical installation regulations and codes of practice.
4.2 | To install an additional 3phase distribution board within new plant room for the water heaters in accordance with current electrical installation regulations and codes of practice
4.3 | Allow for testing and reporting findings.
4.4 | To conduct a handover and supply all necessary documentation / certificates to the Council
4.5 | To comply and manage any matters pertaining to building control / regulations.
CONTINGENCIES |  |  | £
5.1 | Provisional Sum: Allow a provisional sum for unforeseen problems.
---------------------
£
---------------------