**DATED                                                    202[\*]**

|  |  |  |  |
| --- | --- | --- | --- |
|  | (1) | THE MAYOR AND BUrgesses OF THE royal borough OF Kensington and chelsea |  |
|  | (2) | [CONTRACTOR] |  |

|  |  |  |
| --- | --- | --- |
|  | BUILDING CONTRACT  Incorporating and amending the  **JCT Minor Works Building Contract With Contractor's Design, 2016 Edition**  **Relating to CHUMS Resource Centre Works, Henry Dickens Court** |  |



**THIS AGREEMENT is dated**

**BETWEEN**

1. **THE MAYOR AND BURGESSES OF THE ROYAL BOROUGH OF KENSINGTON AND CHELSEA** of Town Hall, Hornton Street, London W8 7NX(Employer, such term to include any successors in title or permitted assigns).
2. **[CONTRACTOR]** incorporated and registered in England and Wales with company number [NUMBER] whose registered office is at [ADDRESS] (Contractor).

BACKGROUND:-

1. The Employer wishes to procure the construction of certain works, including the design of part of those works.
2. The Contractor has agreed to carry out that design and construction work, as required by this agreement.
3. The Employer and the Contractor have agreed to incorporate and amend the JCT Minor Works Building Contract With Contractor's Design, 2016 edition ("**JCT MWD 2016**") as set out in this agreement.

**AGREED TERMS:-**

# Interpretation

The following definitions and rules of interpretation apply in this agreement.

## Definitions:

|  |  |
| --- | --- |
| JCT Articles | 1. the section of the JCT MWD 2016 titled "Articles". |
| JCT Attestation | 1. the section of the JCT MWD 2016 titled "Attestation". |
| JCT Conditions | 1. the section of the JCT MWD 2016 titled "Conditions". |
| JCT Contract Particulars | 1. the section of the JCT MWD 2016 titled "Contract Particulars". |
| JCT Recitals | 1. the section of the JCT MWD 2016 titled "Recitals". |
| Schedule of Amendments | 1. the parties, background, agreed terms and schedules forming this part of this agreement, which amend the JCT MWD 2016. |

## Capitalised terms used in this agreement have the same meanings as in the JCT MWD 2016, unless the meaning in the JCT MWD 2016 is different from, or conflicts with, the meaning given in the Schedule of Amendments, in which case the Schedule of Amendments prevails.

## The schedules form part of this agreement and shall have effect as if set out in full in the body of this agreement. Any reference to this agreement includes the schedules.

## A reference to a company shall include any company, corporation or other body corporate, wherever and however incorporated or established.

## Any obligation on a party not to do something includes an obligation not to allow that thing to be done.

## A reference to this agreement or to any other agreement or document referred to in this agreement is a reference to this agreement or such other agreement or document as varied or novated (in each case, other than in breach of the provisions of this agreement) from time to time.

## References to clauses, schedules and annexes are to the clauses, schedules and annexes of this agreement and references to paragraphs are to paragraphs of the relevant schedule.

## Without prejudice to clause 1.2, in case of any difference, discrepancy or conflict between the Schedule of Amendments and the JCT MWD 2016, the Schedule of Amendments shall prevail.

## Any words following the terms including, include, in particular, for example or any similar expression shall be construed as illustrative only and shall not limit the sense of the words, description, definition, phrase or term preceding those terms.

# Incorporation and amendment of the JCT MWD 2016

## This agreement incorporates and amends the JCT MWD 2016 as follows:

### it incorporates the JCT Recitals, as amended by Part 1 of Schedule 1;

### it incorporates the JCT Articles, as amended by Part 2 of Schedule 1;

### it incorporates the JCT Contract Particulars, as set out at Part 3 of Schedule 1; and

### it incorporates the JCT Conditions, as amended by Part 4 of Schedule 1.

## This agreement does not incorporate the JCT Attestation.

# Governing law and jurisdiction

This agreement and any dispute or claim arising out of or in connection with it or its subject matter or formation (including non-contractual disputes or claims) shall be governed by and construed in accordance with the law of England. The parties hereby submit to the exclusive jurisdiction of the English Courts.

# Counterparts

This Contract may be executed in any number of counterparts, each of which when executed shall constitute a duplicate original, but all the counterparts shall together constitute the one Contract.

This document has been executed as a deed and is delivered on the date stated at the beginning of it.

|  |  |  |
| --- | --- | --- |
| The Common Seal of **THE MAYOR AND BURGESSES OF THE RoYAL BOROUGH OF KENSINGTON AND CHELSEA** was hereunto affixed in the presence of: | ) |  |
|  | ) |  |
|  | ) |  |
|  | ) | ……………………………………………….. |
|  | ) | Authorised signatory |

|  |  |  |
| --- | --- | --- |
| Executed as a deed by **[CONTRACTOR]** | ) |  |
| acting by two directors or by a director and the company secretary | ) |  |
|  | ) |  |
|  | ) | Director |
|  |  |  |
|  |  |  |
|  | ) |  |
|  | ) |  |
|  | ) | Director / Secretary |

1. - Schedule of amendments
2. - Recitals
3. First Recital

Complete the First Recital with this description of the Works:

CHUMS Resource Centre WORKS at Marley House, Henry Dickens Court, St Anns Road, W11 4DJ (as further detailed in the Contract Documents).

1. Second Recital

Complete the Second Recital with this description of the Contractor's Designed Portion:

M&E Items –

A suitable drainage system to serve the kitchen and W/C installation as per the proposed layout.

A domestic hot and cold-water systems suitable to serve the kitchen and W/C installation as per the proposed layout.

A suitable ventilation system to serve the office areas.  The fan units are to be Mitsubishi Lossnay heat recovery units (or equal and approved).

A suitable air conditioning heat pump system to provide heating and cooling in the main open office to suit the new proposed design.  The system is to be a Mitsubishi Mr Slim ceiling mounted cassette unit (or equal and approved).

A suitable air conditioning heat pump system to provide heating and cooling in the small office to suit the new proposed design.  The system is to be a Mitsubishi M Series wall mounted unit (or equal and approved).

A suitable electrical system suitable to serve the proposed layout. The system will consist of a new sub-main distribution board, all containment and all necessary circuit breakers, circuit cabling, isolators, etc. to serve socket outlets, lighting circuits, and small power to all mechanical plant and life safety systems.

A suitable new lighting system suitable for proposed layout for the space including emergency lighting.

If the fire alarm cannot be extended to accommodate the proposed new space, then allow to design, supply and install a new fire alarm system to L1 Category standard and install interlinks to allow it to connect with the existing fire alarm system if practicable.

A suitable Dimplex electric panel heaters (or equal and approved), with integral thermostats and controllers, in the kitchen and WC

Allow to install all power, containment, cabling and controls (including operating buttons, etc.) to the proposed power assisted door position at the entrance to the proposed new space.

(as further detailed in the Contract Documents).

1. Third Recital
   1. Complete the Third Recital with this description of the Contract Drawings:

As attached at Annex A.

* 1. Delete the following:

["a Specification ('the Contract Specification')"]

~~["Work Schedules"]~~

* 1. Delete the final paragraph of the Third Recital and replace with:

"and those documents are attached to this Contract at Annexes A to C (inclusive)."

1. Fourth Recital

Add to the end of the Fourth Recital: "or has otherwise provided a breakdown of the Contract Sum, which is attached at Annex D of this Contract."

1. - Articles
2. Article 2: Contract Sum

Complete Article 2 with this Contract Sum:

[SUM IN WORDS] (£[SUM IN FIGURES])

1. Article 3: Architect / Contract Administrator

Complete Article 3 with this Architect / Contract Administrator:

Rider Levett and Bucknall (RLB) of 15 Colmore Row, Birmingham, West Midlands, B3 2BH (company number 04653580).

Insert the following at the end of Article 3: “The Contractor shall, in good faith, fully cooperate with the Architect / Contract Administrator at all times in the performance of its obligations under this Contract”.

1. Article 4: Principal Designer

Complete Article 4 with this Principal Designer:

The Architect / Contract Administrator

1. Article 5: Principal Contractor

Complete Article 5 with this Principal Contractor:

The Contractor **OR** [NAME OF FIRM] of [ADDRESS] (company number [NUMBER]).

1. New Article 11: Effect of Approval

Insert new Article 11:

"Notwithstanding any other provision of this Contract, the Contractor shall not be relieved from its obligations under this Contract nor shall such obligations be removed, restricted, limited or qualified in any way by the presence of the Employer or the Architect / Contract Administrator or their agents or representatives on the site of the Works, or the carrying out of tests on the instructions of the Employer or the Architect / Contract Administrator or by any instruction, direction, admission, consent, approval, confirmation, sanction, acknowledgement, advice or inspection made or given by or on behalf of the Employer or the Architect / Contract Administrator."

1. - Contract Particulars

| **Clause Reference** | **Subject** | **Particulars** | |
| --- | --- | --- | --- |
| *Fifth Recital and Schedule 2 (paragraphs 1.1, 1.2, 1.5, 1.6, 2.1 and 2.2)* | Base Date | The date of this Contract. | |
| *Fifth Recital and clause 4·2* | Construction Industry Scheme (CIS) | Employer at the Base Date for the purposes of the CIS | is a ‘contractor’ |
| *Sixth Recital* | CDM Regulations | The project is notifiable. | |
| *Seventh Recital* | Framework Agreement (if applicable)  *(State date, title and parties.)* | Not applicable | |
| *Eighth Recital and Schedule 3* | Supplemental Provisions  *(Where neither entry against an item below is deleted, the relevant Supplemental Provision applies.)* | | |
| Collaborative working | Supplemental Provision 1 applies | |
| Health and safety | Supplemental Provision 2 applies | |
| Cost savings and value improvements | Supplemental Provision 3 applies | |
| Sustainable development and environmental considerations | Supplemental Provision 4 applies | |
| Performance indicators and monitoring | Supplemental Provision 5 applies | |
| Notification and negotiation of disputes | Supplemental Provision 6 applies | |
| Where Supplemental Provision 6 applies, the respective nominees of the Parties are | Employer’s nominee: Namratha Mohan  Contractor's nominee: [ ] **[Note: To be completed by Contractor.]**  or such replacement as each Party may notify to the other from time to time. | |
| *Article 7* | Arbitration  *(If neither entry is deleted, Article 7 and Schedule 1 do not apply. If disputes and differences are to be determined by arbitration and not by legal proceedings, it must be stated that Article 7 and Schedule 1 apply.)* | Article 7 and Schedule 1 *(Arbitration)* do not apply | |
| 2.3 | Works commencement date | [INSERT DATE] | |
| 2.3 | Date for Completion | [INSERT DATE]  or such later date for completion as is fixed under clause 2.8 | |
| 2.9 | Liquidated damages | at the rate of £350.00 per week or pro-rata for part thereof | |
| 2.10A | Pre-requisites to practical completion | In addition to the matters listed at clause 2.10A, the following shall be a pre-requisite to achievement of practical completion:  Documentation to be provided before Practical Completion:   * Building Control Completion Certificate * M&E Commissioning Certificates * H&S File | |
| 2.11 | Rectification Period | 12 months from the date of practical completion. | |
| 4.3 | Interim payments - Interim Valuation Dates | The first Interim Valuation Date is the date falling one month after the Works commencement date and thereafter the same day in each calendar month.  **[Note: The JCT MW template provides for monthly valuations and 30 day payment terms (the notional 'due date' is the relevant Interim Valuation Date and the 'final date for payment' is 30 days after the due date). Further amendments will be required if this mechanism needs altering for a particular project (although please bear in mind the Fair Payment Charter and the PCR 2015).]** | |
| 4.3 | Payments due prior to practical completion - percentage of the total value of work etc.  *(The percentage is 95 per cent unless a different rate is stated.)* | 95%  **[Note: The draft assumes a 5% retention from interim payments, reducing to 2.5% on practical completion.]** | |
| 4.3 | Payments becoming due on or after practical completion - percentage of total amount to be paid to the Contractor  *(The percentage is 97.5 per cent unless a different rate is stated.)* | 97.5% | |
| 4.8.1 | Supply of documentation for computation of amount to be finally certified  *(The period is 3 months unless a different period is stated.)* | [3 months] from the date of practical completion | |
| 5.3 | Contractor’s Public Liability Insurance: injury to persons or property - the required level of cover is not less than | £5M for any one occurrence or series of occurrences arising out of one event  **[Note: Contractor to provide evidence of public liability cover.]** | |
| 5.3B | Third party consents, approvals, licences and permissions | The Contractor is responsible for obtaining the following without addition to the Contract Sum:  Building Control Approvals | |
| 5.4A, 5.4B and 5.4C | Insurance of the Works etc. – alternative provisions | Clause 5.4C *(Works and existing structures insurance by other means)* applies.  Insurance of the works is by the Council under its Joint Names policy for All Risks  Insurance for Existing Structures is by the Council but it is not a Joint names policy nor includes any waiver of subrogation for damage to the existing strictures | |
| 5.4A and 5.4B | Percentage to cover professional fees  *(If no other percentage is stated, it shall be 15 per cent.)* | 15 per cent | |
| 5.4C | Insurance arrangements - details of the required policy or policies | are set out in the following document: | |
| 5.8 | Professional indemnity insurance | Minimum limit of indemnity: £5M  Basis on which such insurance is to be held: Any one claim  Duration of insurance: 12 years following practical completion of the Works.  **[Note: Contractor to provide evidence of PI insurance cover.]** | |
| 7.2 | Adjudication | The Adjudicator is to be nominated by the nominating body | |
| Nominating body – where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established) | The Royal Institution of Chartered Surveyors | |

PART 4 – Conditions

1. Clause 1.1
   1. Amend these definitions:
      1. Agreement: add to the end of the definition, before the full stop:

", each as amended by the Schedule of Amendments".

* + 1. Article: add to the end of the definition, before the full stop:

", as amended by Part 2 of the Schedule of Amendments".

* + 1. CDM Regulations: add to the end of the definition, before the full stop:

"and any related guidance requirements issued by the Health and Safety Executive from time to time, or any remaking thereof or any amendments to a regulation therein".

* + 1. Conditions: add to the end of the definition, before the full stop:

", each as amended by Part 4 of the Schedule of Amendments".

* + 1. Contract Particulars: add to the end of the definition, before the full stop:

", as set out in Part 3 of the Schedule of Amendments".

* + 1. Recital: add to the end of the definition, before the full stop:

", as amended by Part 1 of the Schedule of Amendments".

* 1. Add these definitions:

"Construction Products Regulations: the Construction Products Regulations 2013 (SI 2013/1387) and the Construction Products Regulation (305/2011/EU), both as amended by the Construction Products (Amendment etc) (EU Exit) Regulations 2019 (SI 2019/465)."

"Contract Documents: the Agreement, these Conditions and all Schedules and Annexes hereto, the Contract Drawings, the Employer's Requirements, the Contract Specification, the Work Schedules, and the Contractor's priced Contract Specification or Schedule of Rates or pricing breakdown (as applicable)."

“Covid-19 Pandemic: the outbreak of the virus known as Coronavirus or SARS-CoV-2 (recognised as a pandemic by the World Health Organization on 11 March 2020) including any secondary or subsequent resurgence of that virus or a mutated form of the same”.

"Deleterious: materials, equipment, products or kits that are generally accepted, or generally suspected, in the construction industry at the time of specification or use as posing a threat to the health and safety of any person; or posing a threat to the structural stability, performance or physical integrity of the Works or any part or component of the Works; or reducing, or possibly reducing, the normal life expectancy of the Works or any part or component of the Works; or not being in accordance with any relevant British or European Standard, relevant code of practice, good building practice or any applicable agrément certificate issued by the British Board of Agrément; or having been supplied or placed on the market in breach of the Construction Products Regulations."

“Employer’s Policies: the Employer's policies set out at Annex E to this Contract.”

"Funder: a person that has provided, or is to provide, finance in connection with the whole or any part of the Works or the completed Works; or the site of the Works, whether that person acts on its own account, as agent for a syndicate of other parties or otherwise (including, without limitation, any entity that enters or has entered into a ‘forward funding’ or ‘forward purchase’ agreement with the Employer)."

"Key Sub-contractor: any sub-contractor appointed by the Contractor to carry out design works and/or named or identified in Part 1 of Schedule 5 to the Schedule of Amendments, and any replacement of a Key Sub-contractor."

"Material: all designs, drawings, models, plans, specifications, design details, photographs, brochures, reports, notes of meetings, CAD materials, calculations, data, databases, schedules, programmes, bills of quantities, budgets and any other materials provided in connection with the Works (and completed Works) and all updates, amendments, additions and revisions to them and any works, designs, or inventions incorporated or referred to in them."

"Permitted Uses: the design, construction, completion, reconstruction, modification, refurbishment, development, maintenance, facilities management, funding, disposal, letting, fitting-out, advertisement, decommissioning, demolition, reinstatement, extension, building information modelling and repair of the Works (and the completed Works)."

"Professional Consultant: any professional consultant appointed by the Contractor to carry out design services and/or named or identified in Part 1 of Schedule 4 to the Schedule of Amendments and any replacement of a Professional Consultant."

"Purchaser: any person (save for a residential occupier) who takes or agrees to take a freehold interest in the whole or any part of the Works."

“Schedule of Information Requirements: a schedule stating the information that the Contractor requires the Employer, the Architect / Contract Administrator and the Employer’s Persons to release and the required timescales for that release.”

"Standard of Care: all the reasonable skill, care and diligence to be expected of a qualified and experienced architect (or other appropriate professional designer) undertaking the design of works similar in scope, character, value and complexity to the CDP Works."

"Tenant: any person (save for a residential occupier) who takes or agrees to take a leasehold interest in the whole or any part of the Works."

"Third Party Agreements: the agreements, or extracts from agreements, between the Employer and third parties, which may affect the Works, attached at Schedule 7 to the Schedule of Amendments, as supplemented by any instruction from the Architect / Contract Administrator referred to in clause 3.6."

“Wage Levels: means:

* in relation to employees working in London, the minimum wage set by the Resolution Foundation (or any replacement or successor body) on behalf of the Living Wage Foundation (or any replacement or successor body) as the London Living Wage from time to time;
* in relation to employees working outside of London and aged 25 or over, the minimum wage set by the Resolution Foundation ( or any replacement or successor body) on behalf of the Living Wage Foundation (or any replacement or successor body) as the National Living Wage from time to time; and
* in relation to employees working outside of London and aged 24 or under, the national minimum wage.”

1. Clause 1.2

In clause 1.2, after "the Work Schedules" insert ", the Contractor's pricing breakdown". After "override or modify", add "the Schedule of Amendments, "

1. Clause 1.5

Delete "Notwithstanding any other provision of this Contract," and replace with "Subject to clauses 3.1 and 5A of this Contract,"

1. Clause 1.7

In clause 1.7.2 delete "and either Party's consent under clause 3.1" and replace with "or clause 3.1.4".

1. Clause 1.9

Insert a new clause 1.9:

"The appointment of the Contractor under this Contract shall be deemed to have commenced with effect from the date when the Contractor first began to carry out any services or works relating to the Works. To the extent that any such services or works were carried out prior to or otherwise than pursuant to this Contract, the duties and obligations contained in this Contract shall be deemed to apply to the carrying out of those services or works. All payments made in respect of services or works carried out prior to the date of this Contract shall be treated as payments on account of sums due under this Contract."

1. Clause 2.1
   1. In sub-clause 2.1.1, delete "reasonable skill, care and diligence" and replace with "the Standard of Care".
   2. In sub-clause 2.1.1, delete the words ", so far as not described or stated in the Employer's Requirements,".
   3. Delete sub-clause 2.1.2 and replace with: “ensure the proper integration, co-ordination and compatibility of the various components and elements that make up and comprise the CDP Works, one with another and with the remainder of the Works (and comply with regulations 8 to 10 of the CDM Regulations and all Architect/Contract Administrator directions in this regard, subject to the provisions of clause 3.4.2);”
   4. Delete sub-clause 2.1.4 and replace with "Number not used".
2. Clause 2.1A

Insert a new clause 2.1A as follows:

"Design

.1 Without derogating from any other provision in this Contract, the Contractor shall be fully responsible in all respects for the design of the CDP Works including (without limitation) all design prepared or proposed by or on behalf of the Employer before the date of this Contract that forms part of the Employer's Requirements.

.2 Without prejudice to clause 2.1A.1 the Contractor shall be fully responsible in all respects for any design of the CDP Works that is carried out by a professional consultant or specialist designer or sub-contractor that the Contractor has or will employ (including without limitation a person employed at the request of the Employer or novated to the Contractor) whether such design work is carried out before, on or after the date of this Contract.

.3 Without derogating from any other provision in this Contract, the Contractor warrants to the Employer that it shall use the Standard of Care when designing the CDP Works.

.4 The Contractor warrants that its design of the CDP Works complies with Statutory Requirements."

1. Clause 2.1B

Insert new clause 2.1B:

"Audit, Employer Policies, Wage Levels and publicity

.1 The Contractor shall:

.1 at all times maintain complete and accurate records and information as to all work and services carried out, and all sums paid, under this Contract;

.2 afford the Employer and/or the Employer’s designated auditor(s) access to all such records and information at all reasonable times on request; and

.3 provide copies of such records and information as and when reasonably required by the Employer and/or the Employer’s designated auditor(s).

.2 The Contractor shall, and shall procure that the Contractor’s Persons, comply with the Employer’s Policies.

.3 The Contractor shall ensure that staff employed by it, or by any of its sub-contractors, who are engaged on the provision of the Works are paid no less than the relevant Wage Levels.

.4 The Contractor shall not, and shall procure that the Contractor’s Persons shall not without the prior written consent of the Employer publish alone or in conjunction with any other person any articles, illustrations, photographs, videos or press announcements relating to the Works, or otherwise publicise this Contract or the Works, save in accordance with any legal obligation upon the Contractor to do so.”

1. Clause 2.1C

Insert new clause 2.1C:

“Covid-19 precautions

The Contractor undertakes:

.1 to take all practicable steps to prevent the transmission of Covid-19 (and other disease and infection) at the site and generally among the Contractor’s Persons;

.2 to comply, and to require all persons coming onto the site or otherwise performing the Works to comply, at all times with all Statutory Requirements good industry practice, guidance and operational protocols relating to the Covid-19 Pandemic;

.3 to comply with all Covid-19 Pandemic related reporting requirements, data gathering and information sharing requirements reasonably imposed by the Employer from time to time; and

.4 to require its subcontractors (at all levels) to agree a clause equivalent in all material respects to this clause 2.1C.”

1. Clause 2.1D

Insert new clause 2.1D:

“.1 [Note: Amend this opening paragraph as needed to suit the requirements of the particular project] The Contractor acknowledges that the site forms part of *Residential Blocks* and that certain related persons (the “Other Personnel”) will be present during the carrying out of the Works. The Contractor further acknowledges that the Employer may procure the completion of certain works not forming part of this Contract (the “Third Party Works”) during the carrying out of the Works. The Contractor shall:

.1 fully and actively cooperate with the Other Personnel and any contractors engaged in connection with the Third Party Works in the performance of the Contractor’s duties and obligations under this Contract;

.2 comply with all reasonable instructions issued by the Employer (or the Architect / Contract Administrator) in respect of the coordination of the Works with the Third Party Works and the requirements and activities of the Other Personnel; and

.3 take all reasonably practice measures to ensure that no unforeseen interruption or interference is caused by or to the Other Personnel or the Third Party Works in the execution of the Works.

Subject to clause 2.1D.2 and 2.1D.3, the Contractor shall not be entitled to an extension of time or additional payment (whether by addition to the Contract Sum or otherwise) due to the requirements of this clause.

.2 Where and to the extent that the Third Party Works or the requirements and activities of the Other Personnel are not sufficiently detailed in the Contract Documents to enable a competent and experienced contractor to carry out and complete the Works in conjunction with the same, without consequent delay and/or disruption to the Works, then such consequent delay and/or disruption shall entitle the Contractor to apply for an extension of time under clause 2.8;

3. Where and to the extent that the regular progress of the Works is delayed or disrupted due to any impediment, prevention or default (whether by act or omission) by the Other Personnel or any contractor engaged in connection with the Third Party Works, then this shall entitle the Contractor to apply for an extension of time under clause 2.8.”]

1. Clause 2.1E

Insert new clause 2.1E:

"Site conditions

The Contractor has had an opportunity of inspecting the physical conditions (including but not limited to adverse site conditions typically refer to ground conditions [which](https://eur02.safelinks.protection.outlook.com/?url=https%3A%2F%2Fwww.lawinsider.com%2Fdictionary%2Fadverse-ground-conditions&data=05%7C02%7Ccaroline.stone%40rbkc.gov.uk%7C93dbe00ab5a54f2be67f08dc104dfa6c%7C50d8c115b77f4395a3ba3b407caf0d88%7C0%7C0%7C638403174348045525%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000%7C%7C%7C&sdata=C6hgk2%2BgLb20K8VA4fGXFrtHtSKQ7nmdOy0CvsjaxNo%3D&reserved=0) prevent or delay the carrying out of the works or which render them more expensive to carry out) and other conditions of or affecting the site of the CDP Works and shall be deemed to be fully acquainted with the same before the date of this Contract and to have obtained all necessary information as to risks, contingencies and all other circumstances which may influence or affect the execution of the CDP Works. Notwithstanding any other provision of this Contract, no failure on the part of the Contractor to discover or foresee any such condition, risk, contingency or circumstance shall entitle the Contractor to any additional payment (whether by way of an addition to the Contract Sum or otherwise) or an extension of time. As between the Contractor and the Employer, the Contractor shall not and shall not be entitled to rely upon any survey, report or other document prepared by or on behalf of the Employer regarding any such matter as is referred to in this clause 2.1E and the Employer makes no representation or warranty as to the accuracy or completeness of any such survey, report or document. The Employer shall have no liability arising out of or in relation to any such survey, report or document or from any representation or statement, whether negligently or otherwise made, contained in such survey, report or other document.”

1. Clause 2.2
   1. Insert a new clause 2.2.3:

"The Contractor shall not specify or use anything in the Works, which, at the time of specification or use, is Deleterious."

* 1. Insert a new clause 2.2.4:

“The Contractor shall ensure that all goods, materials, products and equipment intended for incorporation in the Works are correctly and properly installed in accordance with manufacturer’s instructions and recommendations. To the extent that the Contractor considers an alternative method of installation is required or would better suit any goods, materials, products or equipment, it shall seek the Architect / Contract Administrator’s prior written approval. Any such approval given by the Architect / Contract Administrator shall not relieve the Contractor from his obligation to ensure that goods, materials, products and equipment are correctly and properly installed.”

1. Clause 2.5

In clause 2.5.1, delete "the Contract Drawings, the Contract Specification, the Work Schedules and the Employer's Requirements" and replace with "documents prepared by the Employer (but excluding the Employer's Requirements)".

* 1. In clause 2.5.2, delete "prepared by the Contractor for the CDP Works" and replace with "relating to the CDP Works, any other documents prepared by or on behalf of the Contractor, and any inconsistency between such documents and any documents prepared by or on behalf of the Employer".

1. Clause 2.8

Insert the following at the end of the first sentence of clause 2.8, before the full stop:

“(such notification to include, without limitation, (i) a proposed revised programme for the Works; and (ii) copies of any related delay notifications or particulars issued by the Contractor’s sub-contractors (such copies to be provided on an open-book basis))”

1. Clause 2.8A

Insert a new clause 2.8A, as follows:

"The Contractor shall not be entitled to any extension of time in respect of any delay attributable to any act, breach of contract, negligence, omission or default by the Contractor or any agent, employee or other person engaged by the Contractor.”

1. Clause 2.8B

Insert a new clause 2.8B as follows:

“Without prejudice to the generality of clause 2.8A, if the Contractor fails to give the notice and/or particulars required under clause 2.8 at the earliest practicable opportunity when a competent and experienced contractor could have given them, then any associated extension of time shall be assessed as if the Contractor had given the notice and/or particulars at that time.”

1. Clause 2.10A

Insert new clause 2.10A:

"It shall be a pre-requisite to practical completion being certified that the Contractor shall have:

.1 completed the Works such that they are free from apparent defects, subject only to minor defects which do not affect or impair the use, enjoyment, occupation and/or fitting out of the Works by the Employer;

.2 delivered all collateral warranties required under this Contract;

.3 provided all records, documents, commissioning data, maintenance hand over schedules, manufacturers warranties, operation certificates and commissioning schedules in relation to the Works, in accordance with the Contract Documents and the Employer's reasonable requirements; and

.4 satisfied any further pre-requisites to practical completion as may be stated in the Contract Particulars."

1. Clause 2.11

Add the following to the end of clause 2.11:

"Any defects, shrinkages and other faults notified in accordance with this clause 2.11 shall be made good by the Contractor within a reasonable time (and forthwith in the case of a defect, shrinkage or other fault raising health and safety issues or preventing occupation or use of the relevant part of the Works). If the Contractor fails to make good any defects, shrinkages or other faults notified by the Employer pursuant to this clause within the time required under this clause then the Employer shall be entitled to instruct another contractor to carry out such works and to recover the cost of the same from the Contractor as a debt and/or to deduct the same from any monies otherwise due to the Contractor."

1. Clause 2.11A

Add a new clause 2.11A after clause 2.11:

"**Snagging list and defects, shrinkages or other faults remaining at practical completion**

Clause 2.11 shall, without limitation, apply to:

.1 any items identified on any snagging list issued by the Architect/Contract Administrator at or around practical completion;

.2 any defects, shrinkages or other faults in the Works at practical completion; and

.3 any incomplete work, forming part of the Works, remaining at practical completion."

1. Clause 2.13

Add a new clause 2.13 after clause 2.12:

"**Copyright**

.1 The Contractor grants to the Employer, with immediate effect, an irrevocable, non-exclusive, non-terminable, royalty-free, world-wide licence to copy and make full use of any Material prepared by or on behalf of the Contractor for any purpose relating to the Works (and the completed Works) including any of the Permitted Uses.

.2 This licence carries the right to grant sub-licences and is transferable to third parties without the Contractor's consent.

.3 The Employer may, at any time (whether before or after completion of the Works, or termination of the Contractor's engagement under this Contract), request a copy or copies of (some or all of) the Material from the Contractor. On the Employer's payment of the Contractor's reasonable charges for providing the copy (or copies), the Contractor shall provide the copy (or copies) to the Employer.

.4 All royalties or other sums payable in respect of the supply and use of any patented articles processes or inventions required in connection with the Works shall be paid by the Contractor and the Contractor shall indemnify the Employer from and against all claims, proceedings, damages, costs, and expenses suffered or incurred by the Employer by reason of the Contractor infringing or being held to infringe any intellectual property rights in the course of or in connection with the Works.

.5 The Contractor hereby unconditionally and for all purposes waives all moral rights to which it is entitled under Part One of Chapter IV of the Copyright Designs and Patents Act 1988 in all Material produced or to be produced by the Contractor pursuant to this Contract (and shall procure an equivalent waiver from its sub-contractors).

.6 The Contractor shall have no liability for use of the Material for any purpose other than that for which it was prepared and/or provided."

1. Clause 2.14

Add a new clause 2.14 after clause 2.13:

"**Third Party Agreements**

.1 The Contractor shall be deemed to have read the Third Party Agreements and to be fully aware of the obligations, risks and liabilities assumed by the Employer under them.

.2 The Contractor shall ensure that no act or default or omission on its part or on the part of any of its employees or sub-contractors in relation to the performance by the Contractor of its obligations under this Contract shall cause, contribute or otherwise give rise to any breach by the Employer of any of its obligations under the Third Party Agreements."

1. Clause 2.15

Insert a new clause 2.15:

"Contractor’s additional information sharing requirements

.1 The Contractor shall at its own cost prepare, and keep updated during the carrying out of the Works, a master programme showing how the Contractor intends to time and sequences the Works (including the design phase, lead-in times for procurement of materials, and the construction phase) in order to achieve practical completion on or before the completion date. The Contractor shall provide a copy of the latest master programme to the Employer whenever reasonably requested and the Employer shall be entitled to require the Contractor to submit a revised programme if at any time it considers that the details do not comply with the requirements of this Contract.

.2 Where and to the extent required by the Employer or the Architect / Contract Administrator, the Contractor shall at its own cost prepare, and keep updated during the carrying out of the Works, a Schedule of Information Requirements.

.3 Without prejudice to its other duties and obligations under this Contract, the Contractor shall provide (at its own cost) such information as the Employer or the Employer’s Persons may require from time to time on the nature, state and progress of the Works (including without limitation information on the selection of goods and materials, buildability, procurement times and construction times).”

1. Clause 3.1

Delete clause 3.1 and replace with:

".1 The Employer may on two occasions without the consent of the Contractor assign or otherwise transfer the benefit of this Contract to any person. In this Contract the term "Employer" shall be construed accordingly.

.2 The Employer shall notify the Contractor of any assignment within 10 Business Days.

.3 The Contractor shall not contend that any person to whom the benefit of this Contract is assigned under this clause 3.1 may not recover any sum under this Contract because that person is an assignee and not a named party to this Contract.

.4 The Contractor shall not assign or charge the benefit of this Contract or any right arising under it without the Employer's prior consent, which the Employer may withhold at its absolute discretion (save that the Employer’s consent shall not be required where and to the extent that the assignment is automatically permitted by virtue of the Business Contract Terms (Assignment of Receivables) Regulations 2018)."

1. Clause 3.2

Insert the following at the end of clause 3.2:

"The Employer shall be entitled (acting reasonably) to require the removal of a person in charge or any other person engaged on the carrying out of the Works if, in the Employer’s opinion, their performance or conduct is or has been unsatisfactory and the Contractor shall promptly remove such person and replace them with such person as the Employer shall first have approved in writing. Any cost incurred by the Contractor in replacing a person in charge or any other person engaged on the carrying out of the Works (in any circumstances) shall be borne by the Contractor. The person in charge shall keep complete and accurate records regarding on-site activity in accordance with any requirements reasonably imposed by the Employer and shall make the same available for inspection by the Employer at all reasonable times.”

1. Clause 3.3
   1. Insert the following at the end of clause 3.3.1:

“The Employer may refuse consent if, without limitation, there are reasonable concerns regarding the proposed sub-contractor’s claims or incidents records, competence, experience and/or organisational capability.”

* 1. In the first paragraph of clause 3.3.2, after "Short Form of Sub-Contract." insert:

"The appointment of all Professional Consultants and Key Sub-Contractors shall be on terms and conditions which are to be approved by the Employer (such approval not to be unreasonably withheld or delayed). The Contractor shall upon reasonable request (but not later than 14 days from request) by the Employer or the Architect / Contract Administrator, provide a full copy of the form of sub-contract to the Employer or the Architect / Contract Administrator (as applicable), redacted as necessary to remove commercially sensitive pricing information only."

* 1. Insert new sub-clause 3.3.2.4:

"where applicable, for the execution and delivery by the sub-contractor, in each case within 10 Business Days of receipt of a written request by the Contractor, of such collateral warranties as comply with this Contract."

1. Clause 3.4
   1. Delete the final sentence of clause 3.4.1 and replace with "If instructions are given orally the Architect / Contract Administrator shall confirm them in writing as soon as reasonably practicable".
   2. Delete clause 3.4.2 and replace with "Not used".
2. Clause 3.6

Insert the following at the end of clause 3.6.1:

"The Architect / Contract Administrator or the Employer may, without invalidating this Contract, issue an instruction supplementing or amending the Third Party Agreements."

1. Clause 3.9
   1. In clause 3.9.4, delete "immediately" and replace with "promptly".
   2. Add new clause 3.9.5:

"where the Contractor is not the Principal Designer but is the Principal Contractor and the Principal Designer's appointment concludes before practical completion of the Works, the Contractor shall review, update and revise the health and safety file in accordance with regulations 12(8) to (10) of the CDM Regulations. Where the Contractor is not the Principal Designer, the Contractor shall further provide (at its own cost) all necessary assistance to and co-operate fully with the Principal Designer in the performance of its duties.”

* 1. Add new clause 3.9.6:

“the Contractor warrants to the Employer that he has the necessary skills, knowledge and experience to undertake all roles performed pursuant to the CDM Regulations under or in connection with this Contract and that it has sufficient resources and will allocate those resources to the fulfilment of such duties.”

* 1. Add a new clause 3.9.7:

“the Contractor hereby warrants that in relation to the preparation of the design of the CDP Works it shall carry out and fulfil, and shall ensure that all sub-contractors responsible for design shall carry out and fulfil, the duties of a designer under the CDM Regulations. The Contractor shall further ensure that all of his consultants, sub-contractors and suppliers shall liaise and co-operate with the Principal Designer.”

1. Clause 3.10

Insert new clause 3.10:

"Project meetings

The Contractor shall attend project meetings convened by the Architect/Contract Administrator upon reasonable notice and at reasonable intervals and representatives of the Employer and the Employer's professional consultants and any other persons authorised by the Employer or the Architect/Contract Administrator (including, without limitation, representatives of Purchasers, Tenants and/or Funders) shall be permitted to attend such meetings."

1. Clause 4.1
   1. Delete the existing text of clause 4.1 and replace with: “The Contract Sum is exclusive of VAT. In relation to each payment under this Contract, the payer shall in addition pay the amount of any VAT properly chargeable in respect of it.”
   2. Insert the following at the end of clause 4.1:

“The Employer confirms that it will receive the Works as an ‘end user’ for the purposes of the Value Added Tax Act (Section 55A) (Specified Services and Excepted Supplies) Order 2019 (the reverse charge for building and construction services), and so will not apply the reverse charge to the supply of the Works. The Contractor shall issue the Employer with VAT invoices, with any VAT charged at the appropriate rate. In the event that the Employer is no longer the end user for these purposes, it will inform the Contractor as soon as reasonably practicable and shall, where legally required to do so, apply the reverse charge in relation to the Works in accordance with the Value Added Tax Act 1994 and related secondary legislation. The Contractor shall not charge VAT on the Works to the extent that the Employer is obliged to apply the reverse charge in accordance with this clause 4.1.”

1. Clause 4.3
   1. In the opening paragraph, delete “the date 7 days after”.
   2. Insert at the end of clause 4.3.2 “and provided that the Contractor has provided reasonable evidence that unencumbered title to the materials and goods shall pass to the Employer upon payment.”
   3. In the final sentence, delete "14 days" and replace with "30 days".
2. Clause 4.5

In clause 4.5.4, delete "5 days" and replace with "1 day".

1. Clause 4.8

In clause 4.8.3, delete “14 days” and replace with “30 days”.

1. Clause 4.10

Insert new clause 4.10:

"Retention

The Employer's interest in the percentage of the total value not included in the amounts of the interim payments to be certified under clause 4.3 shall be:

.1 without fiduciary obligation to the Contractor or any third party;

.2 without obligation to set aside any amount representing that percentage in a separate bank account; and

.3 a full beneficial interest, including a full beneficial interest in any interest accruing on that percentage without obligation to account to the Contractor for any such interest."

1. Clause 5.1

In clause 5.1, after "caused by the carrying out of the Works" insert:

"or of any other obligation pursuant to Section 2 or Section 3 of the Conditions".

1. Clause 5.2

In clause 5.2, after "by reason of the carrying out of the Works" insert:

"or of any other obligation pursuant to Section 2 or Section 3 of the Conditions".

1. Clause 5.3

Insert at the end of clause 5.3.1, before the semi-colon: “and shall have a minimum indemnity limit of £10,000,000 for any one claim.”

1. Clause 5.3A

Add new clause 5.3A after clause 5.3:

"Contractor to prevent nuisance

The Contractor shall prevent any unlawful nuisance (including any unlawful noisy working operations) or other unlawful interference with the rights of any adjoining owner, tenant or occupier or any statutory undertaker, of which the Contractor is or ought reasonably to have been aware, arising out of the carrying out of the Works or of any other obligation pursuant to Section 2 or Section 3 of the Conditions. The Contractor shall assist the Employer in defending any action or proceedings in relation to any such nuisance or interference. The Contractor shall be responsible for and shall indemnify the Employer from and against any and all expenses, liabilities, losses, claims and proceedings resulting from any failure or default by the Contractor in performing its obligations under this clause 5.3A."

1. Clause 5.3B

Add a new clause 5.3B after clause 5.3A:

"**Trespass and third party consents**

.1 Without prejudice to clauses 5.1, 5.2 and 5.3A, the Contractor shall ensure that there is no trespass by the Contractor or the Contractor's Persons (including the oversailing of tower crane jibs) on or over any adjoining or neighbouring property arising out of the carrying out of the Works or of any other obligation pursuant to Section 2 or Section 3 of the Conditions and shall take all reasonable safety and other measures to prevent damage or injury to any persons including the occupiers of adjoining or neighbouring property and members of the public.

.2 The Contractor shall obtain, without addition or adjustment of the Contract Sum, any third party consents, approvals, licences or permissions stated in the Contract Particulars.

.3 If requested by the Employer, the Contractor at its own cost shall provide reasonable assistance (including the provision of copies of drawings and specifications) to the Employer and its nominated representatives and consultants in obtaining any third party consents, approvals, licences or permissions which are not the Contractor's responsibility to obtain under clause 5.3B.2.

.4 The Contractor shall comply and shall procure that all Contractor’s Persons comply in all respects with any third party consents, approvals, licenses or permissions references in this clause 5.3B, as the same may be varied from time to time."

1. Clause 5.6
   1. Insert a new sub-clause 5.6.7:

“If any loss or damage affecting any executed work, Site Materials, the existing structures or their contents is caused or contributed to by the Contractor or the Contractor’s Persons, then the Employer shall be entitled to recover from the Contractor any resulting deductible payable under the relevant insurance policy (whether by deducting such amount from sums due to the Contractor or by claiming the same as a debt).”

1. Clause 5.7

In the opening paragraph of clause 5.7, delete “either Party” and replace with “the Employer”. Delete “the other” and replace with “the Contractor”.

1. Clause 5.8

Add a new clause 5.8 after clause 5.7:

"**Professional indemnity insurance**

The Contractor shall maintain professional indemnity insurance with a minimum limit of indemnity and on the basis and for the duration as set out in in the Contract Particulars, provided that (subject to clause 5.9) such insurance is available at commercially reasonable rates. The Contractor shall maintain that professional indemnity insurance:

.1 with reputable insurers lawfully carrying on insurance business in the UK;

.2 on customary and usual terms and conditions prevailing for the time being in the insurance market; and

.3 on terms that do not require the Contractor to discharge any liability before being entitled to recover from the insurers and that would not adversely affect the rights of any person to recover from the insurers under the Third Parties (Rights Against Insurers) Act 2010.

Whenever the Employer reasonably requests, the Contractor shall send the Employer evidence that such insurance is in force."

1. Clause 5.9

Add a new clause 5.9 after clause 5.8:

"**Commercially reasonable rates**

Any increased or additional premium required by insurers for the insurance referred to in clause 5.8 because of the Contractor's claims record or other acts, omissions, matters or things particular to the Contractor shall be deemed to be within commercially reasonable rates."

1. Clause 5.10

Add a new clause 5.10 after clause 5.9:

"**Evidence of professional indemnity insurance etc.**

.1 The Contractor shall notify the Employer in writing from time to time of any change in its professional indemnity insurance arrangements.

.2 The obligation under this Contract to take out and maintain professional indemnity insurance shall continue notwithstanding termination of the Contract, or determination of the Contractor’s employment hereunder, in either case for any reason whatsoever, including (without limitation) breach by the Employer.

.3 The Contractor shall not do or permit or suffer to be done any act of thing which may vitiate or prejudice the recovery of any sum under any policy or policies of insurance effected by either Party.”

1. Clause 5.11

Add new clause 5.11 after clause 5.10:

"**Key Sub-contractors' professional indemnity insurance**

The Contractor shall procure that the Key Sub-contractors shall maintain professional indemnity insurance in accordance with the required form of sub-contractor's deed of collateral warranty and Part 2 of Schedule 5 to the Schedule of Amendments. Within 10 Business Days of a request from the Employer (or, if later, within 10 Business Days of the appointment of a Key Sub-contractor), the Contractor shall procure and shall send to the Employer evidence that the Key Sub-contractors' insurance referred to in this clause is in force."

1. Clause 5.12

Add a new clause 5.12 after clause 5.11:

"Professional Consultants' professional indemnity insurance

The Contractor shall procure that the Professional Consultants shall maintain professional indemnity insurance in accordance with the required form of professional consultant's deed of collateral warranty and Part 2 of Schedule 4 to the Schedule of Amendments. Within 10 Business Days of a request from the Employer (or, if later, within 10 Business Days of the appointment of a Professional Consultant), the Contractor shall procure and shall send to the Employer evidence that the Professional Consultant's insurance referred to in this clause is in force."

1. Section 5A

Insert a new Section 5A entitled "**Collateral warranties**":

"**5A.1** **Contractor's collateral warranty**

.1 Within 10 Business Days of a request from the Employer, the Contractor shall execute and deliver a deed or deeds of collateral warranty in favour of any [Funder, any Purchaser and any Tenant] identified in the Employer's request, in the form of the Contractor's deed of collateral warranty contained in Schedule 6 to the Schedule of Amendments, with such amendments as the relevant beneficiary may reasonably require.

.2 If the Contractor does not procure execution and delivery of any such warranty within the time period required under clause 5A.1 then, notwithstanding any other term of this Contract, the Employer shall be entitled to withhold all sums due to the Contractor until such time as the required warranty is executed and delivered.

**5A.2** **Sub-contractor collateral warranties**

.1 The Contractor shall ensure, within 10 Business Days of a request from the Employer (or, if later, within 10 Business Days of the appointment of a Key Sub-contractor), that the Key Sub-contractor identified in the request has executed and delivered a deed of collateral warranty in favour of the Employer and/or in favour of any [Funder, any Purchaser and any Tenant] identified in the Employer's request, in the form set out in Part 3 of Schedule 5 to the Schedule of Amendments, with such amendments as the relevant beneficiary may reasonably require.

.2 If the Contractor fails to procure any executed deed of collateral warranty from any Key Sub-contractor within the time period required under clause 5A.2, the Employer in its absolute discretion may withhold payment for the elements of the work undertaken by that Key Sub-contractor and claimed by the Contractor in its application for payment until such time as the required warranty is executed and delivered.

**5A.3 Professional Consultant collateral warranties**

.1 The Contractor shall ensure, within 10 Business Days of a request from the Employer (or, if later, within 10 Business Days of the appointment of a Professional Consultant), that the Professional Consultant identified in the request has executed and delivered a deed of collateral warranty in favour of the Employer and/or in favour of any [Funder, any Purchaser and any Tenant] identified in the request, in the form set out in Part 3 of Schedule 4 to the Schedule of Amendments, with such amendments as the relevant beneficiary may reasonably require.

.2 If the Contractor fails to procure any executed deed of collateral warranty from any Professional Consultant within the time period required under clause 5A.3, the Employer in its absolute discretion may withhold payment for the elements of the work undertaken by that Professional Consultant and claimed by the Contractor in its application for payment until such time as the required warranty is executed and delivered.

**5A.4 Contractor's duty not to terminate or vary appointments or sub-contracts**

The Contractor shall not terminate or vary the appointment of any Professional Consultant or Key Sub-Contractor without the Employer's prior consent, which shall not be unreasonably withheld or delayed."

1. Clause 6.1

Insert a new clause 6.1.5 as follows:

“.5 it becoming subject to a moratorium under Part A1 of the Insolvency Act 1986 or it becoming subject to a restructuring plan under Part 26A Companies Act 2006”.

1. Clause 6.4
   1. Insert new sub-clause 6.4.1.4:

“.4 fails to maintain or provide adequate evidence of any insurance cover required to be procured by the Contractor under this Contract.”

* 1. Insert a new clause 6.4.3:

"The Employer may immediately terminate the Contractor's employment under this Contract by giving written notice, if the Contractor is in material or persistent breach of its obligations under this Contract and fails to rectify such breach within 14 days of being notified of the same."

1. Clause 6.6

Delete the existing text of clause 6.6. and replace with the following:

“.1 The Employer shall be entitled at any time to terminate the Contractor’s employment under this Contract or any other contract with the Employer and recover all its loss if the Contractor, the Contractor’s Persons or anyone acting on the Contractor’s behalf do any of the following things:

.1 offer, give or agree to give to anyone any inducement fee or reward in respect of this Contract or any other contract with the Employer (even if the Contractor does not know what has been done): or

.2 commit an offence under the Bribery Act 2010: or

.3 commit any fraud in connection with this or any other contract with the Employer whether alone or in conjunction with the Employer’s Persons (including any person employed on a permanent temporary or agency arrangement by the Employer): or

.4 give any fee or reward the receipt of which is an offence under sub-section (2) of section 117 of the Local Government Act 1972.

.2 The Employer shall be entitled at any time to terminate the Contractor’s employment under this or any other contract with the Employer if (where this Contract is one to which regulation 73(1) of the PC Regulations applies) the circumstances set out in regulations 73(1)(b) of the PC Regulations apply.

.3 Any clause under this Contract limiting the Contractor’s liability shall cease to apply in circumstances where the Contractor’s employment is terminated pursuant to this clause 6.6.”

1. Clause 6.10
   1. In the final paragraph of clause 6.10.1, delete “either Party, subject to clause 6.10.2,” and replace with “the Employer”. Delete “the other” and replace with “the Contractor”.
   2. Delete clause 6.10.2 and replace with “Not used.”.
2. Clause 8

Insert a new clause 8 as follows:

“Data protection

**Option 1: To be used where the Contractor will NOT have access to any personal data under this contract.**

Italicised wording in this clause 8 shall have the meanings ascribed to it under the Data Protection Act 2018. It is not anticipated that the Contractor will act as a *data processor* of any *personal data* in respect of which the Employer is a *data controller*. To the extent that the Contractor is required by the Employer to act as a *data processor* at any stage, the parties shall, prior to the Contractor acting in this capacity, first agree the terms of a written agreement to set out the ambit of such role. Any *processing* of *personal data* prior to such written agreement being concluded is not authorised by the Employer.”

1. Clause 9

Insert a new clause 9 as follows:

"Anti Slavery

.1 The Contractor shall, and shall procure that the Contractor’s Persons, comply with the Modern Slavery Act 2015 and any related Employer’s Policies.

.2 Without prejudice to the generality of clause 9.1, the Contractor undertakes, warrants and represents that:

.1 neither the Contractor nor any of its officers, employees, agents or subcontractors has:

.1 committed an offence under the Modern Slavery Act 2015 (an “**MSA Offence**”); or

.2 been notified that it is subject to an investigation relating to an alleged MSA Offence or prosecution under the Modern Slavery Act 2015; or

.3 is aware of any circumstances within its supply chain that could give rise to an investigation relating to an alleged MSA Offence or prosecution under the Modern Slavery Act 2015; and

.2 it has implemented due diligence procedures to ensure compliance with the Modern Slavery Act 2015 (and any related Employer’s Policies) in its business and supply chain, and those of its officers, employees, agents or subcontractors, which will be made available to the Employer on request at any time.

.3 The Contractor shall notify the Employer immediately in writing if it becomes aware or has reason to believe that it, or any of its officers, employees, agents or subcontractors have breached or potentially breached any of the Contractor’s obligations under clause 9.1 or clause 9.2. Any such notice shall set out full details of the circumstances concerning the breach or potential breach of the Contractor’s obligations.

.4 Any breach of clause 9.1 or clause 9.2 by the Contractor shall be deemed to be a material breach of this Contract which is not capable of remedy and shall entitle the Employer to terminate the Contractor’s engagement with immediate effect under clause 6.4.3.”

1. JCT MWD 2016, Schedule 1: Arbitration

Delete Schedule 1 to the JCT Conditions and replace with "Schedule 1 not used".

1. JCT MWD 2016, Schedule 2: Fluctuations - Contribution, levy and tax changes

Delete Schedule 2 to the JCT Conditions and replace with "Schedule 2 not used".

1. JCT MWD 2016, Schedule 3: Supplemental Provisions

This agreement incorporates Schedule 3 to the JCT Conditions, amended as follows:

* 1. Insert at the end of paragraph 5.1, before the full stop: “(including any Social Value Requirements detailed at Annex F)”.
  2. Insert a new paragraph 5.4 as follows:

“If at any time it becomes reasonably apparent that the Contractor has not achieved, and will not achieve, the Social Value Requirements, then without limiting the Employer’s other rights and remedies the Employer may deduct any corresponding Social Value Credits from sums due to the Contractor (or otherwise may recover such Social Value Credits as a debt).”

* 1. Insert a new paragraph 5.5 as follows:

“In this paragraph 5:

**Social Value Requirements** means the initiatives detailed at Annex F that the Contractor has committed to implementing as part of its tender, to ensure that the delivery of the Works achieves a wider societal or community benefit.

**Social Value Credits** means the service credits detailed at Annex F that will become chargeable to the Contractor if at any time it becomes reasonably apparent that the Contractor has not achieved, and will not achieve, the Social Value Requirements.”

1. - Parent company guarantee

**Not used**

1. - Performance bond

**Not used**

1. - Professional Consultants, PROFESSIONAL CONSULTANTS' INSURANCE and Professional Consultants' deed of collateral warranty

Not applicable

1. Key Sub-contractors, Key Sub-contractors' insurance and Key Sub-contractors' deed of collateral warranty
2. - Key Sub-contractors

The Key Sub-Contractors identifiable at the date of this Contract are:

* [LIST, BY NAME AND/OR SPECIALISATION]

1. - Key Sub-contractors' professional indemnity insurance

Each Key Sub-Contractor shall maintain professional indemnity insurance in the following amounts on an each and every claim basis:

* [NAME OR SPECIALISM] - £[SUM].

1. - Key Sub-contractor's deed of collateral warranty

**[Note: Attach agreed form(s) of Sub-Contractor collateral warranty (e.g. the Council's amended JCT SCWa/E, SCWa/F and SCWa/P&T warranties).]**

1. - Contractor's deed of collateral warranty

**Not applicable**

1. - Third party agreements

**Not applicable**

Annex A - Contract Drawings

Annex B – Scope of Works / Specification

Annex C - Employer's Requirements

Employers Requirement Process

Annex D - Contractor's pricing breakdown

Annex E - Employer's Policies

Annex F – Social Value

[Note: If not relevant, delete the table and mark this Annex 'Not applicable.']

|  |  |
| --- | --- |
| Social Value Requirement | Social Value Credit |
| [Insert details of each Social Value Requirement, cross-referring to other sections of the Contract Documents if necessary. The Contract must clearly set out what the social value deliverables are, how they will be measured and when they must be delivered by.] | [Insert the corresponding service credit that will become payable if the Social Value Requirement is not met.] |
|  |  |
|  |  |
|  |  |