REQUEST FOR PROPOSAL (RFP)

RSSB_2070 Optimising door closure arrangements to improve boarding and alighting – T1102

SECTION A – TENDER DOCUMENTS

- TENDER INSTRUCTIONS

1.1	Tenders shall be submitted in accordance with the following instructions.  It is important that all the information requested is provided in the format and order specified.  If the Tenderer does not provide all of the information RSSB has requested within the tender pack, RSSB may reject the tender as non-compliant.

1.2	Tenderers must obtain for themselves, at their own responsibility and expense, all information necessary for the preparation of their tender.  Tenderers are solely responsible for any costs and expenses in connection with the preparation and submission of their Tender, and all other stages of the selection and evaluation process.  Under no circumstances will RSSB, or its advisors, be liable for any costs or expenses Tenderers, their sub-contractors, suppliers or advisors incur in this process, including if this tendering process is terminated or amended by RSSB.

1.3	Tenderers are solely responsible for obtaining the information that they consider is necessary in order to prepare the content of their tender and to undertake any investigations they consider necessary in order to verify any information RSSB provides during the procurement process.

1.4	All pages of the tender submission must be sequentially numbered (including any forms to be completed and returned).

1.5	All specifications, plans, drawings, samples and patterns and anything else that RSSB issues in connection with this ITT, remains the property of RSSB and are to be used solely for the purpose of tendering.

1.6	At any time prior to the deadline for receipt of questions, RSSB may modify the tender documents by amendments in writing.

1.7	RSSB (at its sole discretion) may extend the deadline for receipt of Tenders.

RSSB reserves the right to modify or to discontinue the whole of, or any part of, this tendering process at any time and accepts no obligation whatsoever to award a contract.

- GENERAL LEGAL & COMMERCIAL COMPLIANCE

2.1	RSSB will check each tender for completeness and compliance with the tender instructions.  RSSB reserves the right to reject any tenders it considers substantially incomplete, or non-compliant (each tender will be assessed on its own merit, according to the level/importance of omitted or non-compliant content).

- TENDER REQUIREMENTS

3.1	“RSSB” means the contracting authority, seeking to invite suppliers to participate in the procurement process.

“You” or “Supplier” means the legal entity completing these questions, seeking to be invited to the next step of the procurement process Invitation to Tender (ITT)

3.2	Please ensure all questions are completed in full and in the format requested. Failure to do so may result in your submission being disqualified. If the question does not apply you need to clearly state N/A.

3.3	If it is necessary for you to provide additional information this should be provided as an appendix and clearly referenced as part of your declaration.

BACKGROUND INTRODUCTION

3.4	RSSB was established in April 2003. The Company’s primary objective is to facilitate the railway industry’s work to achieve continuous improvement in the health and safety performance of the railways in Great Britain, and thus to facilitate the reduction of risk to passengers, employees and the affected public. The railway is a complex system with multiple interfaces delivered by many different organisations. At RSSB we bring these different organisations together to make collective decisions. We help the rail industry carry out research, understand risk, set standards and improve performance. We provide a constant point of reference in a changing environment.

We support rail in the areas of safety standards, knowledge and innovation and a wide range of cross- industry schemes requiring our knowledge and independence. Our work involves close collaboration, but as technical experts we also appoint suppliers in the wider market to provide an informed view.

Key elements of the company’s remit are to:

- Manage Railway Group Standards on behalf of the industry

- Lead the development of long-term safety strategy for the industry, including the publication of annual Railway Strategic Safety Plans

- Propose change through facilitation of the research and development programme, education and awareness

- Measure, report and inform on health and safety performance, safety intelligence, trends, data and risk

- Support cross-industry groups in national programmes which address major areas of safety concern

- Facilitate the effective representation of the UK rail industry in the development of European legislation and standards that impact on the rail system

RSSB is a not-for-profit company owned by major industry stakeholders. The company is limited by guarantee and is governed by its members, a board and an advisory committee. It is independent of any single railway company and of their commercial interests.

RSSB REPRESENTATIVE

Your main point of contact is Jenny Neill shareditt@rssb.co.uk  or jennyneill@rssb.co.uk

RSSB OVERVIEW

If you wish to find out more about RSSB, please visit our website at www.rssb.co.uk

TIMELINE

| Project Objective | Start Date | End Date |  |
| --- | --- | --- | --- |
| RFP issued | 14th March 2016 |  |  |
| Supplier clarification questions deadline | 14th March 2016 | 4th April 2016 @ 12:00 Noon |  |
| Deadline for Submitting Tenders | 11th April 2016 @12:00 Noon |  |  |
| Estimated notification of award decision | w/c 2nd May 2016 |  |  |
| Target contract commencement date | 16th May 2016 |  |  |

Note: RSSB reserves the right to amend these dates as business requirements demand and will communicate any changes to tenderers.

3.6	Should you have any supplier clarification questions relating to the project, please email these according to the deadline detailed in the project timeline above to ensure that these questions can be addressed. To ensure equal and fair treatment to all suppliers who have submitted a bid, RSSB will circulate all questions and responses anonymously.

Questions should be emailed to: Jenny Neill shareditt@rssb.co.uk

- TENDER EVALUATION

4.1	EVAULATION METHODOLOGY

4.1	In the interests of an open, fair and transparent assessment, this document sets out how RSSB intends to evaluate tender responses.  It outlines the evaluation criteria and respective weightings, as well as the evaluation methodology to be applied.

4.2	EVALUATION PROCESS

4.2.1	The process that will be used to select an appropriate Tenderer and award the contract for this procurement is to check for suitability of the tenderer. If the tenderer does not conform to the minimum requirements Tenders will not be marked.

4.2.2	An evaluation panel consisting of representatives of key stakeholders within RSSB will carry out the evaluation. The procurement team will only act as moderator during the suitability and proposal assessment phases of the evaluation.

  - TENDER EVALUATION CRITERIA AND MINIMUM REQUIREMENTS

4.3.1 	Tenderers must pass all of the Suitability questions in section five, for their RFP to be marked. A fail will automatically result in a non- compliant bid. The Award Criteria relates to the scoring for the specification in this tender, which is used to assess the project specific questions in the tender.

    - In evaluating tenders, the most economically advantageous tender(s) will be sought.  This will be using the evaluation criteria in seven and relates to the attached specification which detail the specified requirements.

    - Tenderers are advised to carefully consider the attached specifications, ask clarification questions to ensure these are understood

- Suitability Criteria:

| Suitability Evaluation Area | Evaluation Question | Pass/Fail |
| --- | --- | --- |
| S1 Supplier’s organisational experience in human factors research | - Please provide a short description of at least two projects, completed within the last three years, in which you delivered human factors research involving users’ mental models, cognitive walk-throughs, gap analysis or another method considered relevant to the scope of this project. | Pass / fail |
| S2 Supplier’s organisational experience in door research | Please provide a short description of at least one project, completed within the last five years, in which you have conducted technical or operational research directly involving user interaction with automatic door systems. | Pass / fail |
| S3 Supplier’s organisational experience of rail environments | Please provide a short description of at least one project, completed within the last three years, that demonstrates your familiarity with, and operational understanding of, railway environments. | Pass / fail |

- AWARD CRITIERIA SCORING TABLE (For Information Only)

| Grade | Definition of grade |
| --- | --- |
| 5 | A wholly excellent Tender Response that (where applicable): - Addresses all aspects of the question in an informed and comprehensive manner; - Demonstrates a thorough understanding of what is being asked for; - Provides evidence of how that understanding can be applied in practice; - Offers full confidence that the Tenderer will deliver the service in full; - Addresses the majority of areas of doubt and uncertainty; and - Provides certain, unambiguous commitments or statements of intent that permit reliance through translation into contractual terms |
| 4 | A good Tender Response that (where applicable): - Addresses all aspects of the question and is generally of a good standard; - Demonstrates a good understanding of what is being asked for; - Provides a worked-up methodical approach; - Offers confidence that the Tenderer will deliver the service in full with limited areas of doubt or uncertainty; - Addresses key areas of doubt and uncertainty; and - Provides commitments that can be translated well into contractual terms |
| 3 | A satisfactory Tender Response that (where applicable): - Addresses the majority of the question and is generally of a good standard but lacks substance or detail in some areas; - Demonstrates an understanding of what is being asked for; - Provides a satisfactory approach; - Offers a general level of confidence that the Tenderer will deliver the service (but with room for doubt in some areas); - Address some areas of doubt and uncertainty; and - Provides some commitments that can be translated well into contractual terms. |
| 2 | A Tender Response that (where applicable): - Addresses some of the question but either lacks relevant information and detail or lacks substance in a manner that would suggest the response is a “model answer”; - Demonstrates some understanding but with a lack of clarity in key areas; - Provides an approach which is not wholly appropriate or viable or lacks evidence; - Shows that the level of confidence that the supplier can deliver does not outweigh the doubt; - Does not address many areas of doubt and uncertainty; and - Does not offer sufficient commitment (with doubt as to the extent to which would translate into contractual terms) |
| 1 | A generally unsatisfactory Tenderer response that (where applicable): - Does not address the question or has omissions; - Lacks understanding in significant areas: - Provides an approach which has gaps or creates concerns; - Shows that the level of confidence that the supplier can deliver is low; - Creates uncertainty; and - Displays significant lack of commitment (with doubt as to the extent to which would translate into contractual terms) |
| 0 | A wholly unsatisfactory Tenderer response that (where applicable): - Provides no response or omissions/oversights that prevent scoring; - Refuses to deliver the requirement; and - Creates concerns so significant that the response would be detrimental to the interests of RSSB |

- EVALUATION CRITIERIA MATRIX

| Evaluation Matrix Evaluation Area | Evaluation Question | Evaluation Criteria | Weight |
| --- | --- | --- | --- |
| EA1 Supplier’s technical competence in human factors research and railway operations | Please provide evidence of your suitable resource with technical competence in human factors research and railway operations. | The Tenderer’s response shows that they have: The resource competence to deliver human factors research The resource competence to deliver rail-specific research The availability of allocated resource to meet the time and scale requirements of their proposal | 20% |
| EA2 Suitability, clarity and robustness of proposed methodology | Please describe your proposed methodology and explain how it will deliver suggestions for short-term improvements and solutions for long-term change in the area of door closure arrangements. | The Tenderer’s response shows that they have: Understood the requirements Proposed an appropriate methodology Described how this will be applied to the specific challenges the work intends to cover | 40% |
| EA3 Project management (resources, budget and risk management) | Please outline who will be a part of the delivery team. Note, it is not necessary to produce bespoke CVs but it is necessary to clearly identify every team member’s role, their relevant experience and contribution to delivery. Please provide adequate allocation of appropriate resources against individual deliverables and timelines. Please describe how you will work with RSSB to ensure that the quality and content of the deliverables is fit for purpose. Please clarify the ways in which you will manage the risks to delivering the project. | The Tenderer’s response shows that they have: Provided a credible plan for delivering successful outcomes to time, quality and cost Identified appropriate ways to engage with RSSB Identified risks and proposed to effective management and mitigation | 20% |
| EA4 Value of project | Please provide a fixed cost for the project and the associated cost break down, and describe how and why this represents value for money. | The score for this criteria will be determined based on comparison to the budget ceiling | 20% |

- SPECIFICATION

# Background

This research defines door closure arrangements as the timing and sequence of door closing and the use of ‘Hustle Alarms’ during train dispatch. Several considerations determine the nature of door closing arrangements on trains, including:

System features (eg the type of doors on each class of train; operational controls; signage and instructions).

Regulations (eg approved warning sounds).

Procedures (ie RIS-3703-TOM, Rail Industry Standard for Passenger Train Dispatch and Platform Safety Measure).

Human factors (ie operators’ compliance with procedures).

There are a variety of door closure arrangements currently in operation on the GB mainline network, and across different rail systems (ie mainline, metro, subway). This lack of consistency may influence passenger understanding and expectation of door operations (eg will placing a hand between the closing doors cause them to fully re-open) and increase the risk of accidents.

The objective of this project is to understand how passengers interact with train doors during boarding and alighting. At present, there is a gap in understanding concerning the effect of door closure arrangements on passengers’ – and different passenger groups’ (frequent commuters, tourists, and the sensory-impaired) – comprehension and behaviour while boarding and alighting.

In January 2015, the industry’s Platform Train Interface Strategy identified the need for research into:

The effect of closing train doors prior to departure on passenger behaviour.

The effect of Hustle Alarms on passenger behaviour.

Additionally, there is increased urgency for this research following a ‘trap and drag’ event at West Wickham station in April 2015. This accident is currently under investigation by the Rail Accident Investigation Board (RAIB), but it appears that the door closure arrangements may have been a contributory factor to the events.

# Project objectives

The objective of this project is to examine how passengers interact with and understand door closure arrangements. This includes examining:

The door closure arrangements, including auditory warnings, used by other modes of transport and in other public environments.

The purpose and effect of Hustle Alarms as used during train door closing.

The mental models that different passenger groups have while boarding and alighting.

The effect of door closure prior to departure (eg to regulate carriage temperature) on passenger behaviour.

The effect of current system features (eg Hustle Alarms, door auto-close function) on passenger behaviour.

The optimal door closing sequence (from a human factors perspective).

To what extent a harmonisation or standardisation of door closure arrangements is feasible in GB rail.

This project will enable greater understanding of passenger behaviour during boarding and alighting. It will:

- Specify grounded, prioritised improvements to the current door closure operations, including:

- Identifying SFAIRP mitigations.

- Outlining the feasibility of standardisation/harmonisation across the GB mainline network.

- Specify innovations in door closure arrangements, including:

- The design of new rolling stock hardware and systems.

- The regulations concerning door closing sequences and warnings (eg to ensure that auditory warnings are intuitive to users).

Please note, for both areas (1 and 2), the supplier must outline and itemise (as far as possible) the necessary post-research and implementation work, including the likely cost of further assessment and analysis of any options identified by this project.

# Scope

| In scope | Out of scope |
| --- | --- |
| Passenger behaviour while boarding/alighting GB mainline network Tone and timing of Hustle Alarms Consideration of “directional alarms” Potential for knowledge transfer from other rail/transport environments (eg Metro systems) | Operators’ understanding and application of door closure arrangements Procedures to manage risk once a passenger has become trapped in doors Investigation into different auditory warnings (eg announcements) Design of door mechanisms and other hardware components (excluding Hustle Alarms) |

# Methodology

RSSB asks suppliers to explain the methodology that they are intending to use to successfully meet the project objectives and cover the scope. This is likely to include:

Engagement with GB rail industry to understand the specific requirements of stakeholders.

A review of existing literature to capture good practice in other countries and from other transport sectors.

Cognitive walk-throughs and behavioural observations to understand passenger perception while boarding and alighting.

Gap analysis to understand how far current behaviour falls short of ideal passenger behaviour in relation to door closure arrangements.

# Deliverables

All deliverables will use an RSSB template and be publically available to RSSB members online via SPARK.

| Deliverable name | Type | Description |
| --- | --- | --- |
| Final report | Report | This report describes the background to the research, the methods used and the project findings. It details the short- and long-term solutions identified by the research and proposes which are suitable for immediate implementation and which will require further development. Additional technical outputs may support this report, as required. |
| (PowerPoint) Executive summary | Presentation | The presentation aligns with the final report. It summarises the findings in an easily accessible manner, fit for presentation to rail industry board-level audiences. |
| (Draft) Research brief | Report | A four page document summarising the research, its findings, and the potential benefits generated. |

# Stakeholder roles and responsibilities

| Party | General role in project | Specific role in deliverables |
| --- | --- | --- |
| Industry sponsor and RSSB sponsor | The Industry and RSSB sponsors act as figureheads for the research, championing its importance and its outputs. Their key role is to provide steer to the research as it progresses and exert pressure on the industry to make use of its findings. | Formally accept deliverables |
| Project supporters | The project supporters represent parts of industry complementary to the sponsor’s organisation. They offer expertise for effective project delivery and support the implementation of findings led by the sponsors through networking, advice and other support. | Endorse deliverables |
| Project steering group | The project steering group ensures the project delivers to industry needs. As such, it helps formulate specifications, assesses tenders, reviews draft and final outputs and other relevant tasks. | Reviews and comments on deliverables |
| Delivery manager | The delivery manager is responsible for the detailed project management including project schedules, cost reporting and other relevant project management tasks. The delivery manager leads the project in organising meetings, etc and ensures timely and effective delivery towards project objectives. | Facilitates technical review and acceptance processes, identifies and monitors corrective actions where needed, including facilitating decision making |
| Technical expert | Throughout the project, the technical expert ensures that the research accurately reflects the technical aspects. Technical aspects can refer to specific issues around railway signalling, track engineering, safety relevant operations or any other specialist field. | Reviews emerging outputs from technical perspective and provides guidance |

# Budget, timescales and dependencies

The budget ceiling for this work is £100,000. RSSB will not consider any bid above this threshold.

Please note, RSSB is seeking bids that demonstrate the best value for the allocated budget and does not anticipate tenders will offer exhaustive research proposals. As such, suppliers must outline the likely post-research steps (ie what necessary work is not included in the bid but might be required to take the research findings forward).

RSSB expects the work to start in May 2016 and finish by January 2017. However, these are indicative dates and RSSB is prepared to consider bids that cannot meet these expectations if suppliers include a robust and realistic project plan.

# Critical success factors and risk management

The following critical success factors define what RSSB consider to be the key outcomes at the end of this project:

The investigation fully considered all factors relating to door closure arrangements identified as ‘in scope’.

The findings adequately acknowledge the context of the GB rail industry (eg the nature of rolling stock manufacture and leasing model).

Some of the identified opportunities for change are cost-effective for industry to implement.

Industry stakeholders (regulators and manufacturers) are interested in and committed to long-term changes to system features.

The project risks identify potential threats to the supplier’s successful delivery of the project. RSSB expects the supplier to identify risks, propose effective management and mitigation measures, and regularly review these risks as the project progresses. RSSB have identified the following initial risks:

The required research is broader than anticipated, increasing cost and delaying delivery.

The research is unable to identify any opportunities for change that are likely to improve passenger safety at the platform-train interface.

There is a lack of stakeholder engagement or availability during delivery.

# Pricing Schedule

Please fill in the excel sheet named Pricing Schedule and return with the Tender response.

The rates contained with the pricing schedule are, unless otherwise expressly agreed between the parties are firm and will not increase with inflation or any other index.

The rates entered shall be deemed to include complete provision for full compliance with the requirements of the Contract.

The rates exclude VAT.

The rates entered in the Pricing Schedule shall include all travel and subsistence costs.

Tenderers must include in the pricing schedules any discounts or any reduced pricing they are proposing to offer to RSSB in delivery of this requirement.

RSSB requires Tenderers to competitively tender against the requirements of the Specification.  Payments to the Contractor for service delivery will be in accordance with the terms and conditions. There will be a milestones payment mechanism linked to satisfactory sign off for the work completed. The supplier should put appropriate milestones in their proposal.

Payments will be made against the milestone schedule as outlined in the template.

- PROCESS AND PREPARATION OF RESPONSES

  - Provide a response to answer the requirements to explain how you will meet the needs of RSSB. Provide evidence to support your response on how you will meet the requirements in the Suitability criteria in section five.

  - Provide a response to answer the requirements to explain how you will meet the needs of RSSB and provide evidence to support your response on how you intend to meet the requirements in the Award Criteria in section seven.

  - The Supplier shall not enter in any agreement or arrangement with any third party which would in any way cause RSSB or its members to incur any financial obligations to the Supplier or any third party.

  - The Supplier shall not approach any RSSB employee, the RSSB representative or its agents to discuss any aspects of the Tender. All communication should be conducted via the nominated representative.

  - The Supplier shall not canvass support for the award of the contract by approaching any employee of RSSB, its representative or its agents.

  - The documents as enclosed are to be accepted in their entirety.   No alteration will be allowed, unless notified and confirmed in writing by RSSB procurement before the date stated for the receipt of tenders. If any alteration is made or these instructions to Suppliers are not fully complied with the tender may be invalidated.

  - The conditions of contract included in this Invitation to Tender apply. The Suppliers standard terms of business or trade will not be accepted.

  - Any requested changes for minor amendments to the conditions of contract must be sent in as a qualification to the contract for consideration. If this is not completed, it is assumed that the Supplier has accepted all terms and conditions detailed and no further changes will be accepted.

  - The Supplier shall be deemed to have satisfied itself as to the nature, extent and the content of the goods, services or works to be provided, the extent of staff required and all other matters, which may affect the tender.

  - All prices quoted to be GBP (unless otherwise requested in the Invitation to   Tender) exclusive Value Added Tax and firm

  - It is the Suppliers responsibility to ensure the tender is correct at the time of submission.  No amendment to the tender will be allowed after the due date.

  - Any questions must be emailed to the main point of contact no less than five days before the return date. Note: questions/responses will be circulated anonymously to all Suppliers invited to tender.

  - Tenders received after the closing date and time will not be considered.

  - RSSB reserves the right to correct any omissions or inaccuracies in the Invitation to Tender and to clarify and/or amend any of RSSBs’ requirements, up to seven days before the return of tenders.

  - All information supplied by RSSB must be treated in confidence and not disclosed to third parties except insofar as this is necessary to obtain sureties or tenders required during the preparation of the Tender.  All information provided by Suppliers will be treated in confidence except in stances where references may be sought.

  - RSSB reserves the right to cancel this Tender at any point and any cost incurred in the preparation of this Tender is at the Bidder’s expense.

  - Tenders must remain open for acceptance for a period of 180 calendar days from the submission date.

- TENDER RESPONSE INSTRUCTIONS

Please fill in the tender response in the format below:

9.1	Legal entity name of Tenderer

9.2	Contact person's name, email address, telephone number and postal address for enquiries relating to this procurement

Name:

Postal address:

Telephone number:

Email address:

9.3	Tenderer’s registered address

9.4	Tenderer’s website address (if available)

9.5	Please tick the box for the legal form of the Tenderer

- Sole Trader ☐ - Partnership ☐ - Limited Liability Partnership ☐ - Private Limited Company ☐ - Public Limited Company ☐ - Local Council ☐ - Voluntary/ charitable/ not for profit organisation ☐ - Other (please specify below) ☐

If ‘Other’ has been selected from the question above please provide details.

If your business is a registered company, charity or any other registered organisation (including limited, non-limited or Industrial and Provident Society), please state your registration number.  This must be the registration number of the Tenderer, providing the country and date of incorporation / registration if other than the UK.

9.6	Name of ultimate parent company (if this applies)

Companies House Registration number of ultimate parent company (if this applies)

- CONDITIONS OF CONTRACT

11.1	Attached in the tender documentation is the terms and conditions in relation to the proposed contract award.

11.2	Qualification of the Contract

Where Tenderers have any queries or concerns with any specific condition of the terms and conditions of the contract, these should be submitted in writing to shareditt@rssb.co.uk as soon as possible, and in any case no later than 10 days prior to the deadline for submission of tenders.  Please ensure the specific condition(s) and proposed amendment(s) are provided.  These will be reviewed by RSSB on a case by case basis, and, if accepted, revised terms and conditions will be issued to all Tenderers.  Failure to accept the terms and conditions of the contract or to qualify the tender in any way, may result in the tender being rejected by RSSB.

APPENDIX 1 CONFLICT OF INTEREST DECLARATION

Tenderers have a continuing duty to disclose actual or potential conflicts of interest in respect of itself, its named sub-contractors and / or consortia members.

Please describe any (potential) conflicts of interest that the Tenderer has identified and how these will be managed*:

If you DO NOT have any conflicts to declare, please tick this box:

Tenderers are reminded that failure to identify material conflicts of interest may lead to rejection of its tender response.

Guidance to Tenderers:

Tenderers should describe in the detail the perceived conflict (how it could be perceived in the context of this procurement) and the measures it will take to mitigate the conflict through the procurement life-cycle and service delivery.

APPENDIX 2 FORM OF TENDER

DECLARATION PROPOSAL FOR THE PROVISION OF OPTOMISING DOOR CLOSURE ARRANGEMENTS TO IMPROVE BOARDING AND ALIGHTING:

Having examined the proposed Contract comprising of:

- The Specification

- The Pricing Schedule

- The Evaluation Criteria

- The Tender Response

As enclosed in the ITT response.  We do hereby tender against the requirements, and terms and conditions of the proposed Contract.

We undertake to keep the tender open for acceptance by RSSB for a period of ninety (90) days from the deadline for receipt of tenders.

We declare that this is a bona fide tender, intended to be genuinely competitive, and that we have not fixed or adjusted the amount of the tender by, or under, or in accordance with, any agreement or arrangement with any other person.  We further declare that we have not done, and we undertake that we will not do, any of the following acts prior to award of this Contract:

- Collude with any third party to fix the price of any number of tenders for this Contract;

- Offer, pay, or agree to pay any sum of money or consideration directly or indirectly to any person for doing, having done, or promising to be done, any act or thing of the sort described herein and above.

Unless and until the Tenderer and RSSB have executed a formal agreement, RSSB acceptance of this tender with all its enclosures shall not constitute a binding contract between us.  We understand that you are not bound to accept the lowest price, or any, tender.

Name of person duly authorised to sign tenders:

Date:	..........................................

Signed:	..........................................

in the capacity of: ................................................................

duly authorised to sign tenders for and on behalf of:

............................................................................

By completing this Declaration and submitting your tender, you have agreed that the statements in this Form of Tender

Auditory warnings systems

http://www.rssb.co.uk/rgs/standards/RIS-3703-TOM%20Iss%202.pdf

‘Trap and drag’ refers to an incident where a person or object becomes trapped in the train doors and is subsequently dragged along the platform by the departing vehicle.

This incident resulted in a passenger suffering life-changing injuries – see http://www.thisislocallondon.co.uk/news/12883007.UPDATE__Woman_found_with__life_threatening_injuries__on_tracks_at_West_Wickham/

So far as is reasonably practicable