Attachment 3 – Statement of Requirements

Provision of Gender Pay Gap Decomposition Analysis

Contract Reference: CCCO25A01

CONTENTS

1.	PURPOSE	3

2.	BACKGROUND TO THE CONTRACTING AUTHORITY	4

3.	OVERVIEW OF THE REQUIREMENT	4

4.	DEFINITIONS	5

5.	SCOPE OF REQUIREMENTS	6

6.	THE REQUIREMENTS	7

7.	KEY MILESTONES AND DELIVERABLES	17

8.	MANAGEMENT INFORMATION/REPORTING	18

9.	volumes	19

10.	continuous improvement	19

11.	Sustainability	19

12.	QUALITY	19

13.	PRICE	21

14.	STAFF AND CUSTOMER SERVICE	21

15.	SERVICE LEVELS AND PERFORMANCE	21

16.	SECURITY AND CONFIDENTIALITY REQUIREMENTS	22

17.	PAYMENT AND INVOICING	22

18.	CONTRACT MANAGEMENT	23

19.	LOCATION	23

# PURPOSE

## The Office for Equality & Opportunity (OEO), within the Cabinet Office (referred to hereafter as the Contracting Authority or the Authority), leads on equality policy including gender equality, race equality, LGBT+ equality, disability equality, socio-economic equality, and the overall framework of equality legislation for the UK. The OEO is central to the government’s commitment to ensuring that every person, no matter their background, has access to the opportunities that allow them to thrive and be treated with respect and dignity.

## This Service Description relates to research that is to be undertaken to support policy development and decision making around the gender pay gap (GPG). The broad aim of this research is to understand the causes of the gender pay gap in the UK. The key objectives are:

## 1.3 Objective 1: Explore the drivers of the GPG and identify barriers and enablers.

## 1.3.1 Research questions:

## What are the drivers and protective factors of the GPG?

## What is their relative importance in driving GPG?

## How has the relative importance of the drivers and protective factors changed over time?

## 1.4 Objective 2: Assess the decomposition analysis findings to understand how the GPG can be reduced.

## 1.4.1 Research questions:

## Why has the relative importance of the drivers and protective factors of the GPG identified by the decomposition analysis changed over time?

## What effective actions can be taken to reduce the identified drivers of the gender pay gap?

## What barriers might prevent the actions identified above from being effective?

## 1.5 Objective 3: Upskill analysts at the Contracting Authority to allow them to independently carry out and interpret decomposition analysis on other equalities issues, such as ethnicity and disability pay gaps.

# BACKGROUND TO THE CONTRACTING AUTHORITY

## The Contracting Authority supports the Prime Minister, and ensures the effective running of government. The Contracting Authority is also the corporate headquarters for the government, in partnership with HM Treasury, and takes the lead in certain critical policy areas. More information about the Contracting Authority can be found on its website.

## The OEO sits within the Contracting Authority. The OEO focuses on disability policy, ethnic disparities, gender equality, LGBT+ rights and the overall framework of equality legislation for the UK including the Equality Act 2010 and sponsorship of the Equality & Human Rights Commission.

# OVERVIEW OF THE REQUIREMENT

## Women’s equality is at the heart of this Government’s missions. The ‘Plan to Make Work Pay’ committed to “finishing the business of ending pay discrimination at work” and Mission 4 'Break down the barriers to opportunity’ of the Government’s manifesto states “... Labour will take action to reduce the gender pay gap, building on the legacy of Barbara Castle’s Equal Pay Act”.

## Over 50 years after the Equal Pay Act and 14 years after the Equality Act, there is still a GPG of 13.1%. This has fallen over time but progress has slowed in recent years. Estimates suggest it may take between 20 and 45 years for the GPG to close completely.

## To accelerate progress, policy and decision makers need a clear understanding of the drivers and protective factors of the GPG.

## These are varied and may reflect the impact of misogyny, that women are more likely to be in part-time work, lower-paid work, take career breaks for caring, and are less likely to be represented in senior business positions.

## In addition to understanding the drivers, it is also important to identify best practices in tackling them in order to ensure any actions are effectively targeted.

## The Contracting Authority is commissioning a decomposition analysis of the GPG to ensure that current policy discussions are based on the latest data available. The outputs will provide an update of previous work, notably Olsen et al. 2018 ‘The gender pay gap in the UK: evidence from the UKHLS‘ and Olsen et al. 2010 ‘The Gender Pay Gap in the UK 1995-2007’. The methodology should aim to replicate previous statistical modelling and framing as much as possible in order to allow comparability, where possible, across time.

## Additionally, the Equality (Race & Disability) Bill will extend equal pay rights to protect workers suffering discrimination on the basis of race or disability. We require the Supplier to deliver a training package in decomposition analysis to upskill analysts at the Authority such that the Authority will be able to undertake future decomposition analyses in house.

## The Authority is looking for a contractor or consortium, with proven relevant experience, to deliver this research project which will involve both quantitative decomposition analysis and qualitative critical evidence review. Suggested methods are included below, however we welcome supplier suggestions and innovation.

# DEFINITIONS

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## Gender Pay Gap (GPG) | ## The gender pay gap measures the difference between median hourly earnings (excluding overtime) of men and women as a proportion of men's median hourly earnings (excluding overtime). It is a measure across all jobs in the UK, not of the difference in pay between men and women for doing the same job. |
| ## Critical evidence review | A detailed analysis of existing research on a topic, and an evaluation of its quality. A critical evidence review should: ● Provide an overview of the current state of knowledge ● Identify gaps in research ● Highlight key findings ● Assess the strengths and weaknesses of the research ● Challenge underlying assumptions ● Identify areas that need further investigation |
| ## Decomposition analysis | Decomposition analysis is a statistical method which breaks the drivers of a variable, for example the gender pay gap, into their constituent parts. |
| ## ‘Grey’ literature | The term ‘grey literature’ refers to any information that is not produced by commercial publishers. It includes research reports, working papers, conference proceedings, these, white papers, and reports produced by government departments, select committees, academics, pressure groups, business and industry. Grey literature may be directly available to the public, or distributed privately within organisations/groups. It may be difficult to discover, access, and evaluate, but this can be addressed through the formulation of sound search strategies. |

# SCOPE OF REQUIREMENTS

## Interested Potential Providers should carefully read the requirements set out below and respond to the questions set out in the response guidance.

## The Supplier is to assume that all requirements are mandatory core requirements and should therefore be included in the core contract price, unless otherwise specified.

## The Supplier is to implement all objectives and processes listed in their approaches once agreed and signed, if requested by the Authority.

## The Supplier will be required to work in close collaboration with the Authority, particularly, but not limited to, on identification of variables to be included in the decomposition analysis.

## The requirements are as follows:

## Inception meeting

## Decomposition analysis of the gender pay gap according to the analytical plan.

## Critical evidence review of research into the GPG, particularly focusing on effective measures for reducing it.

## Provide interim findings to update the Authority on progress.

## Provide an interim training package to update the Authority on progress.

## A final report incorporating findings and recommendations.

## Final training package on conducting decomposition analysis.

# THE REQUIREMENTS

## The following sections outline each requirement in more detail. All requirements should be met by the deadlines outlined in “7. Key Milestones and Deliverables”.

- Inception Meeting

## The Authority requires the Supplier to hold an inception meeting to discuss project planning by the deadline outlined in “7. Key Milestones and Deliverables”. The inception meeting will serve as an introduction between the Supplier and the Authority and will provide an opportunity for project planning and to clarify the scope and focus of analysis. Discussions could include, but are not limited to:

## The research team and their roles and responsibilities.

## A review of potential datasets, the variables they contain and their strengths and weaknesses. The supplier is expected to justify their choice of dataset, and identify timelines, risks and mitigations.

## An analytical plan that outlines the steps for the analysis.

## A discussion of how the proposed analysis contrasts with similar analysis on the GPG, for example by the Office for National Statistics, the Fawcett Society, and previous analysis by the Authority, .

## Anything Authority analysts will need to obtain or have access to for the successful delivery of the training package. This could include, but is not limited to: operating systems, software, and packages.

## A timeline for the project.

## It is anticipated that the Supplier will hold follow up meetings as necessary to ensure the analysis will meet the requirements of the Authority.

## Decomposition Analysis

## The Authority requires the Supplier to source and access data to enable decomposition analysis of the gender pay gap in the UK. Any costs associated with accessing data should be included in the core contract price.

## The Supplier will conduct decomposition analysis on the GPG to address:

## Objective 1: Explore the drivers and protective factors of the GPG

## Research questions:

## What are the drivers and protective factors of the GPG?

## What is their relative importance in driving GPG?

## How has the relative importance of the drivers and protective factors changed over time?

## The Supplier should also be open to emerging themes that are relevant to the subjects and questions throughout the data analysis process, for example differences or changes across geographies, industrial sectors and occupations. The Supplier should highlight information and findings which could help shape actions to close the GPG and which illustrates how employers have a role in closing the GPG.

## The Authority welcomes innovative approaches to the decomposition analysis, but should use previous work as a guide, particularly Olsen et al. 2018 ‘The gender pay gap in the UK: evidence from the UKHLS‘ and Olsen et al. 2010 ‘The Gender Pay Gap in the UK 1995-2007’. The analysis should be similar enough to be compared, where possible, with this previous work.

## The decomposition analysis will highlight the drivers and protective factors of the GPG in the UK. Emerging findings should be shared with the Authority as soon as available in order to inform key policy decisions.

### Critical Evidence Review

## The Supplier shall undertake a critical evidence review of research into the current gender pay landscape to address:

## Objective 2: Assess the decomposition analysis findings to understand how the GPG can be reduced.

## Research questions:

## Why has the relative importance of the drivers and protective factors of the GPG identified by the decomposition analysis changed over time?

## What effective actions can be taken to reduce the identified drivers of the gender pay gap?

## What barriers and enablers might prevent or facilitate the actions identified above from being effective?

## The critical evidence review should focus on:

## Effective actions to reduce the GPG, particularly actions which address the largest drivers of the GPG identified in B. Decomposition analysis.

## Evidence of the drivers of the GPG in the UK that are not quantified in B. Decomposition analysis. This is to address the large “unexplained” component of the GPG found by previous analyses, .

## The supplier should consider a broad range of effective actions to reduce the GPG including, but not limited to, actions by individuals, employers and governments, legislative and non-legislative options, best practice for businesses and educational institutions, and other relevant areas.

## The Supplier should consider the interplay between actions and how that will impact and limit their effectiveness. For example, the effectiveness of investing in childcare may be limited by working patterns. The Supplier should also consider the effects of constraining factors on actions. For example, if societal norms around caring prevent actions on childcare from reaching full utility.

## The Supplier should consider and address the potential effects of planned Government action to improve equalities, such as the Employment Rights Bill and Equality (Race and Disability) Bill.

## The Supplier should advise on further work which might be undertaken to quantify and assess the size of the likely elements of the unexplained component.

## It is expected that the Supplier will have access to an array of literature. The evidence for consideration in the review should include:

## All relevant English language evidence from 2005 - present, including seminal reports from earlier and in other languages if considered relevant and appropriate for the review.

## Published research, grey literature, case law, academic, trade union and other relevant sources.

## International evidence, although when presented this should be framed for the UK context.

## Studies involving quantitative or qualitative methods, or a range of methods.

## A ‘systematic’ method of searching the literature must be used. This should be transparent and well-documented. Clear inclusion/exclusion criteria should be used and documented at the outset of the review to appraise studies included in the final report, along with a bibliography of research, with highlighted quality criteria. Where possible, given the time constraints, the evidence review should adopt the principles of Rapid Evidence Assessments. For more information about Rapid Evidence Assessments, please see the Government Social Research toolkit.

## The Supplier must clearly critically review (i.e. assess the strengths and weaknesses of) and document the following elements of each study considered when reviewing the relevant literature:

## The scope and size of the sample, including response rates.

## The research questions/hypotheses posed.

## The research design.

## The nature and quality of the fieldwork.

## The analysis and the nature and robustness of findings.

## Any evidence gaps and/or limitations associated with the methodology employed.

## How the findings should inform subsequent research.

## The Supplier is required to agree the final search strategy and proposed methodology with the Authority before commencing the critical evidence review.

## It is expected that the Supplier will provide the Authority with access to the underlying components of the critical evidence review, including an Excel spreadsheet of accessed literature and the search, quality and inclusion criteria used. This will remain the intellectual property of the Authority.

### Interim Findings

## Interim findings should be provided to the Authority by the deadlines outlined in “7. Key Milestones and Deliverables”. These findings shall be used for internal purposes only at this stage, therefore outputs do not need to be fully complete. However, they should be fully quality-assured in line with the Aqua Book and presented in a clear and accessible manner so that they can be shared with internal colleagues and stakeholders where necessary.

## Interim findings should contain initial results from both the decomposition analysis and the critical evidence review.

## It is anticipated that the Supplier will hold an informal discussion or presentation of the interim findings with the Authority to aid understanding, communicate early findings and their implications. The supplier should be prepared to discuss comparability with previous analyses and take guidance from the Authority at this stage.

### Interim Training Package

## An interim training package should be delivered to the Authority by the deadlines outlined in “7. Key Milestones and Deliverables”. This will be used to update the Authority on progress and ensure the final training package will meet the needs of the Authority. The interim training package does not need to be fully complete but should:

## Contain draft versions of all three elements required in the final training package: 1) a methodology document, 2) code for carrying out the analysis, and 3) a training presentation. See F. Final training package below for more details of these elements.

## Be sufficiently developed to allow all three elements to be properly assessed against the Authority’s needs.

## Be presented in a clear and accessible manner.

## Include a clear plan and timeline for delivering the final training package.

## It is anticipated that the Supplier will hold an informal discussion or presentation with the Authority on the interim training package to aid understanding, and clarify the scope and focus.

## The Authority requires the supplier to clearly communicate any operating system, software, packages or other stipulations which are needed for the successful delivery of D. Interim training package as part of A. Inception meeting. This is to allow Authority analysts sufficient time to obtain these requirements.

## It is expected the Supplier will modify the final training package based on feedback from the Authority on the interim training package.

## Final Report

## The Supplier is required to produce a final report which should be signed off by the Authority by the deadlines outlined in “7. Key Milestones and Deliverables”. The Supplier should consider a realistic timeline to allow time for review and comment from the Authority and relevant stakeholders prior to this deadline. The report will incorporate the findings of the decomposition analysis and multi-disciplinary literature review to inform the final conclusions and actionable insights.

## The final report should be focused in terms of length (30-35 pages excluding annexes) and include an executive summary and actionable insights. Provision of alternative versions including easy read, large print and BSL should also be considered. The Authority is open to the Supplier suggesting alternative ways of presenting the findings.

## The Supplier is required to generate a chart or infographic to effectively illustrate the key findings of the work to a lay audience. In Olsen et al. 2018,  Figure 1 is an incredibly impactful tool for communicating about the GPG and the Authority requires a data visualisation with the same power for this analysis. The Authority is open to the Supplier suggesting alternative and innovative ways to visualise the key findings.

## The final report (including annexes) should be accessible to a range of audiences. This should include using plain English and avoiding technical jargon where possible.

## The final report will need to incorporate some aspects of the Authority’s style guides. This includes, but is not limited to, accessibility guidance.

## The Supplier is required to ensure that all data, analysis, the final report and annexes have been quality assured in line with the Aqua Book. This is essential for providing the Authority with reasonable assurance of the quality of the work.

## The Authority requires the Supplier to provide the processed dataset used for the decomposition analysis to enable Authority analysts to carry out quality assurance. This dataset will remain the intellectual property of the Authority.

## The Authority requires the final report to include a section discussing how the analysis differs from previous analyses, . This includes, but is not limited to, changes in the dataset, data or variables being unavailable, changes in data collection methods, and changes in analytical approach. The supplier is required to outline the reasons for these differences and caveats for interpreting the results and making comparisons with previous analyses in full.

## The final report should include a discussion of how the proposed analysis contrasts with similar analysis on the GPG, for example by the Office for National Statistics, the Fawcett Society, and previous analysis by the Authority,. This discussion should include any caveats and risks when comparing and contrasting results.

## The Authority requires that drafts of the final report should be fully proofread and signed-off by the Supplier to enable complete and efficient review and sign-off from the Authority.

## To ensure research outputs meet the expectations and requirements of the Authority, drafts should be shared with the Department as early as is practicable. The Authority reserves the right to request iterations of the output or tool until they meet the agreed upon standard. Comments on draft outputs or research tools should be given and dealt with in a timely manner, to be agreed upon between the Supplier and the Authority.

## Final reports must be submitted to the Authority in advance of publication. The final publication dates will be agreed between the Authority and the Supplier in due course.

## The Supplier is required to work closely with the Authority upon publication and ensure all communications are coordinated. Any communication materials to be used by the Supplier should be submitted to the Authority for sign-off or agreement before use.

## It is anticipated that the Supplier will give a presentation to communicate key findings and recommendations from the final report to the Authority and allow for questions and discussion.

## Any outputs from this work, including but not limited to: the literature review, the final report (including annexes), presentation slides and related outputs will remain the intellectual property of the Authority. Decisions regarding the timings and format of reports will be taken by the Authority.

## Final training package

## The Supplier is required to produce a training package to address:

## Objective 3: Upskill analysts at the Authority to allow them to independently carry out and interpret decomposition analysis on other equalities issues, such as ethnicity and disability pay gaps.

## The purpose of this training package is to enable analysts at the Authority to independently carry out decomposition analysis in future. The final training package should be delivered by the deadlines outlined in “7. Key Milestones and Deliverables”.

## The training package is to include the following elements:

## A methodology document detailing everything required to carry out decomposition analysis, including:

## The data sources and variables used in the analysis

## How the data was accessed

## Data cleaning

## Data processing

## What data checks to conduct to ensure data quality and how to carry out these checks

## How to carry out the decomposition analysis

## What robustness tests to conduct to ensure statistical tests are valid i.e. meet their assumptions, and how to carry out these tests

## How to interpret the statistical outputs from the decomposition analysis

## A clear guide on how to accurately write and present the results

## Relevant statistical background to explain the decision making behind the analytical approaches and methods used

## Any other information relevant or useful for carrying out decomposition analysis, including how to incorporate different data types e.g. continuous, factors, binomial

## Code, preferably using the R coding language, for all steps involved in decomposition analysis, including but not limited to: data cleaning, data processing, decomposition analysis, and validity testing. The code should include a dummy or example dataset which can be run through the code.

## A presentation to Authority analysts to aid understanding and provide an opportunity for questions and discussion.

## The methodology document should be a step by step guide on how to carry out decomposition analysis. It should sit alongside and complement the code, referencing which sections or lines of code the methodology document is referring to at each step. The methodology document should use outputs from running the dummy or example dataset through the code to describe how to interpret the results of a decomposition analysis.

## The methodology document should provide guidance and instructions on any differences in methodology needed to carry out decomposition analysis on the disability pay gap and ethnicity pay gap.

## All code should follow best practice for coding. It should be well structured, clearly annotated, and be easily adapted to carry out additional decomposition analysis.

## A final version of the processed dataset should accompany the code to allow Authority analysts to use the code to exactly replicate the results of the decomposition analysis. This dataset will remain the intellectual property of the Authority.

## The presentation should provide a comprehensive run through of the methodology document and code, and provide analysts at the Authority with an opportunity to ask questions.

## Following the presentation, the Supplier is expected to provide eight hours of contact time with Authority analysts to provide support on carrying out decomposition analysis. This contact time could be in the form of emails or meetings.

## Whilst the methodology document (including annexes) and presentation should go into sufficient detail and statistical methods, they should still endeavour to be accessible, use plain English and avoid technical jargon where possible.

## To ensure training materials meet the expectations and requirements of the Authority, drafts should be shared with the Department as early as is practicable. The Authority reserves the right to request iterations of the output or tool until they meet the agreed upon standard. Comments on draft outputs or training tools should be given and dealt with in a timely manner, to be agreed upon between the Supplier and the Authority.

## The Authority requires the supplier to clearly communicate any operating system, software, packages or other stipulations which are needed for the successful delivery of F. Final training package as part of A. Inception meeting. This is to allow Authority analysts sufficient time to obtain these requirements.

## The Authority welcomes innovative approaches to improve the final training package.

## All parts of the training package will remain the intellectual property of the Authority. The Authority may record any presentations for the purpose of future internal training.

# KEY MILESTONES AND DELIVERABLES

## The Authority will measure the quality of the Supplier’s delivery by delivering against the following timetable and milestones. It is expected that the Supplier shall be available to start work immediately on award of contract.

## The research is anticipated to run from May 2025 for approximately 9 months. Our suggested project timeline is shown below. Potential Suppliers should produce a detailed timeline as part of their submission.

## The following indicative timetable sets out the proposed key stages and deliverables:

| ### Milestone | ### Description | ### Delivery date |
| --- | --- | --- |
| ### 1 | ### Award of contract | ### No later than 14/05/2025 |
| ### 2 | ### Project planning and inception meeting including analytical plan | ### No later than 30/05/2025 |
| ### 3 | ### Interim findings presented | ### No later than 31/07/2025 |
| ### 4 | ### Interim training package presented | ### No later than 15/09/2025 |
| ### 5 | ### Draft of final report | ### No later than 14/10/2025 |
| ### 6 | ### Final report (signed off by Authority) | ### No later than 14/11/2025 |
| ### 7 | ### Final training package (signed by Authority) | ### December 2025 |

# MANAGEMENT INFORMATION/REPORTING

## The Supplier must have one lead project manager responsible for all components of the research. The Project Manager for the Contracting Authority will be James Probert, Head of Intersectional Analysis at the OEO.

## The Contracting Authority’s research project manager and/or team will provide advice and guidance on any issues during the course of the project.  Where comments or input are required from the Contracting Authority, the Supplier should allow sufficient time for turnaround and give advance notice where possible.  As a general guide the Contracting Authority will aim to turnaround minor requests within one week and major requests (e.g. commenting on drafts of reports, or checking data outputs) within two weeks. The Supplier should factor these clearance periods into project timings and indicate clearly in any project timetable when such outputs will be submitted for clearance.

## It is expected that project leads for the Contracting Authority and Supplier, plus additional team members as required, will hold regular online progress meetings with the Department's project manager. The frequency of these meetings will vary over the course of the project, however during the project development phase, we expect these meetings to be fortnightly. Frequency will also be dependent on assessment of emerging risk. Expenses for such meetings must be included in the core contract price. These meetings will be accompanied by regular written project updates.

## As part of the management of the research the Supplier will be required to produce and submit the following management information to the Contracting Authority:

## Brief monthly progress updates – to update on progress towards milestones, update the Authority on the latest findings, and management of risks arising.  The format of these reports should be agreed with the Contracting Authority and submitted in advance of the teleconference.

## Monthly contract review updates - to review adherence to objectives and milestones, and consider any course correction required.

# volumes

## Not applicable

# continuous improvement

## The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

## The Supplier should present new ways of working to the Authority during monthly Contract review meetings.

## Changes to the way in which the Services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

# Sustainability

## All meetings to be held virtually, unless specifically requested by the Contracting Authority.

## The Supplier should meet the social value commitment by ensuring that effective measures to deliver any of the following benefits through the contract are made:

## Demonstrate action to increase the representation of disadvantaged people in the contract workforce.

## Support disadvantaged people in developing new skills relevant to the contract, including through training schemes that result in recognised qualifications.

## Demonstrate action to identify and tackle inequality in employment, skills and pay in the contract workforce.

## Support in-work progression to help people, including those from disadvantaged or minority groups, to move into higher paid work by developing new skills relevant to the contract.

# QUALITY

## The Department's contract manager will oversee and record quality assurance of the evaluators design, data collection process, and the reporting and analysis of findings. Where the quality assurance process identifies practices that do not meet the expected standard, or errors in analyses or reports, then the evaluator will need to make changes or correct errors to meet the necessary standards of quality. The evaluators’ considerations of contract will be met when all outputs have been successfully quality assured.

## The Contracting Authority will measure the quality of the Supplier’s delivery by:

## Supplier experience and capability: the supplier will demonstrate excellent project management of delivering projects of similar size and scope, with awareness of risk and proposals for mitigation. Suppliers will also demonstrate experience of delivering research on sensitive topics with diverse field staff and using culturally sensitive practices.

## Research design: the supplier will demonstrate an excellent approach to methodological rigour in qualitative research, ensuring appropriate representation in the sample, quality assurance processes and clear publication plans.

## Project management, data security and ethics: the supplier will be able to meet key milestones and have excellent awareness of ethical issues and means of mitigation. They will also comply with all data security requirements.

## The final report should be focused in terms of length (30-35 pages, excluding annexes) and include an executive summary and actionable insights. The report will incorporate the findings of the lived experience research to inform the final conclusions.

## The Supplier is required to ensure that all data, analysis, the final report and annexes have been quality assured in line with the Aqua Book. The Supplier is expected to provide the Contracting Authority with reasonable assurance that the work has been quality assured.

## All code should follow best practice for coding. It should be well structured, clearly annotated, and be easily used to carry out additional decomposition analysis.

## The final report (including annexes) should be accessible to a range of audiences. This should include using plain English and avoiding technical jargon where possible.

## Provision of alternative versions including easy read, large print and BSL should also be considered. The Authority is open to the Supplier suggesting alternative ways of presenting the findings.

## The final reports will need to incorporate some aspects of the Authority’s style guides. This includes, but is not limited to: accessibility guidance.

## The Supplier is required to work closely with the Authority upon publication and ensure all communications are coordinated. Any communication materials to be used by the Supplier should be submitted to the Authority for sign-off or agreement before use.

# PRICE

## Prices should be inclusive of expenses and exclusive of VAT.

## The Contracting Authority is looking for the most competitive bid that can deliver maximum value for money. This will be assessed in accordance with Attachment 2.

## Usage of, and charges from, third party suppliers should be clearly identified and explained.  The Contracting Authority expects the Supplier to ensure that third party suppliers are commissioned on a clear value for money basis, and that such activities are passed on at cost.

## Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule including VAT and including all other expenses relating to Contract delivery.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

## The Supplier shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

## The Authority will measure the quality of the Supplier’s delivery against timeliness of deliveries and alignment to the Aqua book.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

## Suppliers should confirm they hold either Cyber Essentials or ISO27001 certification.

## The Supplier is required to implement appropriate arrangements for data security at all times, particularly relating to the transmission and storage of personal data. Such procedures must meet the standards outlined in the framework terms and conditions, UK GDPR and the Data Protection Act 2018.

## Processes should be in place for safeguarding against data and code loss, including appropriate risk management procedures. Potential Providers should confirm within their response that such procedures will be implemented and outline the technical measures to be put in place to meet such requirements.

## Although the research may be included in a published report, no information that could identify any individual would be used when presenting findings from the study.

# PAYMENT AND INVOICING

## 17.1 The Suppliers will be invoiced to the following schedules:

| ## Invoice | ## Milestone | ## Description | ## % of Value |
| --- | --- | --- | --- |
| ## 1 | ## 3 | ## Interim findings presented | ## 25% |
| ## 2 | ## 4 | ## Interim training package presented | ## 15% |
| ## 3 | ## 6 | ## Final report signed off by Authority | ## 30% |
| ## 4 | ## 7 | ## Final training package signed off by Authority | ## 30% |

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

## All invoices should be sent directly to Accounts Payable at SSCL. Please send all electronic invoices to our shared service provider at accounts-payable.cab@sscl.gse.gov.uk and copied to the Authority’s finance team at oeofinance@cabinetoffice.gov.uk

## Contracting Authority purchase order numbers must be clearly stated on all invoices. Any supplier invoices received without a valid purchase order number will not be paid and will be sent back.

## Invoices should be submitted to:

### Shared Services Connected Limited,

### CAB Procure to Pay,

### PO Box 405,

### Newport,

### NP10 8FZ

# CONTRACT MANAGEMENT

## The Supplier will be required to implement a structured approach to risk management, outlining the key risks identified and how these will be managed.   This is to include risks relating to project delivery, in addition to presentational risks due to the sensitive nature of this research.

## Potential Suppliers should outline full details of this plan as part of their response, including the course of action to be followed should risks to project delivery arise, e.g. in the case of low response rates and/or slippage.

## As part of the monthly progress reports outlined above, the Supplier should report on performance against relevant milestones and include an update on risks identified and how these will be managed.

## The Contracting Authority will assess performance based on these reports and will require additional meetings with the Supplier if milestones are not met, either in terms of timings or quality.

## Attendance at Contract Review meetings shall be at the Supplier’s own expense.

# LOCATION

## The location of the Services will be carried out at the Supplier’s address.

Cabinet Office website

Office for National Statistics (ONS), released 29 October 2024, ONS website, statistical bulletin, Gender pay gap in the UK: 2024

Trade Unions Congress (TUC), 21 Feb 2024, TUC: Gender pay gap means women work first two months of the year unpaid

PricewaterhouseCooper (PwC), June 2024, Mandatory UK Gender Pay Gap Reporting

Olsen et al., 2018 defined covariates which increase the GPG as ‘drivers’, and covariates which decrease the GPG as ‘protective factors’.

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Olsen, W., Gash, V., Vandecasteele, L., Walthery, P., & Heuvelman, H. (2010). The Gender Pay Gap in the UK 1995-2007: Research report number 1. Government Equalities Office.

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Olsen, W., Gash, V., Vandecasteele, L., Walthery, P., & Heuvelman, H. (2010). The Gender Pay Gap in the UK 1995-2007: Research report number 1. Government Equalities Office.

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Olsen, W., Gash, V., Vandecasteele, L., Walthery, P., & Heuvelman, H. (2010). The Gender Pay Gap in the UK 1995-2007: Research report number 1. Government Equalities Office.

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Olsen, W., Gash, V., Vandecasteele, L., Walthery, P., & Heuvelman, H. (2010). The Gender Pay Gap in the UK 1995-2007: Research report number 1. Government Equalities Office.

Rapid Evidence Assessment Toolkit

The Aqua Book: guidance on producing quality analysis

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Guidance and tools for digital accessibility

The Aqua Book: guidance on producing quality analysis

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Olsen, W., Gash, V., Vandecasteele, L., Walthery, P., & Heuvelman, H. (2010). The Gender Pay Gap in the UK 1995-2007: Research report number 1. Government Equalities Office.

Olsen, W., Gash, V., Sook, K. & Zhang, M. (2018). The gender pay gap in the UK: evidence from the UKHLS (DFE-RR804). London, UK: Department for Education, Government Equalities Office.

Olsen, W., Gash, V., Vandecasteele, L., Walthery, P., & Heuvelman, H. (2010). The Gender Pay Gap in the UK 1995-2007: Research report number 1. Government Equalities Office.

UK Government Analytical Community. (2020). Quality assurance of code for analysis and research (version 2024.1). Office for National Statistics, Analytical Standards and Pipelines hub

The Aqua Book: guidance on producing quality analysis

Guidance and tools for digital accessibility

The Aqua Book: guidance on producing quality analysis