## St.Ives Mushrooms Ind Units SOW
Replacement Industrial Units
at
The Old Mushroom Farm
Halsetown, St Ives
for
St.Ives Mushrooms Ltd
RW Abbott & Associates Ltd
Chartered Surveyors
| Preliminaries |  | £ P
Project
Single Phase- Demolition of existing structure, with replacement steel framed eight unit industrial premises
Employer
St.Ives Mushrooms Limited
The Old Mushroom Farm
Halsetown
St.Ives
TR26 3LZ
Architectural Designer
Gary Wilson
1 Aldreath Cottages
Aldreath Road
Madron
Penzance
Cornwall
TR 20 8ST
Tel 01736-333482
Email igwilson236@btinternet.com
Structural Engineer
( contractors design element)
Drainage Engineer
Jan Clark
EDS
Penstraze Business Park
Truro
TR4 8PN
Tel 01872-306311
Email jan@eadsolutions.co.uk
£ P
Quantity Surveyor, Contract Administrator &
CDM Principal Designer
Richard Abbott MRICS
R W Abbott & Associates Ltd
Chartered Surveyors
Grove Cottage Red Lane
Rosudgeon
TR20 9PU
Tel. 01736-762082
Mob.07966-527140 email richard.w.abbott@talk21.com
Contract
General terms of JCT MWD 2016
Liquidated and ascertained damages £ 650 /week or part thereof
Defects period of 6 months
Retention of 5% during the works and 2.5% for the Defects Period
Project commencement is forecast for early May 2021
Force majeure clause under Extension of Time claims
to include implications of legislative suspensions of work from Covid19/pandemic prevention measures
contractors design portion to include steelframe,cladding
roller doors
Professional Indemnity Insurance of £ 2M to be held
by the main contractor or designing subcontractor.
Site visit- single day for all visits noted in Invitation ot Tender
Site working hours restriction- Monday to Friday 8 to 5.30
Saturday 8 to 12.30 only
Photographic survey of access lane and site conditions
to be undertaken and shared before commencement
| Outline Schedule of Work |  | £ P
Preliminaries
The works are shown on drawings:-
Architectural drawings:
Gary Wilson 023/18/14 & 11
Drainage engineers drawings
EDS J-1337/3401A & 3001A
Western Power Distribution drawing 3599204
It should be noted that there are limited external areas for storage or mixing. Parking is limited to the front of the new building at the lower level and only by arrangement with the clients at the upper levels and drop off only at the upper general paved area. Measures must be put in place to ensure there is no run off from external or internal mixing areas during the works at any time into drains or adjacent land, and all fluids/silt is contained by sand bags or suitable barriers.
Welfare facilities in the site office block may be used.
A welfare unit, separate office and communal wc are available free, but must be kept clean and returned in existing condition.
Water is available from the tap on the lower end of the office block
Phasing/Continuation of the Works
It is proposed that the works are carried out in a single phase. With commencement dependent upon grant approval.
£ P
CDM regulations
The project is notifiable to the HSE under current CDM regulations. A Principal Designer has been appointed and an initial phase specific preconstruction plan has been prepared for the Contractor to respond to.
Use of Services
Use of the clients water and electricity will be permitted, with reasonable use ( meter readings will be taken before commencement). WC facilities will be made available.
Protection
Areas of the property not subject to described works must be protected from damage , including run off of slurry from the works to existing drains
Materials
If any specified materials are no longer available, report back to the designers for re specifying as soon as possible
Compliance
Comply with the following as appropriate:
Any and all regulations made by any authority having jurisdiction over the works
BSI codes of practice and British standards
BRE Digests
Printed directions issued by manufacturers of materials, fittings and appliances used whether specified or not.
Electrical installation/alterations to comply with the latest technical standards of the IEE and an appropriate BS7671 installation and test certificate Is to be produced to comply with the Building Regulations.
Abbreviations
SE- Structural Engineer
OSA-Or Similar Approved
| Preliminaries to Main summary | £
£ P
2 | Demolitions
2.01 | Remove existing steelframe, cladding and masonry to retained floor slab level and dispose
2.02 | Allow credit for salvage cost of recycling the steel frame
2.03 | Make good any above ground retained structures disturbed by the removal of the existing structre
2.04 | Asbestos containing cladding to be removed carefully and as whole as possible to avoid release airborne fibres.
Note asbestos report included in pre-construction plan
2.05 | Existing rear and right hand block boundary walls to be left
intact and protected when existing building removed
| Demolition to summary | £
£
£ P
3 | Site preparation and Foundations
3.01 | Break out existing floor slab around new column bases
3.02 | Excavate for new foundations bases to firm ground
3.03 | Dispose of excavated material offsite
3.04 | Remove any above slab remains of previous structure
and make good surface of slab over disturbed areas
3.05 | Cast new foundation/column bases designed by contractor
3.06 | Make good and backfill around column bases and retained slab surface
| Site Prep & Foundations to Summary | £
£ P
4 | Steel Frame & cladding envelope package
( contractors design element)
4.01 | Provide steel frame on a design, fabricate and install basis,
Steelwork and cladding design to include for imposed load of PV Solar panel array to be installed at a later date.
to include providing calculations for building control, &
Contractors proposals for design life of whole package with a minimum requirement of 20 years
4.02 | Provide plastisol coated uninsulated steel profiled cladding to walls and roof, profile 32/100, 0.7mm or similar approved
4.03 | Provide 140 blockwork masonry party walls fair face pointed to full height for fire barrier, tied vertically to steel frame
4.04 | Provide rainwater goods to ground level, sized for roof area
4.05 | Provide roller shutter doors incorporating pedestrian wicket door, provide contractors proposals
4.06 | Provide 215 masonry block walls at lower level, fair face pointed internally
4.07 | Provide firestopping at perimeter of party walls
4.08 | Frame steelwork for rear window openings
4.09 | Eight white UPVC, fixed pane windows at high level
4.1 | Provide DPC courses between retained slab and new blockwalls
| Steelframe and envelope package to Summary | £
£ P
5 | Storm Drainage
5.01 | Cut edge of existing slab/edge of lower abutting yard paving and install 150mm Aco Highflow or eqivalent slotted grating drainage channel
5.02 | Provide new on site drainage runs as EDS Drawing 3001A
5.03 | Provide new manholes as EDS drawing 3001A
5.04 | Excavate, install and make good yard slab for attenuation tank as EDS drawings 3001A & 3401A
5.05 | Disconnect existing storm drains from exising arrangements
5.05 | Install silt trap manhole as drawings 3001A & 3401A
5.06 | Provide new drain run across neighbours field to leat with working area fully fenced ( provisional)
5.07 | Provide headwall/outfall structure as drawing 3401A ( provisional)
5.08 | Provide rainwater gullies at base of new rainwater downpipes
5.09 | Connect slotted grating channel to new drainage system
| Storm Drainage to Summary | £
£ P
6 | Service trench
6.01 | Provide a 68 metre trench, 750 minimum depth for the new electrical main as Western Power Drawing 3599204 from existing unit 1 pole to the face of the existing unit to the left of the new buildings
6.02 | The trench route to be at the lower level of the two level
paved areas between the office block and existing units 1 to 10
6.03 | Cut out the existing rainwater channel and reinstate on completion for the new service trench line
6.04 | Where the service trench level changes from the higher level by the pole to the 1.3 metre lower level in front of units 1 to 10 a ramped trench rather than vertical drop will be required due to the cable flexibility limitations
6.05 | Collect duct, draw rope, marker tape and surface mounted box from Western Power Depot at Pool
6.06 | Install free issue ducting, marker tape,draw cord and surface box
6.07 | Provide sand bed and surround to ducts ensuring 600mm cover to top of ductwork
6.08 | Make good concrete paving disturbed on trench route
6.09 | Provide submain service trench from new three phase board to each unit, make good concrete, provide and bed and surround, furthest trench end at beginning if eight new unit ( furthest unit right)
6.1 | Note the estate wide water supply borehole is located between the connection pole and the drop to the lower trench level, locate this before major excavations to agree suitable trench route to avoid disturbance or potential polution
| Service trenching to Summary | £
£ P
7 | Electrical works
7.01 | Provide individual sub meters & distribution boards from new 3 phase board into each of the eight new units
7.02 | Provide four suspended two metre LED strip lights in chains in each new unit-
7.03 | Provide four double socket outlets in each new unit
7.04 | Emergency Exit Lighting to each unit ( provisional)
7.05 | Emergency Exit Signage to each unit ( provisional)
| Electricial Works to Summary | £
8 | Provisional sums |  | £ P
8.01 | Provisional sum for Western Power 3 Phase connection |  | 2500
| Provisional sums to main summary | £ | 2500
9 | Dayworks |  | £ P
Include the following Provisional sums for work to be valued on a Daywork basis when expressly authorised:-
Work within normal working day ( 8am to 4.30pm Monday to Friday & Saturday 8am to 12.30pm)
Craftsmen 20 hours@ £ ……./Hour………
Labourers 20 hours@ £…… /Hour……….
Work outside normal working day
Craftsmen 10 hours @ £……….Hour…….
Labourers 10 hours @£………..Hour…..
| Plant/Hire nett cost – allow the sum of £ 500…. |  | 500
Add for profit and overheads…………………………
| Materials nett cost-allow the sum of £ 500……. |  | 500
Add for profit and overheads…………………………
| Subcontractors accounts – allow the sum of £750 |  | 750
Add for profit and overheads ………………………...
| Utility connection accounts - allow the sum of £500 |  | 500
Add for profit and overheads ………………………...
| Total Dayworks to Main Summary | £
10 | General Summary |  | £ P
1 | Preliminaries
2 | Demolition
3 | Site Preparation and excavations
4 | Steelframe and envelope
5 | Storm Drainage
6 | Service trencjhing
7 | Electrical Works
8 | Provisional Sums |  | 2500
9 | Dayworks
| Overall Total- to Tender Form | £
exc. Vat