## Sheet1
CLARIFICATION LOG
Tender: | Supply, installation and commissioning of cranes
Tender Reference: | BUS003_0081-2.2
Published Date: | 2024-05-22
Version number: | 0.4
Number | Clarification | Response | Reply date
1 | Can we have an extension | Yes. Clarifications deadline is now 21 June. Deadline for submission 5th July. | 2024-06-17
2 | Do you know the runway length of the goliath crane? | Allow for up to 80m | 2024-06-17
3 | Dimensions for jib crane | Minimum height 5m, minimum boom- 5m | 2024-06-18
| What is the base material of the dock bottom? It looked fairly sandy/silty when we came down, is the foundation suitable for using a MEWP/Small Crane on? | The foundations for the goliath will be in place prior to assembly, we’ve had core samples taken and a full structural survey is now taking place. The dock it’s self has a concrete base, it was silted up at this time because the gates were off. | 2024-06-20
| What is the situation with road closures? Is there a maximum timeframe, will one lane closure for an extended period be considered? | We exercise road closures on a regular basis, to allow ships into dry dock, we can get away with closing the road for a whole day at a time given enough notice. | 2024-06-20
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: