## Instructions
1 | Title | Project-18427 - HMC Valiant Planned Maintenance and Out of Water Interim MCA Load Line Survey and Outer Bottom Inspection
2 | Mandatory Questions
Any cell bordered in RED is mandatory and requires an answer. Any cells bordered in RED that do not have an answer may render your bid non-compliant.
3 | Instructions
Bidders are requested to complete all lines with a cost in tabs Annex A to Annex E. Cells to be completed by bidders are shaded yellow. Any line submitted without a cost attributed to it will be considered as £0.00 and any further costs incurred in the facilitation of the line will be at the cost of the Supplier. Bidders are requested to select an entry from the drop down menus provided for every acknowledgement cell in Annex A to Annex E. Bidders are requested to fill in the Total Cost line for each Annex on the respective Annex tab. Bidders shall fill in the column I with a number value only. Where requested, bidders must provide detailed information to support their stated cost. this information must be incorperate within document.
4 | Additional Information
Where bidders can not provide a cost or wish to provide more detail than the cell allows, they are requested to fill in a line in the Additional Information tab for each item they wish to add information against.
5 | Communications
If, for any reason, you require assistance, please email: MaritimeProcurement@homeoffice.gov.uk
6 | Declaration
I have read and understood these instructions

## Guidance
Guidance to Bidders
Line | Requirement
1 | All quotations are to be submitted in GBP.
2 | The Bidder offering the lowest quote for a compliant submission will be selected as the preferred Bidder for contract award.
3 | All submissions must contain the mandatory requirements as per Lines 4 to 9 (inclusive) of this Guidance.
4 | Mandatory requirements that qualify the submission as compliant are;
5 | Where requested, the Bidder has submitted costs for all work line-items listed in Annexes A, B, C, D and E of the Bidding Tool provided.
6 | Where applicable, the Bidder has acknowledged all note-items listed in Annexes A, B, C, D and E of the Bidding Tool provided.
7 | Written acknowledgement, by the Bidder, to the Standard UK Government Short Form Terms and Conditions for Goods and Services (attached to the tender advert at the Contracts Finder portal reference) must be stated by the Bidder upon submission.
8 | Written acknowledgement upon submission, by the Bidder, that they have the correct insurance levels as stated in §2.1.1, §2.1.2 and §2.1.3 of the SoR.
9 | The Supplier must submit a letter, alongside the completed Workbook, stating the total costs for;
10 | Annex A;
11 | Annex B;
12 | Annex C;
13 | Annex D;
14 | Annex E; and
15 | Grand Total.
16 | Failure, by the Bidder, to adhere to Lines 4 to 9 (inclusive) may result in the submission being considered non-compliant.
17 | Failure, by the Bidder, to electronically complete the Bidding Tool may result in the submission being considered non-compliant.
18 | Unless specified as Authority supplied, all spare parts and consumables required to complete this requirement, including paint and anodes, are to be provided by the Supplier.
19 | All clarification questions regarding this competition should be submitted via email to MaritimeProcurement@homeoffice.gov.uk no later than 1200hrs, 22nd February 2025. Any clarifications received after this date will not be actioned.
20 | All submissions should be received by the Authority no later than 17:00hrs 28th February 2025.
Declaration
I have read and understood this guidance.

## Annex A
Annex A: General Requirements of Work
Annex A |  | Description | Qty | DoQ | Description of Service | Acknowledgement / Unit Price | Total Firm Cost
1 | Berthing
| Note |  |  |  | The Supplier is to include all costs associated with berthing, shore power, rubbish removal and movements in the submitted quotation and provide the following for the entirety of the contract period.
| 1.01 | Pre-MSER storage | As | Req. | If the proposed start date for the Maintenance and Safety Equipment Recertification work is later than the start date in §5.10 of the Statement of Requirements, the supplier must provide suitable and secure storage of the vessel in the water until the MSER work commences. Please quote a) any daily charge rate and b) the estimated total charge for the supplier's proposed MSER start date.
| 1.1 | Alongside Berthing | 35 | Day | The Supplier must provide appropriately sized, secure, alongside berthing, as required, during this period of works, with a minimum depth of 1m below the keel at Low Water Springs at all times. The duration will be 35 days in total with time allowed in Dry Dock for the work in Annex E and the balance to in a safe, secure alongside berth.
|  |  | 1 | Day
| 1.2 | Movements | As | Req. | The Supplier must arrange at their own cost, any movements of the vessel as required for the entirety of the contract period.
| 1.3 | Means of safe access | As | Req. | Suitable safe access is to be provided to the vessel at all times and at all states of the tide when in the water and a safe secured ladder or steps for access when out of the water.
| 1.4 | Electrical Power | 15000 | kW-h | The supplier will provide electrical power to the vessel for the duration of the contract period. Please quote for the initial quantity of KW-h (see above left) and the cost of additional units if required. Vessel electrical system uses 400-volt, 50 Hz, 63-amp, three phase shore power.
|  |  | 1 | kW-h
| 1.5 | Electrical Connection | 1 | Ea. | Connection and Disconnection of shore power cable as required during the contract period
| 1.6 | Cleanliness | As | Req. | The Supplier will return the vessel to its original state of cleanliness on handover, removing and disposing of any arisings and cleaning all work areas on completion.
| 1.7 | Disposal of Waste | 1 | Ea. | All costs associated with the disposal of any waste during the life of this contract are to be born by the supplier to include approximately 1000 ltrs of oily waste.
2 | Third-party Costs
| 2.1 | Use of third parties | 1 | Contract | Where a requirement stipulates the use of a third party, the Supplier is responsible for arranging the attendance of such suppliers. The Supplier is to include those costs in the section which stipulates their attendance.
| 2.2 | Use of third parties | 1 | Contract | Where a requirement will be carried out by a third party, the Supplier must state in their bid that the third party is available and can complete the requirement as specified in the time period specified in this Statement of Requirements.
3 | Insurance
| 3.1 | Cost of additional Insurance | As | Req. | If required, any additional costs that may be incurred by the Supplier due to the undertaking of a bespoke insurance arrangement are to be included in the quote and the Authority is to be notified and then provided with the appropriate documentary proof following contract award.
4 | MST 7.8m RHIB
| 4.1 | Ashore Stowage | As | Req. | The contractor shall offload the MST 7.8m RHIB from the vessel and stow ashore on suitable hull blocks.
| 4.2 | Movements | 1 | Ea. | When required, the contractor shall lift the MST RHIB onto Owners supplied transport.
| 4.3 | Movements | 1 | Ea. | When required, the contractor shall lift the MST RHIB off Owners supplied transport
| 4.4 | Movements | 1 | Ea. | When required, the contractor shall load the MST RHIB securely back on to the Vessel.
5 | General Provision
| 5.1 | Project Management | 1 | Contract | The Supplier will appoint a Project Manager, as a single point of contact for the Border Force Overseeing Officer (BFOO), for the duration of this requirement. The Suppliers Project Manager is to be available as necessary for the duration of the period. The costs for the Supplier's Project manager should be included as part of the cost of each line-item.
| 5.2 | External Contractors | 1 | Contract | If required, the Supplier is to confirm they will provide support to the external contractors Border Force has engaged with. This will be the provision of manual labour, cranage, tools, removal and disposal of parts if required and costs incurred will be dealt with in the appropriate Annexes of this statement of requirement.
| 5.3 | Accommodation | 1 | Contract | During the contract period the Supplier shall provide reasonable and private office accommodation for use by the Authority at the site where the vessel is being worked on. All costs associated with this provision are to be included in any quote/bid submitted by the Supplier to the Authority.
| 5.4 | BFOO Parking | 1 | Ea. | During the period of maintenance 1 safe and secure parking space should be made available.
| 5.5 | Consumable Fixings | 1 | Contract | All minor consumable fixings, sealants etc. required to carry out this requirement are to be at the expense of the Supplier.
| 5.6 | Secure Storage | 1 | Contract | The Supplier is required to provide an appropriately secure storage area for any of the vessel’s equipment, should anything need to be removed.
| Note |  |  |  | The storage area should not have a negative impact on the item(s) of the vessel’s equipment that has been removed for storage.
| 5.7 | Storage | As | Req. | The Supplier is required to provide a clean, secure, and environmentally controlled storage facility of at least 30m3 for the crew to stow onboard domestic equipment and ancillary items.
| 5.8 | Fork Lift Movements | 6 | Ea. | The Supplier is to provide fork lift movements of stores to the vessel
|  |  | 1 | Ea. |  | Price for additional fork lift movement
| 5.9 | Floor Protection | 1 | Contract | All flooring and bulkheads/partitions in all domestic areas, including the Wheelhouse, which will be accessed by the Supplier’s personnel or contractors, or Authority contractors, are to be provided with non-slip floor protection, up to ½ height of the partition, the use of brown paper or paper cardboard is not enough. Such protection will be replaced as necessary to ensure integrity throughout the project.
Annex A Total Cost

## Annex B
Annex B: Inspection, Testing and Certification of Safety Equipment
Annex B |  |  | Description | Qty | DoQ | Description of Service | Acknowledgement / Unit Price | Total Firm Cost
1 | Requirements for Certification
| Note |  |  |  |  | All line-items contained in this Annex shall be inspected and tested, where required, in accordance with relevant legislation and standards, as appropriate. All line-items shall be issued a separate certificate of inspection and testing. All tasks are to be carried out by an approved examination test house, unless otherwise stated. On completion of all work, the supplier shall provide inspection reports and certification for each separate task.
2 | Documentation
| Note |  |  |  |  | Two copies of all certification required for regulatory compliance, or as requested by the Authority, shall be supplied enclosed in clear envelopes within two four-ring ring binders. Each binder shall be assembled using the ordering and numbering shown in the Authority’s document SOP 08 (SOP 08 will be issued to the successful Supplier). Additionally, an electronic copy of all certificates and test reports shall be forwarded by e-mail to the Authority in .pdf format. All certificates and reports specified and required are to be provided in hard copy folders to the Vessel before departure and electronically emailed to the Authority.
3 | Fire Fighting and Fire Detection. This item not required on this contract.
| Note |  |  |  |  | These tasks are to be carried out by an approved Marine Fire and Safety Contractor. Supplier to arrange. This item not required on this contract
| 3.1 | 3.1.1 | Inspect, Clean and Test | 1 | Ea. | Inspect, clean and function test the Tyco MX T2000 Fire Detection System Detector Heads
|  | 3.1.2 | Inspect Clean and Test | 25 | Ea. | Smoke Detectors
|  | 3.1.3 | Inspect, Clean and Test | 1 | Ea. | Flame Detector
|  | 3.1.4 | Inspect, Clean and Test | 1 | Ea. | Heat Detector
| Note |  |  |  |  | Function Test to be carried out on he following:
| 3.2 | 3.2.1 | Test | 12 | Ea. | Call Points
|  | 3.2.2 | Test | 9 | Ea. | Audible Alarm Units
|  | 3.2.3 | Test | 2 | Ea. | Alarm Indicator beacons.
| Note |  |  |  |  | Inspect the control panel Power Supply Unit (PSU), batteries and connections: noting expiry dates. If batteries are within three months of their expiry date, replacement to be confirmed in consultation with the Border Force Overseeing Officer (BFOO).
| 3.3 | 3.3.1 | Test | 1 | Ea. | Fully function test the system including secondary power mode.
|  | 3.3.2 | Record and Submit | 1 | Ea. | Update test tally and submit formal tabulation of reading results.
| Note |  |  |  |  | Service, Survey and Certify the Engine Room, Fixed CO2 Extinguishing System as follows:
| 3.4 | 3.4.1 | Disconnect | 1 | Ea. | Disconnect the Main CO2 cylinders from the system and insert blanks.
|  | 3.4.2 | Inspect | 1 | Ea. | Visually inspection the whole CO2 system.
|  | 3.4.3 | Blow through | 1 | Ea. | Blow through discharge pipe work system with clean air at a minimum pressure of at least 20 bar.
|  | 3.4.4 | Inspect and test | 0 | Ea. | Undertake the 10-year hydraulic test on the three main 45kg CO2 cylinders.
|  | 3.4.5 | Check | 4 | Ea. | Check the contents and levels of the 3 main 45kg CO2 cylinders and the operating cylinders.
|  | 3.4.6 | Check | 5 | Ea. | Check all flexible hoses for ageing.
|  | 3.4.7 | Check | 3 | Ea. | Check pilot bottle pressures are greater than 120 Bar and within 10% of one another.
|  | 3.4.8 | Inspect and test | 0 | Ea. | Undertake the 10-year hydraulic test on the pilot bottle
|  | 3.4.9 | Check | 1 | Ea. | Function check of the pull handle to activate the cylinder valves, close valves, and check for leakage.
|  | 3.4.10 | Fill | 1 | Ea. | Fill CO2 manifold with (+/- 25 bar) from a CO2 test cylinder (Main valves closed, or sections sealed).
|  | 3.4.11 | Test | 1 | Ea. | Close and disconnect the CO2 test cylinder, check thread connections for leakage.
|  | 3.4.12 | Check | 1 | Ea. | Check operation of pressure gauge and blow through the CO2 pipe work with the CO2 gas in the manifold.
|  | 3.4.13 | Reconnect | 1 | Ea. | On completion, re-connect / re-commission the system.
|  | 3.4.14 | Recommission | 1 | Ea. | Present the re-commissioned system to the BFOO for acceptance.
4 | Fire Extinguishers. This item not required on this contract.
| Note |  |  |  |  | Carry out annual inspection as per manufacturer’s instructions for each item listed and Inspect all fire extinguishers as listed. This item not required on this contract.
| 4.1 |  | Inspect | 8 | Ea. | 5 kg CO2
| 4.2 |  | Inspect | 6 | Ea. | 6 kg Dry Powder
| 4.3 |  | Inspect | 2 | Ea. | 2 kg Dry Powder
| 4.4 |  | Inspect | 4 | Ea. | 9 litre Foam
| 4.5 |  | Inspect | 2 | Ea. | Fire Blanket
| 4.6 |  | Certify | 1 | Ea. | Issue certificate for all items.
5 | Fire Hoses and Nozzles. This item not required on this contract.
| Note |  |  |  |  | The following fire hoses and nozzles are to be examined. On completion of examination they should be tested to 5.25 bar. A certificate of examination and testing shall be issued. This item not required on this contract.
| 5.1 |  | Examine, Test and Certify | 1 | Ea. | 20 meter 1 ½ diam. fire hose and 1 nozzle (Bridge Deck Aft)
| 5.2 |  | Examine, Test and Certify | 1 | Ea. | 10 meter 1 ½ diam. fire hose and 1 nozzle (Boat Deck)
| 5.3 |  | Examine, Test and Certify | 2 | Ea. | 10 meter 1 ½ diam. fire hoses and 1 nozzle (Forward Main Deck)
| 5.4 |  | Examine, Test and Certify | 1 | Ea. | 15 meter 1 ½ diam. fire hose and 1 nozzle (Forward Machinery Space)
| 5.5 |  | Examine, Test and Certify | 1 | Ea. | 20 meter 1 ½ diam. fire hose (Forward Machinery Space)
| 5.6 |  | Examine, Test and Certify | 2 | Ea. | 10 meter 1 ½ diam. fire hoses and 1 nozzle (Engine Room)
| 5.7 |  | Examine, Test and Certify | 2 | Ea. | Attack 100 Nozzle
6 | Breathing Apparatus Equipment. This item not required on this contract.
| Note |  |  |  |  | These maintenance tasks are to be carried out by an approved Draeger service agent. This item not required on this contract.
| 6.1 |  | Maintain, Survey & Test | As | Req. | Carryout required maintenance, survey and testing of Breathing Apparatus Equip, as indicated:
|  | 6.1.1 | Maintain, Survey & Test | 3 | Ea. | Drager PS Lite (Annual survey and maintenance)
|  | 6.1.2 | Maintain, Survey & Test | 2 | Ea. | Draeger CF10 EEBD (Annual survey and maintenance)
|  | 6.1.3 | Maintain, Survey & Test | 9 | Ea. | 9 litre carbon fiber BA cylinders (Annual survey and maintenance)
|  | 6.1.4 | Test | 2 | Ea. | EEBD air cylinders (Annual survey and maintenance)
|  | 6.1.5 | Survey | 3 | Ea. | Sets Fireman’s Equipment (jackets, trousers, flash hoods, helmets, lifeline)
|  | 6.1.6 | Certify | As | Req. | Supply individual certificates for each item’s annual survey and maintenance.
7 | Life Jackets. This item not required on this contract.
| Note |  |  |  |  | These tasks are to be carried out by an MCA/UK Flag State approved Crewsaver service agent. This item not required on this contract.
| 7.1 |  | Inspect and Test | 1 | Ea. | Inspect, service and test inflatable lifejackets:
| 7.2 |  | Inspect and Test | 10 | Ea. | Crewsaver Sea Crusader SOLAS approved inflatable lifejackets, complete with McMurdo locating beacons, are to be Inspected, serviced and tested.
| 7.3 |  | Inspect and Test | As | Req. | Replace CO2 inflation cylinders as necessary.
| 7.4 |  | Inspect and Test | 10 | Ea. | Issue individual certificates of inspection and test.
| 7.5 |  | Report | 1 | Ea. | Report all defects found to the BFOO.
8 | Immersion Suits. This item not required on this contract.
| Note |  |  |  |  | These tasks are to be carried out by an MCA/ UK Flag State approved Crewsaver service agent. This item not required on this contract.
| 8.1 |  | Inspect and Test | 1 | Ea. | Inspect, service and test inflatable immersion suits:
| 8.2 |  | Inspect and Test | 20 | Ea. | Crewsaver Immersion Suits are to be inspected, serviced, and tested.
| 8.3 |  | Inspect and Test | 20 | Ea. | Issue individual certificates of inspection and test.
| 8.4 |  | Report | 1 | Ea. | Report all defects to the BFOO.
9 | EPIRB. This item not required on this contract.
| Note |  |  |  |  | Inspect, service and test Jotron 40 S MK11 EPIRB SN: 20199. This item not required on this contract.
| 9.1 |  | Inspect and Test | 1 | Ea. | Survey and Service EPIRB by an approved service agent.
| 9.2 |  | Inspect and Test | 1 | Ea. | Inspect EPIRB Hydrostatic release expiry date and if less than 1 year remains, renew EPIRB hydrostatic release unit and plastic retaining bolt.
| 9.3 |  | Inspect and Test | 1 | Ea. | Check EPIRB, if less than one year remaining, renew batteries as required.
| 9.4 |  | Report | 1 | Ea. | Issue a service report with a list of the test results and maintenance performed.
10 | Safety and Rescue Equipment. This item not required on this contract.
| 10.1 |  | Inspect & Certify | 1 | Ea. | Inspect and Certify the ‘Helicopter Strop’ rescue sling.
| Note |  |  |  |  | Inspect and Certify the following personal Safety Harness equipment - As required
| 10.2 | 10.2.1 | Inspect & Certify | 1 | Ea. | KRATOS full body harnesses
|  | 10.2.2 | Inspect & Certify | As | Ea. | Seago safety lines.
|  | 10.2.3 | Inspect & Certify | 2 | Ea. | Waist Harnesses
|  | 10.2.4 | Inspect & Certify | 2 | Ea. | 2m restraint lanyards
|  | 10.2.5 | Inspect & Certify | 2 | Ea. | KRATOS two-point body harness
|  | 10.2.6 | Inspect & Certify | 4 | Ea. | Saviour Technical stretcher
| Note |  |  |  |  | These tasks are to be carried out by GlideLoc and SALA approved UK flag service agent, (preferred company Safety At Height. 1 Pennine View, Shepley Lane, Marple, Stockport SK6 7JW) whose details must be notified to the Buyer with the submission of the formal quotation.
| 10.3 | 10.3.1 | Inspect & Certify | 1 | No. | All fixed components of the GlideLoc Mast Installation
|  | 10.3.2 | Inspect & Certify | 2 | Ea. | GlideLoc Fall Arrest Traveler
|  | 10.3.3 | Inspect & Certify | 1 | Ea. | Fall Arrest Block
|  | 10.3.4 | Inspect & Certify | 2 | Ea. | Work Positioning Strap
| Note |  |  |  |  | These tasks are to be carried out by GlideLoc and SALA approved UK flag service agent, (preferred company Safety At Height. 1 Pennine View, Shepley Lane, Marple, Stockport SK6 7JW) whose details must be notified to the Buyer with the submission of the formal quotation.
| 10.4 | 10.4.1 | Inspect & Certify | 2 | Ea. | Miller Full Body Harness to EN361 with back strap
|  | 10.4.2 | Inspect & Certify | 2 | Ea. | Petzl climbers Helmet
|  | 10.4.3 | Inspect & Certify | 1 | Ea. | AG 10 rescue kit including 30m rope and webbing straps
|  | 10.4.4 | Inspect & Certify | 2 | Ea. | Inertia Lanyard
11 | Deck Equipment. This item not required on this contract.
| Note |  |  |  |  | All deck equipment to be tested/inspected under Lifting Operations and Lifting Equipment (LOLER) and MGN 332 Amendment 1 regulations.
12 | Emergency Anchor Recovery Equipment. This item not required on this contract.
| Note |  |  |  |  | The service is to be carried out by an approved test house whose details will be notified to the BFOO. This item not required on this contract.
| 12.1 |  | Inspect, Certify and Test | As | Req. | The following anchor recovery equipment is to be inspected, certified and where appropriate tested:
|  | 12.1.1 | Inspect, Certify and Test | 1 | Ea. | Tractel Turffer tackle block and wire 3200kgs SWL.
|  | 12.1.2 | Inspect, Certify and Test | 1 | Ea. | GS Double fall manual chain block x 6metres HOL 3000kg SWL.
|  | 12.1.3 | Inspect, Certify and Test | 1 | Ea. | Duplex polyester web belt sling terminating in a captive eyed latch hook one end only EWL 840 mm 3000 kgs SWL.
|  | 12.1.4 | Inspect, Certify and Test | 1 | Ea. | Ace grade 8 alloy steel single leg chain, complete with 16/8 Bergok one end and 16/8 shortening clutches the other, EWL 400mm 3,500kgs SWL @ 90 degree.
|  | 12.1.5 | Inspect, Certify and Test | 1 | Ea. | 16 mm diam. single leg wire rope sling terminating in soft eyes EWL 850mm 3000 kgs SWL.
|  | 12.1.6 | Inspect, Certify and Test | 1 | Ea. | 1” Bow shackle 3750 kgs SWL.
|  | 12.1.7 | Inspect, Certify and Test | 8 | Ea. | Screw pin bow shackles.
13 | Emergency Towing Equipment. This item not required on this contract.
| Note |  |  |  |  | The following emergency towing equipment is to be examined, certified and where appropriate tested: This item not required on this contract.
| 13.1 |  | Inspect & Certify | 1 | Ea. | 8 strand multi-plat Towing Line and shackles.
| 13.2 |  | Inspect & Certify | 4 | Ea. | 5.5 tonne D shackles.
| 13.3 |  | Inspect & Certify | 3 | Ea. | 12 tonne bow shackles.
| 13.4 |  | Report | As | Req. | Report all defects found, with work recommendations, to the BFOO.
14 | RHIB Recovery and Securing Equipment. This item not required on this contract.
| Note |  |  |  |  | Inspect and certify the RHIB recovery and securing equipment. This item not required on this contract.
| 14.1 | 14.1.1 | Inspect & Certify | 1 | Ea. | RHIB screw pin “D” shackle
|  | 14.1.2 | Inspect & Certify | 1 | Ea. | RHIB wire rope sling
|  | 14.1.3 | Inspect & Certify | 1 | Ea. | RHIB turnbuckle
|  | 14.1.4 | Inspect & Certify | 1 | Ea. | RHIB quick release pin
|  | 14.1.5 | Inspect & Certify | 1 | Ea. | RHIB 10mm connector
| 14.2 | 14.2.1 | Inspect & Check | 16 | Ea. | Check Rhib recovery capstan spacer bolt torques (M14 stainless a4 @ 118 Newtonmeters) and report torque figure prior to load testing the RHIB recovery capstan.
|  | 14.2.2 | Inspect, Test and Certify | 1 | Ea. | Carry out a Dynamic Load Test of the RHIB Recovery Capstan using a perpendicular load of 1.6 tonnes. On completion of successful test, update test tally and supply test certificate.
|  | 14.2.4 | Inspect, Test and Certify | 1 | Ea. | Survey and certify the RIB recovery equipment 12mm stainless steel rope, safety hook and swivel to a SWL of 1.6 tonnes. On completion of successful survey, update test tally and supply test certificate.
15 | Anchor Capstan. This item not required on this contract.
| 15.1 |  | Inspect and maintain | 1 | Ea | On the anchor clutch assembly, pull the drum, maintain the assembly (removing hardned, overpacked grease etc and regreasing correctly)
| 15.2 |  | Inspect, Measure & Record | 1 | Ea. | Check and record the anchor windlass motor brake air gap
| 15.3 |  | Inspect, Test and Certify | 1 | Ea. | Carry out a Dynamic Load Test of the anchor windlass using a horizontal load of 1.6 tonnes. On completion of successful test, update test tally and supply test certificate.
16 | Mooring Capstan. This item not required on this contract.
| 16.1 |  | Inspect, Test and Certify | 2 | Ea. | Carry out a Dynamic Load Test of the Port and Starboard After Mooring Capstans to 1.15 tonnes. On completion of successful test, update test tally and supply test certificate.
17 | Man Overboard Boat (MOB) System. This item not required on this contract.
| Note |  |  |  |  | The following items are to be carried out by an approved service agents. This item not required on this contract.
| 17.1 |  | Inspect and Maintain | 1 | Ea. | Carry out Annual Inspection and Maintenance of SEC MS2-7-40 MOB Davit.
| 17.2 |  | Inspect, Maintain and Certify | 1 | Ea. | Carry out Annual Inspection and Maintenance of Schat-Harding RRH15 MOB (2078) quick release hook.
18 | Compass Equipment
| Note |  |  |  |  | Adjustment of Magnetic Compasses, Lilley and Gillie MK4
| 18.1 |  | Inspect | 1 | Ea. | The binnacle mounted Lilley & Gillie MK4 magnetic compasses on the wheelhouse top.
| 18.2 |  | Inspect | 1 | Ea. | The spare Lilley & Gillie MK4 magnetic compass held in the messroom.
| 18.3 |  | Carryout | 0 | Ea. | The compass swing of the binnacle mounted Lilley & Gillie MK4 magnetic compasses on the wheelhouse top
| 18.3 |  | On completion | 0 |  | After the compass swing issue a deviation card for the compass to the onboard crew and pass copies to the BFOO.
20 | Miscellaneous. This item not required on this contract.
| 20.1 |  | Test | 2 | Ea. | Radiation leak test Microwave Ovens located in galley and mess deck.
| 20.2 |  | Service | 2 | Ea. | The onboard Oxygen therapy kits, including Oxygen cylinders, is to have its annual service carried out by an approved service agent.
| 20.3 |  | Inspect, Survey and certify | 1 | Ea. | The gangway brow is to be inspected for weld/construction defects. Survey certificates are to be supplied on successful completion.
|  | 20.3.1 | Test | 1 | As Req. | If repair work is undertaken, undertake a load deflection test of 450 kgs
| 20.4 |  | Inspect and Certify | 4 | Ea. | Visual inspection to LOLER of the Steering Chain Blocks located in steering flat.
| 20.5 |  | Inspect and Certify | 1 | Ea. | Visual inspection to LOLER of the Boarding Ladder MBL5011C.
| 20.6 |  | Inspect and Certify | 1 | Ea. | Visual inspection to LOLER of the double section extension Ladder.
Annex B Total Cost

## Annex C
Annex C: Vessel Maintenance Tasks
Annex C |  |  | Description | Qty | DoQ | Description of Service | Acknowledgement / Unit Price | Total Firm Cost
| Note |  |  |  |  | Where it is stipulated in this Requirement that approved engineers/agents are to be used, the Supplier shall submit details, to include business address and contact details, to the Authority, of these engineers/agents who will carry out the work alongside the formal quotation.
1.0 | Deck. This item not required on this contract.
| Note |  |  |  |  | Inspect, Test and replace as required Raised Coaming water-tight hatches and replace hatch seals.
| 1.1 |  | Replace | 1 | Ea. | Hatch Seals on Weather deck Fwd./Lower Deck Fwd. Accommodation. Size of seal is 852mm x 852mm. Total seal length 3,268mm. The seal is 35mm wide and has a depth of 30mm. (The total seal length has been adjusted to account for overlap)
| 1.2 |  | Replace | 1 | Ea. | Hatch Seals on Weather deck / Waist Main Engine Room Access. Size of seal is 653mm x 662mm. Total seal length 2,472mm. The seal is 35mm wide and has a depth of 30mm. (The total seal length has been adjusted to account for overlap)
| 1.3 |  | Replace | 1 | Ea. | Hatch Seals on Weather deck / Port Aft Peak Steering Compartment Access. Size of seal is 660mm x 660mm. Total seal length 2,500mm. The seal is 35mm wide and has a depth of 30mm. (The total seal length has been adjusted to account for overlap)
| 1.4 |  | Replace | 1 | Ea. | Hatch Seals on Weather deck / Stbd Aft Steering Compartment Access. Size of seal is 660mm x 660mm. Total seal length 2,500mm. The seal is 35mm wide and has a depth of 30mm. (The total seal length has been adjusted to account for overlap)
| 1.5 |  | Test | 4 | Ea. | On completion of all work, function test the hatches to prove security and water-tight integrity.
2.0 | Engine Room Dampers. This item not required on this contract.
| Note |  |  |  |  | Inspect, Test and Overhaul dampers and Replace seals.
| 2.1 |  | Replace | 2 | Ea. | Engine room damper seal, port side aft, 2 off. Size of seal to be provided.
| 2.2 |  | Replace | 1 | Ea. | Engine room damper seal, port side aft off side entrance door, 1 off. Size of seal to be provided.
| 2.3 |  | Replace | 2 | Ea. | Engine room damper seal, starboard side aft, 2 off. Size of seal to be provided.
| 2.4 |  | Replace | 1 | Ea. | Engine room damper seal, starboard side aft of sid entrance door, 1 off. Size of seal to be provided.
| 2.5 |  | Test | 6 | Ea. | On completion of all work, function test the damper to prove security and limit switches operate.
3 | Maine Engines: Caterpillar 3516B. This item not required on this contract.
| Note |  |  |  |  | Main Engine lubrication oil capacity is 405 litres (CRB Multi 15/40), Oil and Filters will be supplied by the Authority. In addition to the work detailed herein, both main engines will be subject to annual maintenance tasks contracted separately by the Authority. Work under this requirement must be chronologically arranged to coincide with both the Supplier and Authority scope of work.
| 3.1 |  | Change | As | Req. | Change oil and filters on both Port and Stbd Caterpillar 3516B main engines as per lines 3.2 - 3.5.
| 3.2 |  | Dispose | 900 | Litres | Existing main engine lubrication oil charge is to be pumped out and disposed of in accordance with extant regulations.
| 3.3 |  | Renew | 6 | Ea. | Renew main engine lubrication oil filter (CAT Part 1R-7026) 3 off and not the auxliary filter and dispose of old filters in accordance with extant regulations.
| 3.4 |  | Replenish | 900 | Litres | Replenish the lubrication oil charge.
| 3.5 |  | Change | 10 | Ea. | Renew main engine fuel filter (only change the 5x main filters) [CAT Part 1R-7056] and dispose of in accordance with extant regulations.
4 | Main Engine Port and Starboard Reintjes WLS930 Reduction Gearboxes. This item not required on this contract.
| Note |  |  |  |  | This service is to be completed by an approved Reintjes service agent.
Main Gearbox lubrication oil capacity is 90 litres (Castrol MHP 153), Lube Oil to be supplied by the Authority.
| 4.1 |  | Inspect | 1 | Ea. | Annual external and internal inspection.
|  | 4.1.1 | Inspect | 1 | Ea. | Open the Inspection plates and carryout an internal inspection of the pinions and gearwheels in accordance with Reintjes WLS and WVS maintenance service routines.
|  | 4.1.2 | Test & Adjust | As | Req. | Test all temperature and pressure shut down devices.
|  | 4.1.3 | Test & Adjust | As | Req. | Test all sensors, inter-switches, and alarm systems for correct operation.
|  | 4.1.4 | Dispose | 180 | Litres | Existing gearbox lubricating oil charge is to be pumped out and disposed of in accordance with extant regulations.
|  | 4.1.5 | Renew | 2 | Ea. | Renew the in-use lubricating oil filters (only change the in-use oil filter). To be supplied by approved Reintjes service agent.
|  | 4.1.6 | Change | 2 | Ea. | Change the sinter filters. To be supplied by approved Reintjes service agent.
|  | 4.1.7 | Replenish | 180 | Litres | Replenish the lubricating oil charge.
|  | 4.1.8 | Report | 1 | Ea. | On completion, a Reintjes Service Report is to be provided to the Border Force Overseeing Officer (BFOO) in both hard and electronic copy formats.
5 | Steering Gear Installation. This item not required on this contract.
| Note |  |  |  |  | There are two electronically linked Steering Gear installations each installation has two hydraulic pumps and consequently two starters. Filters to be supplied by the supplier.
| 5.1 |  | Inspect | 2 | Ea. | Carry out visual and physical inspection of the Port and Starboard steering gear installations.
|  | 5.1.1 | Check | As | Req. | Hydraulic leaks.
|  | 5.1.2 | Check | 2 | Ea. | Cylinders and rams for leakage.
|  | 5.1.3 | Check | As | Req. | Tightness / security of linkages and connection.
|  | 5.1.4 | Inspect | As | Req. | Inspect tank anti-vibration mounts.
| 5.2 |  | Replace | 4 | Ea. | Port and Starboard steering system hydraulic filters. Part number Fairey Arlon TXX2-10
| 5.3 |  | Report | 1 | Ea. | Inspection Report is to be provided to the BFOO in both hard and electronic copy formats.
6 | Veth 90 Bow Thruster & Hydraulic System. This item not required on this contract.
| Note |  |  |  |  | Filters are supplied by the authority
| 6.1 |  | Survey and Report | 1 | Ea. | Survey the condition of the Bow Thruster flexible coupling element and the mounting bolts and report findings to BFOO.
|  | 6.1.1 |  |  |  | Drain-down the existing lube oil and dispose of in an environmental facility.
|  | 6.1.2 |  |  |  | Replace lube oil, ensuring all air pockets are vented.
|  | 6.1.3 |  |  |  | Replace lube oil filter.
|  | 6.1.4 |  |  |  | Inspect the drive-coupling between the drive motor and propeller drive shaft. (See ection 6 of the Veth 90 manual)
|  | 6.1.5 |  |  |  | Clean the electronics control box.
|  | 6.1.6 |  |  |  | Check the grounding of the electrical components.
|  | 6.1.7 |  |  |  | Service Report in both hard and electronic copy formats is to be provided to the BFOO along with a working functional demonstration.
| 6.2 |  |  |  |  | The following Bow Thruster hydraulic power pack hydraulic oil filters are to be changed.
|  | 6.2.1 | Replace | 1 | Ea. | Circulation Filter Element No RMF offline OL 1-2 series E26 9317578.
|  | 6.2.2 | Replace | 1 | Ea. | Tank Top Return Filter H33OG20B.
|  | 6.2.3 | Replace | 1 | Ea. | Radial micro filtration conditioning filter RMF KL120/K121R
|  | 6.2.4 | Replace | 3 | Ea. | Inline Filter H160R20N.
| 6.3 | Hydraulic power pack oil heat exchanger.
|  | 6.3.1 | Remove, Disassemble, Maintain and Inspect | 1 | Ea. | Remove, clean, and inspect hydraulic power pack oil heat exchanger.
|  | 6.3.2 | Reassemble and Test | 1 | Ea. | Reassemble using new seals, original end plates (end plates to be replaced if worn with agremment of the BFOO) and conduct pressure test at 5bar for 30 minutes.
|  | 6.3.3 | Refit | 1 | Ea. | Refit heat exchanger.
7 | Emergency Fire Pump. This item not required on this contract.
| Note |  |  |  |  | Service spares are supplied by the Supplier
| 7.1 |  | Service and Report | 1 | Ea. | 50hr service on Lombardini Diesel Firefighting Pump Engine as per manufacturer’s instructions for 250 hours.
| 7.2 |  | Service and Report | 1 | Ea. | Check and service the emergency fire pump discharge sndr valve ensuring free movement.
| 7.3 |  | Report & Demonstration | 1 | Ea. | Service Report in both hard and electronic copy formats is to be provided to the BFOO along with a working functional demonstration.
8 | Portable Salvage Pump. This item not required on this contract.
| Note |  |  |  |  | Service spares are supplied by the Supplier
| 8.1 |  | Service | 1 | Ea. | Carry out 50 Hour service on the Yanmar L48 4.8HP diesel engine as per manufacturer’s instructions for 250 hours.
| 8.2 |  | Report & Demonstration | 1 | Ea. | Service Report in both hard and electronic copy formats is to be provided to the BFOO along with a working functional demonstration.
9 | Domestic Water System. This item not required on this contract.
| Note |  |  |  |  | The Authority will supply any necessary replacements.
| 9.1 |  | Hydrophore (BT) Fresh Water Hydrophore Unit.
|  | 9.1.1 | Disconnect | 1 | Ea. | Disconnect and drain the hydrophore.
|  | 9.1.2 | Inspect | 1 | Ea. | Inspect the hydrophore cylinder and rubber bladder.
|  | 9.1.3 | Maintain | 0 | Ea. | Remove the bladder, clean it with freshwater and sterilize it.
|  | 9.1.4 | Inspect | 1 | Ea. | Inspect the cylinder for excess corrosion, leaks, or damage.
|  | 9.1.5 | Inspect | 0 | Ea. | Inspect the bladder for damage, leaks, or signs of perishing: renew the bladder if necessary.
|  | 9.1.6 | Re-connect | 1 | Ea. | Re-pressurise the air space between the hydrophone cylinder and bladder to 0.2 bar.
|  | 9.1.7 | Test and Report | 1 | Ea. | On completion of all work re-commission the system and function test to the satisfaction of the BFOO and report details.
| 9.2 |  |  |  |  | Domestic Hot FW System:
|  | 9.2.1 | Inspect and Test | 2 | Ea. | Inspect and Pressure Test Daalder domestic fresh water calorifier Heaters (No.1 and No.2) (carry out pressure test to 5 bar for 15 minutes).
|  | 9.2.2 | Inspect | 2 | Ea. | Inspect for leaks and damage.
|  | 9.2.3 | Test | 2 | Ea. | Check pressure setting of PRVs.
|  | 9.2.4 | Record | 2 | Ea. | Supply local tallies to record the pressure and test date and issue ISO 9001 standard certificate of test for Calorifiers and PRVs.
|  | 9.2.5 | Test and Record | 2 | Ea. | Carry out and record insulation test on the 6 kW Heating elements in both calorifiers.
|  | 9.2.6 | Report | 1 | Ea. | Inspection Report is to be provided to the BFOO in both hard and electronic copy formats.
10 | Air Conditioning and Air Handling System. This item not required on this contract.
| Note |  |  |  |  | Service spares and drier filling are supplied by the Supplier
| 10.1 |  |  |  |  | Compressor
|  | 10.1.1 | Replace | 1 | Ea. | Replace the AC Compressor drier filling.
|  | 10.1.2 | Inspect | 1 | Set | Inspect refrigeration system pipework and system.
| 10.2 |  |  |  |  | Air Handling Unit in ventilation plant room
|  | 10.2.1 | Inspect | 2 | Ea. | Inspect the condition of the V- belts driving the ventilation fan.
|  | 10.2.2 | Measure and Adjust | 1 | Req. | Measure the deflection/tension of the v-belts and adjust as required.
|  | 10.2.3 | Inspect & Clean | 2 | Ea. | Remove, clean the conndensate trap [aluminium water trap with table tennis ball within] and refit
| 10.3 |  |  |  |  | Ventilation plant room and Air Handling trunking in Vessel
|  | 10.3.1 | Clean | 1 | Room | Vaccum airborne deposits from plant, bulkheads, deckheads, recirculation flaps and dampers, cable runs, pipework and bulkheads
|  | 10.3.2 | Inspect and clean | 5 | Ea. | Remove washroom and heads exhaust vents, vacuum internals and refit
|  | 10.3.3 | Inspect and clean | 1 | Ea. | Remove punker louvers and vacuum trunking
| 10.4 |  | Test and Report | 1 | Ea. | Carry out function test and provide Inspection Report to the BFOO.
11 | Electrical Distribution. This item not required on this contract.
| Note |  |  |  |  | Tasks to include but not limited to: Insulation testing Continuity testing of earth bonding Function test of current overload devices Function test of anti-condensation heaters Motor bearing condition checks
| 11.1 |  | Check and Record | 1 | Ea. | Check insulation readings on listed circuits.
| 11.2 |  | Check and Record | 1 | Ea. | Check and record insulation readings on all circuits from the following locations:
|  | 11.2.1 | Check and Record | 1 | Ea. | Main switchboard (Engine Room) 415/240V 50Hz.
|  | 11.2.2 | Check and Record | 1 | Ea. | P1 power/lighting distribution board (Engine Room) 415/240V 50Hz.
|  | 11.2.3 | Check and Record | 1 | Ea. | P2 power/lighting distribution board (Forward Machinery Space) 415/240V 50Hz.
|  | 11.2.4 | Check and Record | 1 | Ea. | L3 lighting distribution board (Main Deck Technical Room) 415/240V 50 Hz.
|  | 11.2.5 | Check and Record | 1 | Ea. | L4 lighting distribution board (Wheelhouse) 415/240V 50 Hz.
|  | 11.2.6 | Check and Record | 1 | Ea. | Central distribution board (Wheelhouse) 415/240V 50Hz.
|  | 11.2.7 | Check and Record | 1 | Ea. | AC plant distribution board (Forward Machinery Space) 415/240V 50 Hz.
|  | 11.2.8 | Check and Report | 2 | Ea. | Port and Starboard generator winnings resistance and insulation resistance.
|  |  | Report | 1 | Ea. | Submit formal tabulation of reading results.
| 11.3 |  | Inspect and Test | 1 | Ea. | Shore Power Supply:
|  | 11.3.1 | Inspect and Test | 1 | Ea. | Inspect and Test Shore Power Connection Box and Cable.
|  | 11.3.2 | Report | 1 | Ea. | Submit formal tabulation of reading results.
| 11.4 |  | Check | 1 | Ea. | Earth Bonding:
|  | 11.4.1 | Check | 1 | Ea. | Check Earth Bonding of Shafts, Rudders and Stabilisers.
|  | 11.4.2 | Report | 1 | Ea. | Submit formal tabulation of reading results.
| 11.5 |  | Maintain and Test | 1 | Ea. | Clean, Inspect and Test Starters and Motors for the following:
|  | 11.5.1 | Maintain and Test | 1 | Ea. | Anchor Windlass.
|  | 11.5.2 | Maintain and Test | 2 | Ea. | Port and starboard capstans.
|  | 11.5.3 | Maintain and Test | 1 | Ea. | MOB Boat Davit.
|  | 11.5.4 | Maintain and Test | 4 | Ea. | Steering gear system pumps
|  | 11.5.5 | Maintain and Test | 2 | Ea. | Bilge/general service pumps
|  | 11.5.6 | Maintain and Test | 2 | Ea. | FW hydrophore pumps
|  | 11.5.7 | Maintain and Test | 1 | Ea. | AC pump.
|  | 11.5.8 | Maintain and Test | 1 | Ea. | AC compressor.
| 11.6 |  | Inspect and maintain | 1 | Ea. | Switchboard clean, service and inspection
|  | 11.6.1 | Calibrate | 8 | Ea. | Calibrate all the switchboard gauges
| 11.7 |  | Test | 1 | Ea. | On completion of all work, restore power supply and function test to the satisfaction of the BFOO.
| 11.8 |  | Report | 1 | Ea. | Inspection Report is to be provided to the BFOO in both hard and electronic copy formats.
12 | 240v Portable Appliances. This item not required on this contract.
| 12.1 |  | Test | 180 | Ea. | Carryout and Document PAT on, approximately, 180 items of 240v Appliances.
| 12.2 |  | Test | As | Req. | On completion of satisfactory test, label each appliance with a suitable identification label indicating: - Pass - Date of Test and Initials of Tester.
| 12.3 |  | Report | 1 | Ea. | Submit formal tabulation of reading results.
13 | Super Chlorination of the Domestic Fresh Water System
| Note |  |  |  |  | Carry out Super Chlorination as detailed in, section 13. (Preferred Company OEMAchem, Trinity Court, Brunel Rd, Totton, Southampton SO40 3WX ). Failure to achieve WHO test standards for both potable water and legionella will require re super-chlorination and re-testing at the Suppliers cost, until satisfactory test results which meet WHO standards for potable water are obtained. Task to be carried out earliest opportunity to allow Test results to be completed.
| 13.1 |  | Maintain | 1 | Ea. | Press up the holding tank with treated super chlorination mixture.
| 13.2 |  | Maintain | 1 | Ea. | Run water through ALL taps, hoses, and shower heads: ensuring the super-chlorination concentrate levels are monitored and maintained. Leaving the superchlorinated solution in the system for a minimum of 12 hours.
| 13.3 |  | Maintain | 1 | Ea. | Drain down the system and the holding tank. Disposing of the super chlorinated water in accordance with extant regulations
| 13.4 |  | Maintain | 1 | Ea. | Re-fill up Fresh Water tank, with mains water
| 13.5 |  | Maintain | 1 | Ea. | Run water through ALL taps, hoses, and shower heads
| 13.6 |  | Maintain | 1 | Ea. | Drain down the system and the holding tank. Disposing of the water in accordance with extant regulations
| 13.7 |  | Maintain | 1 | Ea. | Re-fill up Fresh Water tank with mains water
| 13.8 |  | Maintain | 1 | Ea. | Run water through ALL taps, hoses, and shower heads
| 13.9 |  | Maintain | 1 | Ea. | Take water samples of the onboard system and shoreside.
| 13.1 |  | Analyse | 1 | Ea. | Submit samples for analysis of potability and legionary’s disease.
| 13.11 |  | Certify | 1 | Ea. | Provide a certificate of potability and no legionary present upon completion of satisfactory tests.
| 13.12 |  | Supply | 1 | Ea. | Supplier to supply alternative water supply for use on board during process for sanitary purposes.
14 | Main and Emergency Batteries. This item not required on this contract.
| 14.1 |  | Inspect, Maintain and Test | 1 | Ea. | The following four 12-volt battery sets are to have work undertaken as per 14.2 – 14.6.
|  | 14.1.1 | Inspect, Maintain and Test | 2 | Ea. | Port and Stbd in Engine Room.
|  | 14.1.2 | Inspect, Maintain and Test | 1 | Ea. | Port side Weather deck (Emergency Set).
|  | 14.1.3 | Inspect, Maintain and Test | 1 | Ea. | Stbd Eng. Room general service bank.
| 14.2 |  | Inspect, Maintain | 1 | Ea. | Clean the Battery Sets and inspect for damage, corrosion and electrolyte leaks.
| 14.3 |  | Test | 1 | Ea. | Carry out capacity discharge test on each 12-volt battery.
| 14.4 |  | Maintain | 1 | Ea. | Clean connectors / terminals and coat with no-oxide grease (petroleum jelly). Remake any faulty connections.
| 14.5 |  | Check | 1 | Ea. | On completion of all approved work, ensure the Battery is fully charged and restored to the normal operational state.
| 14.6 |  | Report | 1 | Ea. | Pass inspect and test results to the BFOO.
15 | Anchor Cable and Locker
| 15.1 |  | Maintain, Inspect, Report | 1 | Ea. | Anchor cable locker to be opened and vented and at least two gas free certificates issued for work inside.
| 15.2 |  | Maintain | 1 | Ea. | The anchor cable is to be removed from the Cutter and thoroughly cleaned.
| 15.3 |  |  | 1 | Ea. | The Hakkerite lining is to be removed and internal tank coating and structure surveyed.
| 15.4 |  |  | 1 | Ea. | The Contractor shall provide the BFOO a written condition report of the Chain Locker
| 15.5 |  |  |  |  | The Contractor shall prepare and recoat the chain locker in accordance with the International Paint manufacturer’s specifications.
| 15.6 |  |  |  |  | The contractor on complition of the recoating the chain locker is to re-install the Hakkerite linning.
| 15.7 |  | Inspect, Report | 1 | Ea. | Survey and measure the cable stud links against a Lloyds cable specification and report details to the BFOO.
| 15.8 |  | Inspect, Report | 1 | Ea. | Survey and measure the main anchor with links against a Lloyds specification and report details to the BFOO.
| 15.9 |  | Inspect, Report | 1 | Ea. | Survey and measure the spare anchor with links against a Lloyds specification and report details to the BFOO.
| 15.1 |  | Maintain, Clean, Paint | 1 | Ea. | Reapply cable chain length markings, by paint and cable tie methods every ten meters as follows: The number of links painted for equivalent to the length in meters. The middle link to be wire moused. Links to be painted white except for the two outer end links which are painted red. The last ten-meter marker is to be painted all red. Contractor to supply all required International Paint
| 15.11 |  | Maintain | 1 | Ea. | Re-stow the cable in the chain locker with rope tie and lock onto the anchor.
16 |  | MAST Inspection. This item not required on this contract.
Note
| 15.1 |  | Inspection, adjustment | 1 | Set | Inspect both the mast assembly flange bolts and antenna fixings for tightness and tightening if loose.
| 16.2 |  | Report | 1 | Ea. | Pass inspect and test results to the BFOO.
17 |  | Bilge Valves. This item not required on this contract.
| Note |  |  |  |  | Above waterline overboard discharge ship side valves
| 17.1 |  | Inspection, clean and maintain | 1 | Set | The following above waterline ships bilge overboard discharge valves are to have the following work as per 17.2-17.4
|  | 17.1.1 | Inspection, clean and maintain | 2 | Ea. | Engine Room
|  | 17.1.2 | Inspection, clean and maintain | 2 | Ea. | Bow Thruster Room
| 17.2 |  | Inspection, clean and maintain | 1 | Ea. | Dismantle
| 17.3 |  | Inspection, clean and maintain | 1 | Ea. | Remove stem, clean, check valve and seating
| 17.4 |  | Inspection, clean and maintain | 1 | Ea. | Reassembly and check demonstate the operation
| Note |  |  |  |  | Internal Bilge Valves
| 17.5 |  | Inspection, clean and maintain | 1 | Set | The following internal bilge valves are to have the following work as per 17.6-17.8
|  | 17.5.1 | Inspection, clean and maintain | 1 | Ea. | Bow Thruster Space
|  | 17.5.2 | Inspection, clean and maintain | 1 | Ea. | Bilge Eductor
|  | 17.5.2 | Inspection, clean and maintain | 1 | Ea. | Foward Accomodation
| 17.6 |  | Inspection, clean and maintain | 1 | Ea. | Dismantle
| 17.7 |  | Inspection, clean and maintain | 1 | Ea. | Remove stem, clean, check valve and seating
| 17.8 |  | Inspection, clean and maintain | 1 | Ea. | Reassembly and check demonstate the operation
18 |  | Kamewa CPP Power Pack. This item not required on this contract.
| Note |  |  |  |  | Filters are to be supplied by the supplier
| 18.1 |  |  |  |  | The following CPP power pack hydraulic oil filters are to be changed.
|  | 18.1.1 | Replace | 2 | Ea. | UFI (Brand) E SE21 N CC
19 |  | Naiad Stabiliser. This item not required on this contract.
| Note |  |  |  |  | Filters are to be supplied by the supplier
| 19.1 |  |  |  |  | The following stabiliser hydraulic oil filters are to be changed.
|  | 19.1.1 | Replace | 2 | Ea. | Port and Starboard inline filters E29101430
|  | 19.1.2 | Replace | 1 | Ea. | Power pack return filter E29101660
| 19.2 |  |  |  |  | Hydraulic Pump
|  | 19.2.1 | Inspect & maintain | 1 | Ea. | Remove the hydraulic pump from the motor, clean and grease splines as per manufacturers instrutons and refit.
| 19.3 |  | Report & Demonstration | 1 | Ea. | Service Report in both hard and electronic copy formats is to be provided to the BFOO along with a working functional demonstration.
20 |  | Fuel Tank. This item not required on this contract.
Note
| 20.1 |  | Inspect, Maintain and Test | 2 | Ea. | Remove the port and starboard fuel tank quick closing valves and check for restrictions in the suction lines from tank to common line to purifier utilising pipe camera to aid inspection where necessary. On completion refit the quick closing valves and demonstrate the operation to the BFOO.
21 | Mechanical Fitting Labour
| 21.1 |  | Provide | 60 | Ea. | The Supplier is to provide a quote for hours of mechanical fitting labour to be used as needed by the BFOO.
22 | Electrical Labour
| 22.1 |  | Provide | 60 | Ea. | The Supplier is to provide a quote for hours of qualified electrical labour to be used as needed by the BFOO.
23 | Painting Labour
| 23.1 |  | Provide | 180 | Ea. | The Supplier is to provide a quote for hours of painting labour to be used as needed by the BFOO. Painting and preparation to be completed in accordance with the attached International Paint Specification.
| 23.2 |  | Provide | As | Req. | The supplier is to supply all International Paint as required. Painting and preparation to be completed in accordance with the attached International Paint Specification. Please quote for the following: 80 litres of Interphane 990 light weather work grey 40 litres of Interphane 990 extra dark sea grey 40 litres of Interphane 990 white 120 litres of Intershield 300 bronze
24 | Triclad Joint - Steel Deck to Aluminium Superstructure
| Note |  |  |  |  | Triclad material for remedial work and paint to be supplied by the Contractor.
| 24.1 |  |  |  |  | Triclad joints inserted between the steel deck to aluminium superstructures around the
|  | 24.1.1 |  |  |  | Wheelhouse
|  | 24.1.2 |  |  |  | Port and Starboard Exhaust ventilation housings (This item not required on this contract)
|  | 24.1.3 |  |  |  | Port and Starboard stanchions
| 24.2 |  |  |  |  | Are to be cleaned back to good metal, removing all debris and corrosion from on/around the Triclad joints.
| 24.3 |  |  |  |  | A full visual and mechanical survey of the Triclad joint steel to aluminium interface is to be carried out in way off (iwo) heavily corroded areas and then at 4m intervals are around full area.
| 24.4 |  |  |  |  | The survey results are to be presented to the BFOO is a A4 diagrammatic format.
| 24.5 |  |  |  |  | Upon completion of the Triclad joint survey and any remedial action approved by the BFOO, the Triclad joint is to be preserved in accordance with the International Paint scheme from the primer coats onward. The International Paint representative is to provide further instruction on the paint preservation paint scheme.
25 | Tank Spaces
| Note |  |  |  |  | All paint and new hatch joints are to be supplied by the Contractor.
| 25.1 |  |  |  |  | The Vessel has the following tank spaces.
|  | 25.1.1 |  |  |  | Fresh Water Tank
|  | 25.1.2 |  |  |  | Port Fuel Tank
|  | 25.1.3 |  |  |  | Starboard Fuel Tank
|  | 25.1.4 |  |  |  | Fuel Oil Day Tank
|  | 25.1.5 |  |  |  | Bilge Water and Dirty oil holding tank
|  | 25.1.6 |  |  |  | Black Water Tank
|  | 25.1.7 |  |  |  | Grey Water Tank
|  | 25.1.8 |  |  |  | Lubricating (Lube) Oil holding Tank
| 25.2 |  |  |  |  | The 3 x Fuel tanks and Lube oil holding tank are to be pumped dry by the Contractor, with their contents retained in clean containers ashore and free from condensation.
| 25.3 |  |  |  |  | The Fresh water tank, Blige water / Dirty Lube oil holding tank and the black and grey water holding tanks are to be emptied by the Contractor and the contents disposed of in accordance with all relevant environmental legislation.
| 25.4 |  |  |  |  | The Contractor shall provide and include all costs associated for hire of all suitable shoreside tanks or containers for the safe storage of any medium contents as removed from the onboard tanks.
| 25.5 |  |  |  |  | Prior to the contractor replacing retained fuel and lube oil onboard ahead of commencement of Basin Trials, the Contractor shall undertake testing of the retained medium to confirm zero percent water content.
| 25.6 |  |  |  |  | The Contractor shall open, ventilate and issue gas-free certificates for all tanks listed in 25.1 The Contractor shall issue an additional gas free certificate for each tank on completion of all work to enable safe inspection by the BFOO or other parties.
| 25.7 |  |  |  |  | The Contractor shall degrease and clean each tank with fresh water and wipe dry to allow inspection/survey by both the MCA and International Paint surveyor of the internal structure and paint condition at alternate periods.
| 25.8 |  |  |  |  | The Contractor shall prepare and recoat all listed tanks in accordance with the International Paint manufacturer’s specifications.
| 25.9 |  |  |  |  | The Contractor shall remove all materials and equipment used in the tank cleaning from all tanks following the cleaning process.
| 25.1 |  |  |  |  | Prior to the Contractor sealing the tank space hatch(s), the Contractor is to certify in writing to the BFOO, the removal of all cleaning material and confirm the hatch sealed using new gaskets.
Annex C Total Cost:

## Annex D
Annex D: Modifications and Defect Rectification
Annex D |  | Description | Qty | DoQ | Description of Service | Clarification | Total Firm Cost
1
| Note |  |  |  | Port Wheeelhouse door glass replacement
| 1.1 | Replace | 1 | ea | Remove and replace glass in port wheel house door glass in line with Damen drawings. Ref drawing 549852-135-002, glass template 549852-0001. Contractor ro supply a certificate of comformity for the bullet proof glass.
2
Note
3
Note
4
Note
6
Note
7
Note
8
Note
9
Note
10
Note
11
Note
12
Note
13
Note
14
Note
15
Note
16
Note
17
Note
18
Note
19
Note
Annex D Total Cost:

## Annex E
Annex E: Docking, Inspection, testing and Un-docking of the Vessel.
Annex B |  |  | Description | Qty | DoQ | Description of Service | Clarification | Acknowledgement / Unit Price | Total Firm Cost
1 | Docking and Undocking
| Note |  |  |  |  | The Supplier is to include all costs associated with docking and undocking, shore power, rubbish removal and any tug movements in the submitted quotation and provide the following for the entirety of the contract period. |  |  |  | #REF!
| 1.1 | 1.1.1 | Dock and Undocking | 1 | Ea. | The Cutter is to be Slipped, Dry-docked or Synchro-lifted on an Authority approved facility belonging to or leased by the Supplier for a period of at least 3 weeks. All costs for docking, hire of dock, slipway or lift, towage from and to the alongside berth to the dock, slipway or lift are to be included in the Suppliers tender for the duration of the contract.
|  | 1.1.2 | Clean | 1 | Ea. | The underwater area is to be pressure washed with fresh water to remove all slime, marine growth and loose flaking paint (to prevent re-contamination with salt, this should be done in conjunction with the hull and superstructure washing if required to prepare for the subsequent painting of these areas).
|  | 1.1.3 | Inspect | 1 | Ea. | When clean and dry, the Supplier is to carry out a full inspection of the underwater areas photographing and identifying any paint film damage, indentations or shell plate cracking. On completion a written report is to be issued by the Supplier and duly witnessed by the BFOO.
|  | 1.1.4 | Survey | 1 | Ea. | A full survey of existing antifouling paint condition and adhesion to the rudders, appendages, sea inlet, bow thruster, stablizers etc, are to carried out by an international paint representative arranged and costed by the supplier. A written survey report with actions to be undertaken is to be provided by the supplier. The survey report is to be duly witnessed by the BFOO
|  | 1.1.5 | Prior to refloat | 1 | Ea. | On completion of all underwater work inclusive of the re-application of the anti-fouling coating, the Supplier, International Paint Representative and the BFOO are to conduct a joint inspection and complete documentation in respect of a safe to launch certificate in the form of a Supplier Launching Certificate.
2 | Hull Anodes
| Note |  |  |  |  | Carry out inspection of twenty seven (27) sacrificial hull anodes. The Contractor is to supply any anodes and backing material that need replacing with a like for like model anode complete with new rubber backing sheets where appropriate. |  |  |  | #REF!
| 2.1 |  | Remove and inspect | 27 | Ea. | Remove and inspect all anodes and the securing arrangements. Anodes are to be marked to identify the position from which they were removed.
| 2.2 |  | Inspect and replace | 27 | Ea. | Rubber backing sheets.
| 2.3 |  | Inspect and replace |  | Ea. | Re-weld with new, all studs that have become loose/broken or are heavily corroded.
| 2.4 |  | Replace | 27 | Ea. | After completion of anti-fouling painting, reinstall all anodes with rubber backing sheets.
| 2.5 |  | Test | 27 | Ea. | Carry out continuity test between each anode and the hull. Results are to be tabulated and presented to the BFOO.
| 2.6 |  |  |  |  | Potentiometer check for annual survey
|  | 2.6.1 |  |  |  | Once the Cutter has been launched and the hull immersed for over 36 hours
|  | 2.6.2 |  |  |  | Using a silver/silver chloride reference electrode carry out a potential reading at equal distances around the deck.
|  | 2.6.3 |  |  |  | Record the potential readings on a sketch of the hull, recording all details and test points.
|  | 2.6.4 |  |  |  | NB Potential Readings should be between –0.88 and –0.80
| 2.6 |  | Report | 1 | Ea. | Report all defects to the BFOO.
3 | Port and Starboard Propeller Shafts and Bearings
| Note |  |  |  |  | All oils and consumables to be supplied by the Contractor. The spec of oil used is Castrol MHP 153. |  |  |  | #REF!
| 3.1 |  | Drain | 2 | Ea. | Drain down approx 200L per shaft (approx 400L total) of lubricating oil (MHP153) and dispose of in accordance with current legislation.
| 3.2 |  | Remove | 2 | Ea. | Remove port and starboard stern tube bearing access covers and rope guards.
| 3.3 |  | Measure | 2 | Ea. | Take poker gauge clearance readings between the propeller shaft and the bearing. Results are to be tabulated and presented to the BFOO. Supplier to supply calibrated gauges. Please detail the process for taking the readings and how they will be tabulated and presented. | Please respond in the Technical Response Document
| 3.4 |  | Report | 1 | Ea. | Report any defects to the BFOO.
| 3.5 |  | Reassemble | 2 | Ea. | On completion of works, refit the stern tube bearing access covers using new gaskets and reweld rope guards in place.
| 3.6 |  | Refill | 2 | Ea. | Refill the system with approx 200L per shaft of clean MHP153 lubricating oil.
4 | Propeller Hub and Blades
| Note |  |  |  |  | Inspect, Replace damaged Propellor Blades Clean and test function. |  |  |  | #REF!
| 4.1 |  | Clean | 2 | Ea. | All propeller blades port and starboard require cleaning and polishing in situ to the satisfaction of the BFOO. Please provide a full explanation of how this task will be undertaken. | Please respond in the Technical Response Document
| 4.2 |  | Inspect | 2 | Ea. | Inspect security of all fixings and inspect all propeller blades for any damage.
| 4.3 |  | Test | 1 | Ea. | In conjuction with the BFOO and CPP pumps running, test both propellers for full travel astern and ahead when tasks 4.1-4.2 completed.
| 4.4 |  | Report | 2 | Ea. | Report all defects to the BFOO.
5 | Rudders
| Note |  |  |  |  | Remove, inspect, Clean and take measurements. |  |  |  | #REF!
| 5.1 |  | Remove | 2 | Ea. | Remove port and starboard rudders. Please provide a full explanation of how this task will be undertaken. | Please respond in the Technical Response Document
| 5.2 |  | Inspect | 2 | Ea. | Inspect the blades, rudder stocks, bearings and seals for damage and wear.
| 5.3 |  | Measure and test | 2 | Ea. | Measure rudder upper and lower bearing journal clearances and pressure test both rudder blades to 1.5 psi, BFOO to witness testing and present results.
| 5.4 |  | Reassemble | 1 | Ea. | Reassemble both rudders after cleaning with pressure washer and replace seals and bearings if required. Bearings and seals will be supplied by the Authourity.
| 5.5 |  | Report | 1 | Ea. | Pass records and report all defects found with recommendations to the BFOO.
6 | Hull Opening Gratings
| Note |  |  |  |  | Supplier to supply all paint and consumables in accordance (IAW) Vessel paint specification. |  |  |  | #REF!
| 6.1 |  | Remove and clean | 3 | Ea. | Remove, thoroughly clean and inspect the gratings to the following sea chests and internal structure. Please explain, as part of your bid in detail, the process that will be undertaken to carry out this task. | Please respond in the Technical Response Document
|  | 6.1.1 | Remove and clean |  |  | Port engine room
|  | 6.1.2 | Remove and clean |  |  | Starboard engine room
|  | 6.1.3 | Remove and clean |  |  | Bow thruster Space
| 6.2 |  | Paint | 3 | Ea. | On completion of inspection and cleaning of gratings, re-preserve in accordance with the anti-fouling paint scheme and safely store until all other hull and hull valve maintenance including anti-fouling painting within sea chests have been carried out.
| 6.3 |  | Reassemble | 3 | Ea. | Reassemble all gratings ensuring all fixings are securely moused, using new fasteners if required. Please explain, as part of your bid in detail, the process that will be undertaken to carry out this task. | Please respond in the Technical Response Document
7 | Hull Valves
| Note |  |  |  |  | The 3 x 200mm Butterfly valves are to be removed and replaced by Authority supply the remainder are to be cleaned, dismantled and overhauled, then reassembled using new gaskets of suitable design and construction for their intended use and pressure tested (to Lloyds requirements) as described. All removed valves are to be reinstated using new gaskets of suitable design and construction for their intended use. Pressure tests are to be witnessed by the BFOO. |  |  |  | #REF!
| 7.1 |  | Remove, clean or replace | 7 | Ea. | Remove, Clean, inspect and either replace the following valves:
|  | 7.1.1 | Replace | 2 |  | Port and starboard sea chests valves including gearboxes and rod gear ( 2 x 200mm butterfly valves). Authourity supply
|  | 7.1.2 | Replace | 1 |  | Bow Thruster sea chest, including gearboxes and rod gear ( 1 x 200mm butterfly valve). Authourity supply
|  | 7.1.3 | Remove, clean or replace | 1 |  | Sanitary pump overboard discharge ( 1 x 75mm SDNR storm vlave)
|  | 7.1.4 | Remove, clean or replace | 1 |  | Stablizer cooling water overbaord discharge ( 1 x 40mm SDNR valve)
|  | 7.1.5 | Remove, clean or replace | 1 |  | A/C cooling water overboard discharge ( 1 x 75mm SNDR valve)
|  | 7.1.6 | Remove, clean or replace | 1 |  | Bow Thruster room manual bilge pump overboard discharge (1 x 40mm SNDR valve)
|  | 7.1.7 | Replace | 1 |  | Replace Speed log transducer P98 Sea Valve assembly tested to GL Standard. Authority supplied.
| 7.2 |  | Test | 4 | Ea. | On completion of a successful test witnessed by the BFOO, the hull valve fittings are to be re-preserved in accordance with the paint specification.
| 7.3 |  | Test | 3 | Ea. | With the sea strainers removed, the welds are to be subject to a Non-Destructive Test (NDT), a visual inspection of the Stainless Steel housing condition/seal faces and the strainer housing pressure tested to 6 Bar, test to be witnessed by the BFOO.
| 7.4 |  | Reassemble | 7 | Ea. | Re-install all valves using new gaskets and seals and retaining bolts and nuts and complete with new gearbox supplied, torqued to British Standard values for the bolt specification.
8 | Painting of Boot Top and Anti-Fouling on outer bottom
| Note |  |  |  |  | Upon Completion of all items in section 1, painting of underwater area to be carried out as follows:. The Contractor is to supply all International Paint as per Border Force Paint Specification. |  |  |  | #REF!
| 8.1 |  | Prepare | 1 | Ea. | Outer Bottom and boot-top comprising an area of 526 m2 is to be cleaned, prepared and coated as follows: -
| 8.2 |  | Prepare | 1 | Ea. | Additional cleaning by solvent in way of oil,grease and soot contamination build-ups at the waterline, max 25m2
| 8.3 |  | Prepare | 1 | Ea. | Surface, prepare and feather in any areas of detachment, or damage including crazing or blistering, applying surface primer base coating where bare steel is exposed: maximum 10% (52 m2);
| 8.4 |  | Paint | 1 | Ea. | Touching up prepared damaged areas with two coats of antifouling(or boot-topping paint as applicable) maximum 10% (52m2)
| 8.5 |  | Paint | 1 | Ea. | Lastly one full coat of antifouling including the boot top is to be applied to the wet film thickness standards as required in the International Paints Specification (attached)
9 | Ultrasonic Survey of Hull Structure
| Note |  |  |  |  | Special attention is to be paid to hull plating in the wind & water area of the hull sides, the transom, the threshold of the ramp and plating in the after ramp well normally covered by the Hakkerite Planking.
| 9.1 |  | Prepare and test | 1 | Ea. | While the vessel is out of the water and cleaned off all marine growth, and the hakerite planking in the after ramp well removed, and before any re-painting activity has taken place, Carryout a full ultrasonic thickness inspection of the Cutter’s underwater hull and topside in accordance with Lloyds standard ultrasonic procedure and by a Lloyds approved contractor.
| 9.2 |  | Report | 1 | Ea. | Provide a written report of the hull ultrasonic results to the BFOO. Results are to include a graphic presentation of finding on a hull expansion drawing in accordance with Lloyds requirements and are be submitted in both paper format and electronic acrobat.pdf document.
10 | RHIB Slipway
| Note |  |  |  |  | The Contractor is to supply all Paint as per Border Force Paint Specification.
| 10.1 |  | Remove | 1 | Ea. | The RHIB slipway Hakkerite lining is to be removed and the slipway coating and structure surveyed.
| 10.2 |  | Provide | 1 | Ea. | The Contractor shall provide the BFOO a written condition report of the RHIB slipway and Hakkerite.
| 10.3 |  | Prepare | 1 | Ea. | The Contractor shall prepare and recoat the RHIB slipway in accordance with the International Paint manufacturer’s specifications.
| 10.4 |  | Re-instate | 1 | Ea. | The contractor on complition of the recoating of the RHIB slipway is to re-install the Hakkerite linning.
11 | Stern Door Internal
| Note |  |  |  |  | The Contractor is to supply all Paint as per Border Force Paint Specification.
| 11.1 |  | Inspect | 1 | Ea. | Carry out an external material condition survey of the inside of the stern door (slipway side) and report finding to BFOO .
| 11.2 |  | Prepare | 1 | Ea. | The Contractor shall prepare and recoat the slipway side of the stern door in accordance with the International Paint manufacturer’s specifications.
| 11.3 |  |  | 1 | Ea.
Annex E Total Cost

## Quote Total
Annex A Total Cost | 0
Annex B Total Cost | 0
Annex C Total Cost | 0
Annex D Total Cost | 0
Annex E Total Cost | 0
Quote Total Cost | 0

## Additional Information
Additional Information
Ser | Annex | Line | Description | Completed by: | Acknowledged by: | Complete
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32

## Acceptances
1 | Organisation Name
2 | Quote reference
3 | Terms and Conditions
My Organisation accepts the Authorities Terms and Conditions as set out in Project-18427 - HMC Valiant - Intermediate Docking T&Cs?
t
4 | Insurance
My Organisation has the required insurance as stated in Part 2 of Project-18427- HMC Valiant- Intermediate Docking - SOR - V1.0
5 | Cardinal Date Plan
My Organisation has included my Cardinal Date Plan with my organisation's quote as per Part 4 of the SOR, clause 6.3.
6 | Project Management
My Organisation's proposal includes a Project Manager (PM) to liaise with all parties to ensure work is completed to plan
Name of PM
7 | Quote Confirmation
My Organisation has included confirmation of the quote total on letter headed paper?
8 | Emergent Work
My Organisation shall ensure that the Supplier-assigned PM will inform the BFOO if any of the Suppliers employees or contractors have been approached by either; a) the Vessel commander, b) the Vessel’s crew or c) any member of the Authority’s staff to undertake work not specified in this Specification of Requirements or as part of a previously authorised EW task.
9 | Quote Confirmation
My Organisation acknowledges and agrees that the Authority reserves the right to withhold payment from the Supplier, in part or in full, should any, specified or otherwise, condition as expressed in this Specification of Requirements, not be successfully met by the Supplier and to the satisfaction of the BFOO within the specified timeframe?
10 | General
My Organisation accepts that the Authority reserves the right to withdraw this opportunity, for any reason, at any point, prior to contract award?
11 | Filled out by
12 | Position
13 | Date

## SDS (hidden)
Notes | Acknowledge
Acknowledge | Do not Acknowledge
Do not acknowledge
Complete
Yes
Pending
No
Yes
T&C | No
Yes
No
Yes
Pending
No