BATCIS PRIVATE SECTOR SUPPORT STATEMENT OF REQUIREMENT

This Statement of Requirement is split into 14 Sections outlined below with approximate timescales that they will be required for.  The Contractor shall provide a response showing a breakdown in requirement for Years 1 to 3; Year 4; and Year 5 of the contract period, based on the MORPHEUS Programme Schedule for Sections 1 to 8, and proposed dates below for Sections 9 to 14.

1.	MORPHEUS Programme Control Support

- Programme Control Support is responsible to the MORPHEUS Programme Manager for the Programme Control, Project Support & Project Management, which includes the co-ordination of team activity according to Industry best practice and internal ISS-mandated processes.  It delivers the enterprise project management function of monitoring & reporting, planning and change management of the MORPHEUS Programme and also delivers the enterprise project management function of risk, issues and assumptions management as well as stakeholder management.

- Whilst this is MORPHEUS-centric, the Programme Control Support includes tasking that is common across the BATCIS Delivery Team.

- Programme Control Support is an enduring requirement and will start from Contract Award for the full contract period as per the MORPHEUS Programme Schedule.

2.	MORPHEUS Approvals

- To define, agree and deliver the underpinning evidence required to support all MORPHEUS approval submissions, including the Dismounted Situational Awareness (DSA) Project.  The endorsed evidence should be articulated into a concise, reasoned argument, embodied within a Business Case that clearly demonstrates the business need and associated time, cost & performance criteria to the Investment Appraisal Committee (IAC).  Key to this is early, continuous engagement and communication with the Scrutiny and Assurance communities along with Information Systems & Services (ISS), Joint Forces Command (JFC), Army Headquarters (Army HQ) and Other Governmental Departments (OGDs) - Her Majesty’s Treasury (HMT) and Cabinet Office (CO).

- MORPHEUS Approvals team will be an enduring requirement from Contract Award in line with the MORPHEUS Programme Schedule.

3.	MORPHEUS Cost Estimation

- The continued development of the MORPHEUS cost model, in order to support: Ministry of Defence (MOD) financial processes; Investment Decisions; Investment Appraisals; MOD Option process; and commercial price evaluations.

- Cost Estimation support will be an enduring requirement from Contract Award for multiple MORPHEUS Projects in line with the MORPHEUS Programme Schedule.

4.	MORPHEUS Projects

- The relevant MORPHEUS Projects include System Integrator (SI), MORPHEUS Test and Reference Centre (MTRC), Battlefield Management Application (BMA), Enduring Joint Programme Organisation (eJPO), Platform Installation and Fielding and Managed Service Providers (MSPs).

- Timescales and start dates for MORPHEUS Projects vary as per the MORPHEUS Programme Schedule.

5.	MORPHEUS Co-ordinating Design Organisation

- The Co-ordinating Design Organisation is responsible for the engineering management of the MORPHEUS Programme.  It develops, maintains and operates the engineering processes required for MOD to be the System Design Authority for MORPHEUS.

- Engineering support will be required from Contract Award and in line with the MORPHEUS Programme Schedule.

6.	MORPHEUS Joint Programme Organisation

- The Joint Programme Organisation (JPO) is an integrated programme management and engineering organisation, with a physical office in Bristol, but with a much broader geographical membership.  It will manage the execution of the EvO Baseline, reporting to the MORPHEUS Programme Board, and is the focal point for the business transformation of the Authority into the quasi-prime for MORPHEUS and achieving Vendor Independence.

- The MORPHEUS JPO resource will be required from Contract Award and in line with the MORPHEUS Programme Schedule.

7.	MORPHEUS Integrated Logistics Support

- It is MOD policy that Integrated Logistics Support (ILS) will be applied to all product acquisition via the application of Defence Standard Def Stan 00-600, the contracting standard for ILS requirements.

- The ILS team will be an enduring requirement from Contract Award.

8.	MORPHEUS Requirements Support

- The Requirements Team is responsible for the capture, management and tracking of the requirements (what the system must do and how it must do it) throughout the procurement process, from initial concept through to final acceptance.  This work has three main strands. The first centres on engagement with the various end-user communities, to determine what they want to use the system to do; the second is tracking the requirements; and the third is the test and acceptance of the requirement set.

- The MORPHEUS Requirements Support will be required from Contract Award.

9.	Dismounted Situational Awareness

- Dismounted Situational Awareness (DSA) is a MOD-specific, sub-element of MORPHEUS; a Project under the LE TacCIS Programme which seeks to provide a Command, Control, Communications, Computers and Intelligence (C4I) system to support Commanders in Dismounted Close Combat (DCC), who require a lightweight system that will generate a step-change in shared situational awareness and mission effectiveness throughout the dismounted company group.

- The requirement for BATCIS DSA resource will not be needed until Apr 2019 (predicted start date).

10.	BATCIS TRINITY

- BATCIS TRINITY will seek to uplift the current FALCON capability, address major obsolescence, integrate closely with other network capabilities and deliver against future deployed Information Exchange Requirements (IERs).​

- The requirements for TRINITY resource will be from Contract Award and in line with the BATCIS TRINITY Project Schedule for a minimum of 2 years.

11.	BATCIS Support and Engineering Assurance

- Support to the System Engineering Assurance (SEA) team including Security, Safety & Environmental, Technical Trials, E3 and Requirements.

- BATCIS SEA support will be an enduring requirement from Contract Award.

12.	BATCIS TacCIS Subject Matter Experts

- The BATCIS Tactical Communications Information Systems (TacCIS) team is responsible for the programme and project management of a range of in-service tactical CIS equipment and systems, together with providing logistics support and design services for tactical CIS equipment used in the Joint Land Environment.

- Section 12.1 Joint Software Integration Board (JSIB) resource is an enduring requirement from Contract Award.

- Section 12.2 to Section 12.6 TacCIS SME’s will not be required until Apr 2019 in line with the TacCIS projects requirements.

13.	BATCIS TacCIS Support Project

- The TacCIS Support Project (TSP) will provide continued support to all Bowman and other TacCIS equipment from the current contract expiry date 31 Mar 2019 and incorporate the FALCON (and replacement TRINITY) capabilities at the FALCON contract expiry date 31 Dec 2020.

- BATCIS TSP resource will be required from Contract Award in line with the project requirements.

14. 	Additional Support Options to BATCIS

- Fielding/ Conversion Contractor and the MIDaC Re-compete.   For either the Fielding/ Conversion Contractor and/or a MIDaC re-compete, the Contractor shall apply the Project’s lifecycle.  The Project Lifecycle shall include capturing and updating the requirement and creation and updates to associated documentation required to run a competition.

- Training Support - Course and Courseware Design and Development Specific PM Requirements.   The requirement is to work with the Delivery Team Authority (BATCIS) and the Training Requirements Authority (TRA) to design and develop the training courses and training courseware required to support the conversion of Defence personnel from BCIP 5.6 baseline to the EvO system baseline.

Note: The Authority is a procurement organisation and the team provided under this Contract in all SORs will be required to support competitions in addition to their Business as Usual activity.  This may include supporting the creation of tender documentation, conducting tender evaluation and/or moderation and supporting the Authority in negotiations during the competition process. The Authority views these activities as falling within the provisions of Clause 3.5.

MORPHEUS Programme Schedule.   The Contractor shall utilise the MORPHEUS Programme Schedule, as supplied in the Datapack, for Project milestones and delivery dates for the MORPHEUS Programme in Sections 1 to 8 only.

Stakeholder Engagement Statement

The Contractor will be required to use their expertise and act in accordance with Good Industry Practice to identify when engagement of any Stakeholder is required and will undertake the required engagement in order to enable the Contractor to deliver all of the requisite Contractor Deliverables by the date specified in the Programme Schedule or as otherwise specified by the Contract.

The Contractor shall develop all documentation on the Authority SharePoint System to enable live access to documentation as it is developing.

1.0	MORPHEUS Programme Control Support.   Programme Control Support is responsible to the MORPHEUS Programme Manager for the Programme Control & Project Management of BATCIS, which includes the co-ordination of team activity according to Industry best practice and internal ISS-mandated processes.  It delivers the enterprise project management function of monitoring & reporting, planning and change management of the MORPHEUS Programme and also delivers the enterprise project management function of risk, issues and assumptions management as well as stakeholder management.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 1.1 | The Contractor shall manage and maintain the existing MORPHEUS Programme Schedule for the duration of the Contract, known hereafter as the Schedule for the purposes of this Schedule 2. The Contractor shall engage/ liaise on a weekly basis with all relevant stakeholders to review the Schedule and establish any necessary changes to the Schedule including, as a minimum: - MORPHEUS Battlefield Management Application (BMA) Project Manager; - MORPHEUS Test & Reference Centre (MTRC) Project Manager; - MORPHEUS Installation Design & Certification (MIDaC) Project Manager; - MORPHEUS Systems Integrator Project Manager; - MORPHEUS Programme Support Office Lead; - Engineering Delivery Leads for Co-ordinating Design Organisation; - MORPHEUS Risk, Assumptions and Dependency Manager; - Evolve to Open Transition Partner Project Manager; - MORPHEUS Deputy Programme Manager; - BATCIS Senior Commercial Officer; - BATCIS Costings Lead; - MORPHEUS Trials Manager; - MORPHEUS GFA Manager; and - Army Headquarters LE TacCIS SO1. The Schedule shall be maintained in accordance with the MORPHEUS Programme Schedule Product Description and in compliance with the MORPHEUS PSO utilising Enterprise Project Management (EPM 2013). Access to EPM will be provided as an Authority Obligation. | MORPHEUS Programme Schedule maintained to an Authority agreed level in compliance with ISS PMO EPM Guidance on Enterprise Project Management tool | Weekly from Contract Award | Regular 5 Days to Review |
| 1.1.1 | The Contractor shall develop and maintain a Schedule Risk Analysis (SRA) utilising the Predict Tool as per the MORPHEUS PSO and the MORPHEUS Predict Product Description. Access per user for the Predict Tool will be supplied as an Authority Obligation. | Schedule Risk Analysis of the Schedule | Quarterly from Contract Award | Regular 5 Days to Review |
| 1.1.2 | The Contractor shall provide a Schedule Report on the Schedule’s status, which at the minimum, shall include: - issues and bottlenecks on resource to support the MORPHEUS Programme; - summary of the status of key milestones in the Schedule; - the current level of resource float in the Schedule; and - details of proposed changes, including the number of changes requested, approved and rejected. | A MORPHEUS Programme Schedule Report | Monthly from Contract Award | Regular 5 Days to Review |
| 1.2 | The Contractor shall manage and maintain the MORPHEUS Active Risk Management Tool (ARM). To manage and maintain the MORPHEUS ARM, the Contractor shall engage/ liaise on a fortnightly basis with, all relevant stakeholders to update, modify or create risks, including as a minimum: - MORPHEUS Battlefield Management Application (BMA) Project Manager; - MORPHEUS Test & Reference Centre (MTRC) Project Manager; - MORPHEUS Installation Design & Certification (MIDaC) Project Manager; - MORPHEUS Systems Integrator Project Manager; - MORPHEUS Programme Support Office Lead; - Engineering Delivery Leads for Co-ordinating Design Organisation; - MORPHEUS Risk, Assumptions and Dependency Manager; - Evolve to Open Transition Partner Project Manager; - MORPHEUS Deputy Programme Manager; - BATCIS Senior Commercial Officer; - BATCIS Costings Lead; - MORPHEUS Trials Manager; - MORPHEUS GFA Manager; and - Army Headquarters SO1 LE TacCIS. The MORPHEUS ARM shall be managed and maintained in accordance with the MORPHEUS Programme Controls and in accordance with the MORPHEUS ARM Product Description. | An up-to-date MORPHEUS Active Risk Management System | Fortnightly from Contract Award | Regular 5 Days to Review |
| 1.2.1 | The Contractor shall provide a report on the top 10 risks from the MORPHEUS ARM by project area. The report will include the following information for each risk at the minimum: - description of the Risk; - probability of the Risk; - the estimated time impact of the Risk becoming an Issue; - the estimated cost impact of the Risk becoming an Issue; and - any potential mitigation. This will feed into the Project Workbooks. | Report on Top 10 Risks | Monthly from Contract Award | Regular 5 Days to Review |
| 1.2.2 | The Contractor shall provide a report on the status of all risks from the MORPHEUS ARM. The report will include the following information for each risk at the minimum: - description of the Risk; - probability of the Risk; - the estimated time impact of the Risk becoming an Issue; - the estimated cost impact of the Risk becoming an Issue; and - any potential mitigation. This will be presented at a monthly Risk Review Board as per MORPHEUS Programme Controls. | A Report on Risk Status of all Risks | Monthly from Contract Award | Regular 5 Days to Review |
| 1.3 | The Contractor shall manage and maintain the MORPHEUS Assumptions Register. In order to manage and maintain the MORPHEUS Assumptions Register, the Contractor shall as a minimum undertake the following activities: - conduct Assumption Management Analysis weekly; - maintain an up-to-date Master Data Assumptions List; and - engage/ liaise on a fortnightly basis with all relevant stakeholders, including as a minimum: - MORPHEUS Battlefield Management Application (BMA) Project Manager; - MORPHEUS Test & Reference Centre (MTRC) Project Manager; - MORPHEUS Installation Design & Certification (MIDaC) Project Manager; - MORPHEUS Systems Integrator Project Manager; - MORPHEUS Programme Support Office Lead; - Engineering Delivery Leads for Coordinating Design Organisation; - MORPHEUS Risk, Assumptions and Dependency Manager; - Evolve to Open Transition Partner Project Manager; - MORPHEUS Deputy Programme Manager; - BATCIS Senior Commercial Officer; - BATCIS Costings Lead; - MORPHEUS Trials Manager; - MORPHEUS GFA Manager; and - Army Headquarters SO1 LE TacCIS. The Contractor shall manage and maintain the MORPHEUS Assumptions Register in compliance with the MORPHEUS Assumptions Register Product Description and MORPHEUS Programme Controls. | An up-to-date MORPHEUS Assumptions Register | Fortnightly from Contract Award | Regular 5 Days to Review |
| 1.3.1 | The Contractor shall provide a report on Assumptions Management which shall, at the minimum, include: - all new assumptions which have been added to the register since the previous report; - an accurate assessment of the impact to the Schedule if the Assumptions are incorrect. This assessment will take account of any impact to time, cost or resource; and - any exceptions to the Assumptions List. | A report on the status of the Assumptions | Monthly from Contract Award | Regular 5 Days to Review |
| 1.4 | The Contractor shall manage and maintain the MORPHEUS Dependency Register. The Contractor shall as a minimum undertake the following activity: - capture and manage all dependencies for the MORPHEUS Programme, liaising with Army HQ LE TacCIS PSO for monthly updates. The Contractor shall comply with the MORPHEUS Programme Controls and the MORPHEUS Dependency Register Product Description. | An up-to-date and accurate MORPHEUS Dependency Register | Monthly from Contract Award | Regular 5 Days to Review |
| 1.4.1 | The Contractor shall provide a Dependency Management Report which shall, as a minimum, include: - escalations of dependency risks; - changes to dependency timescales; and - impact to the Schedule, and the Project Schedules by performance, cost and time. | Report on Dependency status | Monthly from Contract Award | Regular 5 Days to Review |
| 1.5 | The Contractor shall co-ordinate and manage engagement with the MORPHEUS Programme stakeholder community by undertaking as minimum: - identify the MORPHEUS Programme stakeholder community; - develop appropriate strategies for engagement with the MORPEHUS Programme stakeholder community, which will form part of the Stakeholder Management Plan at 1.5.1; - as required, based upon the engagement strategies development, or guidance from the MORPHEUS Programme Manager or Deputy Programme Manager, engage with identified stakeholders; and report on stakeholder engagement activity undertaken in accordance with 1.5.2. | Conduct stakeholder management and engagement with the MORPHEUS Programme stakeholder community | As required | Regular 5 Days to Review |
| 1.5.1 | The Contractor shall manage and maintain the MORPHEUS Stakeholder Management Plan which shall as a minimum comply with the MORPHEUS Programme Controls and the MORPHEUS Stakeholder Management Product Description. | An up-to-date Stakeholder Management Plan | Monthly from Contract Award | Regular 5 Days to Review |
| 1.5.2 | The Contractor shall provide a Stakeholder Report which shall, as a minimum, include: - details of compliance with the identified stakeholder engagement strategies; and - summaries of the outcomes of stakeholder engagement activities. | Stakeholder Report | Monthly from Contract Award | Regular 5 Days to Review |
| 1.5.3 | The Contractor shall manage and maintain the MORPHEUS Briefing Pack to reflect any developments within the MORPHEUS Programme and Projects in order to brief the MORPHEUS Stakeholder Community. The Contractor shall regularly engage with MORPHEUS Programme staff to understand developments within the MORPHEUS Programme to inform the MORPHEUS Briefing Pack, including as a minimum: - MORPHEUS Battlefield Management Application (BMA) Project Lead; - MORPHEUS Test & Reference Centre (MTRC) Project Lead; - MORPHEUS Installation Design & Certification (MIDaC) Project Lead; - MORPHEUS Programme Support Office Lead; - Engineering Delivery Leads for Coordinating Design Organisation; - MORPHEUS Risk, Assumptions and Dependency Manager; - Evolve to Open Transition Partner Project Manager; - MORPHEUS Deputy Programme Manager; - BATCIS Senior Commercial Officer; - BATCIS Costings Lead; - MORPHEUS Trials Manager; - MORPHEUS GFA Manager; and - Army Headquarters SO1 LE TacCIS. | An up-to-date MORPHEUS Briefing Pack | Monthly from Contract Award | Regular 5 Days to Review |
| 1.5.4 | The Contractor shall, using the MORPHEUS Briefing Pack and any other relevant information, support briefings to all Front Line Commands (FLCs) on the progress of the MORPHEUS Programme. | Briefings to FLCs | Each FLC bi-annually from Contract Award | Regular 5 Days to Review |
| 1.5.5 | The Contractor shall prepare a fortnightly presentation to be delivered to MORPHEUS Programme staff, using the MORPHEUS Briefing Pack and any other relevant information, on the MORPHEUS Programme progress, to be delivered by either the MORPHEUS Programme Manager or Deputy Programme Manager. | MORPHEUS Programme presentation | Fortnightly from Contract Award | Regular 5 Days to Review |
| 1.5.6 | The Contractor shall co-ordinate delivery of progress briefings on the MORPHEUS Projects. Progress briefings will be delivered by the Project Manager leading on the given project. The progress briefings will be delivered to the wider MORPHEUS Programme team. Briefings should be kept to no more than 20 minutes. | Progress Briefing | Quarterly per MORPHEUS Project | Regular 5 Days to Review |
| 1.5.7 | The Contractor shall, in compliance with the requirements of ISO-44001, attend and participate in a breakthrough event with the Authority. The event will be over two days and set the foundation for the relationship. The Contractor shall ensure that suitably empowered individuals are in attendance, the Authority will attend with the BATCIS Management Team. | Breakthrough Event Behaviours Charter Draft Relationship Management Plan | Within 1 Month of Contract Award | Consensus from the Breakthrough Event attendees |
| 1.5.7.1 | During the course of the breakthrough event, the Contractor shall in conjunction with the Authority develop a Behaviours Charter for the Contract taking account of the MORPHEUS Behaviours and JPO Ways of Working. | Behaviours Charter | By the end of the Breakthrough Event | Consensus from the Breakthrough Event attendees |
| 1.5.7.2 | During the course of the two days the Contractor shall, in conjunction with the Authority develop a Draft Relationship Management Plan. The Draft Relationship Management Plan shall take account of other documentation including the Contract and provide links and references where information already exists. The Authority will provide previous examples on the day. The Draft Relationship Management Plan shall as a minimum include the following: - an introduction; - context; - shared project understanding; - partnering relationship; - governance and organisation; - project processes; - building the relationship; - monitoring the relationship; - stakeholder management; and - a Communications Plan. | Draft Relationship Management Plan | By the end of the Breakthrough Event | Consensus from the Breakthrough Event attendees |
| 1.5.7.3 | The Contractor shall deliver, manage and maintain an Exit Plan in accordance with the provisions of Schedule 17 of the Contract. | Exit Plan | As per Schedule 17 | As per Schedule 17 |
| 1.5.7.4 | The Contractor shall engage with the Authority to deliver a Joint Business Continuity Plan for the delivery of the Contract describing roles for both the Authority and the Contractor if a Business Continuity Event arises. The Joint Business Continuity Plan shall, as a minimum, include provisions as per ISO 22301 Business Continuity Management: - Maximum Acceptable Outage (MAO); - Minimum Business Continuity Objective (MBCO); and - Prioritized Timeframes. | Joint Business Continuity Plan | As part of Tender Return | As per Evaluation plan |
| 1.5.7.5 | The Contractor shall achieve ISO 44001 during the term of the Contract. The Contractor shall use the evidence which is developed under this Contract when achieving the accreditation. | ISO 44001 Certification | 24 Months after Contract Award | Regular 5 day review |

Project Support Requirement as per MORPHEUS Evolve to Open (EvO) Programme Schedule.   Project co-ordination & Project Management Support to all Projects within the MORPHEUS Programme.  The following support provisions will apply to all MORPHEUS Projects other than the EvO Transition Partner (TP) Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 1.6 | The Contractor shall provide administrative assistance to the MORPHEUS Programme and MORPHEUS Projects. This activity will include at the minimum: - managing and maintaining the administration of the MORPHEUS Programme and MORPHEUS Projects by filing all relevant information onto the MORPHEUS SharePoint area; - managing and maintaining the MORPHEUS Learning From Experience (LFE) Log; - produce Record of Decisions (RODs) from Project Leads Stand-up Meeting fortnightly; - produce a RODs from the Programme Manager’s Project Review fortnightly; - produce RODs from the One-Star MORPHEUS Programme Board monthly; and - produce RODs for any other meetings that are required. All RODs shall be compliant with the MORPHEUS RODs Product Description. - Providing input to and producing reports as required. | Up-to-date on the MORPHEUS SharePoint area for the MORPHEUS Programme and the MORPHEUS Projects Updated LFE Log RODs for meetings | As required 5 days after Project Milestone completion All RODs to be completed within 2 days of the meetings | Regular 5 Days to Review |
| 1.7 | The Contractor shall provide the support detailed in Sections 1.7.1 to 1.7.8 to the MORPHEUS Project Leads and the MORPHEUS Project Managers. When undertaking the support the Contractor shall, as a minimum, comply with: - ISS PMO policy; - MORPHEUS Programme Controls (whilst a project is managed from the BATCIS floorplate (i.e. pre-competition and during competition); - JPO Policy & Procedures (once a project is On Contract and has transitioned to being managed from the JPO); and - Industry best practice and internal ISS-mandated processes. The Project Management resource will be managed by the MORPHEUS Project Leads as per the Organisational Breakdown Structure. The Authority MORPHEUS Project Leads will manage the PM Support resource at task level, delegating to the appropriate MORPHEUS Project PM as required. |  |  |  |
| 1.7.1 | The Contractor shall follow the MORPHEUS Change Control Process for the MORPHEUS Projects and as a minimum: - check that MORPHEUS Projects documentation and/or documentations conform to the approved MORPHEUS Change Control Process; - ensure the MORPHEUS Projects Project Management Plan (PMP) is coherent with approved MORPHEUS Change Control Process; and - escalate to MORPHEUS Projects Leads any documentation and/or documentations that have not followed the approved MORPHEUS Change Control Process. | MORPHEUS Projects documentation and/or documentations all compliant with approved MORPHEUS Change Control Process | As required for each MORPHEUS Project | Regular 5 Days to Review |
| 1.7.2 | During MORPHEUS Projects competitions, the Contractor shall provide support to the competition Clarification Question process, adhering strictly to the BATCIS Commercial Team guidance, as required. Responsibilities shall include as a minimum: - act as project Point of Contact (POC) for the BATCIS Commercial Team regarding Clarification Questions; - liaise with the BATCIS Commercial Team for the Project when Clarification Questions are received from Industry; - disseminate clarification questions to the appropriate PM/ technical member of the MORPHEUS Programme team, requiring a response in less than four (4) working days; and - co-ordinate the timely return of Clarification Questions to the BATCIS Commercial Team. | Timely response to clarification questions during the competition period of any of the MORPHEUS Projects | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.3 | The Contractor shall support the timely set-up of the Dynamic Pre-Qualification Questionnaire (DPQQ) on Defence Contracts Online (DCO), as required for the MORPHEUS Projects, including as a minimum: - liaising with the BATCIS Commercial Team when setting up the relevant MORPHEUS Project on DCO; - arranging any necessary training (in collaboration with the BATCIS Commercial Team) on DCO; - producing a list of names, roles and email addresses of the staff that will be evaluate the DPQQ; - supporting the BATCIS Commercial Team when adding questions to the DPQQ; and - co-ordinating support to the DPQQ evaluation process once the DPQQ has closed. | DPQQ for relevant MORPHEUS Project set up on DCO List of evaluators for relevant DPQQ | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.3a | The Contractor shall support the timely set-up AWARD (hosted tool for managing competitions), as required, including as a minimum: - liaising with the AWARD supplier alongside the BATCIS Commercial Team when setting up the relevant MORPHEUS Project; - arranging any necessary training (in collaboration with the BATCIS Commercial Team) by the AWARD provider; - undertaking any necessary AWARD training; - producing a list of names of the staff that will be evaluating the tender; - arranging a briefing by the BATCIS Commercial Team to evaluators on the evaluation process; and - performing admin tasks on AWARD during bid evaluation. | Tender set-up on AWARD for relevant MORPHEUS Project List of evaluators for relevant Tender Exercise | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.4 | The Contractor shall support the MORPHEUS Project Managers with Stakeholder Management activities, as required, including as a minimum: - provide information to MORPHEUS Stakeholder Manager when necessary (e.g. to support events) as directed by the MORPHEUS Project Leads and Project Managers; - regularly review the stakeholder matrix to record and manage changes; and - provide ad-hoc stakeholder engagement in a timely manner. | Up-to-date Stakeholder Matrix in the relevant MORPHEUS Project Workbook | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.5 | The Contractor shall support the MORPHEUS Project Managers with project dependencies, including as a minimum: - support maintenance of project dependencies within the MORPHEUS Project Workbook; - assist organisation and co-ordination of Dependency Reviews with MORPHEUS Project Leads and take RODs; - identify impacts of dependencies; and - update and maintain project dependency log within the MORPHEUS Project Workbook. | Up-to-date dependency log in the relevant MORPHEUS Project Workbook | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.6 | The Contractor shall support the configuration management of Authority documentation, including as a minimum: - ensure configuration control practices are adhered to; - Ensure agreed documents are delivered to SharePoint at the direction of the MORPHEUS Project Leads/ Project Managers (excluding the Transition Partner Project); - Create folders on SharePoint as appropriate to accommodate division of documentation. | Document configuration on SharePoint | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.7 | The Contractor shall provide support to the MORPHEUS PSO, including as a minimum: - produce project meeting schedules that are coherent with, and inform the Programme Manager’s meeting schedule; - co-ordinate meeting requests which shall contain Terms of Reference (TOR) for the meeting; - ensure meeting documentation is prepared and collated for attendees; - taking meeting RODs; - send RODs to all attendees, ensuring they are filed in a timely manner on SharePoint; and - manage the timely resolution of any actions from the meetings. | Collated information packs for meeting attendees RODs for meetings | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.7.8 | The Contract shall provide support to the MORPHEUS Industry Days which shall include as a minimum: - assisting the BATCIS Commercial Team with identifying and booking hosting facilities; - assisting the BATCIS Commercial Team with advertising for the event; - producing a list of attendees, which shall include as a minimum; - name; - date of birth; - nationality; - security clearance; and - vehicle registration details. - preparing an Industry Day Pack to be sent out by the BATCIS Commercial Team to attendees; - managing attendee registration on the day; - recording questions raised by Industry on the day; - collating answers and providing to BATCIS Commercial Team for release; and - assisting with any tidy up after the event. | Booked Industry Day Facility Advert for Industry Day List of Attendees Industry Day Pack (as required) Record of Questions and Answers | In line with outputs of the Project Schedule | Regular 5 Days to Review |
| 1.8 | The Contractor shall provide Strategy Support to the Future Project Lead and as a minimum: - maintain & update the MORPHEUS Programme 10 Year Strategy document for review annually; - manage the Future Project Team workflow; - hold quarterly strategy meetings to develop and present on emerging uncertainties and potential issues; - develop the business model to address outcomes from Operational Field Trials (OFT) and User Acceptance events in support of Army HQ; - conduct scoping activities for the first Evolutionary Capability Development (ECD) body of work, covering input from requirements, innovation and obsolescence management; - support to Approvals and evidence generation for Approvals submissions as required (Review Notes, Main Gate Business Case and Information Notes); - maintain and annual update to ECD Capping Paper; - maintain and annual update to ECD Briefing Pack; - Provide input to support to Army HQ benefits management; - provide coherence across the Programme to ensure ECD adoption is in line with Programme 10 Year Strategy, and not ad hoc; - provide, in concert with the BATCIS senior Commercial Officer, an analysis of supply chain conflict of interest for all MORPHEUS Projects; - support business transformation (known as Value Stream 2) in the adoption of new ways of working and Joint Programme Organisation/ Co-ordinating Design Organisation implementation to ensure coherence with EvO and ECD; - assist the Project Managers in the development of the Statements of Requirements (SOR) for the Systems Integrator and Managed Service Providers based on extant strategy. - react to ad-hoc tasking’s from the MORPHEUS Programme Manager as applicable. | Updated Strategy Document Updated Business Model ECD Capping Paper ECD Briefing Pack | Monthly report | Regular 5 Days to Review |
| 1.8.1 | The Contractor shall develop Options for subsequent implementation to the following items, in line with the requirements of the MORPHEUS Programme, to include as a minimum: - Options to address Obsolescence Management for future key management and crypto changes; and - Options to address Whole Fleet Management, supported by Army HQ. | Proposals for Obsolescence Management approach Proposals for Whole Fleet Management approach | Monthly brief to Programme Manager Monthly brief to Programme Manager | Regular 5 Days to Review |
| 1.8.2 | The Contractor shall provide a monthly report providing updates and feedback on all aspects of Strategy Support including as a minimum: - status of the Strategy Document; - status of the Business Model; - status of the ECD Capping Paper; - status of the ECD Briefing Pack; - updates to any proposals due; and - escalations to MORPHEUS Programme Manager. | Monthly Report | Monthly from Contract Award | Regular 5 Days to Review |

1.9	MORPHEUS Test and Trials Manager.   Responsible for detailed planning, management and execution of successful First of Type (FOT) Trials and Operational Field Trials (OFT) through the multiple MORPHEUS Projects as per the MORPHEUS Programme Schedule.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 1.9 | The Contractor shall provide Project Management support to the MORPHEUS Project Lead by managing the First of Type (FOT) and Operational Field Trials (OFT). The Contractor shall ensure the MORPHEUS Trials and resource requirements are implemented into the MORPHEUS Programme Schedule. The Trials Manager will work with Army HQ to establish a relevant governance structure e.g. Steering Groups (SG) and Working Groups (WG) for the MORPHEUS Trials. |  |  |  |
| 1.9.1 | The Contractor shall provide Trials Management support including, as a minimum, the following: - liaise the BATCIS Requirements Team to provide input into any relevant Integrated Test, Evaluation and Assessment Plan (ITEAP). - liaise with the Army HQ Trials Manager to design the FOT and EvO Field Trials, with due consideration to any relevant ITEAP or other document; - liaise with the Army HQ Trials Manager to determine the Aims and Objectives of the Field Trials, with due consideration to any relevant ITEAP or other document; - liaise with the Army HQ Trials Manager to develop Field Trial resourcing requirements and shall submit in a timely manner to enable any trials activity to take place; - liaise with the Army HQ Trials Manager to review the Army SOR for all EvO FOT, EvO OFT and any other MORPHEUS Trials; - liaise with the Army Trials Manager to manage and maintain the Trials Planning scope; - liaise with the BATCIS Requirements Team on relevant system requirements; - liaise with the Co-ordinating Design Organisation (CDO) and MIDaC Project Lead, to manage and maintain the EvO trials and test scenarios; - liaise with the BATCIS Requirements Team on the development of General Dynamics (GD) Test Use Cases; - liaise with the Army HQ Trials Manager to agree user input to the product development, product testing and system testing integration activities and ensure that resource requirements are submitted in a timely manner; and - produce a report upon the progress of all of the aforementioned activities and any other relevant details. | Monthly report on trials progress updates | Monthly from Contract Award | Regular 5 Days to Review |
| 1.9.2 | The Contractor shall create, maintain and manage a MORPHEUS Trials Work Breakdown Structure (WBS) in compliance with Industry best practice. | MORPHEUS Trials Work Breakdown Structure | Drop 1 MACA +2 Monthly Updates | Regular 5 Days to Review |
| 1.9.3 | The Contractor shall engage with other MORPHEUS staff as required to support activities which shall as a minimum include: - maintaining the Schedule; - risk management; - assumptions management; - dependencies management; - budget forecasting process; and - stakeholder management. | Support to updates to other MORPHEUS activities | As required | Regular 5 Days to Review |
| 1.9.4 | The Contractor shall create, maintain and manage a MORPHEUS Trials Project Schedule, in line with the MORPHEUS Programme Controls. The MORPHEUS Trials Project Schedule shall include the following: - all major decision points - including Milestones and key Gateway Reviews ensuring the Project stays on track and taking corrective actions when necessary; - progress and technical reviews; - all deliverables; - all task dependencies; - all schedule assumptions; - all schedule constraints; - the critical path; and - fully resource planned and costs, and task durations. When maintaining or amending the MORPHEUS Trials Project Schedule, the Contractor shall use the MORPHEUS Schedule Change Request process as per MORPHEUS Programme Controls. | MORPHEUS Trials Project Schedule | Drop 1 MACA +3 Monthly Updates | Regular 5 Days to Review |
| 1.9.5 | The Contractor shall produce a MORPHEUS Trials Project Schedule Change Impact Statement, as required, to assess the impact of any potential or upcoming change to the relevant MORPHEUS Project Schedule. This is to consider, as a minimum, the impact on the performance, cost and time of both the relevant Project, and other Programme Projects. | Schedule Change Impact Statement | As required | Regular 5 Days to Review |
| 1.9.6 | The Contractor shall provide the MORPHEUS Trials Project reporting, which as a minimum, shall include: - fortnightly, provide and present a short update on the MORPHEUS Trials Project at the Lead’s Project ‘stand-up’ meeting; - fortnightly, present a formal report to the MORPHEUS Programme Manager Project Review; - monthly, present a formal Project Highlight Report at the One-Star MORPHEUS Programme Board; and - monthly, hold a review with the Army HQ Trials Manager on the progress of the MOPRHEUS Trials Project. Produce RODs for meetings where required. | Presentation of update at the Project ‘stand-up’ meeting Presentation of formal report at MORPHEUS Programme Manager’s Project Review Presentation of formal highlight report the One-Star MORPHEUS Programme Board RODs of Army HQ Trials Managers meeting | As per description. | Regular 5 Days to Review |
| 1.9.7 | The Contractor shall provide Project Management support to the MORPHEUS Project Lead by managing the MORPHEUS Test Team. This is not a traditional, waterfall Test Manager role, although those skills and experience will be critical. The Contractor shall be required to work in a SAFe Agile way with elements of the MORPHEUS solution being designed with test in mind, tested throughout the Design and Development process and finally tested for release at the end of Programme Increments through Solution Demonstrations. The Contractor shall be required to carry out Test Management across multiple engineering teams, including as a minimum: - release and deployment management; - lab/ Environment Planning, Change management; - Test Planning, sequencing, estimation and ability to re-plan to fit dynamic/ agile conditions; and - defect management tracking, triage and resolution. | Monthly report on trials progress updates | Monthly from Contract Award | Regular 5 Days to Review |

1.10	MORPHEUS GFA Lead.   MORPHEUS Projects must manage GFA in a fully aligned and sympathetic way to ensure optimum efficiency and to mitigate the emerging issue.  This will require a GFA strategy, cross-team agreements, co-ordination and overarching management of the GFA activities across the Projects through a dedicated GFA Lead.  This will be required from Contract Award for the duration of the Contract.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 1.10 | The Contractor shall provide GFA management to the MORPHEUS Projects. This will include as a minimum: - co-ordinating the GFA requirement across all of the MORPHEUS Projects; - reviewing all GFA requirements for all MORPHEUS Projects during procurement exercises engaging with the relevant Authority staff to identify the following: - where GFA will be sourced from; - that the GFA will be available at the required time, for the required period; - that there is a procedure in place for transport of GFA to the Contractor; and - that the appropriate Inventory Management tools are included in contracts which require GFA, for example Concordia. - once MORPHEUS Projects are On Contract, the Contractor will be responsible for ensuring Authority compliance with the relevant GFA requirements for each of the MORPHEUS Contracts; - at the conclusion of each of the Contracts, the Contractor shall be responsible for ensuring that GFA has been returned or destroyed as required by the MORPHEUS Project Lead. | Report on GFA position | From Contract Award until competition of Contract | Special Process during competitions with a meeting held specifically to review and confirm GFA obligations can be achieved |
| 1.10.1 | The Contractor shall support the GFA reporting. This shall, as a minimum, include: - fortnightly, present a short GFA update at the Lead’s Project ‘stand-up meeting; - fortnightly, present a formal report to the MORPHEUS Programme Manager Project Review; - monthly, present a formal Highlight Report at the One-Star MORPHEUS Programme Board; and - monthly, meet with each of the MORPHEUS Project Managers to review the GFA situation for each of their projects. Produce RODs for meetings where required. | Short presentation at the Project ‘stand-up meeting Formal report presentation at MORPHEUS Programme Manager Project Review Highlight Report presentation at the MORPHEUS One-Star Programme Board RODs from meeting with each MORPHEUS Project Manager | As per description | Regular 5 Days to Review |
| 1.10.2 | The Contractor shall engage with other MORPHEUS staff as required to support activities which shall as a minimum include: - maintaining the Schedule; - risk management; - assumptions management; - dependencies management; - budget forecasting process; and - stakeholder management. | Support to updates to other MORPHEUS activities | As required | Regular 5 Days to Review |
| 1.10.3 | The Contractor shall engage with the BATCIS Asset Management Team to ensure that the allocation and management of GFE is synchronised across the BATCIS range of Projects. | When required, attendance at the BATCIS Asset Team Meetings | As required |  |
| 1.10.4 | ## The Contractor shall engage with the MORPHEUS Programme Team to verify whether any GFA has any import, export, disclosure or intellectual property restrictions or requires any other necessary consents for use. ## The Contractor shall, where it is able to, assist the Authority with maintaining compliance with any restrictions placed upon any GFA. ## When appropriate, the Contractor is responsible for identifying the relevant trade controls, and working with the Authority to ensure all trade controls are addressed, in so far as they are reasonably able. The Contractor must refer to the Trade Controls Team or MOD Commercial Team for guidance, as appropriate. When appropriate, the Contractor shall consider all aspects of the import and export of controlled technology and goods. This will include the temporary export of such items for e.g. Trials; address how this import/ export process will be handled; and how the Contractor will fully document the controls. The Contractor shall review all GFA documentation. The Contractor shall draw up a Trade Control Plan (TCP), identifying areas where Trade Controls may or should be considered. The Contactor shall create proposals, including timelines, to address such controls. The Contractor shall agree milestones with the Authority to be delivered throughout the Programme. The Contractor shall work to implement the TCP to the agreed timelines. The Contractor shall identify any amendments or changes required throughout the delivery, and notify the Authority immediately once known. Both parties shall agree any changes required. | Identification of GFA restrictions and any necessary consents required Trade Control Plan (TCP) | In line with outputs of the Project Schedule | Add into the GFA approvals for Schedule 4 |
| 1.10.5 | The Contractor shall produce a MORPHEUS Project Schedule Change Impact Statement, as required, to assess the impact of any potential or upcoming change to the relevant MORPHEUS Project Schedule. This is to consider, as a minimum, the impact on the performance, cost and time of both the relevant Project, and other Programme Projects. | MORPHEUS Project Schedule Change Impact Statement | As required |  |
| 1.10.6 | The Contractor shall work with the Project Managers to ensure that GFA is being managed appropriately through the project life cycle – Pre Competition Phase, Competition Phase and Post Competition phase. The Contractor responsibilities at each are listed below: Pre Competition Phase. As part of the Competition Data Pack, the Contractor shall identify pertinent GFA. Subsequent to the identification of the GFA, the Contractor shall be responsible for: - validating any request by the Project Manager for GFA; - confirming with the Project Manager and recording the date and duration GFA is required, the quantity and the method of delivery/ consignment; - identifying and recording, with the Project Manager, any special considerations for Jigs, Tools and Test Equipment; - conducting a check on whether any GFA has a requirement for any necessary consents including, import, export, Intellectual Property Rights or restrictions upon disclosure and identifying what is necessary for compliance; - identification of availability of relevant of GFA for the date and duration it is required; and - if the GFA is not available from stock, notifying the MORPHEUS Project Lead and Commercial Lead that the Authority cannot meet this obligation. Competition Phase. As part of the procurement exercises for each of the MORPHEUS Projects, the Contractor shall review Tenderer’s GFA requests and validate whether or not the Authority can meet these obligations. The Contractor shall be responsible for: - validating any request by Tenderers for GFA with Authority staff, validating as a minimum, quantities, dates required and duration of the GFA holding; - identifying and recording, any special considerations for Jigs, Tools and Test Equipment from tenders; - conducting a check on whether any GFA has a requirement for any necessary consents including, import, export, Intellectual Property Rights or restrictions upon disclosure and identifying what is necessary for compliance; and - if the GFA is not available from Authority holdings, notifying the MORPHEUS Project Lead and Commercial Lead that the Authority cannot meet this obligation. Post Competition Phase. Once the Contract is let, then the Contractor shall: - manage the Authority GFA obligations; and - work with the Authority GFA lead to ensure that GFA is managed to meet Authority GFA obligations. For any additional GFA requests, the Contractor shall validate, approve and engage with Authority staff to meet the additional GFA requirements. The Contractor shall be, as a minimum, responsible for: - validating any request by any relevant Contractor for GFA with Authority staff, validating as a minimum, quantities, dates required and duration of the GFA holding; - identifying and recording any special considerations for Jigs, Tools and Test Equipment; - conducting a check on whether any GFA has a requirement for any necessary consents including, import, export, Intellectual Property Rights or restrictions upon disclosure and identifying what is necessary for compliance; - identification of availability of relevant of GFA for the date and duration it is required; and - if the GFA is not available from stock, notifying the MORPHEUS Project Lead and Commercial Lead that the Authority cannot meet this obligation. | Up-to-date and fully validated and agreed GFA List per MORPHEUS Project Contribution to MORPHEUS Projects Tender Evaluations, validating GFA requirements | As required | Special Process during competitions with a meeting held specifically to review and confirm GFA obligations can be achieved |

- Approvals.   To define, agree and deliver the underpinning evidence required to support all MORPHEUS approval submissions, including the Dismounted Situational Awareness (DSA) Project.  The endorsed evidence should be articulated into a concise, reasoned argument, embodied within a Business Case that clearly demonstrates the business need and associated time, cost & performance criteria to the Investment Appraisal Committee (IAC).  Key to this is early, continuous engagement and communication with the Scrutiny and Assurance communities along with Information Systems & Services (ISS), Joint Forces Command (JFC), Army HQ and Other Governmental Departments (OGDs) – Her Majesty’s Treasury (HMT) and Cabinet Office (CO)).

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 2.1 | The Contractor shall provide Approvals support to the MORPHEUS Programme, as a minimum this shall include: - acting as the day-to-day point of contact within the MORPHEUS Programme for Approvals advice and guidance; and - supporting the Authority Approval Lead and any other MORPHEUS Programme staff by providing direction and guidance on Approval processes which are relevant, examples may include MOD Scrutiny, Information Systems and Services Programme Management Office, Cost Assurance And Scrutiny, Defence Economics, Defence Procurement & Assurance Service, Front Line Commands, Her Majesty’s Treasury and Cabinet Office. | The provision of necessary advice and guidance as required by MORPHEUS Programme staff | On demand | Regular/ through overall monthly report |
| 2.1.1 | The Contractor shall attend a fortnightly Approvals Section Team Review providing updates on current work activity relating to approvals which shall as a minimum include: - risks; - issues; - assumptions; - dependencies; - timelines; - costs; and - escalations. | Updates relevant to areas identified in the description | Fortnightly from Contract Award | Regular 5 Days to Review |
| 2.1.2 | The Contractor shall review, update, manage and maintain as necessary the approvals strategy and plan, outlining the approach to approvals for the current phase and subsequent phases of the MORPHEUS Programme. The Contractor shall create an Integrated Assurance and Approvals Strategy and Plan (IAAP) in order to support the Review Note and any other Approvals submissions. The Contractor shall ensure this document is endorsed by scrutiny and DP&AS. The Contractor shall ensure that the IAAP is reviewed and updated prior to any approval such as Review Notes, Information Notes or Main Gate Business Cases. (see relevant GFI artefact at Schedule 7). | Up-to-date Integrated Assurance and Approvals Strategy and Plan (IAAP) | In line with outputs within the Schedule | Regular 20 Days to Review |
| 2.2 | The Contractor shall draft CAT A Approvals Submissions (Review Notes, Information Notes, Main Gate Business Cases) for the MORPHEUS Programme, working in conjunction with Authority staff in accordance with JSP 655 (noting a degree of customisation is often required as a result of engagement with key stakeholders). The Approvals Submissions shall be prepared for approval by the BATCIS Team Leader, and any other necessary stakeholders in time to allow submission in line with timelines in the Schedule. | MORPHEUS Review Note 4 MORPHEUS Review Note 5 MORPHEUS Information Note 2020 MORPHEUS Main Gate Business Case | As per Schedule | Special Process in Schedule 4/ 5. Reference Circulation Process |
| 2.2.1 | Not used. |  |  |  |
| 2.2.2 | The Contractor shall provide a Frequently Asked Questions (FAQs) document to support Approvals Business Cases (and Information Notes, if applicable). The FAQs shall provide further background and detail that could not be included within the Review Note and are considered evidence by Scrutiny. The Contractor shall author the FAQ documents, utilising input from the MORPHEUS stakeholders. (see relevant GFI artefact at Schedule 7). | MORPHEUS Review Note 4 FAQs MORPHEUS Information Note 2020 MORPHEUS Main Gate | As per Schedule | Special Process in Schedule 4/ 5 |
| 2.2.3 | The Contractor shall manage the circulation and review process for Approvals Submissions (Review Notes, Information Notes, Main Gate Business Cases) from early draft until receipt of an Out-Letter. The Contractor shall ensure all comments from circulations are tracked and recorded within an appropriate tool (for example Microsoft Excel). The Contractor shall co-ordinate and assist in the generation of responses, ensuring they are endorsed by the MORPHEUS Programme Manager. The Contractor shall support and co-ordinate the production of any additional material required as part of any approval submission (for example, Clarification Statements). (see relevant GFI artefact at Schedule 7). | Up-to-date Approvals Submission Action Tracker | From Contract Award | Special Process in Schedule 4/ 5 |
| 2.2.4 | The Contractor shall be responsible for managing and maintaining a MORPHEUS Approvals Plan for each Approvals Submission, covering the period from early Approvals Submission drafts through to Out-Letter received, that shows all approval activity over time (including but not limited to relevant approval boards), taking into account JSP 655 and the availability of senior MOD and Other Government Department (OGD) stakeholders required to support this. (see relevant GFI artefact at Schedule 7). | MORPHEUS Approvals Plan | From Contract Award | Regular 20 Days to Review |
| 2.2.5 | The Contractor shall engage with the MOD Scrutiny Community prior to, and during the period when they draft the Scrutiny Report for MORPHEUS Review Note and Main Gate Business Cases. As a minimum the Contractor shall: - engage with the Scrutiny community to gain early sight of the report as it is being drafted; - robustly challenge the MOD Scrutiny community on any statements within the draft Scrutiny Report that are inaccurate in a timely manner; - ensure all Authority comments against the draft Scrutiny Report are tracked and responses recorded within an appropriate tool (for example Microsoft Excel); and - ensure the Scrutiny Report submitted as part of the draft IAC circulation is as accurate as possible, with all inaccuracies addressed (or mutual agreement to the contrary) in time for the final IAC circulation. (see relevant GFI artefact at Schedule 7). | Scrutiny Report Action Tracker Agreed Scrutiny Report RN4 Agreed Scrutiny Report Main Gate | As per Schedule | Regular/ through overall monthly report |
| 2.3 | The Contractor shall support the identification, articulation, generation and review of appropriate evidence required to support Review Note and Main Gate submissions through the activities details below at Section 2.3.1 to Section 2.3.3. |  |  |  |
| 2.3.1 | The Contractor shall work with the MORPHEUS Management Team and Project Managers to review and update as appropriate the scope of the approval and the associated evidence required. The activity shall draw out the evidence requirement for each project, and define the scope that forms part of the underpinning evidence to support the RN. The Contractor shall provide advice and guidance to the MORPHEUS Management Team and Project Managers as to the most appropriate means of evidence, including the appropriate use of tools and techniques. As a minimum this shall include, the use of cost models, Combined Operation Effectiveness and Investment Appraisal (COEIA), Modelling, Options Analysis and Procurement Strategies. This shall be captured within a Review Note or Main Gate Evidence Summary document that covers as a minimum for each Project/ Aspect the following: - a brief description; - the evidence believed required; - suggested method to generate the evidence; - likely timeline to deliver the evidence; and - who is required. (see relevant GFI artefact at Schedule 7). | Review Note Evidence Summary Main Gate Evidence Summary | From Contract Award until Main Gate IAC | Regular 20 Days to Review |
| 2.3.2 | The Contractor shall run MORPHEUS evidence Working Groups, including leading up to Review Note 4 (a planning assumption of six per year should be used), ensuring, that as a minimum, these are supported by the appropriate Scrutiny and Assurance communities in order to drive the progressive assurance of evidence. The Contractor must ensure that engagement with the Scrutiny and Assurance communities is maintained regularly to avoid delays to approvals. | Evidence Working Groups | From Contract Award until Main Gate Business Case submission | Monthly Report |
| 2.4 | The Contractor shall be responsible for managing the ISS Assurance Review Board (ARB) process required as part of Information Note, Review Note and Main Gate Business Case submission process. For Information Notes, a less formal 2* Review may be acceptable to ISS. | Review Note 4 submitted to ARB Information Note 2020 submitted to ARB Main Gate Business Case submitted to ARB | As per Schedule | Monthly Report |
| 2.4.1 | The Contractor shall ensure the ISS ARB Assurance Report is completed and approved by the relevant stakeholder as part of the ARB submission. This requires the coordination and engagement of the appropriate MORPHEUS, Army HQ, DE&S and ISS stakeholders to complete to obtain their approval. (see relevant GFI artefact at Schedule 7). | ARB Assurance Report | As per Schedule | Regular 20 Days to Review |
| 2.5 | The Contractor shall support the Approvals stakeholder engagement required as part of the Approvals submission process alongside the Approvals Lead (a planning assumption of six per year should be used). As a minimum, this shall include the following: provision of briefing sessions, presentations, workshops and meetings on information relevant to the stakeholder community being engaged, held at various MOD locations. Due consideration shall be given to the MORPHEUS Briefing Pack when preparing these materials to ensure coherence across MORPHEUS. | Stakeholder Engagement | From Contract Award | Monthly Report |
| 2.5.1 | The Contractor shall provide approval briefings to the MORPHEUS stakeholder community, up to Ministerial Level. Approvals briefings shall as a minimum: cover the content of an approval and its general progress, any risks, issues, assumptions, dependencies, timelines, costs and escalations. The approval briefing should be tailored to suit the audience. | Approval briefings | 2 per month from Contract Award | Monthly Report |

3.0	Cost Estimation.   The Contractor shall be required to produce Whole Life Cost (WLC) forecasts, including the provision of suitable and auditable evidence to support cost scrutiny and assurance.  The Contractor shall underpin this by the maintenance and continued development of the MORPHEUS Cost Model, in order to support: MOD Financial Processes; Investment Decisions; Investment Appraisals; MOD Option process; and Commercial price evaluations.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 3.1 | The Contractor shall deliver whole life cost forecasts and/ or cost analysis, broken down at an appropriate level and in line with JSP 507 and JSP 655, against the following deliverables in Section 3.1.1 to Section 3.1.5. To enable the delivery of the required cost estimating physical documentations, the Contractor is required to deliver effective stakeholder management in the following areas as a minimum: - conducting regular engagement with the MORPHEUS Project Leads and Industry participants in competitions or suppliers to understand and capture cost assumptions; - supporting the engagement with assurance and scrutiny communities, for example CAAS, Defence Economics, Scrutineers etc.; - supporting the engagement with the Front Line Commands (FLC) including both budget owner and Senior Responsible Owner (SRO); - supporting to Authority Management Reviews relating to cost; and - providing familiarisation of the MORPHEUS cost estimate and model to the team. | MORPHEUS stakeholder community effectively engaged. Attendance and contribution at Authority Reviews which include cost as a topic Familiarisation Activities | As required | Monthly Report |
| 3.1.1 | The Contractor shall support the MOD Financial Processes for all MORPHEUS Projects including, as a minimum: - provide support to the Forecast of Outturn (FOO) process; - provide support to the Quarterly Review of Project Costs (QRPC) process; and - provide support to National Audit Office (NAO) audits. | Review of MORPHEUS Project Costs | As required | Monthly Report |
| 3.1.2 | The Contractor shall provide support to the MORPHEUS Approvals Team which shall as a minimum include the following activities: - providing support to the affordability case for all MORPHEUS approvals including, as a minimum, delivery of forecast costs at an appropriate breakdown and associated briefing material in line with JSP 655; - providing support to the Value for Money (VfM) case for all MORPHEUS Approvals including, as a minimum, Should Cost Estimates and Investment Appraisals as required in line with JSP 507 and Defence Economics guidance; - providing support to the independent assurance requirements of Cost Assurance and Analysis Services (CAAS) including as a minimum: - Verification and Validation (V&V); - Optimism Bias; and - Independent Cost Estimates (ICE). | Affordability Case for MORPHEUS Approvals Team VfM Case | In line with Section 2.0 (Approvals) of this SOR | Monthly Report |
| 3.1.3 | The Contractor shall provide Cost Estimation support to the MORPHEUS Project Reviews including as a minimum: - providing support to cost assessments including as a minimum cost-benefit and sensitivity analysis of internal MORPHEUS Project options to inform procurement and commercial strategies; - providing support to the MORPHEUS Team internal budget and control processes, including as a minimum, assumptions management; and - providing appropriate briefing material for any stakeholder engagement at all levels to enable informed decision making. | Cost Analysis Report | As required by per MORPHEUS Project | Monthly Report |
| 3.1.4 | The Contractor shall provide Cost Estimation Support to the MOD Options Process, this shall include as a minimum: - providing responses to cost information requests from FLCs including appropriate caveats; and - providing MORPHEUS cost forecasts (and associated briefing material) to support Strategic Defence and Security Review (SDSR) and Annual Budgetary Cycle (ABC) options. | Response to FLC requests MORPHEUS Cost Forecasts | As per Authority agreed timescales | Monthly Report |
| 3.1.5 | The Contractor shall provide Cost Estimation support to each of the MORPHEUS Projects Commercial Price Evaluation process, this shall include as a minimum: - supporting the creation of tender evaluation strategies for relevant MORPHEUS Projects, this will involve: - creating, updating and maintaining the cost evaluation criteria for the tender stage of procurements for the MORPHEUS Projects; - advising the MORPHEUS Project Managers and the BATCIS Finance Team on the affordability evaluation process for each of the MORPHEUS Projects; and - engaging with the Scrutiny Community of the Tender Evaluation process for any of the MORPHEUS Projects. - undertaking an affordability assessment of each of the tenders during the procurement of a MORPHEUS Project; - undertaking the evaluation of the cost and pricing elements of tenders during procurement exercises for the MORPHEUS Projects with the support of BATCIS Finance Team; - undertake and support to the affordability and VfM assessments of MORPHEUS Project tenders, including top-down cost comparison (for example benchmarking) if applicable; - recording any relevant comments to tenders during the assessment phase; and - providing feedback and scores from evaluations undertaken for Tender Assessments Panels. |  | As required by per MORPHEUS Project | Monthly Report |
| 3.2. | The Contractor shall be responsible for the maintenance and operation of the MORPHEUS Cost Model (@Risk based Monte Carlo model), including functional updates, such that the Contractor can deliver the required probabilistic cost forecasts. The Contractor will be responsible for the key cost model inputs which shall include as a minimum: - a robust Cost Data Assumptions List (CDAL), containing as a minimum: - quantified three point estimates against an appropriate breakdown structure; - the CDAL is required to be underpinned by an auditable evidence trail at an appropriate Data Readiness Level (DRL); and - the CDAL must also be consistent with MORPHEUS Programme third order assumptions (3OAs) and the MORPHEUS Master Data Assumptions List (MDAL). - the interpretation and translation of the MOPRHEUS Programme Risk Register and Schedule to meet the input requirements of the MORPHEUS Cost Model. Working with the schedule and risk managers, this may include as a minimum: - rolling up elements of the Schedule to an appropriate level; and/ or - making decisions on how to best reflect schedule risk within the forecast costs. - the use of appropriate accounting treatments (escalation, VAT, foreign exchange, etc) endorsed by the appropriate MOD department. | Robust MORPHEUS Cost Data Assumptions List | As required by per MORPHEUS Project | Monthly Report |
| 3.3 | The Contractor shall provide a Monthly Report on Cost Estimation work carried out and shall include the following headings, as a minimum: - Monthly Summary; - Stakeholder Engagement; - FOO input; - Approvals input; - Project Reviews; and - Cost Model. | Monthly Report | Monthly from Contract Award | Regular 5 day review |

4.0	MORPHEUS Project Management.   The Contractor shall provide Project Management (PM) resource to support the Authority relevant MORPHEUS Project Leads in the management and delivery of the relevant MORPHEUS Projects.  The relevant MORPHEUS Projects include: System Integrator (SI), MORPHEUS Test and Reference Centre (MTRC), Battlefield Management Application (BMA), Platform Installation and Fielding (PI&F), Enduring Joint Programme Organisation (eJPO) and Managed Service Providers (MSPs).

Note #1:  This support excludes support to the Transition Partner Contract (articulated elsewhere in the SOR).

The Contractor PM resource shall utilise generic project management skills and techniques (detailed in the Section 4.1 Table below) and other elements of the Project Lifecycle detailed in the appropriate follow-on Sections (SI, MTRC, BMA, PI&F,  eJPO, MSPs and Trials).

In undertaking the project management support, the Contractor shall ensure that they comply with:

- ISS PMO policy;

- relevant MORPHEUS Programme Controls;

- JPO policy & procedures (once project suppliers are On Contract); and

- with Good Industry Practice on P3M, as captured in APM Body of Knowledge, PRINCE 2 and Managing Successful Programmes.

Project Leads are Crown Servants that are accountable for a project and/ or an activity within the MORPHEUS Programme.

Note #2:  Throughout Section 4, references are made to a number of PM products and processes – access to these documents can be found within the GFI and Product Descriptions listed at Schedule 19.

Generic Activities applicable to all MORPHEUS Projects

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.1 | For each of the relevant MORPHEUS Projects (SI, MTRC, BMA, PI&F, eJPO, MSPs, OTP and Trials) the generic Project Management support shall include as a minimum all sections from 4.1.1 to 4.1.11c: Note: This excludes support to the Transition Partner Contract. | Project management for the relevant MORPHEUS Projects (including SI, MTRC, BMA, PI&F, eJPO, MIDaC & Fielding, OTP, Trials and MSP’s conducted in compliance with the defined policy and procedures | 26 Nov 18 and continues until end of contract | Monthly Report |
| 4.1.1 | The Contractor shall create, manage and maintain the appropriate relevant MORPHEUS Project Work Breakdown Structure (WBS). The Contractor shall update the WBS in line with any feedback from the Authority. | An up-to-date relevant MORPHEUS Project WBS | As required from contract award until end of contract | Regular Review Process 5 Working Days to Review |
| 4.1.2 | The Contractor shall create, manage and maintain the relevant MORPHEUS Project Schedule (non-published on EPM) by, including as a minimum: - all work packages defined in the relevant MORPHEUS Project Work Breakdown Structure; - all major decision points - including Milestones, key Gateway Reviews; - progress and technical reviews; - all Deliverables; - all task dependencies; - all schedule assumptions; - all schedule constraints; - the critical path; - fully resourced plan and costs, and task durations; - risks and risk mitigation actions; - when amending the relevant MORPHEUS Project Schedule, raise any changes which affect the Schedule through the Change Request process (see relevant artefact in the GFI List); and - provide input into the Schedule. Where appropriate the Contractor shall utilise Enterprise Project Management (EPM) in the delivery of this task. | Input to the relevant MORPHEUS Programme Schedule via the schedule Change Request process Input into the relevant MORPHEUS Programme Schedule via fortnightly review meetings Draft Project Schedule (non published on EPM) Mature Project Schedule (non published on EPM) Update and maintain Project Schedule (non published on EPM) | As required from contract award until end of contract As required from contract award until end of contract Dec 18 Jan 19 As required from Jan 19 until end of contract | Regular Review Process 10 Working Days to Review |
| 4.1.2a | The Contractor shall provide fortnightly updates to the appropriate relevant MORPHEUS Project Lead on progress with the relevant MORPHEUS Project through providing a relevant MORPHEUS Project Dashboard in compliance with the relevant MORPHEUS Projects Management Information Dashboard (see relevant GFI artefact at Schedule 7). | Relevant MORPHEUS Project Management Information Dashboard | Fortnightly from contract award until end of contract | Monthly Report |
| 4.1.3 | The Contractor shall provide a Schedule Impact Statement (see relevant PD artefact at Schedule 19) to the relevant MORPHEUS Project Lead of any potential or upcoming change. The statement should consider any performance, cost and time impact to all relevant MORPHEUS Projects and the Programme. | Impact Statement | As required from contract award until end of contract | Monthly Report |
| 4.1.3a | The Contractor shall ensure all changes to projects are managed in accordance with the MORPHEUS Change Control Process (see relevant GFI artefact at Schedule 7). | MORPHEUS Change Control Process | As required from contract award until end of contract | Monthly Report |
| 4.1.4 | The Contractor shall carry out the relevant MORPHEUS Project Resource Allocation Planning (RAP). See relevant PD artefact at Schedule 19. As a minimum the Contractor shall identify the required resources to deliver the Project in conjunction with the relevant MORPHEUS Programme Controls Team, ensuring these are captured within the Project schedule, examples include: - Internal Resources; and - External Resources. | Up-to-date resource requirement for the relevant MORPHEUS Project Schedule Attendance at the relevant MORPHEUS Programme Schedule update meeting Resource Allocation Plan (RAP) In association with the project controls team, update/ maintain resources in the Schedule | As required from contract award until end of contract Fortnightly from contract award until end of contract | Regular Review Process 10 Working Days to Review |
| 4.1.5 | The Contractor shall identify and capture the relevant MORPHEUS Project assumptions. The relevant MORPHEUS Project assumptions shall be recorded in the assumptions tab of the PM Workbook (see relevant GFI artefact at Schedule 7). The Contractor shall apply the relevant MORPHEUS Assumption Management (AM) Process (see relevant GFI artefact at Schedule 7). | An up-to-date Assumptions Log in the relevant MORPHEUS Project PM Workbook. | Fortnightly from contract award until end of contract | Monthly Report |
| 4.1.5a | The Contractor shall review all of the relevant MORPHEUS Project assumptions with the appropriate relevant MORPHEUS Project Lead. The review shall as a minimum consider the following: - key milestones and identify new assumptions/ opportunities against those; - review progress of the delivery of mitigation actions and ensure that they are having the desired assumption reduction impacts; - provide Project Lead approval for escalation of assumptions; - provide Project Lead acceptance that the proposed assumptions will recommended for closure or transfer to issue at the next relevant MORPHEUS Assumption Panels (MAPs); and - perform a quality assurance review of relevant MORPHEUS assumptions for the function. | Participation in the Project Leads Reviews | Day before the relevant MORPHEUS Projects Schedule Review | Monthly Report |
| 4.1.5b | The Contractor shall attend and support the relevant MORPHEUS Project Lead at the relevant MORPHEUS Assumption Panel (MAP) in compliance with the relevant MORPHEUS Assumption Management Process. | Attendance at the appropriate relevant MAP | Monthly | Monthly Report |
| 4.1.5c | Dependencies. The Contractor shall maintain the project dependencies within the PM Workbook (see relevant GFI artefact at Schedule 7), escalating appropriately to the Programme Level Dependency Log. The Contractor shall participate in cross-Project Dependency Reviews. The Contractor shall manage the Project dependencies that exist with the other MORPHEUS Projects e.g. MTRC, SI, PI, MSP Applications, DIO and LSRC. | Participation in the Project Leads Reviews | Day before the relevant MORPHEUS Projects Schedule Review | Monthly Report |
| 4.1.6 | The Contractor shall identify, create, capture, manage and maintain the relevant MORPHEUS Projects risks and issues by undertaking the following activities as a minimum: - recording Project risks and issues in the PM Workbook; - escalating changes to existing risks or issues and any new risks or issues which are created or identified to the appropriate relevant MORPHEUS Project Lead for endorsement; - providing all new or amended risks to the relevant MORPHEUS Risk Manager at the weekly engagement; - capturing and maintaining cross Defence Lines of Development (DLOD) risks within ARM; - input and maintain robust basis of estimates for risks against performance cost & time, and implement a Risk Mitigation Plan for each risk; - identify resources required to manage individual risks; and - apply effective risk management techniques, in accordance with the ASG Identify, Assess, Plan, Do, Review, cycle process. | Up-to-date the relevant tabs of the PM Workbook Update ARM in conjunction with the relevant MORPHEUS Risk Manager | Fortnightly from contract award until end of contract As required from contract award until end of contract | Monthly Report |
| 4.1.6a | The Contractor shall participate in the fortnightly risk and issue review providing input on the relevant MORPHEUS Project risks and issues. | Participation in the appropriate risk and issue review | Fortnightly from contract award until end of contract | Monthly Report |
| 4.1.7 | The Contractor shall work with the Capability Manager (CM) to ensure the relevant MORPHEUS Project outputs are synchronised with cross-DLOD dependencies. The Contractor shall ensure Authority PM and CM reviews are arranged for the relevant MORPHEUS Project with the relevant Capability Manager. The Contractor shall as a minimum: - agree the agenda for the meeting with the Authority PM and CM; and - arrange the location for the meeting. The Contractor shall conduct the PM and CM review in accordance with the Governance Schedule (see relevant PD artefact at Schedule 19). The Contractor shall provide a brief to the relevant MORPHEUS Project Lead on any emerging issues as required. | Organising and participating in the PM and CM review When required attendance at the Monthly relevant MORPHEUS Capability Integration Working Group (CIWG) | One Month prior to CIWG from contract award until end of contract As required from contract award until end of contract | Monthly Report |
| 4.1.8 | The Contractor shall provide the relevant MORPHEUS Project Lead with financial input data to support the MORPHEUS Project Budget Forecasting requirement. The Contractor shall provide Appropriate Financial Data for input into the relevant MORPHEUS Forecast of Outturn (FOO) return. The Contractor shall provide details of the resources consumed (accruals) using the most accurate and up-to-date figures available for the Project. The accruals must be based on the most accurate forecast using past data, along with any relevant new information in respect of resources not yet consumed. | All requisite data to the Authority relevant MORPHEUS Project Leads for input to the FOO Review | Monthly from contract award until end of contract | Monthly Report |
| 4.1.9 | The Contractor shall maintain and complete the Project History and Learning From Experience (LFE) sections contained in the relevant MORPHEUS PM Workbook (see relevant PD artefact at Schedule 19). The Contractor shall capture LFE as events occur and enter it in the LFE section of the relevant MORPHEUS PM Workbook. The Contractor shall plan and conduct periodic LFE workshops with the appropriate relevant MORPHEUS Project Lead and any other relevant stakeholders, at key stages of the project lifecycle (i.e. at the end of the competitions). LFE review stages must be agreed with the relevant MORPHEUS Project Lead one month in advance and included in the Project Schedule. | Input to the LFE section of the PM Workbook Input to the project history section of the PM Workbook Learning From Experience workshop | As required from contract award until end of contract As required from contract award As required from contract award until end of contract end of contract | Monthly Report |
| 4.1.10 | The Contractor shall conduct relevant MORPHEUS Project stakeholder management (in accordance with the stakeholder management plan within the GFI list at Schedule 7). As a minimum this shall include: - creating, updating, managing and maintaining a comprehensive list of stakeholders to the relevant MORPHEUS Project, identifying in particular key stakeholders within the PM Workbook (see relevant artefact in the GFI List); - maintain regular communications with all necessary stakeholders, with a particular focus on key stakeholders; - providing weekly input to the relevant MORPHEUS Programme Stakeholder Management Plan by engaging with the MORPHEUS Programme Stakeholder Manager; - recording the stakeholders ability to effect the relevant MORPHEUS Project; and - complying with Industry best practise and internal ISS procedures relating to stakeholder engagement. | Input to the Stakeholder Management section of the relevant MORPHEUS Project PM Workbook Weekly input to the MORPHEUS Programme Stakeholder Management Plan | As required from contract award until end of contract As required from contract award until end of contract | Monthly Report |
| 4.1.11 | The Contractor shall attend, participate and input into all of the requisite meetings relating to the relevant MORPHEUS Project Governance (see relevant PD artefact at Schedule 19) for this Contract. | Attendance, participation and input to all of the relevant MORPHEUS Project meetings | Fortnightly from contract award until end of contract | Monthly Report |
| 4.1.11a | The Contractor shall on a fortnightly basis provide a short project update at the Project ‘stand-up’ meetings. See relevant PD artefact at Schedule 19. | An update at the Project ‘stand-up meetings’ on the relevant MORPHEUS Project | Fortnightly from contract award until end of contract |  |
| 4.1.11b | The Contractor shall on alternate weeks to the Project ‘stand-up meetings’, present a formal report using the MORPHEUS Project Management Information Dashboard (see relevant GFI artefact at Schedule 7) on the relevant MORPHEUS Project to the MORPHEUS Project Leads at the Project Review. See Governance Schedule 8. | Presentation of a formal report on the relevant MORPHEUS Project at the relevant MORPHEUS Project Lead’s Project Review Meeting. | Fortnightly from contract award until end of contract |  |
| 4.1.11c | The Contractor shall provide input and support to any other reviews which require information concerning the progress, or any other information, on the relevant MORPHEUS Project. The meetings may include, but are not limited to, the Programme Reviews, CIWG and One Star Reviews. See relevant PD artefact at Schedule 19. | Input to any meetings which require information concerning the relevant MORPHEUS Project. | As required from contract award until end of contract |  |

  - MORPHEUS Project - System Integrator (SI) Specific PM Requirements.   The System Integrator will (1) support the Co-ordinating Design Organisation (CDO) in developing future designs and requirements for MORPHEUS beyond the EvO baseline through provision of system development and integration expertise; (2) deliver integrated systems that meet the CDO’s requirements within an agreed time, cost and performance envelope; (3) optimise the MORPHEUS solution across all Defence Lines of Development (DLOD); and (4) respond to emerging user needs as directed by the CDO.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Systems Integrator (SI) Project Manager (PM) in delivering the Systems Integrator Project through its lifecycle.

The SI Project’s lifecycle shall include capturing and updating the requirement and creation and updates to associated documentation required to run a competition (Pre Competition Phase, Section 4.2.1), project managing the competition (Competition Phase, Section 4.2.16) and project managing the System Integrator Contractor (Post Competition Phase, Section 4.2.24).  The System Integrator PM shall utilise generic project management tools and skills in Section 4.1 to deliver the Systems Integrator Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.2.1 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the Authority Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Sections 4.2.1 to 4.2.15 inclusive. |  |  |  |
| 4.2.2 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to start the procurement process. The Early Competition Data Pack will include, as a minimum: - a Procurement Strategy; - mature wording for Prior Information Notice (PIN), including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS SI Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS SI Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the Project, for example security exemptions; - a mature question set for the Pre-Qualification Questionnaire (PQQ); - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially-approved scoring system; - a draft Statement of Requirement (SOR); - a draft acceptance process for the deliverables or outputs to the Project; - when relevant a draft assurance process for the deliverables or outputs to the Project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 4.2.2.a | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. | Final Competition Data Pack | As per Schedule | Schedule |
| 4.2.3 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the MORPHEUS SI Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the MORPHEUS SI GFA List. The Contractor shall provide as a minimum for the MORPHEUS GFA List: - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. See relevant PD artefact at Schedule 19. | Draft MORPHEUS SI Project GFA List Final MORPHEUS SI Project GFA List As required, attend meetings and engage with the MORPHEUS GFA Manager | As per Schedule As required from Nov 18 until end of contract | Regular 20 Working Days (Schedule 4 Special) |
| 4.2.4 | The Contractor shall collate the information required to produce a PIN, in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN, by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. See relevant PD artefact at Schedule 19. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 4.2.5 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the MORPHEUS SI Project, ensuring compliance with the MORPHEUS Procurement Strategy. The Contractor shall ensure that the MORPHEUS Project Lead for the MORPHEUS SI Project approves all updates/ changes to the MORPHEUS SI Procurement Strategy. The MORPHEUS SI Procurement Strategy shall be compliant with the Procurement Strategy supplied as GFI. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 4.2.6 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the MORPHEUS SI Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 4.2.7 | The Contactor shall support the BATCIS Commercial Team when developing the MORPHEUS SI Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - Any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | MORPHEUS SI Contract Notice | As per Schedule | Regular 5 Working Days |
| 4.2.8 | The Contractor shall create, develop and update the MORPHEUS SI supplier selection project, security and technical questions for the MORPHEUS SI Dynamic Pre-Qualification Questionnaire (DPQQ). The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate MORPHEUS Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical questions Mature DPQQ PM/ Technical questions | As per Schedule As per Schedule | Schedule 5 |
| 4.2.9 | The Contractor shall create, develop and update the MORPHEUS SI supplier selection evaluation criteria for the project, security and technical questions for the MORPHEUS SI DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The contract shall produce a list of the evaluators for the assessment of the MORPHEUS SI DPQQ. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.2.10 | The Contractor shall provide a SOR for the MORPHEUS SI Project. The Contractor shall engage with all relevant stakeholders when developing the MORPHEUS SI SOR to ensure that all necessary aspects of delivery are considered. The Contractor shall agree the SOR format with both the BATCIS Commercial Team and the relevant Project Lead. The SOR shall consider the SI Project through the relevant project lifecycle and consider all relevant DLOD areas. As a minimum the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 4.2.11 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the MORPHEUS SI Project. This shall include as a minimum: - the approved MORPHEUS SI SOR; - timelines for activity during the procurement; - providing project management input to the MORPHEUS SI Contract including as a minimum: - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance. ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS SI tender assessment questions; and - the MORPHEUS SI tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 4.2.12 | The Contractor shall create, co-ordinate, update, manage and maintain the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS SI Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS SI Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the Authority Commercial Officer. The Contractor shall ensure that the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS SI Project additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS SI Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least 10 (ten) working days prior to the release of the Tender. | Draft the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS SI Project Mature the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS SI Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.2.13 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the MORPHEUS SI Project. The Contractor shall secure any relevant security exemptions with the support of the Authority Commercial Officer. See relevant GFI artefact at Schedule 7. | MORPHEUS SI Security Aspects Letter | As per Schedule | Schedule 5 |
| 4.2.14 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the MORPHEUS SI Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority SI PM | As per Schedule | Monthly Report |
| 4.2.15 | The Contractor shall at the direction of the MORPHEUS Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the MORPHEUS SI Project, this may as a minimum include: - Industry Days, i.e. Bidder Conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/ As agreed with MORPHEUS Project Lead |
| 4.2.16 | Competition Phase. The Contractor shall ensure the delivery of the competition phase by co-ordinating and managing the delivery of the tasks from Section 4.2.16.1 to Section 4.2.23. |  |  |  |
| 4.2.17 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include as a minimum: - once provided clarification questions from Industry by the Authority Commercial Officer, obtaining a response from the relevant Subject Matter Expert within 3 (three) working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry clarification questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 4.2.18 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, noting the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate, manage and/or undertake the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinating and manging the Authority non-commercial clarification questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements Clear audit trail of Authority clarification questions during the tender assessment phase List of negotiation topics for each tender, if required RODs from the MORPHEUS SI Tender Assessment Panel | As per the Schedule As per the Schedule | Monthly Report Regular 5 Working Days |
| 4.2.19 | At the direction Authority SI PM, the Contractor shall contribute/ co-ordinate Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) in the form of a Bidders Conference. | MORPHEUS SI Project Bidders Conference | As per the Schedule | Regular 5 Working Days |
| 4.2.20 | The Contractor shall provide support to the MORPHEUS SI Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation list of attendees Negotiation Action List Negotiation RODs | As per the Schedule | Regular 5 Working Days |
| 4.2.21 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinating and manging the Authority non-commercial clarification questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs are taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase Record of Decisions from the MORPHEUS SI tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 4.2.22 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19, and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the MORPHEUS Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 4.2.23 | The Contractor shall provide support to the Contract Award phase of the MORPHEUS SI Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the MORPHEUS SI Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender de-brief packs Attendance and contribution to Tender debrief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 4.2.24 | Post Competition Phase. The Contractor shall manage the Activities set out between Section 4.2.24.1 and Section 4.2.29. |  | As per Schedule |  |
| 4.2.25 | The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS SI and the Authority utilising PM tools and techniques, giving due consideration to the provisions and requirements of the MORPHEUS SI Contract. If any dispute arises with the MORPHEUS SI, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and Systems Integrator MORPHEUS SI Monthly Report Relationship Management Section | Monthly up to end of PSS contract | Regular 10 Working Days |
| 4.2.26 | The Contractor shall manage any changes to the MORPHEUS SI Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the MORPHEUS SI SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the MORPHEUS Change Control Procedure | As required | Regular 20 Working Days |
| 4.2.27 | The Contractor shall manage delivery of the MORPHEUS SI. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the MORPHEUS SI Contract; - engaging with the MORPHEUS SI to address any queries regarding deliverables and any issues with the delivery of the MORPHEUS SI Contract; and monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the MORPHEUS SI for improvements to the Contract; and - engaging with an Authority Project Manager to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.2.28 | The Contractor shall engage with the MORPHEUS GFA Manager to ensure the timely delivery of all Authority obligations under the MORPHEUS SI Contract including post contract changes, updates and validations as per Section 4.2.3. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the MOPRHEUS SI Contract | Monthly up to end of PSS contract | Monthly Report |
| 4.2.29 | In addition to MORPHEUS Project Governance meetings, the Contractor shall provide co-ordination and support to relevant SI contract governance meetings. | Formal monthly report Compliance with the MORPHEUS SI Project Governance Schedule | As required up to end of PSS contract | Monthly Report |

4.3	MORPHEUS Test and Reference Centre (MTRC) Specific PM Requirements.   The MTRC will provide independent verification and other roles such as experimentation and reference builds.  This will include the following procurements:

- MTRC facility (Interim and Enduring) - the Interim facility will be used until the procurement of the Enduring MTRC facility, to ensure that testing activity during EvO will not be interrupted.  It is proposed that the Interim facility requirement be met by the Land Systems Reference Centre (LSRC) located in Blandford, Dorset.  The Enduring facility will be an Authority-owned and managed capability that undertakes independent test, reference and assurance activities on behalf of the Authority.  It is intended to develop an enduring capability for Test & Reference within the Defence Estate.  The MTRC functions will include the maintenance of current in-service MORPHEUS systems, support the development of the next MORPHEUS system baseline and enable innovation through experimentation for future capability deliveries.

- MTRC Initial Staff (Architecture Conformance) will require four Full Time Employees (FTEs) to assess the testability of the EvO Architecture at the beginning of the Design Phase.

- MTRC Technical Staff will provide the manpower resource necessary to undertake all MTRC Functions in the MTRC building.

- MTRC Test Equipment will focus on procuring infrastructure (GFX and/ or new buy) that will equip the MTRC building to reflect the capability that the TP has designed.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Test and Reference (MTRC) Project Manager (PM) in delivering the MTRC Project through its lifecycle.

The MORPHEUS Test and Reference Project’s lifecycle shall include capturing and updating the requirement, and creation and updates to associated documentation required to engage the Defence Infrastructure Organisation (DIO) to secure a future MTRC facility.  In addition, the Contractor shall manage the iMTRC requirement via the LSRC contract during its lifecycle and manage the Future MTRC requirement once operational.  The Contractor will manage and support future procurement activities associated with the establishment of the MTRC, whether the Interim and/ or Enduring MTRC capability.  These activities may include the procurement(s) of facility, personnel, equipment and/ or test services.  The procurement(s) will involve pre-competition, competition and post-competition (management) activities.  The MTRC PM shall utilise generic project management tools and skills in Section 4.1 to deliver the MTRC Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.3.1 | iMTRC Requirement. The Contractor shall provide the MORPHEUS Project Management Support to the LSRC for the iMTRC requirement. The Contractor shall manage the following PM activities which include as a support to managing the contract, support to compliance/ governance processes, ensuring the LSRC Contractor meets its contracted deliverables/ deadlines with respect to the iMTRC element of the Contract. Whilst achieving this, the Contractor shall monitor & control the LSRC elements of the Contract, maintaining a focus on deliverables to ensure that the Project stays on track, and recommend corrective action to the MORPHEUS Project Lead and assist the LSRC team with implementation once it has been approved. | Support to managing the contract | As per Schedule As per Schedule | Schedule 5 |
| 4.3.2 | The Contractor shall manage the day-to-day relationship with the LSRC Team and LSRC Contractor utilising PM tools and techniques in Section 4.1. | Formal report | As per Schedule | Schedule 5 |
| 4.3.3 | The Contractor shall work with the LSRC team to implement and manage any changes or additions to the SOR to achieve project outputs, including as a minimum: - provide project/ technical input to the iMTRC requirement contained within the LSRC contract amendments if required; and - updating the iMTRC elements of the Statement of Requirement (SOR) | Update the SOR | As required | Schedule 5 |
| 4.3.4 | The Contractor shall co-ordinate the acceptance of the iMTRC deliverables, including as a minimum: - evaluating operational and technical performance indicators (e.g. KPI) against the Contract Requirements. The Contractor shall provide a recommendation to the Project Lead on the acceptability of the deliverable. | Formal report | As per Schedule | Schedule 5 |
| 4.3.5 | The Contractor shall provide supporting evidence for any iMTRC issues that arise during the course of the LSRC Contract; including as a minimum: - escalation in a timely manner where appropriate; and - provide advice to the Authority Project Lead on the acceptability and impact of alternative solutions and/ or proposals from the LSRC team and/ or Contractor. The Contractor shall provide support to any dispute resolution. | Formal report | Monthly up from to end of PSS contract | Monthly Report |
| 4.3.6 | The Contractor shall as a minimum: - manage the Authority and LSRC Contractor GFX obligations; and - work with the MORPHEUS GFX lead to ensure that GFX is managed in a fully aligned and sympathetic way to ensure optimum efficiency of the GFX. For any additional iMTRC GFX requests, the Contractor shall validate, approve and source the additional GFX requests. This will include as a minimum: - providing justification for the requirement for GFX; - validating any request by the Contractor for GFX during the negotiation; - validate the date required, method of delivery/ consignment etc. for any GFX approved; - identifying any associated special considerations for JTTE (‘Jigs, Tools, etc.); - provide assurance that the appropriate use of ITAR and IPR has been identified for the requested GFX, and that the project complies with the necessary processes; - identification of availability of requested GFX; and - if the GFX item is not available from stock, then arrange new buys. | Formal report | As per Schedule | Monthly Report |
| 4.3.6a | The Contractor shall provide co-ordination and support to relevant LSRC contract governance meetings. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.3.7 | eMTRC Requirement. For the eMTRC process, the Contractor is required to provide SME support to the DIO process which includes but not limited to: 1. Maintenance/ Support to URD – keeping it current and aligned with MORPHEUS strategy; 2. Support to Initial Planning Estimate; 3. Liaison for Design Phase; 4. MORPHEUS interface/ liaison for DIO Business Case process; 5. Support to definition and analysis of costed options; 6. Support to scrutiny processes; 7. Support to procurement (ITT and selection) processes; and 8. Monthly formal report ad hoc briefings supported by slides and/ or papers as appropriate. | Formal report | Monthly until end of contract | Monthly Report |
| 4.3.8 | eMTRC Operational phase. The Contractor shall manage the Activities set out between Section 4.3.8 and Section 4.3.10. The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS eMTRC and the Authority utilising PM tools and techniques and giving due consideration to the provisions and requirements of the DIO facility. If any dispute arises with DIO shall immediately inform the Authority Commercial Officer. | Formal report | Monthly until end of contract | Monthly Report |
| 4.3.8a | As part of the MTRC wider stakeholder engagement activities, the Contractor shall liaise with the ISS Integration Test & Transition team to keep abreast of and remain in step with development of the C4ISR strategy and the Testing Strategic Partner arrangement. This is to include liaison with the JFC sponsor for the LSRC. | Formal report | Monthly until end of contract | Monthly Report |
| 4.3.9 | eMTRC Facilities Liaison. This will include liaison with the host unit on a regular basis to facilitate repair and maintenance of the facility. | Formal report | Monthly until end of contract | Monthly Report |
| 4.3.10 | EvO TP Management. The Contractor shall work collaboratively with the EvO TP Team to help to ensure timely delivery of GD-produced MORPHEUS equipment and software for the MTRC. | Formal report | Monthly until end of contract | Monthly Report |

| Future Procurement Activities |  |  |  |  |
| --- | --- | --- | --- | --- |
| 4.3.11 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the BATCIS Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Sections 4.3.11.1 to 4.3.26 inclusive. |  |  |  |
| 4.3.12 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to start the procurement process. The Early Competition Data Pack will include as a minimum: - a Procurement Strategy; - mature wording for the PIN, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MTRC Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MTRC Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the project, for example security exemptions; - a mature question set for the PQQ; - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially-approved scoring system; - a draft SOR; - a draft acceptance process for the deliverables or outputs to the Project; - when relevant, a draft assurance process for the deliverables or outputs to the Project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. All documentation listed in Section 4.3.11 to Section 4.3.26 shall form part of the Early Competition Data Pack. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 4.3.13 | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. All documentation listed in Section 4.3.11 to Section 4.3.26 shall form part of the Final Competition Data Pack. | Final Competition Data Pack | As per Schedule | Schedule 5 |
| 4.3.14 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the MORPHEUS MTRC Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the MORPHEUS MTRC GFA List. The Contractor shall provide as a minimum for the MORPHEUS GFA List (see relevant PD artefact at Schedule 19): - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. | Draft MORPHEUS MTRC Project GFA List Final MORPHEUS MTRC Project GFA List As required attend meetings and engage with the MORPHEUS GFA Manager | As per Schedule As required from Nov 18 until end of contract | Regular 20 Working Days (Schedule 4 Special) |
| 4.3.15 | The Contractor shall collate the information required to produce a PIN, in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 4.3.16 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the MORPHEUS MTRC Project, ensuring compliance with the MORPHEUS Procurement Strategy. The Contractor shall ensure that the MORPHEUS Project Lead for the MORPHEUS MTRC Project approves all updates/ changes to the MORPHEUS MTRC Procurement Strategy. The MORPHEUS MTRC Procurement Strategy shall be compliant with the Procurement Strategy GFI at Schedule 7. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 4.3.17 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the MORPHEUS MTRC Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 4.3.18 | The Contactor shall support the BATCIS Commercial Team when developing the MORPHEUS MTRC Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | MORPHEUS MTRC Contract Notice | As per Schedule | Regular 5 Working Days |
| 4.3.19 | The Contractor shall create, develop and update the MORPHEUS MTRC supplier selection project, security and technical questions for the MORPHEUS MTRC DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate MORPHEUS Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical questions Mature DPQQ PM/ Technical questions | As per Schedule As per Schedule | Schedule 5 |
| 4.3.20 | The Contractor shall create, develop and update the MORPHEUS MTRC supplier selection evaluation criteria for the project, security and technical questions for the MORPHEUS MTRC DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MTRC DPQQ. The list shall include the name, email address and questions which the individual will be evaluating, the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.3.21 | The Contractor shall provide a SOR for the MORPHEUS MTRC Project. The Contractor shall engage with all relevant stakeholders when developing the MORPHEUS MTRC SOR to ensure that all necessary aspects of delivery are considered. The SOR shall consider the MTRC Project through the relevant project life cycle and consider all relevant DLOD areas. As a minimum, the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum, the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 4.3.22 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the MORPHEUS MTRC Project. This shall include as a minimum: - the approved MORPHEUS MTRC SOR; - timelines for activity during the procurement; - providing project management input to the MORPHEUS MTRC Contract, including as a minimum: - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance. ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS MTRC tender assessment questions; and - the MORPHEUS MTRC tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 4.3.23 | The Contractor shall create, co-ordinate, update, manage and maintain the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MTRC Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MTRC Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the Authority Commercial Officer. The Contractor shall ensure that the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MTRC Project additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MTRC Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Tender. | Draft the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MTRC Project Mature the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MTRC Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.3.24 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the MORPHEUS MTRC Project. The Contractor shall secure any relevant security exemptions with the support of the BATCIS Commercial Team. See relevant GFI artefact at Schedule 7. | MORPHEUS MTRC Security Aspects Letter | As per Schedule | Schedule 5 |
| 4.3.25 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the MORPHEUS MTRC Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority SI PM | As per Schedule | Monthly Report |
| 4.3.26 | The Contractor shall at the direction of the MORPHEUS Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the MORPHEUS MTRC Project, this may as a minimum include: - Industry days, i.e. bidder conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/ As Agreed with MORPHEUS Project Lead |
| 4.3.27 | Competition Phase. The Contractor shall ensure the delivery of the competition phase by co-ordinating and managing the delivery of the tasks from Section 4.3.27 to Section 4.3.34. |  |  |  |
| 4.3.28 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include as a minimum: - once provided clarification questions from Industry by the BATCIS Commercial Team, obtaining a response from the relevant Subject Matter Expert within 3 working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry clarification questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 4.3.29 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinating and manging the Authority non-commercial clarification questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements Clear audit trail of Authority clarification questions during the tender assessment phase List of negotiation topics for each tender, if required Record of Decisions from the MORPHEUS MTRC tender Assessment Panel | As per the Schedule As per the Schedule | Monthly Report Regular 5 Working Days |
| 4.3.30 | At the direction of an Authority Lead, the Contractor shall contribute/ co-ordinate Industry engagement (comprising Presentations, Venue Organisation, and Agenda Development etc.) in the form of a Bidders Conference. | MORPHEUS MTRC Project Bidders Conference | As per the Schedule | Regular 5 Working Days |
| 4.3.31 | The Contractor shall provide support to the MORPHEUS MTRC Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation list of attendees Negotiation Action List Negotiation RODs | As per the Schedule | Regular 5 Working Days |
| 4.3.32 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum; - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and mange the Authority non-commercial clarification questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase Record of Decisions from the MORPHEUS MTRC tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 4.3.33 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19, and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the MORPHEUS Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 4.3.34 | The Contractor shall provide support to the Contract Award phase of the MORPHEUS MTRC Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the MORPHEUS MTRC Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender de-brief packs Attendance and contribution to Tender De-Brief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 4.3.35 | Post Competition Phase. The Contractor shall manage the Activities set out between Section 4.3.35 and Section 4.3.39. |  | As per Schedule |  |
| 4.3.36 | The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS MTRC and the Authority utilising PM tools and techniques, giving due consideration to the provisions and requirements of the MORPHEUS MTRC Contract. If any dispute arises with the MORPHEUS MTRC, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and Systems Integrator MORPHEUS MTRC Monthly Report Relationship Management Section | Monthly up to end of PSS contract | Regular 10 Working Days |
| 4.3.37 | The Contractor shall manage any changes to the MORPHEUS MTRC Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the MORPHEUS MTRC SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the MORPHEUS MTRC Change Control Procedure | As required | Regular 20 Working Days |
| 4.3.7a | The Contractor shall manage delivery of the MORPHEUS MTRC. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the MORPHEUS MTRC Contract; - engaging with the MORPHEUS MTRC to address any queries regarding deliverables and any issues with the delivery of the MORPHEUS MTRC Contract; and monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the MORPHEUS MTRC for improvements to the Contract; and - engaging with an Authority Project Manager to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.3.38 | The Contractor shall engage with the MORPHEUS GFA Manager to ensure the timely delivery of all Authority obligations under the MORPHEUS MTRC Contract including post contract changes, updates and validations. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the MOPRHEUS MTRC Contract | Monthly up to end of PSS contract | Monthly Report |
| 4.3.39 | In addition to MORPHEUS Project Governance meetings, the Contractor shall provide co-ordination and support to relevant MTRC contract governance meetings. | Formal monthly report Compliance with the MORPHEUS MTRC Project Governance Schedule | As required up to end of PSS contract | Monthly Report |

4.4	Battlefield Management Application [BMA] Specific PM Requirements.   BMA will be a suite of one or more software applications and services provided for commanders at all levels in the tactical space.  This will include Geospatial Services, Operating Picture, Mission Planning and Execution.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Battlefield Management Application (BMA) Project Manager (PM) in delivering the BMA Project through its lifecycle.  The BMA project lifecycle includes the BMA (Post Competition Phase, Section 4.4.1).  The BMA PM shall utilise generic project management tools and skills Section 4.1 to deliver the BMA Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.4.1 | BMA Post Competition Phase. The Contractor shall manage the following PM activities which include as a minimum managing the contract, compliance/ governance processes, and ensuring the Contractor meets its contracted deliverables/ deadlines. Whilst achieving this, the Contractor shall monitor & control the contract, maintaining a focus on deliverables to ensure that the project stays on track, and recommend corrective action to the MORPHEUS Project Lead and implement once it has been approved utilising PM tools and techniques in Section 4.1. | Support to managing the BMA contract | From 12/3/18 up to end of PSS contract |  |
| 4.4.2 | The Contractor shall manage and maintain the day-to-day relationship between the BMA supplier and the Authority. If any dispute arises with the BMA supplier, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal report | Monthly up to end of PSS contract |  |
| 4.4.3 | The Contractor shall implement and manage any changes or additions to the BMA SOR to achieve project outputs, including as a minimum: - provide project/ technical input to contract amendments if required; and - updating the SOR. | Update the SOR | As required |  |
| 4.4.4 | The Contractor shall co-ordinate the acceptance of the BMA deliverables, including as a minimum: - evaluating operational and technical performance indicators (e.g. KPI) against the Contract Requirements. The Contractor shall provide a recommendation to the Project Lead on the acceptability of the deliverable. | Formal report | Monthly up to end of PSS contract |  |
| 4.4.5 | The Contractor shall provide supporting evidence for any issues that arise during the course of the BMA Contract; including escalation in a timely manner where appropriate, including as a minimum: - provide advice to the Authority Project Lead on the acceptability and impact of alternative solutions and/ or proposals from the Contractor; and - provide support to any dispute resolution. | Formal report | Monthly up to end of PSS contract |  |
| 4.4.6 | The Contractor shall as a minimum: - manage the Authority and BMA Contractor GFX obligations; and - work with the MORPHEUS GFX lead to ensure that GFX is managed in a fully aligned and sympathetic way to ensure optimum efficiency of the GFX. For any additional GFX requests, the Contractor shall validate, approve and source the additional BMA GFX requests: This will include as a minimum: - providing justification for the requirement for GFX; - validating any request by the Contractor for GFX during the negotiation; - validating the date required, method of delivery/ consignment etc. for any GFX approved; - identifying any associated special considerations for JTTE (‘Jigs, Tools, etc.); - provide assurance that the appropriate use of ITAR and IPR has been identified for the requested GFX, and that the Project complies with the necessary processes; - identification of availability of requested GFX; and - if the GFX item is not available from stock, then arrange new buys. | Formal report | Monthly up to end of PSS contract |  |
| 4.4.7 | In addition to MORPHEUS Project Governance meetings, the Contractor shall provide co-ordination and support to relevant BMA contract governance meetings. | Formal report | As required up to end of PSS contract |  |

4.5	Platform Installation and Fielding (Specific PM Requirements).   PI&F capabilities will address the integration design, certification, conversion and installation of the MORPHEUS system delivered by the TP and Sub-System Design Organisations, having been integrated and installed by the MORPHEUS Installation Design and Certification (MIDaC) and Platform OEMs, and tested by the TP during EvO D&D phases.  The Fielding element is support of the EvO Operational Field Trials (including certification of additional design lines), and then the fielding and conversion of all of the platforms (including maritime, but aviation is TBD) that are due to be fitted with EvO, in order to deliver both IOC and FOC for EvO.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Platform Installation and Fielding (PI&F) Project Manager (PM) in delivering the PI&F Project through its lifecycle.  The PI&F project lifecycle shall include the MORPHEUS Installation Design and Certification (MIDaC) (Post Competition Phase, Section 4.5.1).  Depending on the Fielding Strategy and Systems Integrator role, the PI&F PM could include competing for a Fielding/ Conversion contractor and possibly re-competing the MIDaC (see OPTION for Fielding/ Conversion contractor and the MIDaC re-compete).  The PI&F PM shall utilise generic project management tools and skills in Section 4.1 to deliver the PI&F Project.

| Programme Schedule Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.5.1 | MIDaC Post Competition Phase. The Contractor shall manage the following PM activities which include as a minimum managing the contract, compliance/ governance processes, ensuring the Contractor meets its contracted deliverables/ deadlines. Whilst achieving this, the Contractor shall monitor & control the contract, maintaining a focus on deliverables to ensure that the project stays on track, and recommend corrective action to the MORPHEUS Project Lead and implement once it has been approved utilising PM tools and techniques in Section 4.1. | Support to managing the MIDaC contract | From 12/3/18 up to end of PSS contract |  |
| 4.5.2 | The Contractor shall manage and maintain the day-to-day relationship between the PI&F supplier, relevant Platform Teams and the Authority. If any dispute arises with the PI&F supplier, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal report | Monthly up to end of PSS contract |  |
| 4.5.3 | The Contractor shall implement and manage any changes or additions to the MIDAC SOR to achieve project outputs, including as a minimum: - provide project/ technical input to contract amendments if required; and - updating the SOR. | Update the SOR | As required |  |
| 4.5.4 | The Contractor shall co-ordinate the acceptance of the MIDaC deliverables, including as a minimum: - evaluating operational and technical performance indicators (e.g. KPI) against the Contract Requirements. The Contractor shall provide a recommendation to the Project Lead on the acceptability of the deliverable. | Formal report | Monthly up to end of PSS contract |  |
| 4.5.5 | The Contractor shall provide supporting evidence for any issues that arise during the course of the MIDaC Contract; including escalation in a timely manner where appropriate. Including as a minimum: - provide advice to the Authority Project Lead on the acceptability and impact of alternative solutions and/ or proposals from the Contractor; and - provide support to any dispute resolution. | Formal report | Monthly up to end of PSS contract |  |
| 4.5.6 | The Contractor shall as a minimum: - manage the Authority and MIDaC Contractor GFX obligations; and - work with the MORPHEUS GFX lead to ensure that GFX is managed in a fully aligned and sympathetic way to ensure optimum efficiency of the GFX. For any additional GFX requests, the Contractor shall validate, approve and source the additional MIDAC GFX requests: This will include as a minimum: - providing justification for the requirement for GFX; - validating any request by the Contractor for GFX during the negotiation; - validate the date required, method of delivery/ consignment etc. for any GFX approved; - identifying any associated special considerations for JTTE (‘Jigs, Tools, etc.); - provide assurance that the appropriate use of ITAR and IPR has been identified for the requested GFX, and that the Project complies with the necessary processes; - identification of availability of requested GFX; and - if the GFX item is not available from stock then arrange new buys. | Formal report | Monthly up to end of PSS contract |  |
| 4.5.7 | In addition to MORPHEUS Project Governance meetings, the Contractor shall provide Coordination and support to relevant MIDaC contract governance meetings. | Formal report | As required up to end of PSS contract |  |

4.6	Training Project Management.   The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the Training Project Manager (PM) in delivering the Training Project through its lifecycle.

The MORPHEUS Training Project shall ensure that training is provided for the Operational Field Trials (OFT) and for the Conversion of individuals from the BCIP 5.6 baseline to the EvO system baseline, this will be in accordance with the future Consolidated Training Needs Report.  The Training Project lifecycle activities shall include:

- Capturing and updating the Provision of a Training Needs Analysis (TNA) for Training Requirements Authority (TRA) acceptance.

- Managing the design of courses and courseware for OFT and Conversion (including pilot courses for these).

- Ensuring Training Systems and Simulation Programme (TSSP) receives the EvO System Software for inclusion in Collective Training.

- Project Managing and assuring all BMA training documentations.

- Project Managing and assuring all GD training documentations.

The Training project lifecycle may include the procurement(s) of a training provider.  This would involve pre-competition, competition and post-competition (management) activities (see Option).

The Training PM shall utilise generic project management tools and skills in Section 4.1 to deliver the Training Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.6.1 | The Contractor shall provide support to the MORPHEUS Project Leads and Training Requirements Authority to ensure the most appropriate methods and media are used in the design of courseware. Specific tasks include as a minimum: - attend the MORPHEUS Training Working Group (TWG) meetings, contributing subject matter expertise and recommendations where required; - attend the MORPHEUS Training Needs Analysis (TNA) Steering Group (TNASG), contributing subject matter expertise and recommendations where required; - confirm viability of the recommendations on methods and media made within the Training Needs Report (TNR) within performance, time and cost boundaries; and - keep the MORPHEUS Project Lead and other appropriate BATCIS team stakeholders informed of activities and work undertaken. | Contractor to abide by meeting minutes and provide input/ feedback as required. Monthly progress meetings with Project Lead Formal TRA reviews (likely quarterly) | Likely quarterly Monthly As required |  |
| 4.6.2 | The Contractor shall support all MORPHEUS Projects by supplying and assessing training related requirements. This will include as a minimum: - development of Training-related Invitation to Tender (ITT/ ITN) documentations; - evaluation, down-selection and debrief of any tenderers relating to training functions; - evaluation, moderation of tenderers’ responses, conduct negotiations and assess BAFOs; - Industry engagement (comprising Presentations, Agenda Development); and - provide training statements of requirements to the competitions. | Support to MORPHEUS Projects | As required from 12/3/18 until end of contract |  |
| 4.6.3 | The Contractor shall ensure that all training documentations from the TP and MORPHEUS Projects are managed, quality assured and accepted as per their contracts. This will include as a minimum: - acting as the interface between the OEM and the Training Requirements Authority and the Training Working Group; - ensuring sufficient time in the schedule is provided for reviews and acceptance by all parties; - managing the progress of the consolidated TNA from General Dynamics; - managing the Training Material from General Dynamics; - managing the BMA TNA, for inclusion into the consolidated TNA; - managing the BMA Training Materials; - managing other MORPHEUS Project Training related deliverables; and - ensuring Training Systems and Simulation Programme (TSSP) receives the EvO System Software for inclusion in Collective Training | Attend (and where necessary, chair) OEM monthly meetings. Attend TNA Steering Group meetings. Attend Training Working Group meetings. | Monthly Quarterly Quarterly |  |
| 4.6.4 | The Contractor shall, if required, support the LE TacCIS Programme to develop a MORPHEUS Training Strategy for EvO and Training Options for Main Gate. The Contractor shall support the Training Needs Analysis (TNA) Steering Group by providing MORPHEUS SME input. | TNA Steering Group held | Quarterly from 12/3/18 until end of contract Quarterly from 12/3/18 until end of contract |  |
| 4.6.5 | The Contractor shall work with internal BATCIS Training Quality Assurance to conduct Assurance on Training Design and Delivery (including the Training Courseware) and provide feedback to the Training Requirements Authority. This will include as a minimum: - assuring the Pilot, OFT and Conversion Courses are fit for purpose (in accordance with the Formal Training Statement); and - conducting External Evaluation on the Training Delivery in accordance with the DSAT process in JSP 822: Defence Systems Approach to Training (v3.0 Mar/Apr 17). Providing the result back to the Training Requirements Authority. Working with the Courseware team and Training Deliverers to make amendments to their deliverables. | Quarterly Report | Quarterly from 12/3/18 until end of contract |  |

4.8	Enduring Joint Programme Organisation (eJPO) Specific PM Requirements.   Fundamental to achieving collaborative working between the Authority and Industry is the establishment of a JPO; an integrated programme management and engineering organisation.  The JPO is fundamental for delivery of the MORPHEUS procurement strategy, enduring for the length of the MORPHEUS programme (2045 as a minimum).

Under EvO, an Interim JPO (iJPO), has been established in a privately leased physical office in North Bristol, within walking distance of MOD Abbey Wood.  The facility is leased until 2020.

At the expiry of the EvO TP contract in Dec 2020, the iJPO will cease to exist and the MOD Enduring JPO (eJPO) will stand-up to continue the JPO function over the remaining life of MORPHEUS.  To ensure an effective transition from the iJPO, the eJPO must be already in place and functioning before the expiry of the iJPO.  This requires a transition period where the eJPO building is fitted with IT, tools and other equipment and the transfer of staff and contractors from the iJPO can take place.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Enduring Joint Programme Organisation (eJPO) Project Manager (PM) in delivering the eJPO Project through its lifecycle.

The MORPHEUS eJPO Project lifecycle shall include capturing and updating the requirement, and creation and updates to associated documentation required to engage the Defence Infrastructure Organisation (DIO) to secure a future eJPO facility.  In addition, the Contractor shall manage the future eJPO requirement once operational.  The Contractor will manage and support future procurement activities associated with the maintenance of the eJPO capability.  Establishing an eJPO may include the procurement(s) of IT, tools, furniture and white goods.  The procurement(s) will involve pre-competition, competition and post-competition (management) activities.  The eJPO PM shall utilise generic project management tools and skills as per the relevant parts of Section 4.1 to deliver the eJPO Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
| 4.8 | eJPO Requirement. For the eJPO process, the Contractor is required to provide SME support to the DIO process which includes but not limited to: 1. maintenance/ support to URD – keeping it current and aligned with MORPHEUS strategy; 2. support to Initial Planning Estimate; 3. liaison for Design Phase; 4. MORPHEUS interface/ liaison for DIO Business Case process; 5. support to definition and analysis of costed options; 6. support to scrutiny processes; 7. support to procurement (ITT and selection) processes; and 8. monthly formal report ad hoc briefings supported by slides and/ or papers as appropriate. | Formal report | Monthly until end of contract |  |
| 4.8.1 | The Contractor shall manage and maintain the day-to-day relationship between the DIO and the Authority utilising PM tools and techniques and giving due consideration to the provisions and requirements of the DIO facility. If any dispute arises with the DIO, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal Report | Monthly until end of contract |  |
| 4.8.2 | eJPO Facilities Liaison. This will include liaison with the host unit on a regular basis to facilitate repair and maintenance of the facility. | Formal Report | Monthly until end of contract |  |
| 4,8.3 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the BATCIS Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Section 4.8.3 to Section 4.8.18 inclusive. |  |  |  |
| 4.8.4 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to commence the procurement process. The Early Competition Data Pack will include as a minimum: - a Procurement Strategy; - mature wording for a PIN, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS eJPO Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS eJPO Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the Project, for example security exemptions; - a mature question set for the PQQ; - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially approved scoring system; - a draft SOR; - a draft acceptance process for the deliverables or outputs to the Project; - when relevant a draft assurance process for the deliverables or outputs to the Project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 4,8,5 | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. | Final Competition Data Pack | As per Schedule | Schedule 5 |
| 4.8.6 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the MORPHEUS eJPO Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the MORPHEUS eJPO GFA List. The Contractor shall provide as a minimum for the MORPHEUS GFA List (see relevant PD artefact at Schedule 19): - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. | Draft MORPHEUS eJPO Project GFA List Final MORPHEUS eJPO Project GFA List As required attend meetings and engage with the MORPHEUS GFA Manager | As per Schedule As required from Nov 18 until end of contract | Regular 20 Working Days (Schedule 4 Special) |
| 4.8.7 | The Contractor shall collate the information required to produce a PIN, in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 4.8.8 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the MORPHEUS eJPO Project, ensuring compliance with the MORPHEUS Procurement Strategy. The Contractor shall ensure that the MORPHEUS Project Lead for the MORPHEUS eJPO Project approves all updates/ changes to the MORPHEUS eJPO Procurement Strategy. The MORPHEUS eJPO Procurement Strategy shall be compliant with the Procurement Strategy PD at Schedule 19. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 4.8.9 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the MORPHEUS eJPO Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 4.8.10 | The Contactor shall support the BATCIS Commercial Team when developing the MORPHEUS eJPO Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | MORPHEUS eJPO Contract Notice | As per Schedule | Regular 5 Working Days |
| 4.8.11 | The Contractor shall create, develop and update the MORPHEUS eJPO supplier selection project, security and technical questions for the MORPHEUS eJPO DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate MORPHEUS Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical questions Mature DPQQ PM/ Technical questions | As per Schedule As per Schedule | Schedule 5 |
| 4.8.12 | The Contractor shall create, develop and update the MORPHEUS eJPO supplier selection evaluation criteria for the project, security and technical questions for the MORPHEUS eJPO DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS eJPO DPQQ. The list shall include the name, email address and questions which the individual will be evaluating, the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.8.13 | The Contractor shall provide a SOR for the MORPHEUS eJPO Project. The Contractor shall engage with all relevant stakeholders when developing the MORPHEUS eJPO SOR to ensure that all necessary aspects of delivery are considered. The SOR shall consider the eJPO Project through the relevant project lifecycle and consider all relevant DLOD areas. As a minimum, the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 4.8.14 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the MORPHEUS eJPO Project. This shall include as a minimum: - the approved MORPHEUS eJPO SOR; - timelines for activity during the procurement; - providing project management input to the MORPHEUS eJPO Contract, including as a minimum; - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance. ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS eJPO tender assessment questions; and - the MORPHEUS eJPO tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 4.8.15 | The Contractor shall create, co-ordinate, update, manage and maintain the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS eJPO Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS eJPO Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the BATCIS Commercial Team. The Contractor shall ensure that the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS eJPO Project additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS eJPO Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Tender. | Draft the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS eJPO Project Mature the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS eJPO Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.8.16 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the MORPHEUS eJPO Project. The Contractor shall secure any relevant security exemptions with the support of the BATCIS Commercial Team. See relevant GFI artefact at Schedule 7. | MORPHEUS eJPO Security Aspects Letter | As per Schedule | Schedule 5 |
| 4.8.17 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the MORPHEUS eJPO Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority SI PM | As per Schedule | Monthly Report |
| 4.8.18 | The Contractor shall at the direction of the MORPHEUS Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the MORPHEUS eJPO Project, this shall as a minimum include: - Industry Days, i.e. Bidder Conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/As Agreed with MORPHEUS Project Lead |
| 4.8.19 | Competition Phase. The Contractor shall ensure the delivery of the competition phase by co-ordinating and managing the delivery of the tasks from Section 4.8.19 to Section 4.8.26. |  |  |  |
| 4.8.20 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include as a minimum: - once provided clarification questions from Industry by the BATCIS Commercial Team, obtaining a response from the relevant Subject Matter Expert within three (3) working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry clarification questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 4.8.21 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RoDs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase List of negotiation topics for each tender, if required RODs from the MORPHEUS eJPO Tender Assessment Panel | As per Schedule As per Schedule | Monthly Report Regular 5 Working Days |
| 4.8.22 | At the direction of an Authority Lead, the Contractor shall contribute/ co-ordinate Industry engagement (comprising Presentations, Venue Organisation, and Agenda Development etc.) in the form of a Bidders Conference. | MORPHEUS eJPO Project Bidders Conference | As per Schedule | Regular 5 Working Days |
| 4.8.23 | The Contractor shall provide support to the MORPHEUS eJPO Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation list of attendees Negotiation Action List Negotiation RODs | As per Schedule | Regular 5 Working Days |
| 4.8.24 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements Clear audit trail of Authority clarification questions during the tender assessment phase RODs from the MORPHEUS eJPO Tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 4.8.25 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19, and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the MORPHEUS Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 4,8,26 | The Contractor shall provide support to the Contract Award phase of the MORPHEUS eJPO Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the MORPHEUS eJPO Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender de-brief packs Attendance and contribution to Tender debrief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 4.8.27 | Post Competition Phase. The Contractor shall manage the Activities set out between Sections 4.8.27 and Sections 4.8.32. |  | As per Schedule |  |
| 4.8.28 | The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS eJPO and the Authority utilising PM tools and techniques, giving due consideration to the provisions and requirements of the MORPHEUS eJPO Contract. If any dispute arises with the MORPHEUS eJPO, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and Systems Integrator MORPHEUS eJPO Monthly Report Relationship Management Section | Monthly up to end of PSS contract | Regular 10 Working Days |
| 4.8.29 | The Contractor shall manage any changes to the MORPHEUS eJPO Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the MORPHEUS eJPO SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the MORPHEUS eJPO Change Control Procedure | As required | Regular 20 Working Days |
| 4.8.30 | The Contractor shall manage delivery of the MORPHEUS eJPO. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the MORPHEUS eJPO Contract; - engaging with the MORPHEUS eJPO to address any queries regarding deliverables and any issues with the delivery of the MORPHEUS eJPO Contract; and monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the MORPHEUS eJPO for improvements to the Contract; and - engaging with an Authority Project Manager to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.8.31 | The Contractor shall engage with the MORPHEUS GFA Manager to ensure the timely delivery of all Authority obligations under the MORPHEUS eJPO Contract including post contract changes, updates and validations. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the MOPRHEUS eJPO Contract | Monthly up to end of PSS contract | Monhtly Report |
| 4.8.32 | The Contractor shall manage the MORPHEUS eJPO project in accordance with the Governance process (see relevant PD artefact at Schedule 19). | Formal monthly report Compliance with the MORPHEUS eJPO Project Governance Schedule | As required up to end of PSS contract | Monthly Report |

4.9	Managed Service Providers (MSPs) Specific PM Requirements.   MSPs will be responsible for fulfilling a service level agreement for the supply of proven, integrated and integrate-able equipment within the scope of their supply; which is otherwise known as their “Lot”, delivering in a Service Integration context aligned to the ISS Defence as a Platform (DaaP) and the MORPHEUS Target Operating Model (TOM) initiatives.

Managed Service Providers (MSPs) – Infrastructure.   The Infrastructure MSP will be responsible for the processing and network enabling hardware and software and the core system management and security functions.  Both man portable and platform installed.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Infrastructure MSP Project Manager (PM) in delivering the Infrastructure MSP Project through its lifecycle.

The Infrastructure MSP Project’s lifecycle shall include capturing and updating the requirement and creation and updates to associated documentation required to run a competition (Pre Competition Phase, Section 4.9.1 to Section 4.9.15); project managing the competition (Competition Phase, Section 4.9.16 to Section 4.9.23); and project managing the Infrastructure MSP Contractor (Post Competition Phase, Section 4.9.24 to Section 4.9.29).  The Infrastructure MSP PM shall utilise generic project management tools and skills in Section 4.1 to deliver the Infrastructure MSP Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
|  | Managed Service Providers (MSPs) – Infrastructure |  |  |  |
| 4.9 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the BATCIS Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Section 4.9.1 to Section 4.9.15. |  |  |  |
| 4.9.1 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to start the procurement process. The Early Competition Data Pack will include as a minimum: - a Procurement Strategy; - mature wording for a PIN, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MSP Infrastructure Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MSP Infrastructure Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the project, for example security exemptions; - a mature question set for the PQQ; - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially-approved scoring system; - a draft SOR; - a draft acceptance process for the deliverables or outputs to the Project; - when relevant a draft assurance process for the deliverables or outputs to the Project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 4.9.2 | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. | Final Competition Data Pack | As per Schedule | Schedule 5 |
| 4.9.3 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the MORPHEUS MSP Infrastructure Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the MORPHEUS MSP Infrastructure GFA List. The Contractor shall provide as a minimum for the MORPHEUS GFA List: - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. See relevant PD artefact at Schedule 19. | Draft MORPHEUS MSP Infrastructure Project GFA List Final MORPHEUS MSP Infrastructure Project GFA List As required attend meetings and engage with the MORPHEUS GFA Manager | As per Schedule As required from Nov 18 until end of contract | Regular 20 Working Days (Schedule 4 Special) |
| 4.9.4 | The Contractor shall collate the information required to produce a Prior Information Notice (PIN), in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. See relevant PD artefact at Schedule 19. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 4.9.5 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the MORPHEUS MSP Infrastructure Project, ensuring compliance with the MORPHEUS Procurement Strategy. The Contractor shall ensure that the MORPHEUS Project Lead for the MORPHEUS MSP Infrastructure Project approves all updates/ changes to the MORPHEUS MSP Infrastructure Procurement Strategy. The MORPHEUS MSP Infrastructure Procurement Strategy shall be compliant with the Procurement Strategy template at Schedule 7. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 4.9.6 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the MORPHEUS MSP Infrastructure Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 4.9.7 | The Contactor shall support the BATCIS Commercial Team when developing the MORPHEUS MSP Infrastructure Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | MORPHEUS MSP Infrastructure Contract Notice | As per Schedule | Regular 5 Working Days |
| 4.9.8 | The Contractor shall create, develop and update the MORPHEUS MSP Infrastructure supplier selection project, security and technical questions for the MORPHEUS MSP Infrastructure Dynamic Pre-Qualification Questionnaire (DPQQ). The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate MORPHEUS Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical questions Mature DPQQ PM/ Technical questions | As per Schedule As per Schedule | Schedule 5 |
| 4.9.9 | The Contractor shall create, develop and update the MORPHEUS MSP Infrastructure supplier selection evaluation criteria for the project, security and technical questions for the MORPHEUS MSP Infrastructure DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MSP Infrastructure DPQQ. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least ten (10) working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation Criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.9.10 | The Contractor shall provide a SOR for the MORPHEUS MSP Infrastructure Project. The Contractor shall engage with all relevant stakeholders when developing the MORPHEUS MSP Infrastructure SOR to ensure that all necessary aspects of delivery are considered. The Contractor shall agree the SOR format with the BATCIS Commercial Team and the relevant Project Lead. The SOR shall consider the MSP Infrastructure Project through the relevant project life cycle and consider all relevant DLOD areas. As a minimum the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 4.9.11 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the MORPHEUS MSP Infrastructure Project. This shall include as a minimum: - the approved MORPHEUS MSP Infrastructure SOR; - timelines for activity during the procurement; - providing project management input to the MORPHEUS MSP Infrastructure Contract including as a minimum: - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance, ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS MSP Infrastructure tender assessment questions; and - the MORPHEUS MSP Infrastructure tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 4.9.12 | The Contractor shall create, co-ordinate, update, manage and maintain the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Infrastructure Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Infrastructure Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the BATCIS Commercial Team. The Contractor shall ensure that the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Infrastructure Project additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MSP Infrastructure Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Tender. | Draft the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Infrastructure Project Mature the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Infrastructure Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.9.13 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the MORPHEUS MSP Infrastructure Project. The Contractor shall secure any relevant security exemptions with the support of the BATCIS Commercial Team. See relevant GFI artefact at Schedule 7. | MORPHEUS MSP Infrastructure Security Aspects Letter | As per Schedule | Schedule 5 |
| 4.9.14 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the MORPHEUS MSP Infrastructure Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority MSP Infrastructure PM | As per Schedule | Monthly Report |
| 4.9.15 | The Contractor shall at the direction of the MORPHEUS Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the MORPHEUS MSP Infrastructure Project, this may as a minimum include: - Industry Days, i.e. Bidder Conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/As Agreed with MORPHEUS Project Lead |
| 4.9.16 | Competition Phase. The Contractor shall ensure the delivery of the competition phase by co-ordinating and managing the delivery of the tasks from Section 4.9.16 to Section 4.9.23. |  |  |  |
| 4.9.17 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include as a minimum: - once provided clarification questions from Industry by the BATCIS Commercial Team, obtaining a response from the relevant Subject Matter Expert within three (3) working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry clarification questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 4.9.18 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements Clear audit trail of Authority clarification questions during the tender assessment phase List of negotiation topics for each tender, if required RODs from the MORPHEUS MSP Infrastructure Tender Assessment Panel | As per the Schedule. As per the Schedule. | Monthly Report Regular 5 Working Days |
| 4.9.19 | At the direction of an Authority Lead, the Contractor shall contribute/ co-ordinate Industry engagement (comprising Presentations, Venue Organisation, and Agenda Development etc.) in the form of a Bidders Conference. | MORPHEUS MSP Infrastructure Project Bidders Conference | As per the Schedule. | Regular 5 Working Days |
| 4.9.20 | The Contractor shall provide support to the MORPHEUS MSP Infrastructure Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation List of Attendees Negotiation Action List Negotiation Record of Decisions | As per the Schedule. | Regular 5 Working Days |
| 4.9.21 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase RODs from the MORPHEUS MSP Infrastructure Tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 4.9.22 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19, and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the MORPHEUS Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 4.9.23 | The Contractor shall provide support to the Contract Award phase of the MORPHEUS MSP Infrastructure Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the MORPHEUS MSP Infrastructure Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender debrief packs Attendance and contribution to Tender debrief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 4.9.24 | Post Competition Phase. The Contractor shall manage the Activities set out between Section 4.9.24 to Section 4.9.29. |  | As per Schedule |  |
| 4.9.25 | The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS MSP Infrastructure Project and the Authority utilising PM tools and techniques, giving due consideration to the provisions and requirements of the MORPHEUS MSP Infrastructure Contract. If any dispute arises with the MORPHEUS MSP Infrastructure, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and Systems Integrator MORPHEUS MSP Infrastructure Monthly Report Relationship Management Section | Monthly up to end of PSS contract | Regular 10 Working Days |
| 4.9.26 | The Contractor shall manage any changes to the MORPHEUS MSP Infrastructure Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the MORPHEUS MSP Infrastructure SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the MORPHEUS Change Control Procedure | As required | Regular 20 Working Days |
| 4.9.27 | The Contractor shall manage delivery of the MORPHEUS Systems Integrator. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the MORPHEUS MSP Infrastructure Contract; - engaging with the MORPHEUS MSP Infrastructure Project Manager to address any queries regarding deliverables and any issues with the delivery of the MORPHEUS MSP Infrastructure Contract; and - monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the MORPHEUS MSP Infrastructure Project Manager for improvements to the Contract; and - engaging with an Authority Project Manager to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.9.28 | The Contractor shall engage with the MORPHEUS GFA Manager to ensure the timely delivery of all Authority obligations under the MORPHEUS MSP Infrastructure Contract including post contract changes, updates and validations. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the MOPRHEUS MSP Infrastructure Contract | Monthly up to end of PSS contract | Monthly Report |
| 4.9.29 | The Contractor shall manage the MORPHEUS MSP Infrastructure Project in accordance with the Governance process (see relevant PD artefact at Schedule 19). | Formal monthly report Compliance with the MORPHEUS MSP Infrastructure Project Governance Schedule | As required up to end of PSS contract | Monthly Report |

4.10	Managed Service Providers (MSPs) – Bearers Specific PM Requirements.   Provides the over-the-air communication devices to meet the needs of the distributed force elements.  Both man-portable and platform installed.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS Bearers MSP Project Manager (PM) in delivering the MSP Bearers Project through its lifecycle.

The MSP Bearers Project’s lifecycle shall include capturing and updating the requirement and creation and updates to associated documentation required to run a competition (Pre Competition Phase, Section 4.10.1 to Section 4.10.15), project managing the competition (Competition Phase, Section 4.10.16 to Section 4.10.23) and project managing the MSP Bearers Contract (Post Competition Phase, Section 4.10.24 to Section 4.10.29).  The MSP Bearers PM shall utilise generic project management tools and skills as per Section 4.1 to deliver the MSP Bearers Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
|  | Managed Service Providers (MSPs) – Bearers |  |  |  |
| 4.10.1 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the BATCIS Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Section 4.10.1 to Section 4.10.15 inclusive. |  |  |  |
| 4.10.2 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to commence the procurement process. The Early Competition Data Pack will include as a minimum: - a Procurement Strategy; - mature wording for a PIN, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MSP Bearers Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MSP Bearers Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the project, for example security exemptions; - a mature question set for the Pre-Qualification Questionnaire (PQQ); - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially-approved scoring system; - a draft SOR; - a draft acceptance process for the deliverables or outputs to the project; - when relevant a draft assurance process for the deliverables or outputs to the project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 4.10.2.a | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant, a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. | Final Competition Data Pack | As per Schedule | Schedule 5 |
| 4.10.3 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the MORPHEUS MSP Bearers Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the MORPHEUS MSP Bearers GFA List. The Contractor shall provide as a minimum for the MORPHEUS GFA List: - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. See relevant PD artefact at Schedule 19. | Draft MORPHEUS MSP Bearers Project GFA List Final MORPHEUS MSP Bearers Project GFA List. As required attend meetings and engage with the MORPHEUS GFA Manager. | As per Schedule As required from Nov 18 until end of contract | Regular 20 Working Days (Schedule 4 Special?) |
| 4.10.4 | The Contractor shall collate the information required to produce a PIN, in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. See relevant PD artefact at Schedule 19. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 4.10.5 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the MORPHEUS MSP Bearers Project, ensuring compliance with the MORPHEUS Procurement Strategy. The Contractor shall ensure that the MORPHEUS Project Lead for the MORPHEUS MSP Bearers Project approves all updates/ changes to the MORPHEUS MSP Bearers Procurement Strategy. The MORPHEUS MSP Bearers Procurement Strategy shall be compliant with the Procurement Strategy template at Schedule 7. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 4.10.6 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the MORPHEUS MSP Bearers Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 4.10.7 | The Contactor shall support the BATCIS Commercial Team when developing the MORPHEUS MSP Bearers Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - Any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | MORPHEUS MSP Bearers Contract Notice | As per Schedule | Regular 5 Working Days |
| 4.10.8 | The Contractor shall create, develop and update the MORPHEUS MSP Bearers supplier selection project, security and technical questions for the MORPHEUS MSP Bearers Dynamic Pre-Qualification Questionnaire (DPQQ). The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate MORPHEUS Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical questions Mature DPQQ PM/ Technical questions | As per Schedule As per Schedule | Schedule 5 |
| 4.10.9 | The Contractor shall create, develop and update the MORPHEUS MSP Bearers supplier selection evaluation criteria for the project, security and technical questions for the MORPHEUS MSP Bearers DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MSP Bearers DPQQ. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least ten (10) working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation Criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.10.10 | The Contractor shall provide a Statement of Requirement (SOR) for the MORPHEUS MSP Bearers Project. The Contractor shall engage with all relevant stakeholders when developing the MORPHEUS MSP Bearers SOR to ensure that all necessary aspects of delivery are considered. The Contractor shall agree the SOR format with the BATCIS Commercial Team and relevant Project Lead. The SOR shall consider the MSP Bearers Project through the relevant project lifecycle and consider all relevant DLOD areas. As a minimum, the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 4.10.11 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the MORPHEUS MSP Bearers Project. This shall include as a minimum: - the approved MORPHEUS MSP Bearers SOR; - timelines for activity during the procurement; - providing project management input to the MORPHEUS MSP Bearers Contract including as a minimum: - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance, ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS MSP Bearers tender assessment questions; and - the MORPHEUS MSP Bearers tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 4.10.12 | The Contractor shall create, co-ordinate, update, manage and maintain the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Bearers Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Bearers Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the BATCIS Commercial Team. The Contractor shall ensure that the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Bearers Project additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MSP Bearers Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least ten (10) working days prior to the release of the Tender. | Draft the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Bearers Project Mature the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Bearers Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.10.13 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the MORPHEUS MSP Bearers Project. The Contractor shall secure any relevant security exemptions with the support of the BATCIS Commercial Team. See relevant GFI artefact at Schedule 7. | MORPHEUS MSP Bearers SAL | As per Schedule | Schedule 5 |
| 4.10.14 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the MORPHEUS MSP Bearers Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority MSP Bearers PM | As per Schedule | Monthly Report |
| 4.10.15 | The Contractor shall at the direction of the MORPHEUS Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the MORPHEUS MSP Bearers Project, this may as a minimum include: - Industry Days, i.e. Bidder Conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/ As agreed with MORPHEUS Project Lead |
| 4.10.16 | Competition Phase. The Contractor shall ensure the delivery of the competition phase by co-ordinating and managing the delivery of the tasks from Section 4.10.16 to Section 4.10.23. |  |  |  |
| 4.10.17 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include as a minimum: - once provided clarification questions from Industry by the BATCIS Commercial Team, obtaining a response from the relevant Subject Matter Expert within 3 working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry clarification questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 4.10.18 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase List of negotiation topics for each tender, if required RODs from the MORPHEUS MSP Bearers Tender Assessment Panel | As per the Schedule As per the Schedule | Monthly Report Regular 5 Working Days |
| 4.10.19 | At the direction Authority Lead, the Contractor shall contribute/ co-ordinate Industry engagement (comprising Presentations, Venue Organisation, and Agenda Development etc.) in the form of a Bidders Conference. | MORPHEUS MSP Bearers Project Bidders Conference | As per the Schedule | Regular 5 Working Days |
| 4.10.20 | The Contractor shall provide support to the MORPHEUS MSP Bearers Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation list of attendees Negotiation Action List Negotiation RODs | As per the Schedule | Regular 5 Working Days |
| 4.10.21 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum; - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs are taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase RODs from the MORPHEUS MSP Bearers Tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 4.10.22 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19, and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the MORPHEUS Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 4.10.23 | The Contractor shall provide support to the Contract Award phase of the MORPHEUS MSP Bearers Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the MORPHEUS MSP Bearers Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender debrief packs Attendance and contribution to Tender debrief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 4.10.24 | Post Competition Phase. The Contractor shall manage the Activities set out between Section 4.10.24 and Section 4.10.29. |  | As per Schedule |  |
| 4.10.25 | The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS MSP Bearers Project and the Authority utilising PM tools and techniques, giving due consideration to the provisions and requirements of the MORPHEUS MSP Bearers Contract. If any dispute arises with the MORPHEUS MSP Bearers, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and Systems Integrator MORPHEUS MSP Bearers Monthly Report Relationship Management Section | Monthly up to end of PSS contract | Regular 10 Working Days |
| 4.10.26 | The Contractor shall manage any changes to the MORPHEUS MSP Bearers Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the MORPHEUS MSP Bearers SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the MORPHEUS Change Control Procedure | As required | Regular 20 Working Days |
| 4.10.27 | The Contractor shall manage delivery of the MORPHEUS Bearers Project. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the MORPHEUS MSP Bearers Contract; - engaging with the MORPHEUS MSP Bearers PM to address any queries regarding deliverables and any issues with the delivery of the MORPHEUS MSP Bearers Contract; and - monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the MORPHEUS MSP Bearers PM for improvements to the Contract; and - engaging with an Authority Project Manager to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.10.28 | The Contractor shall engage with the MORPHEUS GFA Manager to ensure the timely delivery of all Authority obligations under the MORPHEUS MSP Bearers Contract including post contract changes, updates and validations. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the MOPRHEUS MSP Bearers Contract | Monthly up to end of PSS contract | Monthly Report |
| 4.10.29 | The Contractor shall manage the MORPHEUS MSP Bearers Project in accordance with the Governance process (see relevant PD artefact at Schedule 19). | Formal monthly report Compliance with the MORPHEUS MSP Bearers Project Governance Schedule | As required up to end of PSS contract | Monthly Report |

4.11	Managed Service Providers (MSPs) – Applications Specific PM Requirements.   Includes user facing and common service software applications utilising hosting and enabling services from the infrastructure layer.  The MSP should provide a software architecture and integration framework which should enable rapid delivery of new/ modified applications in response to end user needs.

The Contractor shall provide project management support to the MORPHEUS Project Leads by acting as the MORPHEUS MSP Applications Project Manager (PM) in delivering the MSP Applications Project through its lifecycle.

The MSP Applications Project’s lifecycle shall include capturing and updating the requirement and creation and updates to associated documentation required to run a competition (Pre Competition Phase, Section 4.11.1 to Section 4.11.15), project managing the competition (Competition Phase, Section 4.11.16 to Section 4.11.23) and project managing the MSP Applications Contract (Post Competition Phase, Section 4.11.24 to Section 4.11.29).  The MSP Applications PM shall utilise generic project management tools and skills as per Section 4.1 inclusive to deliver the MSP Applications Project.

| Serial ID | Description/ Deliverables | Outputs | Output date | Acceptance |
| --- | --- | --- | --- | --- |
|  | Managed Service Providers (MSPs) – Applications |  |  |  |
| 4.11.1 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the Authority Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Section 4.11.1 and Section 4.11.15 inclusive. |  |  |  |
| 4.11.2 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to commence the procurement process. The Early Competition Data Pack will include as a minimum: - a Procurement Strategy; - mature wording for Prior Information Notice (PIN), including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MSP Applications Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the MORPHEUS MSP Applications Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the project, for example security exemptions; - a mature question set for the pre-qualification questionnaire (PQQ); - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially-approved scoring system; - a draft Statement of Requirement (SOR); - a draft acceptance process for the deliverables or outputs to the project; - when relevant a draft assurance process for the deliverables or outputs to the project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 4.11.2.a | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. | Final Competition Data Pack | As per Schedule | Schedule 5 |
| 4.11.3 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the MORPHEUS MSP Applications Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the MORPHEUS MSP Applications GFA List. The Contractor shall provide as a minimum for the MORPHEUS GFA List: - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. See relevant PD artefact at Schedule 19. | Draft MORPHEUS MSP Applications Project GFA List Final MORPHEUS MSP Applications Project GFA List As required attend meetings and engage with the MORPHEUS GFA Manager | As per Schedule As required from Nov 18 until end of contract | Regular 20 Working Days (Schedule 4 Special?) |
| 4.11.4 | The Contractor shall collate the information required to produce a Prior Information Notice (PIN), in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. See relevant PD artefact at Schedule 19. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 4.11.5 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the MORPHEUS MSP Applications Project, ensuring compliance with the MORPHEUS Procurement Strategy. The Contractor shall ensure that the MORPHEUS Project Lead for the MORPHEUS MSP Applications Project approves all updates/ changes to the MORPHEUS MSP Applications Procurement Strategy. The MORPHEUS MSP Applications Procurement Strategy shall be compliant with Procurement Strategy template at Schedule 7. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 4.11.6 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the MORPHEUS MSP Applications Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 4.11.7 | The Contactor shall support the BATCIS Commercial Team when developing the MORPHEUS MSP Applications Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - Any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | MORPHEUS MSP Applications Contract Notice | As per Schedule | Regular 5 Working Days |
| 4.11.8 | The Contractor shall create, develop and update the MORPHEUS MSP Applications supplier selection project, security and technical questions for the MORPHEUS MSP Applications Dynamic Pre-Qualification Questionnaire (DPQQ). The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate MORPHEUS Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical questions Mature DPQQ PM/ Technical questions | As per Schedule As per Schedule | Schedule 5 |
| 4.11.9 | The Contractor shall create, develop and update the MORPHEUS MSP Applications supplier selection evaluation criteria for the project, security and technical questions for the MORPHEUS MSP Applications DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MSP Applications DPQQ. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least ten (10) working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation Criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.11.10 | The Contractor shall provide a SOR for the MORPHEUS MSP Applications Project. The Contractor shall engage with all relevant stakeholders when developing the MORPHEUS MSP Applications SOR to ensure that all necessary aspects of delivery are considered. The Contractor shall agree the SOR format with the BATCIS Commercial Team and relevant Project Lead. The SOR shall consider the MSP Applications Project through the relevant project life cycle and consider all relevant DLOD areas. As a minimum the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 4.11.11 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the MORPHEUS MSP Applications Project. This shall include as a minimum: - the approved MORPHEUS MSP Applications SOR; - timelines for activity during the procurement; - providing project management input to the MORPHEUS MSP Applications Contract including as a minimum: - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance, ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS MSP Applications tender assessment questions; and - the MORPHEUS MSP Applications tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 4.11.12 | The Contractor shall create, coordinate, update, manage and maintain the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Applications Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Applications Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the BATCIS Commercial Team. The Contractor shall ensure that the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Applications Project additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the MORPHEUS MSP Applications Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least 10 working days prior to the release of the Tender. | Draft the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Applications Project Mature the tender assessment questions and the tender assessment questions evaluation criteria for the MORPHEUS MSP Applications Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 4.11.13 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the MORPHEUS MSP Applications Project. The Contractor shall secure any relevant security exemptions with the support of the BATCIS Commercial Team. See relevant GFI artefact at Schedule 7. | MORPHEUS MSP Applications SAL | As per Schedule | Schedule 5 |
| 4.11.14 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the MORPHEUS MSP Applications Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority MSP Applications PM | As per Schedule | Monthly Report |
| 4.11.15 | The Contractor shall at the direction of the MORPHEUS Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the MORPHEUS MSP Applications Project, this may as a minimum include: - Industry days, i.e. Bidder Conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/As Agreed with MORPHEUS Project Lead |
| 4.11.16 | Competition Phase. The Contractor shall ensure the delivery of the competition phase by co-ordinating and managing the delivery of the tasks from Section 4.11.16 to Section 4.11.23. |  |  |  |
| 4.11.17 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include as a minimum: - once provided clarification questions from Industry by the BATCIS Commercial Team, obtaining a response from the relevant Subject Matter Expert within three (3) working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry clarification questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 4.11.18 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase List of negotiation topics for each tender, if required RODs from the MORPHEUS MSP Applications Tender Assessment Panel | As per Schedule As per Schedule | Monthly Report Regular 5 Working Days |
| 4.11.19 | At the direction Authority Lead, the Contractor shall contribute/ co-ordinate Industry engagement (comprising Presentations, Venue Organisation, and Agenda Development etc.) in the form of a Bidders Conference. | MORPHEUS MSP Applications Project Bidders Conference | As per Schedule | Regular 5 Working Days |
| 4.11.20 | The Contractor shall provide support to the MORPHEUS MSP Applications Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation list of attendees Negotiation Action List Negotiation Record of Decisions | As per Schedule | Regular 5 Working Days |
| 4.11.21 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum: - co-ordinate and manage all non-commercial clarification questions by engaging with relevant subject matter experts and providing a response to non-commercial clarification questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the appropriate MORPHEUS Project Lead; - co-ordinate and manage the Authority non-commercial clarification questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial clarification questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry clarification questions during the tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority clarification questions during the tender assessment phase RODs from the MORPHEUS MSP Applications Tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 4.11.22 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19), and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the MORPHEUS Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 4.11.23 | The Contractor shall provide support to the Contract Award phase of the MORPHEUS MSP Applications Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the MORPHEUS MSP Applications Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender debrief packs Attendance and contribution to Tender debrief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 4.11.24 | Post Competition Phase. The Contractor shall manage the Activities set out between Section 4.11.24 and Section 4.11.29. |  | As per Schedule |  |
| 4.11.25 | The Contractor shall manage and maintain the day-to-day relationship between the MORPHEUS MSP Applications Project and the Authority, utilising PM tools and techniques, giving due consideration to the provisions and requirements of the MORPHEUS MSP Applications Contract. If any dispute arises with the MORPHEUS MSP Applications, the Contractor shall immediately inform the Authority Commercial Officer. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and Systems Integrator MORPHEUS MSP Applications Monthly Report Relationship Management Section | Monthly up to end of PSS contract | Regular 10 Working Days |
| 4.11.26 | The Contractor shall manage any changes to the MORPHEUS MSP Applications Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the MORPHEUS MSP Applications SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the MORPHEUS Change Control Procedure | As required | Regular 20 Working Days |
| 4.11.27 | The Contractor shall manage delivery of the MORPHEUS MSP Applications. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the MORPHEUS MSP Applications Contract; - engaging with the MORPHEUS MSP Applications Project to address any queries regarding deliverables and any issues with the delivery of the MORPHEUS MSP Applications Contract; and monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the MORPHEUS MSP Applications Project for improvements to the Contract; and - engaging with an Authority Project Manager to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS contract | Monthly Report |
| 4.11.28 | The Contractor shall engage with the MORPHEUS GFA Manager to ensure the timely delivery of all Authority obligations under the MORPHEUS MSP Applications Contract including post contract changes, updates and validations. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the MOPRHEUS MSP Applications Contract | Monthly up to end of PSS contract | Monthly Report |
| 4.11.29 | The Contractor shall manage the MORPHEUS MSP Applications Project in accordance with the Governance process (see relevant PD artefact at Schedule 19). | Formal monthly report Compliance with the MORPHEUS MSP Applications Project Governance Schedule | As required up to end of PSS contract | Monthly Report |

4.12	Co-ordinating Design Organisation (CDO) PM Role.   As the Authority increases its responsibility as the System Design Authority for MORPHEUS, there will be an increasing amount of internal technical activity that will be required to be run on a formal project basis.  There is therefore a requirement for PM support to internal CDO activities.  This is distinct from the PM support to formal acquisition activities in which the CDO plays a role described in Sections below.

| Serial ID | Description/ Deliverables | Outputs | Output date |  |
| --- | --- | --- | --- | --- |
| 4.12 | The Contractor shall provide Project Management support to the MORPHEUS Chief Engineer managing internally-initiated CDO projects. |  |  |  |
| 4.12.1 | The Contractor shall create, manage and maintain the appropriate CDO Project Work Breakdown Structure (WBS). The Contractor shall update the WBS in line with any feedback from the Authority. | An up-to-date CDO Project WBS | As required from contract award until end of contract | Regular Review Process |
| 4.12.2 | The Contractor shall identify and capture the CDO Project assumptions. The CDO Project assumptions shall be recorded in the assumptions tab of the Project PM Workbook (see relevant GFI artefact at Schedule 7). The Contractor shall apply the relevant MORPHEUS Assumption Management (AM) Process (see relevant GFI artefact at Schedule 7). | An up-to-date Assumptions Log in the CDO Project PM workbook | Fortnightly from contract award until end of contract | Monthly Report |
| 4.12.3 | The Contractor shall attend and support the CDO Chief Engineer at the relevant MORPHEUS Assumption Panels (MAPs) in compliance with the relevant MORPHEUS Assumption Management Process. | Attendance at the appropriate relevant MAPs | Monthly | Monthly Report |
| 4.12.4 | The Contractor shall review all of the CDO Project assumptions with the appropriate CDO Chief Engineer. The review shall as a minimum consider the following: - key milestones and identify new assumptions/ opportunities against those; - review progress of the delivery of mitigation actions and ensure that they are having the desired assumption reduction impacts; - provide Chief Engineer approval for escalation of assumptions; - provide Chief Engineer acceptance that the proposed assumptions will recommended for closure or transfer to issue at the next relevant MAPs; and - perform a quality assurance review of CDO assumptions for the function. | Participation in the Chief Engineers Reviews | Day before the relevant MORPHEUS Projects Schedule Review | Monthly Report |
| 4.12.5 | Dependencies. The Contractor shall maintain the project dependencies within the project management Workbook (see relevant GFI artefact at Schedule 7), escalating appropriately to the Programme Level Dependency Log. The Contractor shall participate in cross-Project dependency reviews. The Contractor shall manage the project dependencies that exist with the other MORPHEUS Projects e.g. MTRC, System Integrator, Platform Integration, Applications MSP, DIO and LSRC. | Participation in the Chief Engineers Reviews | Day before the relevant MORPHEUS Projects Schedule Review | Monthly Report |
| 4.12.6 | The Contractor shall identify, create, capture, manage and maintain the relevant MORPHEUS Projects risks and issues by undertaking the following activities as a minimum: - recording Project risks and issues in the PM Workbook; - escalating changes to existing risks or issues and any new risks or issues which are created or identified to the appropriate relevant MORPHEUS Chief Engineer for endorsement; - providing all new or amended risks to the relevant MORPHEUS Risk Manager at the weekly engagement; - capturing and maintaining cross Defence Lines of Development risks within ARM; - input and maintain robust basis of estimates for risks performance cost & time and implement a Risk Mitigation Plan for each risk; - identify resources required to manage individual risks; and - apply effective risk management techniques, in accordance with the ASG Identify, Assess, Plan, Do, Review, cycle process. | Up-to-date the relevant tabs of the PM workbook Update ARM in conjunction with the relevant MORPHEUS Risk Manager | Fortnightly from contract award until end of contract As required from contract award until end of contract | Monthly Report |
| 4.12.7 | The Contractor shall participate in the fortnightly risk and issue review providing input on the CDO Project risks and issues. | Participation in the appropriate risk and issue Review | Fortnightly from contract award until end of contract | Monthly Report |
| 4.12.8 | The Contractor shall maintain and complete the Project History and Learning From Experience (LFE) Sections contained in the relevant MORPHEUS Project PM Workbook (see relevant PD artefact at Schedule 19). The Contractor shall capture LFE as events occur and enter it in the LFE section of the relevant MORPHEUS Project PM Workbook. The Contractor shall plan and conduct periodic LFE workshops with the appropriate CDO Chief Engineer and any other relevant stakeholders, at key stages of the project lifecycle (i.e. at the end of the competitions). LFE review stages must be agreed with the CDO Chief Engineer one month in advance and included in the Project Schedule. | Input to the LFE section of the PM Workbook Input to the project history section of the PM Workbook LFE workshop | As required from contract award until end of contract | Monthly Report |
| 4.12.9 | The Contractor shall attend, participate and input into all of the requisite meetings relating to the CDO Project Governance (see relevant PD artefact at Schedule 19) for this Contract. | Attendance, participation and input to all of the relevant MORPHEUS Project meetings | Fortnightly from contract award until end of contract | Monthly Report |

- Co-ordinating Design Organisation (CDO).   The CDO is responsible for the engineering management of the MORPHEUS Programme.  It develops, maintains and operates the engineering processes required for MOD to be the System Design Authority for MORPHEUS.  It is led by the MORPHEUS Chief Engineer and supports the Programme throughout the systems engineering lifecycle.

Note: For SOR 5.0 where reference is made to EvO, after December 2020 these requirements ought to be read as being for both EvO and MORPHEUS and accordingly be considered enduring.  References to the EvO Transition Partner (EvO TP) ought to also be read as the MORPHEUS Systems Integrator which replaces the EvO TP.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 5.1 | The Contractor shall provide the Technical Management of the CDO, including as a minimum the following: - maintaining and updating the Systems Engineering Management Strategy (SEMS) for the MORPHEUS Programme in consultation with the MORPHEUS Programme Manager and the MORPHEUS Chief Engineer; and - maintaining and updating the Systems Engineering Management Plan (SEMP) for the CDO, including development and documentation of any engineering processes required in consultation with the MORPHEUS Chief Engineer and the Technical Authority Lead. | Annual update to SEMS Bi-annual update to SEMP | Sep Jun and Dec updates | Regular 10 day review |
| 5.1a | The Contractor shall produce a monthly report on the progress of engineering activities which shall as a minimum include status updates, and as attachments to the report the outputs of, the following activities: - maintaining the Agile Task List (Kanban) for the CDO. As a minimum the Agile Task List shall be populated, updated, reviewed and available via the MORPHEUS CDO SharePoint to all CDO team members; - organising, invite attendees, record RODs and chair the fortnightly engineering team meetings. The Contractor shall collate briefing material for the meeting provided by Engineering Team members and provide sufficient copies for all attendees; - acting as the CDO point of contact for the Transformation Activities being supported by the Transition Partner (TP) in the Joint Programme Organisation (JPO). The Contractor shall engage, consult and co-ordinate with the TP JPO Chief Engineer, and the MORPHEUS Chief Engineer to identify and develop required engineering governance and processes for the Authority’s CDO and MORPHEUS Programme. - engage, consult and co-ordinate with the MORPHEUS Chief Engineer, the Technical Authority Lead, and the Lead Architect to manage the CDO technical resource, both Crown Servant and PSS, across all CDO locations including: vendor facilities, JPO and BATCIS to undertake the Authority responsibilities for design, assurance and TP knowledge transfer; - co-ordinating and managing all Engineering reporting including status reports, scheduling activity, risk, MDAL as requested by the MORPHEUS Programme PSO; - managing and administering the CDO change management process; and - organise, invite attendees and record RODs fortnightly for Change Review Boards with the CDO Leadership Team and any other relevant stakeholders where appropriate. | Monthly Engineering Activities Report inclusive of the output. | Monthly | Monthly Report |
| 5.2 | Systems Engineering Support. The following sections describe the technical tasks that shall be undertaken by the Contractor in the CDO in support of the systems engineering lifecycle. In general, all individuals that contribute to these tasks will require Systems Engineering competencies, but individuals will be required in addition to demonstrate specific technical subject matter expertise in one or more of the following specialties as a minimum detailed in Section 5.2.1 to Section 5.2.11: - Application and Application Infrastructure Design, including Virtualisation and Cloud Technologies; - Information Management; - Voice and Multimedia Services; - System and Security Management; - Network technologies, including specialisations relevant to the tactical domain; - Radio and Bearer integration, including Radio Frequency engineering and co-site mitigation; and - Physical (platform) integration, including Generic Vehicle Architecture, power technologies and Electromagnetic and Environmental Effects (E3). |  |  |  |
| 5.2.1 | The Contractor shall provide support to the MORPHEUS Strategy Pillar and the Army Capability Teams in developing options for future MORPHEUS Capability Releases, including as a minimum: - advising and participating in innovation activities, engaging, consulting and coordinating with Army Sponsors, Industry and the Research Community; - acting as the MORPHEUS CDO point of contact into Army Experimentation activities; - acting as the MORPHEUS CDO point of contact into any relevant Dstl research programme, advising the Army on research requirements, supporting research demonstrations, evaluating research deliverables and producing technical summaries; and - undertaking Technology Watch. The Contractor shall capture the outputs from all of these activities in a bi-annual research summary and technology report which shall provide suitably detailed recommendations on whether any Technical Feasibility and/ or Option Trade Studies should be undertaken. | Bi-annual research summary and tech watch report | Jun and Dec updates | Regular 10 day review |
| 5.2.1a | The Contractor shall have the capability to undertake Technical Feasibility and Options Trade Studies: these shall be tasked through the Schedule 10 Tasking Order Procedure. | Technical Feasibility and Options Trade Study Report | As required | As agreed |
| 5.2.2 | The Contractor shall undertake for the MORPHEUS Architecture Technical Lead role including ensuring coherence with wider architecture activities in ISS and Army HQ, this shall include as a minimum: - maintaining the Architecture Management Strategy (AMS), taking account of, as a minimum, complementing and aligning with the MORPHEUS Systems Engineering Management Plan, detailing the approach to development and coherence of the MORPHEUS Architecture with the wider Defence enterprise; - maintaining and updating as required (working with ISS Design) the MORPHEUS Service Architecture, with particular emphasis on: - updating the mapping between MORPHEUS Service Architecture and MORPHEUS Target System Architecture; and - publishing the MORPHEUS Service Architecture to the Tactical Architecture Forum (TAF) periodically. | Bi-annual update to AMS Bi-annual update and publication to Morpheus Service Architecture | Jun and Dec updates Sep and Mar | Regular 10 day review |
| 5.2.2a | The Contractor shall as part of the Architectural Leadership activity undertake and provide a report on as a minimum the following activities: - supporting the MORPHEUS Chief Engineer in attending the quarterly ISS Deployed Architecture Steering Group; - providing the technical secretariat function to the MORPHEUS Architecture Working Group (AWG) (including the functions of the TAF Technical Coherence Group); - supporting the ongoing development and maintenance of the Army Operating Model, including working with the Army Enterprise Architecture Lead; - supporting the development of any Service Design Packages to which MORPHEUS will contribute (including support to the Capability Introduction process as required); - supporting MORPHEUS submissions to the Design Authority Board; - leading the co-ordination with other Architectural Authorities across Defence, particularly the Land Technical Authority with regard to co-ordination with the Generic Vehicle Architecture (GVA), the Generic Soldier Architecture (GSA) and Generic Base Architecture (GBA) including attendance and participation in appropriate technical working groups; and - conducting requirements identification and capture activities (using MBSE techniques) working with the Army and ISS architect communities, as well as system users, in support of future capability releases in the Evolutionary Capability Development Phase. | Monthly Architecture Activities Report Hold quarterly AWG meetings and produce RODs for the meetings | Monthly from Contract Award | Monthly Report |
| 5.2.2.b | The Contractor shall have the capability to undertake requirements analysis, using the MORPHEUS Service/ Target System Architecture, working in conjunction with the BATCIS Requirements Team, when changes arise to any of the following areas: - changes in User requirements; - technical issues including obsolescence; and - innovation opportunities. The architecture requirement analysis reports shall be tasked through the Schedule 10 Tasking Order Procedure. | Architecture Requirement Analysis Report | As required | As agreed |
| 5.2.3 | The Contractor shall provide technical support to the Strategy and Approvals team. This shall include as a minimum: - supporting engagement with the Scrutiny community, including preparation and presentation of answers to Clarification Questions from the Scrutiny community; - creating, updating, managing and maintaining the technical elements of Procurement Strategies for MORPHEUS Programme competitions; and - creating, updating, managing and maintain the technical elements for the development of Review and Information notes and associated documentation including Frequently Asked Questions. | Written Clarification answers and Presentations Technical elements of procurement strategies Technical input to Review and Information Notes | As required by the Schedule | Monthly Report |
| 5.2.4 | The Contractor shall provide technical support to the Project Management Team in development of the materials to enable all procurements relating to MORPHEUS, including as a minimum: - creating, updating, managing and maintaining technical specifications, technical pre-qualification questions and evaluation criteria, technical tender assessment questions and evaluation criteria, technical elements of the tender pack and statements of requirements for the MORPHEUS Programme competitions. | Up-to-date Technical Specifications and Statements of Requirements Up-to-date technical PQQ and evaluation criteria Up-to-date technical Tender questions and evaluation criteria Up-to-date Engineering elements of the Tender Pack | See Schedule specified in Sections 4.1 through 4.10 above | Regular - day review |
| 5.2.4a | The Contractor shall undertake and report on, as a minimum, all of the following activities when the Authority is undertaking competitions; - providing technical support to Industry Days, including as a minimum: - preparation of briefing material; - delivering presentations; and - participation in briefings and panels. - during competitions, providing responses to Clarification Questions raised by Industry at any stage of the procurement, within three (3) working days; - assessing bidder responses to the MORPHEUS Programme competitions, both at the pre-qualification stage and tender stage recording robust, and commercially appropriate justifications for scoring using any tool the Authority requires; - providing technical input to negotiations as required; and - supporting the Tender Assessment Panels in support of the moderation bid evaluation. | CDO support to competitions monthly report Attendance and participation in Industry Days and Bidders Conferences Attendance and participation in Tender Assessment Panels Clarification Question responses | As required by the Schedule | Monthly Report |
| 5.2.5 | The Contractor shall support the CDO in the management of the MORPHEUS Target System Architecture (MTSA). The MORPHEUS System Model is captured in SysML and managed in the PTC Integrity Modeller toolset, including as a minimum: - Support activities corresponding to the development and direction setting of the MORPHEUS Target System Architecture specifically: - attendance and participation at the EvO System Coherence Team (ESCoT) meetings providing relevant technical representation according to the technical priorities set by the MORPHEUS Chief Engineer and the MORPHEUS Technical Authority; - advance preparation of technical discussion material to support ESCoT working sessions; - provide technical leadership and chair ESCoT sub-groups on an as-required basis; - provide technical guidance to the design and development of TAF workshops as required by the TAF Manager; and - provide technical support to the execution of TAF workshops as required by the TAF manager, including preparation of supporting materials, technical facilitation of workshop discussions and preparation of workshop outputs. | MORPHEUS Target System Architecture Technical Development Report | Quarterly from delivery of the MTSA | Regular 10 days review |
| 5.2.5a | The Contractor shall manage the MORPHEUS Target System Architecture (MTSA) in the PTC Integrity Modeller toolset, including as a minimum: - provide tool administration services, including managing the user-base for the tool; - manage the coherence of the JPO MTSA model with the EvO repository used by the EvO TP; - produce extracts from the repository in the form of the MORPHEUS Architecture Document Suite to support CDO business including industry engagement; and - provide configuration management of a DDS open standard for the development and maintenance of the MORPHEUS DDS Network Message Set (NMS) Configuration Items (DDS NMS CIs). | MORPHEUS Target System Architecture Model usage and status report | Quarterly from delivery of the MTSA | Regular 10 days review |
| 5.2.5b | The Contractor shall undertake a study into available alternative SysML toolsets, paying particular regard, as a minimum, to cost of ownership, and Industry penetration. Industry engagement should be via the Tactical Architecture Forum (TAF). Make a recommendation to either remain with the current (Integrity Modeller) toolset, or propose an alternative toolset. Note that any task to translate the current model into a future toolset would likely fall to the future MORPHEUS System Integrator. | MORPHEUS Model toolset recommendation report | Apr 2019 | Regular 10 day review |
| 5.2.6 | The Contractor shall engage with current or potential suppliers of MORPHEUS services or goods to assess EvO/ MORPHEUS Architectural and Design Artefacts (AAs) for a Solution Building Block (SBB), and undertake an assessment and testing regime, including as a minimum: - an assessment as to whether the SBB conforms to the MORPHEUS Architecture Principles; - an assessment as to whether the SBB features conform to the agreed Openness Tests; - an assessment as to the suitability and appropriateness of the design decisions; - an assessment of the clarity, comprehension and completeness of the AAs such that it can be exploited by other developers; and - an assessment that the AA includes sufficient information to allow the Authority to be Vendor Independent. | Architecture and Design Assessment and Conformance Report for each SBB | On-going from CA + 1 months | Regular 10 day review |
| 5.2.6a | There are expected to be a total of 120 SBBs. The AAs associated with all SBBs will undergo logical and openness assessment. The assessments may be based on formal deliverables of AAs, or may be based on evidence gained from working closely alongside current supplier agile development teams. The Contractor shall provide a monthly summary of the progress in these assessments, including as a minimum: - statistics regarding the number of AAs available, the number assessed and the number remaining; - statistics regarding the number of SBBs available, the number assessed and the number remaining; - statistics regarding the provisional results of these assessments, including the number of passes, fails and pending further information; - reasoning behind assessment failures; - details regarding tests defined, including whether Industry standard or bespoke; and - remedial actions required. | Architecture and Design Dashboard Report | Monthly from CA + 1 month | Regular 10 day review |
| 5.2.7 | The Contractor shall provide strategic guidance to and leadership of the Tactical Architecture Forum (TAF), supporting the MORPHEUS Chief Engineer and working closely with the CDO Architecture team, and the CDO Systems Engineering team including as a minimum: - management of the TAF Portal, including developing a TAF engagement plan, in conjunction with the MORPHEUS stakeholder and communications manager, to support the assurance activities of the CDO; - manage the receipt, acknowledgement, and response to TAF comments on the MORPHEUS Service and System Architecture, supported by the Systems Engineering team; - Organise technical Industry engagement ‘surgeries’ for one-to-one receipt and response to Industry comments on architectural documentations: - Booking of meeting room facilities in BATCIS or at the JPO; and - Organisation and diary management of CDO systems engineering representation to support meeting. - Organise up to four architectural deep-dive workshops per year including: - Organisation and booking of a venue for up to 40 delegates, including refreshments; - Preparation of visual aid materials (supported by the systems engineering team); - Management of registration arrangements, including checking of security clearances and IPR agreements where appropriate; and - Communications before and after the event including leading on the preparation of meeting notes. - Organisation of up to one TAF Plenary event per year including: - Organisation and booking of a venue for up to 200 delegates, including refreshments; - Preparation of visual aid materials (supported by the systems engineering team); - Management of registration arrangements, including checking of security clearances and IPR agreements where appropriate; and - Communications before and after the event including leading on the preparation of meeting notes. The Contractor shall provide a monthly report on the TAF Activities providing suitable detail on the key outputs of all of the activities in Section 5.2.7 undertaken in the month. The Contractor shall ensure that all documentation is checked with the BATCIS Commercial Team, at B2 level or above, unless otherwise agreed with the Authority prior to release to the TAF. | Monthly TAF Activities Report | Monthly | Monthly Report |
| 5.2.7a | The Contractor shall update, manage and maintain the TAF document suite, including as a minimum: - the TAF strategy document; - the TAF Terms of Reference; and - The TAF Frequently Asked Questions document. The Contractor shall ensure that all documentation is checked with the BATCIS Commercial Team, at B2 level or above, unless otherwise agreed with the Authority prior to release to the TAF. | TAF Strategy – Annually TAF TOR – Annually TAF FAQ – Bi-annually | Jun Jun Jun, Dec | Regular 10 day review |
| 5.2.8 | The Contractor shall support the MORPHEUS Technical Authority Lead to provide technical leadership of the MORPHEUS Design including as a minimum the following: - develop design options and conduct systems analysis and design partitioning trade studies in order to understand implementation options for service and capability uplifts using performance models where appropriate in support of design analysis and trade studies; - produce technical performance specifications for applications and MORPHEUS subsystems; and - maintain the system performance model for the MORPHEUS system. Note that systems trade studies may require the formation of a multi-disciplinary team involving a number of systems engineering specialties. | Decision Analysis Report Technical Performance Specification | As required As required | Regular 10 day review |
| 5.2.9 | The Contractor shall provide Systems Engineering Support to the MORPHEUS Technical Authority on the design and integration assurance of the MORPHEUS Projects, including as a minimum, the EvO Systems Design, the Enhanced High Capacity Data Radio (EnHCDR) and the BMA System Design. This shall include as a minimum: - systems engineering input, as directed by the MORPHEUS Technical Authority Lead, across all systems engineering specialties, to the development process, including as a minimum: - support to prioritisation of Epics, working with the User, the Authority Requirements Team and the MORPHEUS suppliers; - support to Programme Increment Planning activities, working with the User, the Authority Requirements Team and the MORPHEUS suppliers; - liaison, as required, with the agile team Product Owners and their technical teams to support prioritisation and technical decision making; - liaison, as required, with the supplier systems team; and - informal review of supplier deliverables in advance of formal delivery. - systems engineering input, as directed by the MORPHEUS Technical Authority Lead, across all systems engineering specialties, to the System Integration process, including as a minimum: - attendance at Integration planning activities; - provision of technical support to Systems Integration demonstrations and events; - review and prioritisation of systems integration issues; and - support to problem solving and issues resolution. The Contractor shall provide a monthly report with suitable detail on key outputs relating to the activities which have been undertaken in the month, this shall also make reference to activities in Section 5.2.9a. | Assurance Activities Report to CDO Assurance Lead RODs in the JPO Decisions Log | Monthly As required | Monthly Report |
| 5.2.9a | The Contractor shall conduct formal Technical reviews of MORPHEUS Supplier deliverables in accordance with the published process: - use of the Authority tool for recording and categorising appropriate comments; - completion of technical review activities within the contracted timescales; - support to the Chief Engineer or Technical Authority Lead by attendance at Authority pre-review meetings, or attendance at review meetings; and - support to the Engineering Manager in checking supplier completion of review actions. | Formal review comments recorded in MORPHEUS Assurance Management Tool | As required | Monthly Report |
| 5.2.10 | The Contractor shall provide technical support to test and acceptance activities for all MORPHEUS Projects, including the following activities as a minimum: - support the development of test strategies, working with the Army sponsors and MORPHEUS Suppliers; - support the development of the requirement for the interim and enduring MORPHEUS Test and Reference Centre (MTRC); - support the development of test planning; - support the development of test scripts; - support the knowledge transfer from the Transition Partner of the system test and acceptance activities to the JPO; - conduct Verification and Validation on TP’s system and subsystem test scripts; and - support the integration of MORPHEUS test and reference into the broader ISS Integration, Test and Transition (IT&T) strategy. | Engineering input to the Test strategies, plans and scripts | As required in line with the Schedule | Monthly Report |
| 5.2.11 | The Contractor shall provide systems engineering support to the MORPHEUS Platform Integration Team, including: - manage and maintain the rationalised set of MORPHEUS Design Lines, including support to the Technical Authority on configuration change management; - support to the MORPHEUS Platform Integration Group and the LE TacCIS Integration Working Group; - development of System Requirements for the integration of MORPHEUS, working in conjunction with the Platform Design Authorities; and - propose changes to the EvO Design by raising platform integration issues into the MORPHEUS Change Management process. | MORPHEUS Design Line updates | As required | Regular 5 day review |
| 5.3 | The Contractor shall support the Chief Engineer in the production of Safety and Environmental documentation related to the MORPHEUS Programme, including as a minimum: - provide advice and guidance on Safety and Environmental factors related to the design of the MORPHEUS System being produced by EvO TP; - reviewing, assuring, commenting and feeding back on Safety and Environment aspects of MORPHEUS Supplier documentation; - organise, invite attendees and produce RODs for the MORPHEUS Project Safety and Environmental Panel; and - manage, maintain and update the MORPHEUS Hazard Log. | Input to Engineering team meetings reporting on progress & issues Bi-annual update to the MORPHEUS Safety and Environmental Management Plan Up-to-date MORPHEUS Hazard Log | Fortnightly Jun and Dec As required | Regular 10 day review |
| 5.4 | The Contractor shall support the Chief Engineer and the MORPHEUS Security Manager in undertaking the necessary activities to ensure that the EvO solution reaches accreditation, and will as a minimum: - manage, maintain and update the EvO risk assessment to support the accreditation Transition Partner Contract; - manage, maintain, and update the MORPHEUS Accreditation Strategy; - organise, invite attendees and record RODs for the Security Working Group (SWG) and the Security Technical Liaison Meeting (STLM) (on a minimum of a quarterly basis); - support the prioritised work programme from the SWG (on a minimum of a quarterly basis) including, as a minimum, the IdAM approach, Data at Rest solution, Crypto strategy. The SWG will direct the priority of the outputs, however, all outputs will be required; and - review, assess, comment and feedback on the EvO Security Architecture and Design. | - Up-to-date MORPHEUS Accreditation Strategy - Up-to-date EvO Risk Assessment - RODs for SWG and STLM - IdAM Approach - Data at Rest solution - Crypto Strategy | - As required - As required - As required - As directed by the SWG - As directed by the SWG - As directed by the SWG | Regular 10 day review |
| 5.4a | The Contractor shall support the Chief Engineer and the MORPHEUS Security Manager in undertaking the necessary activities to ensure that the MORPHEUS Projects reach accreditation, and will as a minimum: - support the MORPHEUS Project Managers in producing Security Aspect Letters as appropriate for each of the MORPHEUS Projects; and - provide security advice and guidance to the MORPHEUS Project Managers as required. | MORPHEUS Security Activities Report – Accreditation Elements | Monthly | Monthly Report |
| 5.4b | The Contractor shall support the MORPHEUS Lead Architect in specifying the security aspects of the MORPHEUS role in the Deployed Enterprise: - engage with the ISS Deployed Architect and the ISS Principal Cyber and Information Assurance Architect to ensure that MORPHEUS remains coherent with the broader ISS Intent for security in deployed; - document the MORPHEUS role in the Enterprise Security and System Management (ESySM) architecture; and - contribute to the ISS Gateways strategy, including understanding the MORPHEUS role in the evolution to a Protected Core Architecture (Deployed). The Contractor shall provide a monthly report with suitable detail on key outputs relating to the activities which have been undertaken in the month, this shall also make reference to activities in Section 5.4. | MORPHEUS Security Activities Report | Monthly | Monthly Report |
| 5.5 | Chief Engineer Role. The Chief Engineer function will be provided by a senior, suitably experienced, full-time equivalent. The Chief Engineer takes overall responsibility for the engineering elements (incl. Safety) of the MORPHEUS Programme and will report directly to the MORPHEUS Programme Manager. The Chief Engineer will provide monthly reports and will report at the One-Star Programme Board as required. The Contractor shall provide the Chief Engineer who will be responsible for the following, as a minimum: - Providing advice to the MORPHEUS Projects on engineering policy, rules and guidance to ensure that repeatable successful outcomes are achieved throughout; - The implementation and maintenance of effective engineering governance arrangements in the Programme and provide assurance to the MORPHEUS Programme Manager on the ‘safe and professional’ status of the Programme; - Promoting the use of high-level engineering plans (including SEMS, SEMP, Architecture Management Plan, Safety Management Plan etc.) for the Programme; - Proactively ensuring that the correct levels and currency of SQEPs are supporting the Programme, highlighting areas of risk/ concern to the MORPHEUS Programme Manager for appropriate action; - Supporting the senior engineers by liaising with respective roles within ISS to co-ordinate activities between ISS, BATCIS and the MORPHEUS contractors; - Leading the implementation of Agile SAFe in the Programme; - Attending (or through delegation) the MORPHEUS Project Boards, Working Groups (WGs), etc. and ensure that outputs of the activities are implemented; - Responsible for the successful implementation and operation of the engineering elements of the JPO; - Carry out day-to-day management and leadership of MORPHEUS CDO (engineering team); - Ensure that the engineering function contributes to the overall Programme procurement approach and that the approach is cognisant of the evolving Architectural and Systems Design; - Ensure the Architecture development is fully supported by ISS and Army architects. Build relationships across ISS, DE&S, Army HQ (and other Front Line Commands) and wider Industry to ensure MORPHEUS is consistent with other evolving projects and programmes; - Provide senior engineering management representation at the internal: MORPHEUS Programme Manager Project Review meeting (fortnightly), MORPHEUS Programme Manager Management Team meeting (alternate fortnightly); Technical Working Groups and Engineering Team meetings (to co-ordinate and prioritise the work of the technical work-streams) and routine Risk Reviews; - Provide management and oversight of technical domain related risks and establish appropriate risk mitigation plans. In conjunction with the engineering domain leads and the Programme Risk Manager, update and maintain the engineering risks, issues and opportunities registers – particularly progress being made against mitigation plans. - Establish and maintain a close day-to-day working relationship with the Transition Partner’s Chief Engineer; enabling early identification of issues and successes; - Ensure the proposed methods for regulating openness are effective in controlling the Transition Partner delivery of an open architecture and support the work of the TAF to achieve this aim. | Chief Engineer Report One-Star Programme Board Reporting | Monthly from Contract Award | Regular - day review |

- Joint Programme Organisation.   The Joint Programme Organisation (JPO) is an integrated programme management and engineering organisation, with a physical office in Bristol, but with a much broader geographical membership.  It will manage the execution of the EvO Baseline, reporting to the MORPHEUS Programme Board, and is the focal point for the business transformation of the Authority into the quasi-prime for MORPHEUS and achieving Vendor Independence.  It will manage and execute a planning and change process that integrates all key stakeholders to ensure the delivery of EvO, and subsequently MORPHEUS, that meets the User’s needs and expectations within Performance, Cost and Time budget.  It is underpinned by a collaborative working environment that provides a single source of truth for the Programme that keeps all stakeholders all-informed and simplifies governance and reporting.

Note: The Authority does not know the form and location of the Enduring JPO, however, the requirement for support to the JPO will endure past the end of the EvO TP Contract to support the future MORPHEUS Supply Chain.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 6.1 | The Contractor shall manage the assurance process of multiple projects in line with the Evolve to Open (EvO) Transition Partner (TP) Contract, through its lifecycle. The Projects are: - CONDUCTOR. CONDUCTOR is a layered logical grouping of de-coupled, independent integration services that enable the Tactical Internet. - MANAGE. MANAGE is a suite of system management applications and services. - MPPS. Modular Platform Processing System is a product suite that provides an open, scalable and modular hardware solution suitable for soldier, vehicle, and static platforms. This shall include, as a minimum: - manage the schedules for the Projects (utilising Enterprise Project Management & Shared Data Environment), ensuring the project stays on track and take corrective actions when necessary; - implement and manage project changes and interventions to achieve project outputs; (following the MORPHEUS Change Control Process); - ensure RAIDO is captured and managed using relevant tools (MS Excel, ARM, ADMIS, MDAL); - track project deliverables & Milestones using Enterprise Project Management & JPO’s Programme controls tools, in line with the EvO TP Contract; - work in conjunction with the Business Capability team (team responsible for enabling business transformation and delivery of the JPO) to deliver the TP Contract within contracted timescales; - work on the Military Capability (the delivery of the EvO Architecture, System Design and Baseline) of the EvO TP Contract; - engage and support the Trials Management team to execute trials activities for the EvO TP Contract; - liaise with Stakeholders to achieve Project objectives (on weekly basis as a minimum), including as a minimum: - General Dynamics UK; - Army HQ; and - CDO. - establish and support appropriate Project governance. Ensure alignment with other Projects’ governance structure; - review and comment on deliverables and output; - manage assurance reviews including attendance on a minimum of two (2) a month; - review and comment on outputs from Review meetings within five (5) working days of release; and - monitor and manage the timely resolution of any actions from Review meetings relating to Projects. | Status updates Comments on Deliverables | Status update Monthly report at the end of each month from Contract Award | Regular 5 day review |
| 6.1.1 | The Contractor shall update the Project PM Workbooks and provide a monthly report on the Project which, as a minimum, shall include: - an update on progress against the Work Breakdown Structure (WBS); - the status of Risk, Assumptions, Issues, Dependency & Opportunities (RAIDO) relating to the Projects in Section 6.1; and - track and report project performance. | Monthly Report PM Workbook update | Monthly report at the end of each month from Contract Award | Regular 5 day review |
| 6.2 | The Contractor shall monitor and manage the trial of the Capability to provide Tactical Internet capabilities for the MORPHEUS system. - plan, manage and execute trials and test activities using the JPO’s tools and frameworks particularly IBM Rational Toolset; - manage the Schedule (utilising Enterprise Project Management & Shared Data Environment), ensuring the Project stays on track and take corrective actions when necessary. Implement and manage project changes and interventions to achieve project outputs; - ensure RAIDO is captured and managed using relevant tools (MS Excel, ARM, ADMIS, MDAL); - track project deliverables & Milestones using Enterprise Project Management & the JPO’s Programme controls tools; - work in conjunction with the Business Capability team (team responsible for enabling business transformation and delivery of the JPO) to deliver the EvO TP Contract within contracted timescales; - work on the Military Capability (the delivery of the EvO Architecture, System Design and Baseline) of the EvO TP Contract; - liaise with Stakeholders including: - General Dynamics UK; - Army HQ; and - CDO. - establish and support appropriate Project governance. Ensure alignment with other Projects’ governance structure; - review and comment on deliverables and output; - EvO Project reviews management and attendance on a minimum of two (2) a month; - review and comment on outputs from meetings within five (5) working days of release; and - manage the timely resolution of any actions from meetings. | Status updates Comments on Deliverables | Status updates Monthly report at the end of each month from Contract Award | Regular 5 day review |
| 6.2.1 | The Contractor shall provide monthly report on C4I Project, to include: - progress against the WBS; - Risk, Assumptions, Issues, Dependency & Opportunities (RAIDO) status; and - track and report Project performance. | Monthly Report PM Workbook update | Monthly report at the end of each month from Contract Award | Regular 5 day review |
| 6.3 | The Contractor shall manage the Business Capability Project through its lifecycle. The Business Capability will deliver a Joint Programme Organisation (Facility and IT Services) and the Enabling Business Transformation (EBT) documentations. Business Capability PM. To have specific delivery of the nine (9) Project areas of: integration, scope, communication, time, cost, procurement, quality, HRM and risk against the TP: - utilising project management process to monitor, control and report on progress; - ensuring the Project stays on track and take corrective actions when necessary; - work in conjunction with suppliers to develop Business Transformation and Implementation Plans; - support the development of Operating Model Designs, Operational Improvement and Process Innovation; - plan, manage and champion change initiatives; - plan and manage staff on-boarding; - support the creation and execution of communication plans in relation to Business Transformation; - track project deliverables & Milestones using Enterprise Project Management & the JPO’s Programme controls tools; - work in conjunction with the Military Capability (the delivery of the EvO Architecture, System Design and Baseline) team to deliver the EvO TP Contract within contracted timescales; - work on the Business Capability (the delivery of the JPO and enabling business transformation) of the EvO TP Contract; - Liaise with Stakeholders including: - General Dynamics UK; - Army HQ; and - CDO. - establish and support appropriate Project governance. Ensure alignment with other Projects’ governance structure; - review and comment on deliverables and output; - EvO Project reviews management and attendance on a minimum of two (2) a month; - review and comment on outputs from meetings within five (5) working days of release; - manage the timely resolution of any actions from meetings. | Status updates Comments on Deliverables | Status updates Monthly report at the end of each month from Contract Award | Regular 5 day review |
| 6.3.1 | The Contractor shall provide monthly report on Business Capability Project, to include: - progress against the WBS; - Risk, Assumptions, Issues, Dependency & Opportunities (RAIDO) status; and - track and report Project performance. | Monthly Report PM workbook update Induction Pack Update | Monthly from Contract Award | Regular 5 day review Regular |

- Integrated Logistics Support.   It is MOD policy that Integrated Logistics Support (ILS) will be applied to all product acquisition via the application of Defence Standard Def Stan 00-600, the contracting standard for ILS requirements.  With the cancellation of Joint Service Publication JSP886 all MOD policy, processes and guidance for ILS, its elements and associated disciplines, can be found within the Defence Logistic Framework (DLF).  The requirements within Defence Standard Def Stan 00-600 will be tailored to meet the specific project needs using the policy, processes, advice and guidance within the DLF.

Note:  Work to define the Enduring Support Solution is now expected to be resourced in Statement of Requirement 7 rather than Statement of Requirement 13.  Additionally, for SOR 7.0 where reference is made to EvO, after  December 2020 these requirements ought to be read as being for both EvO and MORPHEUS and accordingly be considered enduring.  References to the EvO Transition Partner (EvO TP) ought to also be read as the MORPHEUS Systems Integrator which replaces the EvO TP.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 7.1 | The Contractor shall update, manage and maintain the BATCIS ILS Strategy in line with all relevant standards, including as a minimum: - Def Stan 00-600; and - The Defence Logistics Framework. | ILS Strategy | Monthly Review from Contract Award | Regular 5 day review |
| 7.2 | The Contractor shall update, manage and maintain the current BATCIS Supportability Analysis Strategy. The Contractor shall tailor the Supportability Analysis to ensure the incorporation of all projects within the MORPHEUS Programme. Input will be required from a number of internal and external stakeholders, including as a minimum: - MORPHEUS Project Delivery Leads for Battlefield Management Application (BMA), MORPHEUS Test & Reference Centre (MTRC), Platform Installation and Training; - MORPHEUS Project Support Office Lead; - Engineering Delivery Leads for CDO; - Risk, Assumptions and Dependency Manager; - Evolve to Open Transition Partner Project Manager; - Commercial Lead; - Costings Lead; and - Army HQ. | Supportability Analysis Strategy | Monthly from Contract Award | Regular 5 day review |
| 7.3 | The Contractor shall update, manage and maintain the BATCIS Use Study. | Use Study | As required | Regular 5 day review |
| 7.4 | The Contractor shall update, manage and maintain, in conjunction with the BATCIS Requirements Team, the ILS Supply requirements for the MORPHEUS System Requirements Document (SRD). | Up-to-date System Requirements Document | Monthly from Contract Award | Regular 5 day review |
| 7.4a | The Contractor shall update, manage and maintain the Authority Support Solution Development Tool (SSDT). The SSDT is an Information Systems & Services (ISS) mandated tool that provides a record of support solution development activity in a format which is coherent and consistent across Defence Equipment & Support (DE&S). | Up-to-date SSDT | Monthly from Contract Award | Regular 5 day review |
| 7.4b | The Contractor shall update, manage and maintain the Integrated Logistics Support Plan (ILSP) and Integrated Logistics Support Elements Plan including, as a minimum the following areas: - Supply Support; - Technical Documentation and Information; - Reliability and Maintainability (R&M); - Support and Test Equipment (S&TE); - Manpower and Human Factors; - Packaging, Handling, Storage and Transportation (PHS&T); - Disposal; - Software Support; - Facilities; - Supportability, Testing and Verification (including Logistics Demonstration); - Configuration Management; - In-Service Support and Monitoring; and - Obsolescence. | Up-to-date ILS Plan and ILS Elements Plan | Monthly from Contract Award | Regular 5 day review |
| 7.5 | The Contractor shall act as the focal point and support all ILS activities relating to the EvO TP Contract, to include as a minimum: - review of all deliverables for the EvO TP Contract; - attendance at all ILS reviews with EvO TP (formal and informal) – approximately twice-a-month formal meetings; - attendance at all internal ILS stakeholder reviews (formal and informal); and - support the development and refinement of the ILS Process. | Attendance and participation in relevant ILS meetings | As required | Monthly Report |
| 7.5a | The Contractor shall ensure the EvO System and all of its supporting documentation is compliant with the ILS requirements of the EvO TP Contract, and provide commentary and feedback where non-compliance occurs through the monthly report. | Comments and feedback on ILS Deliverables for EvO TP Contract | Monthly from Contract Award | Regular 5 day review |
| 7.5b | The Contractor shall engage with the EvO TP to support the transfer of the EvO System ILS solution to the BATCIS In-Service Support team. This shall include as a minimum: - updates and changes to the ILS Strategy; - updates and changes to the ILS Supportability Strategy; - updates and changes to the ILS Use Study; - updates and changes to the MORPHEUS System Requirements Document from an ILS perspective; - updates and changes to the Support Solution Development Tool; - updates and changes to the ILS Plan & ILS Elements Plan; - updates and changes to the Enduring Support Solution Strategy; and - updates and changes to the Enduring Support Solution Options Analysis. | Transfer of the EvO System ILS Solution | As per MORPHEUS local project schedules | Regular 10 day review |
| 7.6 | The Contractor shall act as the focal point and support all ILS activities relating to the MORPHEUS Projects, including as a minimum: - creation, contribution and/ or updates to associated competition deliverables including: - SOR; - WBS; - Contract Schedules; - Project Schedule; - Contract Data Requirements List (CDRL); and - contributing and updating the ILS evaluation questions and evaluation criteria at each stage of the competition. | SOR Contract Schedules Project Schedule Evaluation Questions and Evaluation Criteria | As per MORPHEUS local project schedules | Regular 5 day review |
| 7.7 | The Contractor shall support the BATCIS In-Service Support Team with the continuing development and implementation of the Enduring Support Solution (post fielding of the MORPHEUS Solution), to include as a minimum: - updating, managing and maintaining the Enduring Support Solution Strategy in compliance with Enduring Support Solution Strategy Product Description; - updating, managing and maintaining the Enduring Support Solution Options Analysis in compliance with the Enduring Support Solution Options Analysis Product Description; and - incorporating updates into the monthly ILS report. | Up-to-date Enduring Support Solution Strategy Up-to-date Enduring Support Solution Options Analysis | Monthly from Contract Award | Regular 5 day review |
| 7.8 | The Contractor shall provide a monthly report to the BATCIS ILS Manager on the following: - updates and changes to the ILS Strategy; - updates and changes to the ILS Supportability Strategy; - updates and changes to the ILS Use Study; - updates and changes to the MORPHEUS System Requirements Document from an ILS perspective; - updates and changes to the Support Solution Development Tool; - updates and changes to the ILS Plan & ILS Elements Plan; - updates and changes to the Enduring Support Solution Strategy; and - updates and changes to the Enduring Support Solution Options Analysis. | Monthly ILS Report | Monthly from Contract Award | Regular 5 day review |

- Requirements Support.   The Requirements Team is responsible for the capture, management and tracking of the requirements (what the system must do and how it must do it) throughout the procurement process, from initial concept through to final acceptance.  This work has three main strands.  The first centres on engagement with the various end-user communities, to determine what they want to use the system to do.  These User Requirements are translated into a set of System Requirements, which describe how the system is to behave, to enable the user to do their job.  The different levels of requirements within the hierarchy are mapped to one another, to ensure that all facets of the procurement can ultimately be traced back to the need of the user – the ‘Golden Thread’.  Formal change management processes are followed, to allow the requirements to change in response to changing user need, whilst making sure that the knock-on impacts of any changes are understood before they are made.

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable Review Timelines and Category of Deliverable |
| --- | --- | --- | --- | --- |
| 8.1 | The Contractor shall support to the BATCIS Requirements Team on behalf of the MORPHEUS Programme to manage, create, maintain, review and provide input into the following, as a minimum: - maintain the traceability of Agile requirements fulfilment to the URD via the VVRM construct described in the Acquisition Operating Framework (AOF); - the User Requirements Document and liaise with the user community to ensure that the user requirement remains up to date; - the Morpheus SRD; - track the delivery of SRs through the agile process and within the EvO Design; - the requirements in DOORS; - the ITEAP; - contribute to the development of, Capability Acceptance Test Cases, First of Type (FOT) scenarios, Field Trial serials and Logistic Demonstration serials; - support Army HQ in developing the user acceptance process and incorporating it in to the ITEAP; - the user acceptance; - requirements and Test and Acceptance documentation; - engage with ISS IT&T; and - provide Requirements and Test/ Acceptance input to BATCIS Commercial Team. | URD SRD ITEAP Capability Cases | As required through the Programme and Project Schedules |  |
| 8.2 | The Contractor shall provide support to EvO TP Contract activities, which will include as a minimum: - tracking and informing requirement orientated aspects of the Agile process, including as a minimum: - attending the monthly planning meetings, which will occasionally be held at GDUK sites; - attending the fortnightly review meetings, which will occasionally be held at GDUK sites; leading on the collegiate writing of Use Cases on an ad hoc basis; - advise the EvO TP on the correct interpretation of requirements within the MORPHEUS Systems Requirement Document; and - provide greater requirement fidelity to those requirements which undergo iterative definition. - provide information to User representatives throughout the Agile process; - attend assurance activity at third party locations and report on the level of assurance attained; - ensuring GD adhere to the ITEAP; - the EvO SRD (i.e. MORPHEUS SRD + EvO Compliance Statement) throughout the life of the EvO TP Contract; - TP Architecture and Design documentation which have an impact on requirements; - the TP Value Stream Kanban (setting priorities of the capabilities throughout the Contract); and - any other requirements questions at PI Planning and during the PI. (The TP and the Authority identify requirements questions, etc. as part of PI planning; these are then answered over the following 3 month period). | Use Case(s) VVRM EvO SRD | As required Ongoing Every 6 months 1 month prior to departure | Regular 5 day review |
| 8.3 | The Contractor shall provide future support to MORPHEUS projects, including as a minimum: - the MIDAC SOR and the Platform Integration requirements. Supporting the Test and Acceptance of the individual platforms and conversion; - the derivation of ECDs and tracking the requirements through the appropriate delivery process through to completion; and - the SI and MSP Contracts. This includes the Knowledge Transfer and developing the requirement for the Contract. | As required in addition to the Monthly report | As per MORPHEUS Programme and Project Schedules | Regular 5 day review |
| 8.4 | The Contractor shall provide Requirements support to the following MORPHEUS Projects: TIBR, DSA, MTRC, BMA & MSP to include the following activities, as a minimum: - track and inform requirement orientated aspects of the respective procurement process: - attend monthly planning meetings, occasionally at third party locations; - attend fortnightly review meetings, occasionally at third party locations; - support the capturing of requirements in accordance with the AOF; - participate in the ad hoc review of bid responses; - participate in the writing and review of requirement related sections of future contracts; - lead the collegiate writing of Use Cases on an ad hoc basis; - provide requirement input to the integration of Project capabilities with EvO TP capability; - on an ad hoc basis advise on the correct interpretation of requirements; - on an ad hoc basis provide greater requirement fidelity to those that will undergo iterative definition; and - contribute to the development of Capability Acceptance Test Cases, First of Type (FOT) scenarios, Field Trial serials and Logistic Demonstration serials. - maintain the traceability of Agile requirements fulfilment to the URD via the VVRM construct described in the AOF; - lead on the collaborative development of the ITEAPs in accordance with the principles laid down in the AOF; - provide on an ad hoc basis information to User representatives throughout the Agile process; - attend ad hoc assurance activity at third party locations and report on the level of assurance attained; - support to the project SOR’s by providing relevant input; - supporting the development of Project User Stories/ Requirements; and - tracking the delivery of the Project Requirements throughout the process of delivering the Project. | Use Case(s) VVRMs ITEAPs | As required Ongoing As required Every 6 months 1 month prior to departure | Regular 5 day review |
| 8.5 | The Contractor shall provide a monthly report providing updates to the MORPHEUS Programme, including the following as a minimum: - updates to User Cases; - updates to the ITEAP’s; - updates to the SRD; - updates to URD’s; - updates to Capability cases; and - input supplied to MORPHEUS Projects. | Monthly Report | Monthly from Contract Award | Regular 5 day review |