9.0	Dismounted Situational Awareness (DSA)

Project Control.   Project Control Support is responsible for the Project Control & Project Management of the DSA Project, which includes the co-ordination of team activity according to Industry best practise and ISS internal mandated processes.  It delivers the enterprise project management function: of monitoring & reporting; planning and change management; risk, issues and assumptions management; benefits management; and stakeholder management of the DSA Project.

Project Management.   The Contractor shall provide Project Management (PM) resource to support the Authority Project Lead in the management and delivery of the DSA Project.

Engineering Support.   Engineering support will be technical and engineering expertise to deliver Technical Subject Matter Expertise and to support DSA competitions.

| Serial ID | Description/ Deliverables | Outputs | Output Date | Acceptance |
| --- | --- | --- | --- | --- |
| 9.1 | The Contractor shall provide Project Management support which shall include as a minimum Section 9.1 to Section 9.11c. | Project Management for DSA, conducted in compliance with the defined policy and procedures | For duration of the Contract | Monthly Report |
| 9.1.1 | The Contractor shall create, manage and maintain the DSA Project Work Breakdown Structure (WBS). The Contractor shall update the WBS in line with any feedback from the Authority. | An up-to-date DSA Project WBS | For duration of the Contract | Regular Review Process 5 Working Days to Review |
| 9.1.2 | The Contractor shall create, manage and maintain the DSA Project Schedule (non-published on EPM) by, including as a minimum; - all work packages defined in the Project WBS; - all major Decision Points - including Milestones, key Gateway Reviews; - progress and technical reviews; - all Deliverables; - all task dependencies; - all schedule assumptions; - all schedule constraints; - the critical path; - fully resourced plan and costs, and task durations; - risks and risk mitigation actions; - when amending the DSA Project Schedule, raise any changes which affect the Schedule through the Change Request process (see relevant artefact in the GFI list) and; - provide input into the Programme Schedule. Where appropriate the Contractor shall utilise Enterprise Project Management (EPM) in the delivery of this task. | Input to the DSA Project Schedule via the Schedule Change Request Process Input into the MORPHEUS Programme Schedule via fortnightly Review Meetings Draft Project Schedule (non published on EPM) Mature Project Schedule (non published on EPM) Update and maintain Project Schedule (non published on EPM) | As required for the duration of the Contract | Regular Review Process 10 Working Days to Review |
| 9.1.2a | The Contractor shall provide fortnightly updates to the Authority Project Lead on DSA progress through providing a DSA Project Dashboard in compliance with the MORPHEUS Projects Management Information Dashboard (see relevant GFI artefact at Schedule 7). | DSA Project Management Information Dashboard | As required for the duration of the Contract | Monthly Report |
| 9.1.3 | The Contractor shall provide a Schedule Impact Statement (see relevant PD artefact at Schedule 19) to the Authority Project Lead of any potential or upcoming change. The Statement should consider any performance, cost and time impact to all relevant MORPHEUS Projects and the Programme. | Impact Statement | As required from Contract Award until end of Contract | Monthly Report |
| 9.1.4 | The Contractor shall ensure all changes to the DSA Project are managed in accordance with the MORPHEUS Change Control Process (see relevant GFI artefact at Schedule 7). | MORPHEUS Change Control Process | As required from Contract Award until end of Contract | Monthly Report |
| 9.1.4a | The Contractor shall carry out DSA Resource Allocation Planning (RAP). See relevant PD artefact at Schedule 19. As a minimum, the Contractor shall identify the required resources to deliver the Project in conjunction with the MORPHEUS Programme Controls Team, ensuring these are captured within the Project Schedule. Examples include: - Internal Resources; and - External Resources. | Up-to-date resource requirement for the DSA Project Schedule Attendance at the MORPHEUS Programme Schedule update meeting Resource Allocation Plan (RAP) In association with the Programme Controls Team, update/ maintain resources in the Schedule | As required from Contract Award until end of Contract Fortnightly from Contract Award until end of Contract | Regular Review Process 10 Working Days to Review |
| 9.1.5 | The Contractor shall identify and capture the DSA Project Assumptions. The DSA Project assumptions shall be recorded in the assumptions tab of the Project PM Workbook (see relevant GFI artefact at Schedule 7). The Contractor shall apply the relevant MORPHEUS Assumption Management (AM) Process. | An up-to-date Assumptions Log in the DSA Project PM workbook | Fortnightly from Contract Award | Monthly Report |
| 9.1.5a | The Contractor shall review all of the DSA Project Assumptions with the Authority Project Lead. The review shall as a minimum consider the following: - key milestones and identify new assumptions/ opportunities against those; - review progress of the delivery of mitigation actions and ensure that they are having the desired assumption reduction impacts; - provide Project Lead approval for escalation of assumptions; - provide Project Lead acceptance that the proposed assumptions will recommended for closure or transfer to issue at the next relevant MORPHEUS Assumption Panels (MAPs); and - perform a quality assurance review of relevant MORPHEUS assumptions for the function. | Participation in the Project Lead’s Review | Day before the DSA Project Schedule Review | Monthly Report |
| 9.1.5b | The Contractor shall attend and support the Authority Project Lead at the appropriate MORPHEUS Assumption Panels (MAPs) in compliance with the relevant MORPHEUS Assumption Management Process. | Attendance at the appropriate MAPs | Monthly | Monthly Report |
| 9.1.5c | Dependencies. The Contractor shall maintain the DSA Project Dependencies within the Project Management Workbook (see relevant GFI artefact at Schedule 7), escalating appropriately to the Programme-level Dependency Log. The Contractor shall participate in cross-Project Dependency Reviews. The Contractor shall manage the Project Dependencies that exist with the other MORPHEUS Projects e.g. System Integrator, Platform Integration, MSP Applications, DIO and LSRC. | Participation in the Project Lead’s Review | Day before the DSA Project Schedule Review | Monthly Report |
| 9.1.6 | The Contractor shall identify, create, capture, manage and maintain the DSA Project risks and issues by undertaking the following activities as a minimum: - recording DSA Project risks and issues in the PM Workbook; - escalating changes to existing risks or issues and any new risks or issues which are created or identified to the Authority Project Lead for endorsement; - providing all new or amended risks to the relevant MORPHEUS Risk Manager at the weekly engagement; - capturing and maintaining cross Defence Lines of Development (DLOD) risks within ARM; - input and maintain robust basis of estimates for risks performance cost & time and implement a Risk Mitigation Plan for each risk; - identify resources required to manage individual risks; and - apply effective risk management techniques, in accordance with the ASG Identify, Assess, Plan, Do, Review, cycle process. | Up-to-date the relevant tabs of the PM Workbook Update ARM in conjunction with the MORPHEUS Risk Manager | Fortnightly from Contract Award until end of Contract As required from Contract Award until end of Contract | Monthly Report |
| 9.1.6a | The Contractor shall participate in the fortnightly risk and issue review providing input on the relevant MORPHEUS Project risks and issues. | Participation in the appropriate Risk and Issue Review | Fortnightly from Contract Award until end of Contract | Monthly Report |
| 9.1.7 | The Contractor shall work with the Army HQ Capability Manager (CM) to ensure the relevant MORPHEUS Project outputs are synchronised with cross-DLOD dependencies. The Contractor shall ensure Authority Project Manager (PM) and CM jointly review the DSA Project, on an at least a monthly basis. The Contractor shall, as a minimum: - agree the agenda for the review meeting with both the PM and CM; and - arrange the location for the review meeting. The Contractor shall conduct the PM and CM review in accordance with the (see relevant PD artefact at Schedule 19). The Contractor shall provide a brief to the Authority Project Lead on any emerging issues as required. | Organising and participating in the PM and CM Review When required, attendance at the Army-HQ Capability Integration Working Group (CIWG) | One month prior to CIWG from Contract Award until end of Contract As required from Contract Award until end of Contract | Monthly Report |
| 9.1.8 | The Contractor shall provide the Authority Project Lead with financial input data to support the MORPHEUS Project Budget Forecasting requirement. The Contractor shall provide appropriate financial data for input into the relevant MORPHEUS Forecast of Out-Turn (FOO) return. The Contractor shall provide details of the resources consumed (accruals) using the most accurate and up-to-date figures available for the Project. The accruals must be based on the most accurate forecast using past data, along with any relevant new information in respect of resources not yet consumed. | All requisite data to the Authority Project Lead, for input to the FOO Review | Monthly from Contract Award until end of Contract | Monthly Report |
| 9.1.9 | The Contractor shall maintain and complete the Project History and Learning From Experience (LFE) sections contained in the DSA Project PM Workbook (see relevant PD artefact at Schedule 19). The Contractor shall capture LFE as events occur and enter it in the LFE section of the DSA Project PM Workbook. The Contractor shall plan and conduct periodic LFE workshops with the Authority Project Lead and any other relevant stakeholders, at key stages of the Project lifecycle (i.e. at the end of the competitions). LFE review stages must be agreed with the Authority Project Lead one month in advance and included in the Project Schedule. | Input to the LFE Section of the PM Workbook Input to the Project History Section of the PM Workbook LFE workshop | As required from Contract Award until end of Contract As required from Contract Award As required from Contract Award until end of Contract | Monthly Report |
| 9.1.10 | The Contractor shall conduct relevant MORPHEUS Project Stakeholder Management (in accordance with the Stakeholder Management Plan within the GFI List at Schedule 7). As a minimum this shall include; - creating, updating, managing and maintaining a comprehensive list of stakeholders to the DSA Project, identifying in particular key stakeholders within the PM Workbook (see relevant artefact in the GFI List); - maintain regular communications with all necessary stakeholders, with a particular focus on key stakeholders; - providing weekly input to the MORPHEUS Programme Stakeholder Management Plan, by engaging with the MORPHEUS Programme Stakeholder Manager; - recording the stakeholders ability to effect the DSA Project; and - complying with Industry best practise and internal ISS procedures relating to stakeholder engagement. | Input to the Stakeholder Management Section of the DSA Project PM Workbook Weekly input to the MORPHEUS Programme Stakeholder Management Plan | As required from Contract Award until end of Contract As required from Contract Award until end of Contract | Monthly Report |
| 9.1.11 | The Contractor shall attend, participate and input into all of the requisite meetings relating to DSA Project Governance (see relevant PD artefact at Schedule 19) for this Contract. | Attendance, participation and input to all of the DSA Project meetings | Fortnightly from Contract Award until end of Contract | Monthly Report |
| 9.1.11a | The Contractor shall, on a fortnightly basis, provide a short DSA Project Update at the Project ‘Stand-Up’ meetings. See relevant PD artefact at Schedule 19. | An update at the Project ‘Stand-Up meetings’ on the DSA Project | Fortnightly from Contract Award until end of Contract |  |
| 9.1.11b | The Contractor shall, on alternate weeks to the Project ‘Stand-Up meetings’, present a formal report using the MORPHEUS Project Management Information Dashboard (see relevant GFI artefact at Schedule 7) on the DSA Project to the MORPHEUS Project Leads at the Project Review. See Project Governance at PD or Schedule 19. | Presentation of a formal report on the DSA Project at the Authority Project Lead’s Project Review meeting | Fortnightly from Contract Award until end of Contract |  |
| 9.1.11c | The Contractor shall provide input and support to any other meetings or reviews which require information concerning the progress, or any other information, on the DSA Project. The meetings or reviews may include, but are not limited to, the One-Star Programme Review, the One-Star Section Review and the Army HQ-sponsored CIWG. See relevant PD artefact at Schedule 19. | Input to any meetings which require information concerning the DSA Project | As required from Contract Award until end of Contract |  |
| 9.1.11d | The Contractor shall support the MORPHEUS Approvals and Cost Estimation functions in the management and delivery of a DSA Approval Note for the Assessment Phase (AP) and report on such activities through the DSA Project Governance. | AP Review Note | Apr 2021 |  |

| 9.6 | Change Control. The Contractor will maintain, manage and report on a Change Control process in accordance with the MORPHEUS Change Control processes and report changes for approval to the DSA Project Governance for approval or escalation as determined. | Change Control Log | Monthly from Contract Award | Regular 5 day Review |
| --- | --- | --- | --- | --- |
| 9.7 | Engineering Support. The Contractor shall provide a DSA Engineering Support Service that will, as a minimum: - Support the DSA competition by utilising the Authority’s project management process. The main responsibilities for the DSA Engineering Support Service will include the following: - Development of artefacts to support the Authority’s procurement process as per those items in SOR 4.0 regarding competitions; and - conducting bid evaluation and moderation against the defined Evaluation Criteria. | Updated DSA Pulse 1 CDP IAW Annex A to the core SOW: To support the DSA DPQQ and DSA ITT. Industry Engagement Artefacts | DSA Competition expected FY21/ 22 | Regular 10 day Review |

| 9.8.1 | Pre Competition Phase. The Contractor shall produce the documentation and provide support to the Authority Commercial Team for the non-commercial elements required in Tender Preparation as detailed in Section 9.8.1 to Section 9.8.17. |  |  |  |
| --- | --- | --- | --- | --- |
| 9.8.2 | The Contractor shall work with the BATCIS Commercial Team to create, manage, produce and maintain an Early Competition Data Pack that includes the documentation required to start the procurement process. The Early Competition Data Pack will include as a minimum: - a Procurement Strategy; - mature wording for Prior Information Notice (PIN), including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the DSA Contract, including as a minimum the start date, duration, value and scope; - mature wording for the Contract Notice, including a short summary of the requirement, exhaustive details on security requirements for the requirement, a detailed description of the requirement, details of all options required for the DSA Contract, including as a minimum the start date, duration, value and scope; - all relevant exemptions to the project, for example security exemptions; - a mature question set for the pre-qualification questionnaire (PQQ); - a complete list of evaluators for the PQQ; - a mature evaluation strategy for the PQQ with an Authority commercially-approved scoring system; - a draft Statement of Requirement (SOR); - a draft acceptance process for the deliverables or outputs to the Project; - when relevant a draft assurance process for the deliverables or outputs to the Project; - a draft GFA List; - a draft list of relevant standards for inclusion in the Contract; - a draft governance schedule for the Contract; - a draft Exit Plan; - draft Key Performance Indicators and contributions to the other incentivisation provisions; - a draft list of evaluators for the procurement; and - a draft evaluation strategy for the tender documentation. | Early Competition Data Pack | As per Schedule | Schedule 5 |
| 9.8.3 | Final Competition Data Pack. The Contractor shall create, manage and maintain produce a Final Competition Data Pack that includes the documentation required to enter the tender phase of the procurement process. The Final Competition Data Pack will include as a minimum: - a finalised and approved SOR; - a finalised acceptance process for the deliverables or outputs to the Project; - when relevant a finalised assurance process for the deliverables or outputs to the Project; - a robust and approved GFA List; - a complete list of relevant standards for inclusion in the Contract; - an approved governance schedule for the Contract; - a draft Exit Plan; - finalised Key Performance Indicators and contributions to the other incentivisation provisions; - a finalised list of evaluators for the procurement; - a finalised evaluation strategy for the tender documentation; - any contribution to the Negotiation Strategy, where relevant if there are areas we anticipate negotiating over; and - all necessary contributions to the tender pack. | Final Competition Data Pack | As per Schedule | Schedule 5 |
| 9.8.4 | The Contractor shall identify all relevant and necessary GFA for the purposes of the delivery of the DSA Project. The Contractor shall engage with the MORPHEUS GFA Manager when developing the DSA GFA List. The Contractor shall provide as a minimum for the GFA List (see relevant PD artefact at Schedule 19): - each item of GFA and a justification for it; - the quantity of GFA necessary; - the source of the GFA; - the date it will be required from; and - the duration it will be required for. | Draft DSA Project GFA List Final DSA Project GFA List As required, attend meetings and engage with the GFA Manager | As per Schedule As required from Nov 18 until end of Contract | Regular 20 Working Days (Schedule 4 Special?) |
| 9.8.5 | The Contractor shall collate the information required to produce a PIN, in compliance with the relevant European Procurement Regulations. They shall provide input to the BATCIS Commercial Team when they are drafting the PIN by co-ordinating and engaging with relevant stakeholders to ensure all relevant information is provided in a timely manner to the BATCIS Commercial Team for the PIN. This shall include as a minimum: - proposed start date of the tendering process; - estimated value of the Contract; - timescales of the procurement and contract delivery; and - a high level description of the requirement. | Project Information required by the BATCIS Commercial Team to draft a PIN | If required | Regular 5 Working Days |
| 9.8.6 | The Contractor shall, where necessary create, update, manage and maintain the Procurement Strategy for the DSA Project, ensuring compliance with the Procurement Strategy. The Contractor shall ensure that the Authority Project Lead for the DSA Project approves all updates/ changes to the DSA Procurement Strategy. The DSA Procurement Strategy shall be compliant with the Procurement Strategy PD at Schedule 19. | Draft Procurement Strategy Mature Procurement Strategy | As per Schedule As per Schedule | Regular 20 Working Days |
| 9.8.7 | The Contractor shall engage with the BATCIS Commercial Team to provide input to the DSA Commercial Strategy. | Input to Commercial Strategy | As per Schedule | Monthly Report |
| 9.8.8 | The Contactor shall support the BATCIS Commercial Team when developing the DSA Contract Notice. As a minimum this shall include providing the following: - contract name; - location of delivery; - timelines for the competition; - a high level description of the requirement which is less than 400 characters with spaces; - a detailed description of the requirement which is less than 3800 characters with spaces; - the estimated value of the requirement, including any options; - an outline of the options which shall include where possible, value, requirements, dates and any other relevant information; - all security information including as a minimum Cyber Risk, Cyber Essentials Classification, Personal Security requirements and any other relevant security standards/ sensitivities; and - any other relevant additional information to the Contract Notice as stipulated by the Project Lead or BATCIS Commercial Team. | DSA Contract Notice | As per Schedule | Regular 5 Working Days |
| 9.8.9 | The Contractor shall create, develop and update the DSA supplier selection project, security and technical questions for the DSA Dynamic Pre-Qualification Questionnaire (DPQQ). The Contractor shall engage with all of the relevant stakeholders to ensure appropriate questions are included for an effective down-selection in full consideration of the requirement. The Contractor shall as a minimum ensure questions are considered for: - the Supply Chain, specifically whether overseas delivery would be an issue; - previous supplier experience on similar work; - technical facilities required for delivery; - requisite facility security clearances; and - relevant Cyber Essentials questions. The Contractor shall obtain approval from the BATCIS Commercial Team and the appropriate Authority Project Lead at least five (5) working days prior to release of the DPQQ, noting BATCIS Head Commercial must also read and approve the DPQQ prior to authorising its release. | Draft DPQQ PM/ Technical Questions Mature DPQQ PM/ Technical Questions | As per Schedule As per Schedule | Schedule 5 |
| 9.8.10 | The Contractor shall create, develop and update the DSA supplier selection evaluation criteria for the Project, security and technical questions for the DSA DPQQ. The Contractor shall engage with all of the relevant stakeholders to ensure appropriate evaluation criteria are developed for the questions. The Contractor shall produce a list of the evaluators for the assessment of the DSA DPQQ. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The DPQQ evaluators list shall be supplied to the BATCIS Commercial Team at least ten (10) working days prior to the release of the Contract Notice and DPQQ. | Draft Evaluation Criteria Mature Evaluation Criteria Approved list of the DPQQ Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 9.8.11 | The Contractor shall provide a SOR for the DSA Project. The Contractor shall engage with all relevant stakeholders when developing the DSA SOR to ensure that all necessary aspects of delivery are considered. The SOR shall consider the DSA Project through the project lifecycle and consider all relevant DLOD areas. As a minimum, the Contractor shall engage the following stakeholders: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; and - the relevant requirement and technical subject matter experts. As a minimum the SOR shall include details of the following for each line item: - a serial ID; - a description of the line item; - the date for delivery for the line item; - any relevant GFA for the line item; and - the acceptance process for the line item. | Draft SOR | As per Schedule | Schedule 5 |
| 9.8.13 | The Contractor shall provide support to the BATCIS Commercial Team for the development of the Tender Documentation for the DSA Project. This shall include as a minimum: - the approved DSA SOR; - timelines for activity during the procurement; - providing project management input to the DSA Contract including, as a minimum: - calculations for Liquidated Damages when relevant; - any relevant requirements for rights of termination; - any relevant requirements for step-in rights; - the governance structure for the Contract i.e. reviews; - product descriptions; - incentivisation provisions; - payment provisions; - any requirements for Exit Plans; - any requirements for Business Continuity Plans; - all relevant Standards such as Quality Assurance, ISOs, BSs and/ or JSPs; - the acceptance, and where relevant assurance, processes for delivery; - all relevant definitions to the Contract; - the GFA List; - any specific IPR considerations; - any key personnel; and - all information concerning options. - supporting getting the tender documentation onto the AWARD tool; - the MORPHEUS DSA tender assessment questions; and - the MORPHEUS DSA tender assessment questions evaluation criteria. | Draft ITN Mature ITN | As per Schedule As per Schedule | Schedule 5 |
| 9.8.14 | The Contractor shall create, co-ordinate, update, manage and maintain the Tender Assessment Questions and the Tender Assessment Questions Evaluation Criteria for the DSA Project. The Contractor shall engage with all relevant stakeholders and subject matter experts in order to create the Tender Assessment Questions and the Tender Assessment Questions Evaluation Criteria for the DSA Project. As a minimum this shall include: - the relevant security subject matter expert; - the relevant safety and environmental subject matter expert; - the relevant ILS subject matter expert; - the relevant training subject matter expert; - the relevant requirement and technical subject matter experts; - the MORPHEUS Finance Team; - the MORPHEUS Cost Estimator; and - the BATCIS Commercial Team. The Contractor shall ensure that the Tender Assessment Questions and the Tender Assessment Questions Evaluation Criteria for the DSA Project, additionally cover all relevant aspects of delivery including as a minimum: - schedule; - values and behaviours; - standards compliance; - exit plans; - evaluation of assumptions and dependencies (GFA); - business continuity plans; and - any other relevant areas. The Contractor shall produce a list of the evaluators for the assessment of the DSA Tender. The list shall include the name, email address and questions which the individual will be evaluating; the list shall give due consideration to the availability and other commitment of individuals so as to avoid any delays in delivery. The Tender evaluators list shall be supplied to the BATCIS Commercial Team at least ten (10) working days prior to the release of the Tender. | Draft the Tender Assessment Questions and the Tender Assessment Questions Evaluation Criteria for the DSA Project Mature the Tender Assessment questions and the Tender Assessment Questions Evaluation Criteria for the DSA Project Approved list of the Tender Assessment Panel | As per Schedule As per Schedule As per Schedule | Schedule 5 |
| 9.8.15 | The Contractor shall engage with the BATCIS Security Team to produce a Security Aspects Letter (SAL) for the DSA Project. The Contractor shall secure any relevant security exemptions with the support of the BATCIS Commercial Team. See relevant GFI artefact at Schedule 7. | DSA Security Aspects Letter | As per Schedule | Schedule 5 |
| 9.8.16 | The Contractor shall engage with an Authority PM to create a Request for Contract Action (RCA) for the DSA Project. The Contractor shall provide the following information: - actual data: price and approvals value; - finance details: codes for Management Grouping, UIN, BLB, RAC, LPC, TLB, HLB, VAT rating; and - contract details: being able to answer certain simple questions on Proc Strat, QA Requirements; commercial details (e.g. reverse auctions), Security, Delivery performance etc. | Relevant RCA information provided to the Authority DSA PM | As per Schedule | Monthly Report |
| 9.8.17 | The Contractor shall at the direction of the Authority Project Lead contribute and co-ordinate with the BATCIS Commercial Team and necessary Industry engagement (comprising Presentations, Venue Organisation, Agenda Development etc.) regarding the DSA Project, this may as a minimum include: - Industry Days, i.e. Bidder Conferences; - 1 to 1 sessions between the Authority and Industry; and - Requests for Information prior to market engagement to inform the procurement process and requirements set. | As required | As required from Nov 18 until 24/06/20 | Monthly Report/As Agreed with MORPHEUS Project Lead |
| 9.8.18 | Competition Phase. The Contractor shall ensure the delivery of the Competition Phase by co-ordinating and managing the delivery of the tasks. |  |  |  |
| 9.8.19 | The Contractor shall work with the BATCIS Commercial Team to provide support to the DPQQ during the Supplier Selection Phase. The support shall include, as a minimum: - once provided Clarification Questions from Industry by the BATCIS Commercial Team, obtaining a response from the relevant Subject Matter Expert within 3 working days; - emailing and/ or briefing evaluators in how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - ensuring the DPQQ Assessment Panel is organised by having meeting invites sent out and meeting rooms booked as necessary; - supporting the evaluation of the DPQQ by co-ordinating and managing the technical and project assessment of the DPQQ responses from Industry, including ensuring completion of justifications for scores; and - co-ordinating and managing the project and technical comments against the scores to be released as part of the de-briefing packs for competitions. | Clear audit trail of Industry Clarification Questions during the Supplier Selection phase RODs from DPQQ Assessment Panel | From 30/07/19 to 06/09/19 | Monthly Report Regular 5 Working Days |
| 9.8.20 | The Contractor shall provide support to the tender process, this shall include as a minimum: - co-ordinate and manage all non-commercial Clarification Questions by engaging with relevant subject matter experts and providing a response to non-commercial Clarification Questions to the BATCIS Commercial Team within three (3) working days; - arrange a briefing for evaluators on how evaluations should be completed, the Contractor should engage with the BATCIS Commercial Team for guidance on this; - participate in the evaluation of the tender returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the tender returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the Authority Project Lead; - co-ordinating and manging the Authority non-commercial Clarification Questions regarding the tender returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial Clarification Questions to Industry; - ensure the Tender Assessment Panel is arranged by having meeting rooms booked and meeting invites sent out; - create, manage and maintain a list of non-commercial areas which will require negotiation as part of the tender process, if required; and - ensure a formal RoDs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry Clarification Questions during the Tender phase Evaluators briefing Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements. Clear audit trail of Authority Clarification Questions during the Tender Assessment phase List of negotiation topics for each tender, if required RODs from the DSA Tender Assessment Panel | As per Schedule As per Schedule | Monthly Report Regular 5 Working Days |
| 9.8.21 | The Contractor shall arrange for a DSA Bidders Conference to be conducted not less than a fortnight after the initial release of the Tender Documentation to Industry. | DSA Project Bidders Conference | As per Schedule | Regular 5 Working Days |
| 9.8.22 | The Contractor shall provide support to the DSA Project negotiations. This shall include as a minimum: - creating, managing and maintaining the actions list from the negotiations for both the Authority and each tenderer; - monitoring the timely completion of all actions from the negotiations; - participating in the negotiations at the direction of the BATCIS Commercial Team; and - recording all decisions made during the negotiations. | Negotiation List of Attendees Negotiation Action List Negotiation RODs | As per Schedule | Regular 5 Working Days |
| 9.8.23 | The Contractor shall support the Best and Final Offer (BAFO) phase of the competition following the negotiation phase. The Contractor shall as a minimum: - co-ordinate and manage all non-commercial Clarification Questions by engaging with relevant subject matter experts and providing a response to non-commercial Clarification Questions to the BATCIS Commercial Team within three (3) working days; - participate in the evaluation of the BAFO returns including, as a minimum, reviewing and providing feedback on all dependencies (GFA) the tenderers have placed upon the Authority; - co-ordinate and manage the non-commercial assessment of the BAFO returns, monitoring and reporting on individuals progress and ensuring timely completion, escalating any issues to the Authority Project Lead; - co-ordinate and manage the Authority non-commercial Clarification Questions regarding the BAFO returns. The Contractor shall engage with the BATCIS Commercial Team for the release of any Authority non-commercial Clarification Questions to Industry; - ensure the Tender Assessment Panel for the BAFO is arranged by having meeting rooms booked and meeting invites sent out; and - ensure a formal RODs is taken of the Tender Assessment Panel and its outcome. | Clear audit trail of Industry Clarification Questions during the Tender phase Daily report on the progress of Tender Assessments Evaluation outcome of Tenderer GFA requirements Clear audit trail of Authority Clarification Questions during the Tender Assessment phase RODs from the DSA Tender Assessment Panel |  | Monthly Report Regular 5 Working Days |
| 9.8.24 | The Contractor shall prepare and have approved a Commitment Case (CC) in accordance with the relevant PD artefact at Schedule 19, and Spend Management System Case (SMS) in accordance with the relevant GFI artefact at Schedule 7. The Contractor shall ensure that the Authority Project Lead has approved the final CC and SMS prior to submission. | Draft SMS Mature SMS Draft CC Mature CC | As per Schedule | Regular 5 Working Days |
| 9.8.25 | The Contractor shall provide support to the Contract Award phase of the DSA Project, this shall include as a minimum: - contributing and co-ordinating to the tender de-brief packs following the BAFO Tender Assessment Panel for the DSA Project; - when required, attending the debrief sessions with tenderers and co-ordinating the attendance of all required evaluators from the competition; - engage with an Authority Project Manager to raise a requisition for the contract on CP&F; - contributing to the Contract Award Notice to be issued once a preferred supplier has been selected; and - providing support by co-ordinating the non-commercial response in the event of legal challenge. | Non-commercial elements of Tender debrief packs Attendance and contribution to Tender debrief sessions Input to the Contract Award Notice | As per Schedule | Regular 20 Working Days |
| 9.8.26 | Post Competition Phase. The Contractor shall manage the Activities set out in Section 9.8.27 to Section 9.8.31. |  | As per Schedule | . |
| 9.8.27 | The Contractor shall manage and maintain the day-to-day relationship between the DSA Project and the Authority, utilising PM tools and techniques, giving due consideration to the provisions and requirements of the DSA Contract. If any dispute arises with the DSA Project, the Contractor shall immediately inform the BATCIS Commercial Team. | Formal monthly report Feedback on the relationship in the monthly governance meeting between the Authority and DSA DSA Monthly Report Relationship Management Section | Monthly up to end of PSS Contract | Regular 10 Working Days |
| 9.8.28 | The Contractor shall manage any changes to the DSA Contract in compliance with the Change Control Procedure (see relevant GFI artefact at Schedule 7) within the Contract and in co-ordination with the BATCIS Commercial Team. If any changes are required to the DSA SOR, the Contractor shall co-ordinate with relevant technical Subject Matter Experts to articulate the change. | Change through the DSA Change Control Procedure | As required | Regular 20 Working Days |
| 9.8.29 | The Contractor shall manage delivery of the DSA Project. This shall include as a minimum: - ensuring that relevant deliverable owners review and accept deliverables within the timescales stated within the DSA Contract; - engaging with the DSA to address any queries regarding deliverables and any issues with the delivery of the DSA Contract; and monitoring compliance with the Key Performance Indicators i.e. gathering evidence to support monthly reviews for failures or compliance with the KPIs; - identifying appropriate areas for continuous improvement by engaging with Authority stakeholders and reviewing proposals put forward by the DSA for improvements to the Contract; and - engaging with the Authority Project Lead to receipt milestones on CP&F once deliverables have been accepted. | Formal monthly report | Monthly up to end of PSS Contract | Monthly Report |
| 9.8.30 | The Contractor shall engage with the GFA Manager to ensure the timely delivery of all Authority obligations under the DSA Contract including post contract changes, updates and validations. | Formal monthly report GFA delivered in accordance with the GFA Schedule of the DSA Contract | Monthly up to end of PSS Contract | Monthly Report |
| 9.8.31 | The Contractor shall manage the DSA Project in accordance with the Governance process (see relevant PD artefact at Schedule 19). | Formal monthly report Compliance with the DSA Project Governance Schedule | As required up to end of PSS Contract | Monthly Report |