13 	TacCIS SUPPORT PROJECT (TSP)

Background.   The TacCIS Support Project (TSP) has been established to develop a single coherent Support Solution for all equipment delivered by the BATCIS Delivery team.  It will provide continued support to all Bowman and other TacCIS equipment from the current contract expiry dates of 31 Mar 2019 and incorporate the FALCON (and replacement TRINITY) capabilities at the FALCON contract expiry date of 31 Dec 2020.  The project consists of a core Project and change Control functions overseeing 3 Work Packages:

a.	Logistic Support Contract (LSC).   This contract will be competed to provide demand and inventory management services including storage and distribution.  It will also facilitate repair and overhaul, capital spares procurement and inventory purchases (SOIP).  This requirement is planned to run from contract award 2018 until 1 Oct 2020.

b.	Design Services Contract (DSC).   These contracts will be single source arrangements with all companies that have IPR with respect to TacCIS equipment.  The contracts will provide an ongoing System Design Authority capability and a tasking mechanism for any necessary Post Design Services that might be required. This requirement is planned to run from contract award 2018 until 1 Apr 2019.

Project Control.   Project Control Support is responsible for the Project Control & Project Management of the TSP Project, which includes the co-ordination of team activity according to project management principles, Association of Project Management (APM) and Managing Successful Projects (MSP) and controls. It delivers the enterprise project management function Monitoring & Reporting, Planning and Change management of the TSP Project and also delivers the enterprise project management function of risk, issues and assumptions management as well as Change and Benefits Management and Stakeholder Management.

Change Management.   Change Management is the establishing and management TSP Project change impacts, management, outcomes and benefits as well internal and external communications and stakeholder management.

Requirement will start from Contract Award

| Serial ID | Description/ Deliverables | Outputs | Output date | Deliverable reviews |
| --- | --- | --- | --- | --- |
|  | Project Control |  |  |  |
| 13.1 | The Contractor shall create, manage and maintain a TSP Project Schedule. The schedule requires input from a number of internal stakeholders on a weekly basis including the following as a minimum: - MORPHEUS Programme Controls Office; - BOWMAN, TacCIS In Svc teams; - FALCON and TRINITY Project staff; - Army HQ key stakeholders; and - Commercial and Costings. The TSP Project Schedule shall be maintained in accordance with the MORPHEUS Programme Schedule Product Description utilising the Ministry of Defence supplied Enterprise Project Management tool. The Contractor shall be compliant with the Programme controls that have been established by the MORPHEUS Programme Controls Team. | Maintained project schedule to Plan Quality Level 5 on Enterprise Project Management tool Monthly report on schedule status. | Monthly from Contract Award | Regular 5 Day Review |
| 13.1.1 | The Contractor shall provide a report on the TSP Schedule status to the TSP Project Governance and the MORPHEUS Programme Office including as a minimum: - Issues and Bottlenecks on resource; - Summary of Key Milestones; and - Current level of float in the schedule. Proposed changes, including number of changes requested, approved and rejected. | Report on schedule status | Monthly from Contract Award | Regular 5 Day Review |  |
| 13.2 | The Contractor shall create, manage and maintain a TSP Risk Register and Schedule with input from: - MORPHEUS Programme Office and Technical Leads; - BOWMAN, TacCIS In Svc teams; - FALCON and TRINITY Project staff; and - Army HQ key stakeholders. The Schedule shall adhere to ISS Best Practice and Risk Register will conform with the | Risk Register Schedule | Monthly from Contract Award | Regular 5 Day Review |
| 13.2.1 | The Contractor shall support the MORPHEUS Risk Manager in the analysis and maintenance of the TSP risk schedule within the existing Active Risk Management System (ARM). | Schedule Risk Analysis Maintained Risk Register in the ARM tool | Monthly from Contract Award | Regular 5 Day Review |
| 13.2.2 | The Contractor shall provide a report on the top ten TSP risks to the TSP Project Governance and the MORPHEUS Programme Office including as a minimum, information on: - Cost; - Time; and - Impact. | Report on Risk Status | Monthly from Contract Award | Regular 5 Day Review |
| 13.3 | The Contractor shall create, manage and maintain the TSP Assumptions Register including carrying out the following tasks utilising supplied Ministry of Defence tools Microsoft Excel: - Conduct Assumption Management analysis weekly; and - Maintain up to date Master Data Assumptions List and report monthly on exceptions. The system requires input from a number of internal stakeholders on a weekly basis across MORPHEUS, STSP and Army HQ. The Contractor shall be compliant with the Programme controls that have been established by the MORPHEUS Programme Controls Team. | Maintain Assumption Register Provide monthly Report | Monthly from Contract Award | Regular 5 Day Review |
| 13.3.1 | The Contractor shall provide a monthly report to the TSP Project Governance (as required) and the MORPHEUS Programme Office on Assumptions Management including as a minimum: - Latest Assumptions added to register; - Impact to project schedules by time, cost and resource; and - Exceptions to the Assumptions List. | Report on Assumptions Status | Monthly from Contract Award | Regular 5 Day Review |
| 13.4 | The Contractor shall create, manage and maintain a TSP Dependency Register including as a minimum: - capturing and managing all internal & external dependencies for the TSP Project; and - liaising as required with MORPHEUS Programme functions, STSP functions and Army Stakeholders. The Dependency register should be readable in Microsoft Excel. The Contractor shall be compliant with the Programme controls that have been established by the MORPHEUS Programme Controls Team. | Dependency Register | Monthly from Contract Award | Regular 5 Day Review |
| 13.4.1 | The Contractor shall provide a monthly report on TSP dependency management to the MORPHEUS Programme Office and TSP Project Governance as required, including as a minimum: - Escalations of dependency risks; - Changes to dependency timescales; and - Impact to project schedules by time, cost & resource. | Report on Dependency status | Monthly from contract award | Regular 5 Day Review |
| 13.5 | The Contractor shall support the MORPHEUS Approvals and Cost Estimation Functions in the management and delivery of an anticipated Qty 2 TSP Review Notes and report on such activities through the TSP Project Governance. | AP Review Note | Apr 2021 | Regular 5 Day Review |
|  | Change Control |  |  |  |
| 13.6 | The Contractor will maintain, manage and report on a Change Control process in accordance with the MORPHEUS Change Control processes and report changes for approval to the TSP Project Governance for approval or escalation as determined. | Change Control Log | Monthly from Contract Award | Regular 5 Day Review |
| 13.7 | The Contractor shall create, manage and maintain a TSP Project Narrative, signed off by TSP Project Governance, the TSP Project Narrative will be produced in liaison with the MORPHEUS Communications Manager and shall include asa a minimum: - a clear statements of intent; - rational; - customers; - Capabilities; - Outcomes; and - Benefits. | TSP Project Narrative | Apr 2021 | Regular 5 Day Review |
| 13.7.1 | The Contractor shall create, manage and maintain an internal and external communications plan in liaison with the MORPHEUS Communications Manager and manage approvals and changes through the TSP Project Governance. | Communications Plan | Monthly from Contract Award | Regular 5 Day Review |
| 13.7.2 | The Contractor will support the MORPHEUS Communications Manager in the creation of TSP specific communications material and in the delivery of the TSP internal and external communications plans as required. | Communications artefacts as required | Monthly from Contract Award | Regular 5 Day Review |
| 13.8 | The Contractor shall create, manage and maintain a benefits map detailing project outputs, capabilities, outcomes and benefits in accordance with the LE TacCIS Benefits Management processes, and report on and manage benefit changes as required through the project governance. | Benefits Profile and Map | Apr 2021 | Regular 5 Day Review |
| 13.9 | The Contractor shall create, manage and maintain the TSP Stakeholder Management Plan, Stakeholder List and Stakeholder Map, including as a minimum: - Establishing the TSP Stakeholder Map and List including scope of interest/ responsibilities; - Establishing the TSP Stakeholder Management Plan; - Pro-actively managing these relationships and the push and pull of information; - Updating the Stakeholder Management List and Plan monthly; and - Liaison with the MORPHEUS Communications Manager. | Stakeholder List and Management Plan | Monthly from Contract Award | Regular 5 Day Review |
| 13.10 | Provide a Monthly report on Stakeholder Management to Project Governance, including as a minimum: - Latest Additions to the Stakeholder List; - Changes to the Stakeholder List; - Changes to the Stakeholder Management Plan; and - Significant events from the Stakeholder Management Plan activities. | Stakeholder Management Plan Report | Monthly from Contract Award | Regular 5 Day Review |
|  | Logistic Support Contract Support (Work package) |  |  |  |
| 13.11 | The Contractor shall support the LSC competition by utilising the Authority’s project management process. The main responsibilities will include providing support to the following: - LSC input to Project Approvals (RN); - Development and maintenance of Invitation to Negotiate (ITN) artefacts; - Evaluation, moderation of tenderers’ responses, conduct negotiations and assess BAFOs; - Selection of LSC supplier, debrief of unsuccessful tenderers and finalise contract; - Contract mobilization; - Contribute to, and coordinate, Industry engagement (comprising Presentations, Agenda Development); and - Conduct competition learning from experience (LFE) events. The Authority specifically requires subject matter expertise to enable the Authority to act as an intelligent Customer and enable the Authority to evaluate the Logistic solutions proposed by the bidders and support the Authority in negotiations as a subject matter expert. In order to assist the Authority in being an intelligent customer the Authority requires the Contractor to have knowledge of industry best practice in the following areas: - Modelling using historical data and anticipated future activity to develop an inventory management annual plan; and - Optimising the reverse supply chain through flexible procurement of spares and repairs. Knowledge of MOD Logistic practices in the following areas will be required on a full time basis: - Extant Log (IS) including MOD Inventory Management Systems, demand management systems and asset tracking systems; - Third line repair facilities and practices; and - Utilisation of common MOD warehousing solutions and commodity management systems. | Review Note Input Support to the Initial and Final Tender Packs Evaluation and Moderation Activity for Bids Final Tender Report Debrief Reports Industry Engagement event LFE Report | Sep 18 Sep 18 | Regular 5 Day Review |
| 13.12 | The Contractor shall provide a transition management function to oversee the change from the incumbent supplier to a potential new supplier. This will include as a minimum: - Production of a report detailing any risks, assumptions and dependencies that the winning supplier’s transition plan may present to the Authority; - Regular reports of progress of contractor against agreed plan; and - Register of all GFX dependencies that contractor highlights and manage responses on behalf of the Authority. | Risk Report Highlight report | Commencing on receipt of Out-Letter Approx May 19 One month from receipt of plan. Monthly from receipt of plan Monthly from receipt of plan | Regular 5 Day Review |
|  | Design Service Contract Support (Work package) |  |  |  |
| 13.13 | The Contractor shall support the DSC single source souricng activity by utilising the Authority’s project management process. The main responsibilities for the TSP Engineering Support Service will include the following: - DSC input to Project Approvals (RN); - Development and maintenance of Invitation to Negotiate (ITN) artefacts; - Evaluation, moderation of tenderers’ responses, conduct negotiations and assess BAFOs; - Finalise contract; - Contract mobilization; - Contribute to, and co-ordinate, Industry engagement (comprising Presentations, Agenda Development); and - Conduct competition learning from experience (LFE) events. The Authority specifically requires subject matter expertise to enable the Authority to act as an intelligent Customer and enable the Authority to evaluate the Design Support solutions proposed by the Bidder and support the Authority in negotiations as a subject matter expert. Knowledge of MOD Design Authority functions in the following areas will be required on a full time basis: - Safety case management and related activities. - Security accreditation. - Configuration control. - Obsolescence management. - Helpdesk, incident and problem management. - Software management including application integration and patching. - Specific technical knowledge of the BOWMAN COMBAT Infrastructure Platform (BCIP) will also be advantageous with the anticipation that this could be leveraged from across the wider BPSS team. | Review Note Input Support to the Initial and Final Tender Packs Evaluation and Moderation activity for Bids Final Tender Report Industry Engagement event LFE Report | Mar 19 Mar 19 | Regular 5 Day Review |