## Sheet1
WBS | Task Name | % Complete | Duration | Start | Finish
1 | Morpheus - EvO FOC Schedule | 18% | 2571 days | Mon 06/03/17 | Fri 18/06/27
1.1 | Programme Key Milestones | 0% | 2252 days | Mon 06/03/17 | Mon 09/03/26
1.1.1 | Programme Start Date | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.1.2 | RN3 Out letter | 100% | 0 days | Wed 15/03/17 | Wed 15/03/17
1.1.3 | TP Contract Award | 100% | 0 days | Fri 24/03/17 | Fri 24/03/17
1.1.4 | Information Note 2017 Out letter | 100% | 0 days | Fri 09/02/18 | Fri 09/02/18
1.1.5 | RN4 Out letter * | 0% | 0 days | Wed 23/01/19 | Wed 23/01/19
1.5.7.3 | DSC Minor: RN4 Outletter Received | 0% | 0 days | Wed 23/01/19 | Wed 23/01/19
1.4.1.10.3 | DSC Main: RN4 Outletter Received | 0% | 0 days | Wed 23/01/19 | Wed 23/01/19
1.1.8 | RN5 Out letter | 0% | 0 days | Tue 02/07/19 | Tue 02/07/19
1.2.1.29 | LSC: RN5 Outletter received | 0% | 0 days | Tue 02/07/19 | Tue 02/07/19
1.1.10 | Information Note 2019 Out letter | 0% | 0 days | Wed 02/10/19 | Wed 02/10/19
1.1.11 | MGBC Out letter * | 0% | 0 days | Fri 16/07/21 | Fri 16/07/21
1.1.12 | JPO Facility (TP Final) Operational | 100% | 0 days | Fri 29/09/17 | Fri 29/09/17
1.1.13 | eJPO Facility Ready | 0% | 0 days | Fri 19/11/21 | Fri 19/11/21
1.1.14 | 7 Platform Capability fully Operational | 0% | 0 days | Mon 10/06/19 | Mon 10/06/19
1.1.15 | 20 Platform Capability fully Operational | 0% | 0 days | Thu 06/02/20 | Thu 06/02/20
1.1.16 | 30 Platform Capability fully Operational | 0% | 0 days | Thu 03/12/20 | Thu 03/12/20
1.1.17 | eMTRC Option Operational | 0% | 0 days | Thu 19/10/23 | Thu 19/10/23
1.1.18 | OTP Contract Start Date | 100% | 0 days | Fri 28/07/17 | Fri 28/07/17
1.1.19 | PSS (Re-Competed) Contract Start Date | 0% | 0 days | Wed 27/06/18 | Wed 27/06/18
1.1.20 | SI Contract Start Date | 0% | 0 days | Wed 29/04/20 | Wed 29/04/20
1.1.21 | PI Contract Start Date | 0% | 0 days | Fri 14/09/18 | Fri 14/09/18
1.1.22 | BMA Contract Start Date | 0% | 0 days | Tue 11/09/18 | Tue 11/09/18
1.1.23 | EnHCDR Contract Start Date | 0% | 0 days | Fri 27/07/18 | Fri 27/07/18
1.1.24 | Fielding Partner Contract Start Date | 0% | 0 days | Thu 22/04/21 | Thu 22/04/21
1.1.25 | EvO Release Control Point | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.1.26 | EvO IOC | 0% | 0 days | Fri 21/04/23 | Fri 21/04/23
1.1.27 | EvO FOC | 0% | 0 days | Mon 09/03/26 | Mon 09/03/26
1.2 | Programme Management | 12% | 2125 days | Mon 06/03/17 | Wed 03/09/25
1.2.1 | Programme Controls | 12% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1 | Enduring Activities | 11% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.1 | Manage Programme Controls Team | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.2 | Maintain 3rd Order Assumptions outside of ADMIS | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.3 | Maintain and Update MDAL | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.4 | Maintain EvO FOC Schedule | 12% | 2083 days | Wed 05/04/17 | Tue 05/08/25
1.2.1.1.5 | Maintain Issues and Issues Management Plan | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.6 | Conduct Risk reviews and maintain Risk Register | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.7 | Conduct ongoing Quarterly SRA | 11% | 2059 days | Fri 12/05/17 | Tue 05/08/25
1.2.1.1.8 | Manage Dependencies | 10% | 2050 days | Thu 25/05/17 | Tue 05/08/25
1.2.1.1.9 | Collect and Report Management Information | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.10 | Maintain and Update CMIS | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.1.1.11 | Maintain Programme Planning Products | 9% | 2025 days | Fri 30/06/17 | Tue 05/08/25
1.2.1.1.12 | Prepare and submit Programme Controls Monthly Reports | 0% | 1777 days | Thu 28/06/18 | Tue 05/08/25
1.2.1.2 | Breakthrough Event | 0% | 17 days | Thu 28/06/18 | Fri 20/07/18
1.2.1.2.1 | Agree scope and prepare for the Breakthrough Event | 0% | 15 days | Thu 28/06/18 | Wed 18/07/18
1.2.1.2.2 | Attend Breakthrough Event | 0% | 2 days | Thu 19/07/18 | Fri 20/07/18
1.2.1.2.3 | Develop a Draft Relationship Management Plan & Behaviours Charter | 0% | 2 days | Thu 19/07/18 | Fri 20/07/18
1.2.1.2.4 | Breakthrough Event Complete | 0% | 0 days | Fri 20/07/18 | Fri 20/07/18
1.2.1.3 | ISO 44001 | 0% | 1760 days | Mon 23/07/18 | Tue 05/08/25
1.2.1.3.1 | Achieve ISO 44001 | 0% | 403 days | Mon 23/07/18 | Mon 02/03/20
1.2.1.3.2 | ISO 44001 Achieved | 0% | 0 days | Mon 02/03/20 | Mon 02/03/20
1.2.1.3.3 | Maintain ISO 44001 | 0% | 1357 days | Tue 03/03/20 | Tue 05/08/25
1.2.1.4 | EvO FOC Schedule | 100% | 22 days | Mon 06/03/17 | Tue 04/04/17
1.2.1.4.1 | Develop Baseline EvO FOC Schedule | 100% | 22 days | Mon 06/03/17 | Tue 04/04/17
1.2.1.4.2 | EvO FOC Schedule Baselined | 100% | 0 days | Tue 04/04/17 | Tue 04/04/17
1.2.1.4.3 | Update Schedule Change Control Log to include EvO FOC Schedule | 100% | 5 days | Mon 06/03/17 | Fri 10/03/17
1.2.1.4.4 | Change Log Updated | 100% | 0 days | Fri 10/03/17 | Fri 10/03/17
1.2.1.5 | Management of Risks | 100% | 50 days | Mon 06/03/17 | Wed 17/05/17
1.2.1.5.1 | Produce Risk Management Project Instruction | 100% | 35 days | Mon 06/03/17 | Tue 25/04/17
1.2.1.5.2 | Review Risk Management Project Instruction | 100% | 10 days | Wed 26/04/17 | Wed 10/05/17
1.2.1.5.3 | Update Risk Management Project Instruction | 100% | 5 days | Thu 11/05/17 | Wed 17/05/17
1.2.1.5.4 | Risk Management Project Instruction approved | 100% | 0 days | Wed 17/05/17 | Wed 17/05/17
1.2.1.6 | Schedule Risk Network | 100% | 24 days | Wed 05/04/17 | Thu 11/05/17
1.2.1.6.1 | Develop schedule risk network | 100% | 14 days | Wed 05/04/17 | Wed 26/04/17
1.2.1.6.2 | Review schedule risk network | 100% | 5 days | Thu 27/04/17 | Thu 04/05/17
1.2.1.6.3 | Update schedule risk network | 100% | 5 days | Fri 05/05/17 | Thu 11/05/17
1.2.1.6.4 | Schedule risk network approved | 100% | 0 days | Thu 11/05/17 | Thu 11/05/17
1.2.1.7 | Schedule Risk Analysis | 56% | 793 days | Fri 12/05/17 | Mon 13/07/20
1.2.1.7.1 | Conduct SRA for Input to RN4 | 100% | 103 days | Fri 12/05/17 | Thu 05/10/17
1.2.1.7.2 | Update SRA for Input to RN4 | 72% | 166 days | Fri 06/10/17 | Fri 08/06/18
1.2.1.7.3 | Conduct SRA for Input to RN5 | 0% | 50 days | Fri 29/06/18 | Fri 07/09/18
1.2.1.7.4 | Conduct SRA for Input to MGBC | 0% | 80 days | Wed 18/03/20 | Mon 13/07/20
1.2.1.8 | Manage Dependencies | 100% | 55 days | Mon 06/03/17 | Wed 24/05/17
1.2.1.8.1 | Develop Dependencies Register | 100% | 30 days | Mon 06/03/17 | Tue 18/04/17
1.2.1.8.2 | Review Dependencies Register | 100% | 15 days | Wed 19/04/17 | Wed 10/05/17
1.2.1.8.3 | Update Dependencies Register | 100% | 10 days | Thu 11/05/17 | Wed 24/05/17
1.2.1.8.4 | Dependencies Register Baselined | 100% | 0 days | Wed 24/05/17 | Wed 24/05/17
1.2.1.9 | Programme Controls Function Management Plan | 100% | 80 days | Mon 06/03/17 | Thu 29/06/17
1.2.1.9.1 | Produce Draft PCF Management Plan | 100% | 35 days | Mon 06/03/17 | Tue 25/04/17
1.2.1.9.2 | Review Draft PCF Management Plan | 100% | 20 days | Wed 26/04/17 | Wed 24/05/17
1.2.1.9.3 | Update Plan following review | 100% | 25 days | Thu 25/05/17 | Thu 29/06/17
1.2.1.9.4 | PCF Management Plan Approved | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.2.1.10 | Programme Planning Products | 100% | 60 days | Mon 03/04/17 | Thu 29/06/17
1.2.1.10.1 | Identify Programme Planning Products | 100% | 10 days | Mon 03/04/17 | Tue 18/04/17
1.2.1.10.2 | Develop and Approve Programme Planning Products | 100% | 50 days | Wed 19/04/17 | Thu 29/06/17
1.2.1.10.3 | Programme Planning Products Approved | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.2.2 | Quality Management | 6% | 2035 days | Fri 30/06/17 | Tue 19/08/25
1.2.2.1 | Maintain and Execute Quality Management Plan | 2% | 1839 days | Tue 20/02/18 | Mon 30/06/25
1.2.2.2 | Maintain Continuous Improvement Plan, Conduct Process Audits and Improve Project Processes | 9% | 2035 days | Fri 30/06/17 | Tue 19/08/25
1.2.3 | Resource Management | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.3.1 | Maintain and Execute Human Resource Plan | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.4 | Cost Management | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.4.1 | Maintain Cost Models | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.4.2 | Conduct FOO Activities | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.4.3 | Conduct QPRC Activities | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.4.4 | Manage, Review and submit ABC Options (Annual Process) | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.5 | Programme Governance | 13% | 2115 days | Mon 06/03/17 | Tue 19/08/25
1.2.5.1 | Refine Current Governance Model | 100% | 30 days | Mon 06/03/17 | Tue 18/04/17
1.2.5.2 | Review Refined Governance Model | 100% | 20 days | Wed 19/04/17 | Wed 17/05/17
1.2.5.3 | Update Governance Model following Review | 100% | 30 days | Thu 18/05/17 | Thu 29/06/17
1.2.5.4 | Governance Model Approved | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.2.5.5 | Maintain TLMP | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.5.6 | Produce documents for NAO Reviews & Support as required | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.5.7 | Senior Management of MORPHEUS Programme | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.5.8 | Maintain Governance Model | 9% | 2035 days | Fri 30/06/17 | Tue 19/08/25
1.2.6 | Stakeholder Management | 11% | 2125 days | Mon 06/03/17 | Wed 03/09/25
1.2.6.1 | First version Stakeholder Management Plan | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.2.6.2 | Update Stakeholder Management Plan following review | 100% | 120 days | Mon 06/03/17 | Thu 24/08/17
1.2.6.3 | Stakeholder Management Plan Approved | 100% | 0 days | Fri 08/12/17 | Fri 08/12/17
1.2.6.4 | Prepare and Produce Communication Plan | 100% | 10 days | Mon 06/03/17 | Fri 17/03/17
1.2.6.5 | Review Communication Plan | 100% | 25 days | Mon 20/03/17 | Tue 25/04/17
1.2.6.6 | Update Communication Plan following Review | 100% | 85 days | Wed 26/04/17 | Thu 24/08/17
1.2.6.7 | Communication Plan Approved | 100% | 0 days | Fri 08/12/17 | Fri 08/12/17
1.2.6.8 | Maintain and Execute Communication Plan | 4% | 1930 days | Mon 11/12/17 | Wed 03/09/25
1.2.6.9 | Maintain Stakeholder Management Plan | 4% | 1930 days | Mon 11/12/17 | Wed 03/09/25
1.2.6.10 | Prepare and Produce Stakeholder briefing packs | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.7 | LFE | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.7.1 | Develop LFE Log | 100% | 20 days | Mon 06/03/17 | Fri 31/03/17
1.2.7.2 | Maintain LFE log | 12% | 2085 days | Mon 03/04/17 | Tue 05/08/25
1.2.8 | Develop and Maintain IKM Plan | 1% | 1855 days | Tue 06/03/18 | Tue 05/08/25
1.2.8.1 | Develop IKM Plan | 45% | 40 days | Tue 06/03/18 | Wed 02/05/18
1.2.8.2 | Review IKM Plan | 0% | 10 days | Thu 03/05/18 | Thu 17/05/18
1.2.8.3 | Update IKM Plan | 0% | 5 days | Fri 18/05/18 | Thu 24/05/18
1.2.8.4 | IKM Plan Approved | 0% | 0 days | Thu 24/05/18 | Thu 24/05/18
1.2.8.5 | Maintain and Execute IKM plan | 0% | 1800 days | Fri 25/05/18 | Tue 05/08/25
1.2.9 | Project Management & Support | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.9.1 | Management & Support to Project Competitions | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.2.10 | Approvals Support | 22% | 1206 days | Mon 06/03/17 | Fri 24/12/21
1.2.10.1 | Support to the Approvals Processes | 22% | 1206 days | Mon 06/03/17 | Fri 24/12/21
1.3 | Transition Partner Project- GD | 99% | 946 days | Fri 17/03/17 | Thu 24/12/20
1.3.1 | TP Project Review Milestones | 0% | 935 days | Mon 03/04/17 | Thu 24/12/20
1.3.1.1 | TP Project Start - (ID9) | 100% | 0 days | Mon 03/04/17 | Mon 03/04/17
1.3.1.2 | GD Project Kick-Off | 100% | 0 days | Mon 10/04/17 | Mon 10/04/17
1.3.1.3 | GD Hold Architecture Requirements Review | 100% | 0 days | Tue 02/05/17 | Tue 02/05/17
1.3.1.4 | Integrated Baseline Reviews (System Design, HS&E, ILS, Trng, Security IBRs) | 100% | 0 days | Tue 25/04/17 | Tue 25/04/17
1.3.1.5 | JPO IT Services Monthly Review | 100% | 0 days | Fri 30/06/17 | Fri 30/06/17
1.3.1.6 | PI01 Complete - (ID513) | 100% | 0 days | Fri 30/06/17 | Fri 30/06/17
1.3.1.7 | EvO Architecture Review (EvO AR) | 100% | 0 days | Tue 04/07/17 | Tue 04/07/17
1.3.1.8 | MORPHEUS Architecture Review (MAR) | 100% | 0 days | Tue 04/07/17 | Tue 04/07/17
1.3.1.9 | MTRC Lab Design Document Assurance Review | 100% | 0 days | Mon 03/07/17 | Mon 03/07/17
1.3.1.10 | Platform Integration & Fielding Competition Requirements Review (PIFCRR) | 100% | 0 days | Mon 17/07/17 | Mon 17/07/17
1.3.1.11 | BMA Technical Specification Competition Requirements Review | 100% | 0 days | Thu 03/08/17 | Thu 03/08/17
1.3.1.12 | JPO Assurance Reviews (Enabling Business Transformation - EBT MR & EBTR) | 100% | 0 days | Thu 05/10/17 | Thu 05/10/17
1.3.1.13 | Assurance Review1 - (ID23 &24) | 100% | 0 days | Thu 05/10/17 | Thu 05/10/17
1.3.1.14 | PI02 Complete - (ID514) | 100% | 0 days | Fri 22/09/17 | Fri 22/09/17
1.3.1.15 | MTRC Lab Design Document Assurance Review | 100% | 0 days | Tue 05/12/17 | Tue 05/12/17
1.3.1.16 | PI03 Complete - (ID515) | 100% | 0 days | Fri 15/12/17 | Fri 15/12/17
1.3.1.17 | EnHCDR+ Technical Specification Competition Requirements Review | 100% | 0 days | Wed 17/01/18 | Wed 17/01/18
1.3.1.18 | PI04 Complete - (ID516) | 100% | 0 days | Fri 23/03/18 | Fri 23/03/18
1.3.1.19 | Platform Integration & Fielding Assurance Review (PIFAR) | 0% | 0 days | Tue 17/04/18 | Tue 17/04/18
1.3.1.20 | BMA Technical Specification Assurance Review | 0% | 0 days | Thu 19/04/18 | Thu 19/04/18
1.3.1.21 | Assurance Review2 - (ID30 & 31) | 0% | 0 days | Thu 19/04/18 | Thu 19/04/18
1.3.1.22 | PI05 Complete - (ID517) | 0% | 0 days | Fri 15/06/18 | Fri 15/06/18
1.3.1.23 | PI06 Complete - (ID518) | 0% | 0 days | Fri 21/09/18 | Fri 21/09/18
1.3.1.24 | EnHCDR+ Technical Specification Acceptance Review | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.1.25 | BMA Technical Specification Acceptance Review | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.1.26 | DSA Pulse 2/3 Technical Specification Assurance Review | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.1.27 | HS&E Acceptance Review (HSEAR) | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.1.28 | Security Management Acceptance Review (SMAR) | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.1.29 | Assurance Review3 - (ID35 & 36) | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.1.30 | PI07 Complete - (ID519) | 0% | 0 days | Fri 14/12/18 | Fri 14/12/18
1.3.1.31 | PI08 Complete - (ID520) | 0% | 0 days | Fri 29/03/19 | Fri 29/03/19
1.3.1.32 | Assurance Review4 - (ID37 & 38 ) | 0% | 0 days | Tue 02/04/19 | Tue 02/04/19
1.3.1.33 | EvO System Integration Readiness Review - Interim (EvO SIRR-I) | 0% | 0 days | Wed 03/04/19 | Wed 03/04/19
1.3.1.34 | PI09 Complete - (ID521) | 0% | 0 days | Fri 21/06/19 | Fri 21/06/19
1.3.1.35 | EvO Architecture Acceptance Review (EvO AAcR) Notification | 0% | 0 days | Fri 09/08/19 | Fri 09/08/19
1.3.1.36 | EvO Architecture Acceptance Review (EvO AAcR) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.1.37 | Platform Integration & Fielding Acceptance Review (PIFAcR) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.1.38 | Capability Acceptance Test Case Review (CATCR) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.1.39 | DSA Pulse 2/3 Technical Specification Acceptance Review | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.1.40 | PI10 Complete - (ID522) | 0% | 0 days | Fri 27/09/19 | Fri 27/09/19
1.3.1.41 | Assurance Review5 - (ID40 & 41) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.1.42 | PI11 Complete - (ID523) | 0% | 0 days | Fri 20/12/19 | Fri 20/12/19
1.3.1.43 | Capability Acceptance Test Procedure Review (CATPR) | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.3.1.44 | PI12 Complete - (ID524) | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.3.1.45 | Assurance Review6 - (ID47 & 48) | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.3.1.46 | EvO System Integration Readiness Reviews - Final (EvO SIRR-F) | 0% | 0 days | Wed 20/05/20 | Wed 20/05/20
1.3.1.47 | Lab-based Acceptance Test Readiness Review (LBATRR) Notification | 0% | 0 days | Thu 04/06/20 | Thu 04/06/20
1.3.1.48 | MTRC Lab Design Document Acceptance Review (MTRCAR) Notification | 0% | 0 days | Thu 11/06/20 | Thu 11/06/20
1.3.1.49 | Manufacture Plan Assurance Review (MPR) | 0% | 0 days | Mon 29/06/20 | Mon 29/06/20
1.3.1.50 | PI13 Complete - (ID525) | 0% | 0 days | Tue 30/06/20 | Tue 30/06/20
1.3.1.51 | Lab-based Acceptance Test Readiness Review (LBATRR) | 0% | 0 days | Thu 23/07/20 | Thu 23/07/20
1.3.1.52 | MTRC Lab Design Document Acceptance Review (MTRCAR) | 0% | 0 days | Thu 30/07/20 | Thu 30/07/20
1.3.1.53 | MORPHEUS Architecture Acceptance Review (MAAcR) Notification | 0% | 0 days | Wed 12/08/20 | Wed 12/08/20
1.3.1.54 | Logistics Support & Maintainability Demonstration Readiness Review (LSMDRR) | 0% | 0 days | Mon 28/09/20 | Mon 28/09/20
1.3.1.55 | MORPHEUS Architecture Acceptance Review (MAAcR) | 0% | 0 days | Wed 30/09/20 | Wed 30/09/20
1.3.1.56 | HS&E Acceptance Review (HSEAR) | 0% | 0 days | Wed 30/09/20 | Wed 30/09/20
1.3.1.57 | Security Management Acceptance Review (SMAR) | 0% | 0 days | Wed 30/09/20 | Wed 30/09/20
1.3.1.58 | PI14 Complete - (ID526) | 0% | 0 days | Wed 30/09/20 | Wed 30/09/20
1.3.1.59 | First of Type Field Test Readiness Review (FTFTRR) | 0% | 0 days | Mon 26/10/20 | Mon 26/10/20
1.3.1.60 | EvO System Acceptance Test Review (SATR) Notification | 0% | 0 days | Mon 12/10/20 | Mon 12/10/20
1.3.1.61 | EvO System Acceptance Test Review (EvO SATR) | 0% | 0 days | Mon 30/11/20 | Mon 30/11/20
1.3.1.62 | ILS Acceptance Review (ILSAR) | 0% | 0 days | Mon 30/11/20 | Mon 30/11/20
1.3.1.63 | Manufacture Plan Acceptance Review | 0% | 0 days | Mon 30/11/20 | Mon 30/11/20
1.3.1.64 | Training Systems Acceptance Review (EvO TAcR) | 0% | 0 days | Mon 30/11/20 | Mon 30/11/20
1.3.1.65 | PI15 Complete - (ID527) | 0% | 0 days | Tue 22/12/20 | Tue 22/12/20
1.3.1.66 | JPO IT Services Enabling Acceptance Review | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.3.1.67 | Enabling Business Transformation Acceptance Review | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.3.1.68 | End of TP Project - (ID11) | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.3.2 | TP Project - Dependencies from GD to MOD | 99% | 861 days | Fri 16/06/17 | Thu 19/11/20
1.3.2.1 | GD Supply Platform Installation Guidelines Document (Draft) - (ID21) | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.3.2.2 | GD Supply System BOM (Draft) - (ID21) | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.3.2.3 | GD Supply Generic Complex Fit PSD (Draft) - (ID21) | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.3.2.4 | GD Supply Platform Installation Guidelines Document (Baselined) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.5 | GD Supply System BOM (Baselined) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.6 | GD Supply Generic EvO Fit PSD, inc. Complex Fit with VIP Panel (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.7 | GD Supply Remaining PSDs for EvO Fits (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.8 | GD Supply Remaining BOMs (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.9 | GD Supply Cable Specification Document (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.10 | GD Supply IKEE Cables, MPPS Space Models ["EvO Drop 1"] - (ID226) | 0% | 0 days | Thu 03/05/18 | Thu 03/05/18
1.3.2.11 | GD Supply Cable ICDs (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.12 | GD Supply Product EMC Information (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.13 | GD Supply Product Tempest Information (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.14 | GD Supply CAT Testing Procedures (Draft) - (ID28) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.3.2.15 | GD Supply PPM or Final Space Models for Two Platforms (1 legacy, 1 Future) - (ID229) | 0% | 0 days | Tue 29/01/19 | Tue 29/01/19
1.3.2.16 | GD Supply Product Safety Cases (Mature Hazard log and ALARP) - (ID38) | 0% | 0 days | Wed 03/04/19 | Wed 03/04/19
1.3.2.17 | GD Supply QTMs for 3 Platforms (2 Legacy, 1 Future) - (ID230) | 0% | 0 days | Mon 09/12/19 | Mon 09/12/19
1.3.2.18 | GD Supply QTMs for the remaining 7 Platforms - (ID231) | 0% | 0 days | Fri 31/01/20 | Fri 31/01/20
1.3.2.19 | GD Supply CAT Testing Procedures (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.20 | GD Supply Equipment Maintenance Procedures (Latest Version available at Feb 2020) | 0% | 0 days | Mon 10/02/20 | Mon 10/02/20
1.3.2.21 | GD Supply Generic Complex Fit PSD (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.22 | GD Supply Remaining PSDs for EvO Fits (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.23 | GD Supply Remaining BOMs (Latest version as at Feb 2020) | 0% | 0 days | Mon 10/02/20 | Mon 10/02/20
1.3.2.24 | GD Supply Cable Specification Document (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.25 | GD Supply Cable ICDs (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.26 | GD Supply Product EMC Information (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.27 | GD Supply Product Tempest Information (Final) - (ID46) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.3.2.28 | GD Supply Early Draft of MTRC LDD - (ID20) | 100% | 0 days | Fri 16/06/17 | Fri 16/06/17
1.3.2.29 | GD Supply Information for BMA Competition - (ID22) | 100% | 0 days | Thu 03/08/17 | Thu 03/08/17
1.3.2.30 | GD Supply Baseline of MTRC LDD - (ID26) | 100% | 0 days | Thu 02/11/17 | Thu 02/11/17
1.3.2.31 | GD Supply EnHCDR+ Replacement Information needed for Procurement - (ID27) | 100% | 0 days | Wed 17/01/18 | Wed 17/01/18
1.3.2.32 | GD Supply Training Scoping Report | 100% | 0 days | Tue 06/02/18 | Tue 06/02/18
1.3.2.33 | GD Supply BMA Technical Specification (ID29) | 100% | 1 day | Thu 22/03/18 | Thu 22/03/18
1.3.2.34 | GD Supply EvO Computing Platforms | 0% | 0 days | Thu 15/03/18 | Thu 15/03/18
1.3.2.35 | GD Supply EvO Reference Model / Access to System Integration Lab | 100% | 0 days | Thu 15/03/18 | Thu 15/03/18
1.3.2.36 | GD Supply first set of equipment (Mix of PPMs and QTMs) and functional software to iMTRC - (ID234) | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.3.2.37 | GD Supply 6 Platforms worth of kit (Mix of PPMs and QTMs) and functional software to iMTRC - 7 in total - (ID235) | 0% | 0 days | Thu 25/04/19 | Thu 25/04/19
1.3.2.38 | GD Complete Delivery of an additional 10 Platforms worth of kit (QTMs) and functional software to iMTRC - 30 in total - (ID243) | 0% | 0 days | Thu 19/11/20 | Thu 19/11/20
1.3.2.39 | GD Supply Operator and Maintainer Manuals for their Equipment | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.3.2.40 | GD Start Supporting Installation of iMTRC Equipment | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.3.2.41 | GD Supply HRS / SRS for Products for BMA & EnHCDR+ - (IDs 32 & 33) | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.3.2.42 | GD Supply 30 QTMs of TMR 304s - (ID237) | 0% | 0 days | Thu 04/10/18 | Thu 04/10/18
1.3.2.43 | GD Supply 54 QTMs of TCS 300s - (ID238) | 0% | 0 days | Mon 14/01/19 | Mon 14/01/19
1.3.2.44 | GD Supply 9 QTMs of VPUs - (ID239) | 0% | 0 days | Mon 13/01/20 | Mon 13/01/20
1.3.2.45 | GD Supply 25 QTMs of TLAs - (ID240) | 0% | 0 days | Thu 13/06/19 | Thu 13/06/19
1.3.2.46 | GD Supply 9 QTMs of TMR 314s - (ID241) | 0% | 0 days | Tue 13/08/19 | Tue 13/08/19
1.3.2.47 | GD Supply 9 QTMs of SADD's - (ID242) | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.3.2.48 | GD Supply TNA Report Delivery for TRA Acceptance available at AR6 | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.3.2.49 | GD Supply Final version of MTRC LDD - (ID55) | 0% | 0 days | Thu 30/07/20 | Thu 30/07/20
1.3.2.50 | GD Final Delivery of TNA Report and Training material | 0% | 0 days | Thu 15/10/20 | Thu 15/10/20
1.3.3 | TP Project - Dependencies from MOD to GD | 0% | 923 days | Fri 17/03/17 | Tue 24/11/20
1.3.3.1 | MOD Supply GD with Platform Survey Report | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.3.3.2 | MOD supply GFI for Architecture and Design Programme Start (D1-1b,D1-3b,D1-4b,D1-5b,D3-1b,D3-2b,D3-3b,D3-4b,D3-5b,D3-6b,D3-8b, D3-10b,D3-12b,D3-13b,D3-28b,D14-1b,D14-2b,D15-1b,D16-2b,D16-5b,D3-30b,D3-31b) | 100% | 0 days | Mon 03/04/17 | Mon 03/04/17
1.3.3.3 | MOD Approve Access to Legacy GFI | 100% | 0 days | Mon 03/04/17 | Mon 03/04/17
1.3.3.4 | MOD Supply Technical Documentation Pack for 117 and 152 Radios | 100% | 0 days | Mon 03/04/17 | Mon 03/04/17
1.3.3.5 | MOD Supply GFE for CAN Lab Programme Start (D3-1a,D3-2a,D3-3a,D13-1a) | 100% | 0 days | Thu 31/08/17 | Thu 31/08/17
1.3.3.6 | MOD Supply GFI to GD MACA3 (D16-2b) | 100% | 0 days | Fri 23/06/17 | Fri 23/06/17
1.3.3.7 | MOD Supply GFE to GD MACA3 (D3-1a) | 100% | 0 days | Fri 23/06/17 | Fri 23/06/17
1.3.3.8 | MOD Supply GD with Common Services Drop of BMA | 0% | 0 days | Thu 15/08/19 | Thu 15/08/19
1.3.3.9 | MOD Supply GFI to GD MACA5 (D1-1b,D2-1b,D2-2b,D2-3b,D2-4b,D16-1b,D16-4b,D3-4b) | 100% | 0 days | Thu 24/08/17 | Thu 24/08/17
1.3.3.10 | MOD Supply GFE to GD MACA6 (D3-1a) | 100% | 0 days | Mon 25/09/17 | Mon 25/09/17
1.3.3.11 | MOD Supply GFI to GD MACA6 (D3-14b,D3-29b) | 100% | 0 days | Thu 12/10/17 | Thu 12/10/17
1.3.3.12 | MOD Supply GFE for UK Lab MACA9 (D3-1a,D3-2a,D3-3a,D3-13a) | 100% | 0 days | Fri 22/12/17 | Fri 22/12/17
1.3.3.13 | MOD Supply GFI to GD MACA12 (D12-1b,D3-15b) | 100% | 0 days | Fri 23/03/18 | Fri 23/03/18
1.3.3.14 | MOD Supply GFE to GD MACA12 (D3-3a,D3-12a) | 100% | 0 days | Fri 23/03/18 | Fri 23/03/18
1.3.3.15 | MOD Supply Technical Proposals, Compliance Statements & Other GFI for BMA | 0% | 0 days | Tue 06/11/18 | Tue 06/11/18
1.3.3.16 | MOD Supply Technical Proposals, Compliance Statements & Other GFI for EnHCDR | 0% | 0 days | Wed 28/03/18 | Wed 28/03/18
1.3.3.17 | MOD Supply GFE to GD MACA15 (D3-2a,D3-3a) | 0% | 0 days | Mon 25/06/18 | Mon 25/06/18
1.3.3.18 | MOD Supply GFE to GD MACA18 (D3-7a,D3-11a) | 0% | 0 days | Mon 24/09/18 | Mon 24/09/18
1.3.3.19 | MOD Supply Results of Openness Tests for BMA MACA 36 (D5-4b) | 0% | 0 days | Mon 17/02/20 | Mon 17/02/20
1.3.3.20 | MOD Supply Results of Openness Tests for EnHCDR+ MACA36(D7-3b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.3.3.21 | MOD Supply Initial Drop of BMA MACA24 (D5-1a) | 0% | 0 days | Fri 22/02/19 | Fri 22/02/19
1.3.3.22 | MOD Supply GVA Reference System MACA24 (D3-4a) | 0% | 0 days | Mon 25/03/19 | Mon 25/03/19
1.3.3.23 | MOD Supply GFE to GD MACA24 (D7-1a,D5-1a,D3-19b,D3-27b,D3-19b,D3-9a,D3-6a,D3-5a,D3-4a,D3-3a) | 0% | 0 days | Fri 22/03/19 | Fri 22/03/19
1.3.3.24 | MOD Supply GFE for UK Lab MACA25 (D1-1a) | 0% | 0 days | Wed 24/04/19 | Wed 24/04/19
1.3.3.25 | MOD Supply GFI to GD MACA25 (D1-2b,D4-1b) | 0% | 0 days | Wed 24/04/19 | Wed 24/04/19
1.3.3.26 | MOD Supply Documentation for BMA Software MACA 36 (D5-3b) | 0% | 0 days | Mon 17/02/20 | Mon 17/02/20
1.3.3.27 | MOD Supply Full Functionality Version of BMA MACA35 (D5-1a) | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.3.3.28 | MOD Supply Documentation for EnHCDR+ Software MACA 36 (D7-4b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.3.3.29 | MOD Supply GFE to GD MACA33 (D3-10a) | 0% | 0 days | Tue 24/12/19 | Tue 24/12/19
1.3.3.30 | MOD Supply BMA Product Qualification Document MACA36 (D5-1b) | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.3.3.31 | MOD Supply BMA Product Certificate of Conformance MACA 36 (D5-2b) | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.3.3.32 | MOD Supply EnHCDR+ Product Qualification Document MACA36 (D7-1b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.3.3.33 | MOD Supply EnHCDR+ Product Certificate of Conformance & Certification / Verification Test Results MACA36 (D7-2b & D7 -5b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.3.3.34 | MOD Supply Final Drop of BMA MACA38 (D5-1a) | 0% | 0 days | Thu 14/05/20 | Thu 14/05/20
1.3.3.35 | MOD Supply GFI to GD MACA36 (D7-5b,D7-4b,D7-3b,D7-2b,D7-1b,D6-5b,D6-4b, D6-3b,D6-2b,D6-1b,D5-5b,D5-4b,D5-3b,D5-2b,D5-1b,D3-17b,D3-16b,D13-1b) | 0% | 0 days | Tue 24/03/20 | Tue 24/03/20
1.3.3.36 | MOD Supply GFE to GD MACA36 (D3-14a) | 0% | 0 days | Tue 24/03/20 | Tue 24/03/20
1.3.3.37 | MOD Supply Single Drop of EnHCDR MACA24 (D7-1a) | 0% | 0 days | Fri 17/05/19 | Fri 17/05/19
1.3.3.38 | FOT Field Test Readiness Review MACA43 | 0% | 0 days | Wed 14/10/20 | Wed 14/10/20
1.3.3.39 | FOT Field Tests Completed MACA44 | 0% | 0 days | Thu 19/11/20 | Thu 19/11/20
1.3.3.40 | MOD Supply GFI to GD MACA 44 (D9-1b) | 0% | 0 days | Tue 24/11/20 | Tue 24/11/20
1.3.3.41 | MOD GFX Deliverables to GD Complete | 0% | 0 days | Tue 24/11/20 | Tue 24/11/20
1.4 | Future Projects Activities (Strategy) | 30% | 2205 days | Mon 06/03/17 | Wed 24/12/25
1.4.1 | Enduring Activities | 14% | 2205 days | Mon 06/03/17 | Wed 24/12/25
1.4.1.1 | Organise, Hold and Report on Strategy Meetings | 12% | 2085 days | Mon 03/04/17 | Tue 05/08/25
1.4.1.2 | Evidence Working Groups | 28% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.4.1.3 | Manage the SI Work stream 17/18 | 100% | 144 days | Fri 01/09/17 | Thu 29/03/18
1.4.1.4 | Manage the SI Work stream 18/19 Onwards | 0% | 1937 days | Tue 03/04/18 | Wed 24/12/25
1.4.1.5 | Engage with Army HQ on Benefits Management for LE TACIS Programme | 26% | 936 days | Mon 03/04/17 | Thu 24/12/20
1.4.1.6 | Update and Maintain ECD Maturity Roadmap and Plan | 0% | 603 days | Thu 02/08/18 | Thu 24/12/20
1.4.2 | Key Deliverables | 58% | 891 days | Mon 06/03/17 | Thu 24/09/20
1.4.2.1 | RN4 Scope and Approval Strategy | 100% | 250 days | Mon 06/03/17 | Mon 05/03/18
1.4.2.1.1 | Define Scope of RN4 | 100% | 40 days | Mon 06/03/17 | Wed 03/05/17
1.4.2.1.2 | Circulate and Agree Scope | 100% | 210 days | Thu 04/05/17 | Mon 05/03/18
1.4.2.1.3 | Scope Agreed | 100% | 0 days | Mon 05/03/18 | Mon 05/03/18
1.4.2.2 | Strategy Evidence Updates Required - RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.1 | Maintain Overarching Procurement Strategy | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.2 | EnHCDR Long Term Requirement Update RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.3 | JPO Enduring Update RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.4 | Fielding strategy Army HQ Update RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.5 | Draft Proc Strat Fielding Partner Update RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.6 | Maintain System Integrator strategy for RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.7 | Update eMTRC Procurement Strategy RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.8 | Training Delivery Strategy Update RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.9 | Update MSP Capping Paper RN4 | 71% | 160 days | Fri 13/10/17 | Thu 07/06/18
1.4.2.2.10 | RN4 Evidence Produced | 0% | 0 days | Thu 07/06/18 | Thu 07/06/18
1.4.2.3 | RN5 Scope and Approval Strategy | 8% | 175 days | Mon 12/03/18 | Fri 16/11/18
1.4.2.3.1 | Define Scope of RN5 | 35% | 40 days | Mon 12/03/18 | Wed 09/05/18
1.4.2.3.2 | Circulate and Agree Scope | 0% | 135 days | Thu 10/05/18 | Fri 16/11/18
1.4.2.3.3 | Scope Agreed | 0% | 0 days | Fri 16/11/18 | Fri 16/11/18
1.4.2.4 | Strategy Evidence Updates Required - RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.1 | Maintain Overarching Procurement Strategy | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.2 | EnHCDR Long Term Requirement RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.3 | JPO Enduring RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.4 | Fielding strategy Army HQ RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.5 | Draft Proc Strat Fielding Partner RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.6 | Maintain eMTRC Procurement Strategy RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.7 | Training Delivery Strategy RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.8 | Maintain MSP Capping Paper RN5 | 0% | 100 days | Fri 29/06/18 | Fri 16/11/18
1.4.2.4.9 | RN5 Evidence Produced | 0% | 0 days | Fri 16/11/18 | Fri 16/11/18
1.4.2.5 | Strategy Updates Required - MGBC | 0% | 245 days | Thu 03/10/19 | Thu 24/09/20
1.4.2.5.1 | Start Updating Strategy Documents as required for MGBC Submission | 0% | 159 days | Thu 03/10/19 | Tue 26/05/20
1.4.2.5.2 | Finish Updating Strategy Documents to address evidence requirements for MGBC Submission | 0% | 86 days | Wed 27/05/20 | Thu 24/09/20
1.4.2.5.3 | MGBC Evidence Produced | 0% | 0 days | Thu 24/09/20 | Thu 24/09/20
1.4.2.6 | ECD Maturity Roadmap & Plan | 100% | 106 days | Mon 03/04/17 | Mon 04/09/17
1.4.2.6.1 | Produce Draft ECD Maturity Roadmap & Plan | 100% | 102 days | Mon 03/04/17 | Tue 29/08/17
1.4.2.6.2 | Draft ECD Maturity Roadmap & Plan Issued for Comment | 100% | 0 days | Tue 29/08/17 | Tue 29/08/17
1.4.2.6.3 | Update Draft ECD Maturity Roadmap & Plan | 100% | 2 days | Wed 30/08/17 | Thu 31/08/17
1.4.2.6.4 | ECD Maturity Roadmap & Plan Approved | 100% | 2 days | Fri 01/09/17 | Mon 04/09/17
1.4.2.6.5 | Review Draft ECD Maturity Roadmap & Plan | 100% | 0 days | Mon 04/09/17 | Mon 04/09/17
1.4.2.7 | Project Strategy Document | 100% | 242 days | Mon 03/04/17 | Wed 21/03/18
1.4.2.7.1 | Produce Updated Projects Strategy Document | 100% | 227 days | Mon 03/04/17 | Wed 28/02/18
1.4.2.7.2 | Draft Updated Projects Strategy Document Issued for Comment | 100% | 0 days | Wed 28/02/18 | Wed 28/02/18
1.4.2.7.3 | Review Updated Projects Strategy Document | 100% | 10 days | Thu 01/03/18 | Wed 14/03/18
1.4.2.7.4 | Update Projects Strategy Document to address review comments | 100% | 5 days | Thu 15/03/18 | Wed 21/03/18
1.4.2.7.5 | Update Projects Strategy Document Approved | 100% | 0 days | Wed 21/03/18 | Wed 21/03/18
1.4.2.8 | Innovation Management Recommendations Report | 100% | 200 days | Mon 03/04/17 | Mon 22/01/18
1.4.2.8.1 | Produce Draft Innovation Management Recommendations Report | 100% | 185 days | Mon 03/04/17 | Fri 22/12/17
1.4.2.8.2 | Draft Innovation Management Recommendations Report Issued for Comment | 100% | 0 days | Fri 22/12/17 | Fri 22/12/17
1.4.2.8.3 | Review Draft Innovation Management Recommendations Report | 100% | 10 days | Tue 02/01/18 | Mon 15/01/18
1.4.2.8.4 | Update Draft Innovation Management Recommendations Report | 100% | 5 days | Tue 16/01/18 | Mon 22/01/18
1.4.2.8.5 | Innovation Management Recommendations Report Approved | 100% | 0 days | Mon 22/01/18 | Mon 22/01/18
1.4.2.9 | Systems Integration Annex | 100% | 118 days | Fri 01/09/17 | Wed 21/02/18
1.4.2.9.1 | Updated SI Proc Strat Annex Issued for Comment | 100% | 103 days | Fri 01/09/17 | Wed 31/01/18
1.4.2.9.2 | Updated SI Proc Strat Annex Issued for Comment | 100% | 0 days | Wed 31/01/18 | Wed 31/01/18
1.4.2.9.3 | Review Updated SI Annex | 100% | 10 days | Thu 01/02/18 | Wed 14/02/18
1.4.2.9.4 | Update SI Annex | 100% | 5 days | Thu 15/02/18 | Wed 21/02/18
1.4.2.9.5 | Updated SI Annex Approved | 100% | 0 days | Wed 21/02/18 | Wed 21/02/18
1.4.2.10 | Operational Service Management | 100% | 248 days | Mon 03/04/17 | Thu 29/03/18
1.4.2.10.1 | Produce OSM Document | 100% | 145 days | Mon 03/04/17 | Fri 27/10/17
1.4.2.10.2 | Updated OSM Issued for Comment | 100% | 0 days | Fri 27/10/17 | Fri 27/10/17
1.4.2.10.3 | Review Updated OSM Document | 100% | 63 days | Mon 30/10/17 | Thu 01/02/18
1.4.2.10.4 | Update OSM Document | 100% | 40 days | Fri 02/02/18 | Thu 29/03/18
1.4.2.10.5 | OSM Strategy Document Approved | 100% | 0 days | Wed 28/03/18 | Wed 28/03/18
1.5 | Information Note 2017 | 100% | 234 days | Mon 06/03/17 | Fri 09/02/18
1.5.1 | Evidence Generation | 100% | 160 days | Mon 06/03/17 | Fri 20/10/17
1.5.1.1 | Collate evidence for Information Note 2017 | 100% | 160 days | Mon 06/03/17 | Fri 20/10/17
1.5.2 | Information Note 2017 Drafting | 100% | 103 days | Fri 23/06/17 | Wed 15/11/17
1.5.2.1 | IN outline Scope & Strategy | 100% | 5 days | Fri 23/06/17 | Thu 29/06/17
1.5.2.2 | IN Drafting - Skeleton | 100% | 5 days | Fri 30/06/17 | Thu 06/07/17
1.5.2.3 | Review of IN Skeleton Draft | 100% | 5 days | Fri 07/07/17 | Thu 13/07/17
1.5.2.4 | Update IN Draft following BATCIS Review | 100% | 5 days | Fri 14/07/17 | Thu 20/07/17
1.5.2.5 | 1 Star Review of IN Skeleton Draft | 100% | 15 days | Fri 21/07/17 | Thu 10/08/17
1.5.2.6 | Develop Main IN | 100% | 36 days | Fri 11/08/17 | Mon 02/10/17
1.5.2.7 | IN FAQ Drafting | 0% | 10 days | Fri 11/08/17 | Thu 24/08/17
1.5.2.8 | BATCIS Joint Review | 100% | 3 days | Tue 03/10/17 | Thu 05/10/17
1.5.2.9 | IN Update | 100% | 3 days | Fri 06/10/17 | Tue 10/10/17
1.5.2.10 | IN Update (Assurance Review 1 & GW0) | 100% | 3 days | Wed 11/10/17 | Fri 13/10/17
1.5.2.11 | Programme Manager Circulation with Hd BATCIS | 100% | 3 days | Mon 16/10/17 | Wed 18/10/17
1.5.2.12 | IN Update | 100% | 1 day | Thu 19/10/17 | Thu 19/10/17
1.5.2.13 | Hd BATCIS engagement (ISS, AHQ) | 100% | 5 days | Fri 20/10/17 | Thu 26/10/17
1.5.2.14 | IN 2017 Issued to CDIO / SRO | 100% | 9 days | Thu 26/10/17 | Wed 08/11/17
1.5.2.15 | Brief up to ISS DIR DEV, CEO and SRO | 100% | 1 day | Thu 09/11/17 | Thu 09/11/17
1.5.2.16 | Final Sign off by all and brief Head Office | 100% | 2 days | Fri 10/11/17 | Mon 13/11/17
1.5.2.17 | IN Update | 100% | 2 days | Tue 14/11/17 | Wed 15/11/17
1.5.2.18 | IN 2017 Endorsed | 100% | 0 days | Wed 15/11/17 | Wed 15/11/17
1.5.3 | DP&AS IAC Circulation | 100% | 56 days | Thu 16/11/17 | Fri 09/02/18
1.5.3.1 | IN Documents sent to DP&AS & JFC | 100% | 2 days | Thu 16/11/17 | Fri 17/11/17
1.5.3.2 | DP&AS IAC Initial Covering Letter | 100% | 3 days | Thu 16/11/17 | Mon 20/11/17
1.5.3.3 | I Note Circulation to ARMY / JFC ( Out of Committee) | 100% | 29 days | Tue 21/11/17 | Mon 08/01/18
1.5.3.4 | BATCIS address DP&AS Comments | 100% | 2 days | Mon 08/01/18 | Wed 10/01/18
1.5.3.5 | I Note submit to DP&AS Final | 100% | 0 days | Wed 10/01/18 | Wed 10/01/18
1.5.3.6 | DP&AS IAC Final Prep for Circulation | 100% | 2 days | Thu 11/01/18 | Fri 12/01/18
1.5.3.7 | I Note IAC Circulation (Out of Committee) | 100% | 17 days | Mon 15/01/18 | Tue 06/02/18
1.5.3.8 | DP&AS Produce IAC Outletter | 100% | 3 days | Wed 07/02/18 | Fri 09/02/18
1.5.3.9 | I Note 2017 Outletter Received | 100% | 0 days | Fri 09/02/18 | Fri 09/02/18
1.6 | Review Note 4 | 48% | 441 days | Wed 19/04/17 | Wed 23/01/19
1.6.1 | Evidence Generation | 57% | 362 days | Wed 19/04/17 | Wed 26/09/18
1.6.1.1 | IAAP | 85% | 270 days | Wed 19/04/17 | Thu 17/05/18
1.6.1.1.1 | RN4 IAAP Update Process | 100% | 20 days | Wed 19/04/17 | Wed 17/05/17
1.6.1.1.2 | RN4 Update existing IAAP | 100% | 140 days | Fri 11/08/17 | Mon 05/03/18
1.6.1.1.3 | RN4 Review updated IAAP | 90% | 20 days | Tue 06/03/18 | Wed 04/04/18
1.6.1.1.4 | RN4 Engagement Assurance / scrutiny | 0% | 20 days | Thu 05/04/18 | Wed 02/05/18
1.6.1.1.5 | RN4 Update Document post scrutiny engagement | 0% | 10 days | Thu 03/05/18 | Thu 17/05/18
1.6.1.1.6 | RN4 IAAP Version 2 released | 0% | 0 days | Thu 17/05/18 | Thu 17/05/18
1.6.1.2 | Cost model | 52% | 232 days | Mon 23/10/17 | Wed 26/09/18
1.6.1.2.1 | RN4 SRA Available | 0% | 0 days | Fri 08/06/18 | Fri 08/06/18
1.6.1.2.2 | RN4 3OAs Available | 0% | 0 days | Wed 25/04/18 | Wed 25/04/18
1.6.1.2.3 | RN4 Accounting Treatments & FOREX confirmed with Defence Economics | 100% | 0 days | Fri 24/11/17 | Fri 24/11/17
1.6.1.2.4 | RN4 Support to developing evidence | 72% | 150 days | Mon 23/10/17 | Fri 01/06/18
1.6.1.2.5 | RN4 Briefing (including compiling briefing packs) | 72% | 150 days | Mon 23/10/17 | Fri 01/06/18
1.6.1.2.6 | RN4 Update to Cost Model | 0% | 28 days | Wed 02/05/18 | Tue 12/06/18
1.6.1.2.7 | RN4 Affordability Assessment | 0% | 20 days | Tue 15/05/18 | Tue 12/06/18
1.6.1.2.8 | RN4 Finalise Cost Model | 0% | 15 days | Wed 13/06/18 | Tue 03/07/18
1.6.1.2.9 | RN4 Cost MDAL | 72% | 150 days | Mon 23/10/17 | Fri 01/06/18
1.6.1.2.10 | RN4 Cost Risk Register | 72% | 150 days | Mon 23/10/17 | Fri 01/06/18
1.6.1.2.11 | RN4 Investment Appraisal | 0% | 60 days | Mon 09/04/18 | Tue 03/07/18
1.3.11 | LSSP: BAFO Evaluation Complete | 0% | 0 days | Mon 14/05/18 | Mon 14/05/18
1.6.1.2.13 | RN4 Review Updated Cost Model with BATCIS TL and Update as required | 0% | 10 days | Wed 04/07/18 | Tue 17/07/18
1.6.1.2.14 | RN4 Raise CAAS Work Request Form DP122 | 100% | 1 day | Mon 30/10/17 | Mon 30/10/17
1.6.1.2.15 | RN4 PT Engagement With CAAS | 51% | 200 days | Tue 31/10/17 | Mon 20/08/18
1.6.1.2.16 | RN4 CAAS Verification | 0% | 15 days | Wed 18/07/18 | Tue 07/08/18
1.6.1.2.17 | RN4 CAAS Validation | 0% | 15 days | Tue 07/08/18 | Wed 29/08/18
1.6.1.2.18 | RN4 CAAS Independent Cost Estimate (ICE) | 51% | 200 days | Tue 31/10/17 | Mon 20/08/18
1.6.1.2.19 | RN4 CAAS Schedule Risk Analysis (SRA) | 0% | 20 days | Wed 18/07/18 | Tue 14/08/18
1.6.1.2.20 | RN4 CAAS 3rd Party Assurance | 51% | 200 days | Tue 31/10/17 | Mon 20/08/18
1.6.1.2.21 | RN4 CAAS Optimism Bias (OB) | 0% | 5 days | Wed 18/07/18 | Tue 24/07/18
1.6.1.2.22 | RN4 CAAS Approvals Team (CAT) Report | 0% | 20 days | Thu 30/08/18 | Wed 26/09/18
1.6.1.3 | Additional Evidence | 99% | 83 days | Mon 12/02/18 | Tue 12/06/18
1.6.1.3.1 | LFE Review in Prep for RN4 | 100% | 6 days | Mon 12/02/18 | Mon 19/02/18
1.6.1.3.2 | RN4 LFE Record Update | 100% | 5 days | Tue 20/02/18 | Mon 26/02/18
1.6.1.3.3 | RN4 Future Projects Strategy Update completed | 0% | 0 days | Thu 07/06/18 | Thu 07/06/18
1.6.1.3.4 | RN4 eMTRC Update | 0% | 0 days | Wed 16/05/18 | Wed 16/05/18
1.4.1.7.2.6 | Approval of Initial Affordability | 0% | 0 days | Tue 12/06/18 | Tue 12/06/18
1.6.1.3.6 | RN4 TSP DSC Initial Affordability Evaluation Complete | 0% | 0 days | Tue 12/06/18 | Tue 12/06/18
1.6.1.3.7 | All RN4 Evidence Complete | 0% | 0 days | Thu 07/06/18 | Thu 07/06/18
1.6.2 | Review Note 4 Approval | 20% | 431 days | Thu 04/05/17 | Wed 23/01/19
1.6.2.1 | JROC | 0% | 12 days | Wed 18/04/18 | Thu 03/05/18
1.6.2.1.1 | RN4 Prepare for JROC | 0% | 5 days | Wed 18/04/18 | Tue 24/04/18
1.6.2.1.2 | RN4 Submit documents to JROC | 0% | 0 days | Tue 24/04/18 | Tue 24/04/18
1.6.2.1.3 | RN4 JROC Circulation | 0% | 5 days | Wed 25/04/18 | Tue 01/05/18
1.6.2.1.4 | RN4 JROC Meeting | 0% | 1 day | Wed 02/05/18 | Wed 02/05/18
1.6.2.1.5 | RN4 Rework following JROC | 0% | 1 day | Thu 03/05/18 | Thu 03/05/18
1.6.2.1.6 | RN4 JROC Complete | 0% | 0 days | Thu 03/05/18 | Thu 03/05/18
1.6.2.2 | RN4 | 45% | 338 days | Thu 04/05/17 | Thu 06/09/18
1.6.2.2.1 | RN4 Approvals Kick off EWG Prep | 100% | 70 days | Thu 04/05/17 | Thu 10/08/17
1.6.2.2.2 | RN4 Approvals Kick off EWG | 100% | 2 days | Fri 11/08/17 | Mon 14/08/17
1.6.2.2.3 | RN4 Scope and Plan | 100% | 10 days | Mon 12/02/18 | Fri 23/02/18
1.6.2.2.4 | RN4 Skeleton Drafting | 35% | 69 days | Mon 26/02/18 | Wed 06/06/18
1.6.2.2.5 | RN4 BATCIS /D Info Skeleton Review | 0% | 5 days | Thu 07/06/18 | Wed 13/06/18
1.6.2.2.6 | RN4 Update Skeleton | 0% | 5 days | Thu 14/06/18 | Wed 20/06/18
1.6.2.2.7 | RN4 Skeleton Complete | 0% | 0 days | Wed 20/06/18 | Wed 20/06/18
1.6.2.2.8 | RN4 drafting | 0% | 20 days | Thu 21/06/18 | Wed 18/07/18
1.6.2.2.9 | RN4 FAQ Drafting | 0% | 20 days | Thu 21/06/18 | Wed 18/07/18
1.6.2.2.10 | RN4 FAQ BATCIS / D Info Review | 0% | 5 days | Thu 19/07/18 | Wed 25/07/18
1.6.2.2.11 | RN4 FAQ Update | 0% | 5 days | Thu 26/07/18 | Wed 01/08/18
1.6.2.2.12 | RN4 Update Including Completed Figures | 0% | 3 days | Thu 02/08/18 | Mon 06/08/18
1.6.2.2.13 | RN4 Desk Level Review (Including JFC / Army / ISS / Scrutiny) | 0% | 5 days | Tue 07/08/18 | Mon 13/08/18
1.6.2.2.14 | RN4 Update | 0% | 3 days | Tue 14/08/18 | Thu 16/08/18
1.6.2.2.15 | RN4 Issued to 1Stars | 0% | 0 days | Thu 16/08/18 | Thu 16/08/18
1.6.2.2.16 | RN4 1* Sign Off | 0% | 5 days | Fri 17/08/18 | Thu 23/08/18
1.6.2.2.17 | RN4 Post Sign Off Update | 0% | 2 days | Fri 24/08/18 | Tue 28/08/18
1.6.2.2.18 | RN4 Issued to 2 Stars | 0% | 0 days | Tue 28/08/18 | Tue 28/08/18
1.6.2.2.19 | RN4 2 Star Sign Off | 0% | 5 days | Wed 29/08/18 | Tue 04/09/18
1.6.2.2.20 | RN4 Update | 0% | 2 days | Wed 05/09/18 | Thu 06/09/18
1.6.2.2.21 | RN4 Endorsed for ARB | 0% | 0 days | Thu 06/09/18 | Thu 06/09/18
1.6.2.3 | ARB Assurance - To be aligned to Evidence Time lines | 0% | 66 days | Fri 22/06/18 | Mon 24/09/18
1.6.2.3.1 | RN4 Independent SME assurance reports | 0% | 40 days | Fri 22/06/18 | Thu 16/08/18
1.6.2.3.2 | RN4 Independent SME Assurance Reports Complete | 0% | 0 days | Thu 16/08/18 | Thu 16/08/18
1.6.2.3.3 | RN4 Financial Assurance | 0% | 40 days | Fri 22/06/18 | Thu 16/08/18
1.6.2.3.4 | RN4 Financial Assurance Complete | 0% | 0 days | Thu 16/08/18 | Thu 16/08/18
1.6.2.3.5 | RN4 Commercial Assurance | 0% | 40 days | Fri 22/06/18 | Thu 16/08/18
1.6.2.3.6 | RN4 Commercial Assurance Complete | 0% | 0 days | Thu 16/08/18 | Thu 16/08/18
1.6.2.3.7 | RN4 SS Delivery Assurance (a-j) | 0% | 40 days | Fri 22/06/18 | Thu 16/08/18
1.6.2.3.8 | RN4 ISS Delivery Assurance (a-j) Complete | 0% | 0 days | Thu 16/08/18 | Thu 16/08/18
1.6.2.3.9 | RN4 ISS Self Assurance Report | 0% | 2 days | Fri 17/08/18 | Mon 20/08/18
1.6.2.3.10 | RN4 ISS Self Assurance Report Complete | 0% | 0 days | Mon 20/08/18 | Mon 20/08/18
1.6.2.3.11 | RN4 ARB Assurance Review Meeting (desk level) | 0% | 1 day | Fri 29/06/18 | Fri 29/06/18
1.6.2.3.12 | RN4 ARB Assurance Review Meeting (desk level) | 0% | 1 day | Mon 16/07/18 | Mon 16/07/18
1.6.2.3.13 | RN4 ARB Assurance Review Meeting (desk level) | 0% | 1 day | Tue 14/08/18 | Tue 14/08/18
1.6.2.3.14 | RN4 ISS ARB Circulation Prep | 0% | 1 day | Fri 07/09/18 | Fri 07/09/18
1.6.2.3.15 | RN4 ARB Submission | 0% | 0 days | Fri 07/09/18 | Fri 07/09/18
1.6.2.3.16 | RN4 ISS ARB Circulation | 0% | 5 days | Mon 10/09/18 | Fri 14/09/18
1.6.2.3.17 | ISS ARB Meeting | 0% | 1 day | Mon 17/09/18 | Mon 17/09/18
1.6.2.3.18 | RN4 ISS ARB Complete | 0% | 0 days | Mon 17/09/18 | Mon 17/09/18
1.4.1.9.2 | RN4 Input Complete | 0% | 0 days | Tue 07/08/18 | Tue 07/08/18
1.5.6.3 | DSC Minor: RN4 Input Complete | 0% | 0 days | Tue 24/07/18 | Tue 24/07/18
1.6.2.3.21 | RN4 Update | 0% | 5 days | Tue 18/09/18 | Mon 24/09/18
1.6.2.3.22 | RN4 ISS ARB Endorsement | 0% | 0 days | Mon 24/09/18 | Mon 24/09/18
1.6.2.4 | DP&AS Draft-circulation | 0% | 22 days | Mon 24/09/18 | Wed 24/10/18
1.6.2.4.1 | RN4 Draft Scrutiny report Received | 0% | 0 days | Wed 26/09/18 | Wed 26/09/18
1.6.2.4.2 | RN4 Review and Address Scrutiny Report Comments | 0% | 20 days | Thu 27/09/18 | Wed 24/10/18
1.6.2.4.3 | RN4 sent to DP&AS | 0% | 0 days | Mon 24/09/18 | Mon 24/09/18
1.6.2.4.4 | RN4 DP&AS Collate the Submission | 0% | 4 days | Tue 25/09/18 | Fri 28/09/18
1.6.2.4.5 | RN4 Draft Circulation (1 and 2 Star ) | 0% | 10 days | Mon 01/10/18 | Fri 12/10/18
1.6.2.4.6 | RN4 Draft Comments collated by DP&AS | 0% | 1 day | Mon 15/10/18 | Mon 15/10/18
1.6.2.4.7 | RN4 Update following comments | 0% | 3 days | Tue 16/10/18 | Thu 18/10/18
1.6.2.4.8 | RN4 Draft Circulation Complete | 0% | 0 days | Thu 18/10/18 | Thu 18/10/18
1.6.2.5 | JFC 2 Star Circulation | 0% | 7 days | Thu 18/10/18 | Mon 29/10/18
1.6.2.5.1 | RN4 sent to JFC 2 Stars | 0% | 0 days | Thu 18/10/18 | Thu 18/10/18
1.6.2.5.2 | RN4 JFC 2 Star Circulation | 0% | 5 days | Fri 19/10/18 | Thu 25/10/18
1.6.2.5.3 | RN4 Update | 0% | 2 days | Fri 26/10/18 | Mon 29/10/18
1.6.2.5.4 | RN4 JFC 2 Star Endorsement | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.6.2.6 | IAC | 0% | 15 days | Mon 29/10/18 | Mon 19/11/18
1.6.2.6.1 | RN4 Final Scrutiny Report | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.6.2.6.2 | RN4 Review and Address Scrutiny Report Comments | 0% | 10 days | Tue 30/10/18 | Mon 12/11/18
1.6.2.6.3 | RN4 Submitted to DPAS | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.6.2.6.4 | RN4 DP&AS Collate Final IAC Submission | 0% | 4 days | Tue 30/10/18 | Fri 02/11/18
1.6.2.6.5 | RN4 IAC Circulation (OOC) | 0% | 10 days | Mon 05/11/18 | Fri 16/11/18
1.6.2.6.6 | RN4 IAC Meeting | 0% | 1 day | Mon 19/11/18 | Mon 19/11/18
1.6.2.6.7 | RN4 IAC Endorsement | 0% | 0 days | Mon 19/11/18 | Mon 19/11/18
1.6.2.7 | Ministerial / Treasury Circulation | 0% | 41 days | Tue 20/11/18 | Wed 23/01/19
1.6.2.7.1 | RN4 Min Sub Preparation | 0% | 3 days | Tue 20/11/18 | Thu 22/11/18
1.6.2.7.2 | RN4 Ministerial Review | 0% | 15 days | Fri 23/11/18 | Thu 13/12/18
1.6.2.7.3 | RN4 CST (Treasury Review) | 0% | 15 days | Fri 14/12/18 | Fri 11/01/19
1.6.2.7.4 | RN4 Complete Cabinet Office Review | 0% | 5 days | Mon 14/01/19 | Fri 18/01/19
1.6.2.7.5 | RN4 DP&AS Out letter Preparation | 0% | 3 days | Mon 21/01/19 | Wed 23/01/19
1.6.2.7.6 | RN4 Ministerial Approval / Out letter | 0% | 0 days | Wed 23/01/19 | Wed 23/01/19
1.7 | Review Note 5 | 3% | 334 days | Thu 01/03/18 | Tue 02/07/19
1.7.1 | Evidence Generation | 4% | 282 days | Thu 01/03/18 | Mon 15/04/19
1.7.1.1 | IAAP | 11% | 200 days | Thu 01/03/18 | Wed 12/12/18
1.7.1.1.1 | Phase 2 IAAP Update Process | 100% | 20 days | Thu 01/03/18 | Wed 28/03/18
1.7.1.1.2 | Update existing IAAP | 1% | 120 days | Thu 29/03/18 | Wed 19/09/18
1.7.1.1.3 | Review updated IAAP | 0% | 20 days | Thu 20/09/18 | Wed 17/10/18
1.7.1.1.4 | Engagement Assurance / scrutiny | 0% | 20 days | Thu 18/10/18 | Wed 14/11/18
1.7.1.1.5 | Update Document post scrutiny engagement | 0% | 20 days | Thu 15/11/18 | Wed 12/12/18
1.7.1.1.6 | IAAP Version 2 released | 0% | 0 days | Wed 12/12/18 | Wed 12/12/18
1.7.1.2 | Cost model | 3% | 272 days | Thu 15/03/18 | Mon 15/04/19
1.7.1.2.1 | SRA Available | 0% | 0 days | Fri 07/09/18 | Fri 07/09/18
1.7.1.2.2 | 3OAs Available | 0% | 0 days | Thu 21/06/18 | Thu 21/06/18
1.7.1.2.3 | Accounting Treatments & FOREX confirmed with Defence Economics | 0% | 0 days | Thu 02/08/18 | Thu 02/08/18
1.7.1.2.4 | Support to developing RN5 evidence | 0% | 70 days | Fri 13/07/18 | Fri 19/10/18
1.7.1.2.5 | Briefing (including compiling briefing packs) | 0% | 70 days | Fri 13/07/18 | Fri 19/10/18
1.7.1.2.6 | Update to Cost Model | 0% | 60 days | Fri 13/07/18 | Fri 05/10/18
1.2.1.18.11 | Evaluate LSC Logistic Support Affordability | 0% | 30 days | Mon 02/07/18 | Fri 10/08/18
1.2.2.1.2 | Input to RN5 for LSC Transition activity | 0% | 0 days | Thu 02/08/18 | Thu 02/08/18
1.7.1.2.9 | Finalise Cost Model for RN5 | 0% | 10 days | Mon 08/10/18 | Fri 19/10/18
1.7.1.2.10 | IA MDAL | 16% | 70 days | Thu 15/03/18 | Tue 26/06/18
1.7.1.2.11 | IA Risk Register | 16% | 70 days | Thu 15/03/18 | Tue 26/06/18
1.7.1.2.12 | Investment Appraisal | 0% | 60 days | Mon 22/10/18 | Mon 21/01/19
1.7.1.2.13 | Review Updated Cost Model with BATCIS TL and Update as required | 0% | 10 days | Tue 22/01/19 | Mon 04/02/19
1.7.1.2.14 | Raise CAAS Work Request Form DP122 | 0% | 1 day | Mon 30/04/18 | Mon 30/04/18
1.7.1.2.15 | PT Engagement With CAAS | 0% | 120 days | Tue 01/05/18 | Thu 18/10/18
1.7.1.2.16 | CAAS Verification | 0% | 15 days | Tue 05/02/19 | Mon 25/02/19
1.7.1.2.17 | CAAS Validation | 0% | 15 days | Tue 26/02/19 | Mon 18/03/19
1.7.1.2.18 | CAAS Independent Cost Estimate (ICE) | 0% | 120 days | Tue 01/05/18 | Thu 18/10/18
1.7.1.2.19 | CAAS Schedule Risk Analysis (SRA) | 0% | 20 days | Tue 05/02/19 | Mon 04/03/19
1.7.1.2.20 | CAAS 3rd Party Assurance | 0% | 120 days | Tue 01/05/18 | Thu 18/10/18
1.7.1.2.21 | CAAS Optimism Bias (OB) | 0% | 5 days | Tue 05/02/19 | Mon 11/02/19
1.7.1.2.22 | CAAS Approvals Team (CAT) Report | 0% | 20 days | Tue 19/03/19 | Mon 15/04/19
1.7.1.3 | Additional Evidence | 0% | 87 days | Mon 13/08/18 | Wed 12/12/18
1.7.1.3.1 | RN5 Strategy Update completed | 0% | 0 days | Fri 16/11/18 | Fri 16/11/18
1.7.1.3.2 | Benefits and RAID Analysis on eMTRC | 0% | 44 days | Mon 13/08/18 | Fri 12/10/18
1.7.1.3.3 | All RN5 Evidence Complete | 0% | 0 days | Wed 12/12/18 | Wed 12/12/18
1.7.2 | Review Note 5 Approval | 0% | 314 days | Thu 29/03/18 | Tue 02/07/19
1.7.2.1 | JROC | 0% | 12 days | Thu 18/10/18 | Fri 02/11/18
1.7.2.1.1 | Prepare for JROC | 0% | 5 days | Thu 18/10/18 | Wed 24/10/18
1.7.2.1.2 | Submit documents to JROC | 0% | 0 days | Wed 24/10/18 | Wed 24/10/18
1.7.2.1.3 | JROC Circulation | 0% | 5 days | Thu 25/10/18 | Wed 31/10/18
1.7.2.1.4 | JROC Meeting | 0% | 1 day | Thu 01/11/18 | Thu 01/11/18
1.7.2.1.5 | Rework following JROC | 0% | 1 day | Fri 02/11/18 | Fri 02/11/18
1.7.2.1.6 | JROC Complete | 0% | 0 days | Fri 02/11/18 | Fri 02/11/18
1.7.2.2 | RN5 | 1% | 202 days | Thu 29/03/18 | Mon 21/01/19
1.7.2.2.1 | LFE Review in Prep for RN5 | 10% | 10 days | Thu 29/03/18 | Fri 13/04/18
1.7.2.2.2 | LFE Report in Prep for RN5 | 0% | 5 days | Mon 16/04/18 | Fri 20/04/18
1.7.2.2.3 | RN5 Approvals Workshop Prep | 1% | 70 days | Thu 29/03/18 | Tue 10/07/18
1.7.2.2.4 | RN5 Approvals Workshop | 0% | 2 days | Wed 11/07/18 | Thu 12/07/18
1.7.2.2.5 | RN5 outline Strategy | 0% | 5 days | Wed 01/08/18 | Tue 07/08/18
1.7.2.2.6 | RN5 Skeleton Drafting | 0% | 10 days | Wed 08/08/18 | Tue 21/08/18
1.7.2.2.7 | BATCIS Review RN5 Skeleton | 0% | 5 days | Wed 22/08/18 | Wed 29/08/18
1.7.2.2.8 | Update RN5 Skeleton | 0% | 5 days | Thu 30/08/18 | Wed 05/09/18
1.7.2.2.9 | CDIO Review of RN5 Skeleton | 0% | 5 days | Thu 06/09/18 | Wed 12/09/18
1.7.2.2.10 | RN5 Skeleton Endorsed | 0% | 0 days | Wed 12/09/18 | Wed 12/09/18
1.7.2.2.11 | BATCIS / RN5 Approval Plan | 0% | 5 days | Thu 13/09/18 | Wed 19/09/18
1.7.2.2.12 | RN5 drafting | 0% | 20 days | Thu 20/09/18 | Wed 17/10/18
1.7.2.2.13 | RN5 FAQ Drafting | 0% | 20 days | Thu 20/09/18 | Wed 17/10/18
1.7.2.2.14 | BATCIS Joint Review | 0% | 5 days | Thu 18/10/18 | Wed 24/10/18
1.7.2.2.15 | RN5 Update | 0% | 5 days | Thu 25/10/18 | Wed 31/10/18
1.7.2.2.16 | BATCIS Joint Review | 0% | 3 days | Thu 01/11/18 | Mon 05/11/18
1.7.2.2.17 | RN5 Update Including Complete Evidence | 0% | 5 days | Thu 06/12/18 | Wed 12/12/18
1.7.2.2.18 | Desk Level Review (Including JFC / Army / Scrutiny) | 0% | 5 days | Thu 13/12/18 | Wed 19/12/18
1.7.2.2.19 | RN5 Update | 0% | 3 days | Thu 20/12/18 | Mon 24/12/18
1.7.2.2.20 | RN5 Issued to 1Stars | 0% | 0 days | Mon 24/12/18 | Mon 24/12/18
1.7.2.2.21 | RN5 1* Sign Off | 0% | 5 days | Wed 02/01/19 | Tue 08/01/19
1.7.2.2.22 | RN5 Post Sign Off Update | 0% | 2 days | Wed 09/01/19 | Thu 10/01/19
1.7.2.2.23 | RN5 Issued to CDIO / SRO | 0% | 0 days | Thu 10/01/19 | Thu 10/01/19
1.7.2.2.24 | RN5 CDIO / SRO Sign Off | 0% | 5 days | Fri 11/01/19 | Thu 17/01/19
1.7.2.2.25 | RN5 Update | 0% | 2 days | Fri 18/01/19 | Mon 21/01/19
1.7.2.2.26 | RN5 Endorsed | 0% | 0 days | Mon 21/01/19 | Mon 21/01/19
1.7.2.3 | ARB Assurance - To be aligned to Evidence Time lines | 0% | 66 days | Tue 30/10/18 | Wed 06/02/19
1.7.2.3.1 | Independent SME assurance reports | 0% | 40 days | Tue 30/10/18 | Mon 24/12/18
1.7.2.3.2 | Independent SME Assurance Reports Complete | 0% | 0 days | Mon 24/12/18 | Mon 24/12/18
1.7.2.3.3 | Financial Assurance | 0% | 40 days | Tue 30/10/18 | Mon 24/12/18
1.7.2.3.4 | Financial Assurance Complete | 0% | 0 days | Mon 24/12/18 | Mon 24/12/18
1.7.2.3.5 | Commercial Assurance | 0% | 40 days | Tue 30/10/18 | Mon 24/12/18
1.7.2.3.6 | Commercial Assurance Complete | 0% | 0 days | Mon 24/12/18 | Mon 24/12/18
1.7.2.3.7 | ISS Delivery Assurance (a-j) | 0% | 40 days | Tue 30/10/18 | Mon 24/12/18
1.7.2.3.8 | ISS Delivery Assurance (a-j) Complete | 0% | 0 days | Mon 24/12/18 | Mon 24/12/18
1.7.2.3.9 | ISS Self Assurance Report | 0% | 2 days | Wed 02/01/19 | Thu 03/01/19
1.7.2.3.10 | ISS Self Assurance Report Complete | 0% | 0 days | Thu 03/01/19 | Thu 03/01/19
1.7.2.3.11 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Tue 06/11/18 | Tue 06/11/18
1.7.2.3.12 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Wed 21/11/18 | Wed 21/11/18
1.7.2.3.13 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Thu 20/12/18 | Thu 20/12/18
1.7.2.3.14 | ISS ARB Circulation Prep & RN5 Update | 0% | 1 day | Tue 22/01/19 | Tue 22/01/19
1.7.2.3.15 | RN5 ARB Submission | 0% | 0 days | Tue 22/01/19 | Tue 22/01/19
1.7.2.3.16 | ISS ARB Circulation | 0% | 5 days | Wed 23/01/19 | Tue 29/01/19
1.7.2.3.17 | ISS ARB Meeting | 0% | 1 day | Wed 30/01/19 | Wed 30/01/19
1.7.2.3.18 | ISS ARB Complete | 0% | 0 days | Wed 30/01/19 | Wed 30/01/19
1.2.1.21 | RN5 Input finalised | 0% | 0 days | Fri 01/02/19 | Fri 01/02/19
1.7.2.3.20 | RN5 Rework | 0% | 5 days | Thu 31/01/19 | Wed 06/02/19
1.7.2.3.21 | ISS ARB Endorsement | 0% | 0 days | Wed 06/02/19 | Wed 06/02/19
1.7.2.4 | DP&AS Draft-circulation | 0% | 20 days | Wed 06/02/19 | Wed 06/03/19
1.7.2.4.1 | Draft Scrutiny report | 0% | 0 days | Wed 06/02/19 | Wed 06/02/19
1.7.2.4.2 | Review and Address Scrutiny Report Comments | 0% | 18 days | Thu 07/02/19 | Mon 04/03/19
1.7.2.4.3 | RN5 Documents sent to DP&AS | 0% | 0 days | Wed 06/02/19 | Wed 06/02/19
1.7.2.4.4 | DP&AS Collate the Submission | 0% | 4 days | Thu 07/02/19 | Tue 12/02/19
1.7.2.4.5 | Draft Circulation (1 and 2 Star ) | 0% | 10 days | Wed 13/02/19 | Tue 26/02/19
1.7.2.4.6 | Draft Comments collated by DP&AS | 0% | 1 day | Wed 27/02/19 | Wed 27/02/19
1.7.2.4.7 | Rework of RN5 following comments | 0% | 5 days | Thu 28/02/19 | Wed 06/03/19
1.7.2.4.8 | Draft RN5 Circulation Complete | 0% | 0 days | Wed 06/03/19 | Wed 06/03/19
1.7.2.5 | JFC 2 Star Circulation & CDIO Decision Conference | 0% | 86 days | Thu 08/11/18 | Fri 15/03/19
1.7.2.5.1 | JFC RN5 Update Briefs (desk level) | 0% | 1 day | Thu 08/11/18 | Thu 08/11/18
1.7.2.5.2 | JFC RN5 Update Briefs (desk level) | 0% | 1 day | Fri 07/12/18 | Fri 07/12/18
1.7.2.5.3 | JFC RN5 Update Briefs (desk level) | 0% | 1 day | Tue 15/01/19 | Tue 15/01/19
1.7.2.5.4 | JFC RN5 Update Briefs (desk level) | 0% | 1 day | Wed 13/02/19 | Wed 13/02/19
1.7.2.5.5 | RN5 Documents sent to JFC 2 Stars | 0% | 0 days | Wed 13/02/19 | Wed 13/02/19
1.7.2.5.6 | JFC 2 Star & CDIO Circulation | 0% | 4 days | Thu 07/03/19 | Tue 12/03/19
1.7.2.5.7 | CDIO (JFC AHQ) Decision Conference | 0% | 1 day | Wed 13/03/19 | Wed 13/03/19
1.7.2.5.8 | RN5 Rework | 0% | 2 days | Thu 14/03/19 | Fri 15/03/19
1.7.2.5.9 | JFC 2 Star & CDIO Endorsement | 0% | 0 days | Fri 15/03/19 | Fri 15/03/19
1.7.2.6 | IAC | 0% | 32 days | Fri 15/03/19 | Thu 02/05/19
1.7.2.6.1 | Final Scrutiny Report | 0% | 0 days | Mon 15/04/19 | Mon 15/04/19
1.7.2.6.2 | Review and Address Scrutiny Report Comments | 0% | 10 days | Tue 16/04/19 | Wed 01/05/19
1.7.2.6.3 | RN5 Submitted to DPAS | 0% | 0 days | Fri 15/03/19 | Fri 15/03/19
1.7.2.6.4 | DP&AS Collate Final IAC Submission | 0% | 4 days | Mon 18/03/19 | Thu 21/03/19
1.7.2.6.5 | IAC Circulation | 0% | 10 days | Fri 22/03/19 | Thu 04/04/19
1.7.2.6.6 | IAC Meeting | 0% | 1 day | Thu 02/05/19 | Thu 02/05/19
1.7.2.6.7 | IAC Endorsement | 0% | 0 days | Thu 02/05/19 | Thu 02/05/19
1.7.2.7 | Ministerial / Treasury Circulation | 0% | 41 days | Fri 03/05/19 | Tue 02/07/19
1.7.2.7.1 | DP&AS Preparation | 0% | 3 days | Fri 03/05/19 | Wed 08/05/19
1.7.2.7.2 | Ministerial Review | 0% | 15 days | Thu 09/05/19 | Thu 30/05/19
1.7.2.7.3 | CST (Treasury Review) | 0% | 15 days | Fri 31/05/19 | Thu 20/06/19
1.7.2.7.4 | Cabinet Office Review | 0% | 5 days | Fri 21/06/19 | Thu 27/06/19
1.7.2.7.5 | DP&AS Out letter Preparation | 0% | 3 days | Fri 28/06/19 | Tue 02/07/19
1.7.2.7.6 | Ministerial Approval / Out letter - RN5 | 0% | 0 days | Tue 02/07/19 | Tue 02/07/19
1.8 | Information Note 2019 | 0% | 175 days | Thu 24/01/19 | Wed 02/10/19
1.8.1 | Evidence Generation | 0% | 77 days | Thu 24/01/19 | Wed 15/05/19
1.8.1.1 | Collate evidence for Information Note 2019 | 0% | 77 days | Thu 24/01/19 | Wed 15/05/19
1.8.2 | Information Note 2019 Drafting | 0% | 90 days | Wed 03/04/19 | Mon 12/08/19
1.8.2.1 | IN outline Scope & Strategy | 0% | 4 days | Wed 03/04/19 | Mon 08/04/19
1.8.2.2 | IN Drafting | 0% | 5 days | Thu 16/05/19 | Wed 22/05/19
1.8.2.3 | BATCIS Review of IN | 0% | 5 days | Thu 23/05/19 | Thu 30/05/19
1.8.2.4 | Update IN following BATCIS Review | 0% | 5 days | Fri 31/05/19 | Thu 06/06/19
1.8.2.5 | CDIO Review of IN | 0% | 5 days | Fri 07/06/19 | Thu 13/06/19
1.8.2.6 | IN Develop Mature | 0% | 10 days | Fri 14/06/19 | Thu 27/06/19
1.8.2.7 | IN FAQ Drafting | 0% | 8 days | Fri 14/06/19 | Tue 25/06/19
1.8.2.8 | BATCIS Joint Review | 0% | 3 days | Fri 28/06/19 | Tue 02/07/19
1.8.2.9 | IN Update | 0% | 3 days | Wed 03/07/19 | Fri 05/07/19
1.8.2.10 | Desk Level Review (Including JFC / ARMY) | 0% | 9 days | Mon 08/07/19 | Thu 18/07/19
1.8.2.11 | IN Update | 0% | 3 days | Fri 19/07/19 | Tue 23/07/19
1.8.2.12 | IN 2019 Issued to 1Stars | 0% | 0 days | Tue 23/07/19 | Tue 23/07/19
1.8.2.13 | IN 1* Sign Off (Including JFC / ARMY) | 0% | 5 days | Wed 24/07/19 | Tue 30/07/19
1.8.2.14 | IN Update | 0% | 2 days | Wed 31/07/19 | Thu 01/08/19
1.8.2.15 | IN 2019 Issued to CDIO / SRO | 0% | 0 days | Thu 01/08/19 | Thu 01/08/19
1.8.2.16 | IN CDIO / SRO Sign Off | 0% | 5 days | Fri 02/08/19 | Thu 08/08/19
1.8.2.17 | IN Update | 0% | 2 days | Fri 09/08/19 | Mon 12/08/19
1.8.2.18 | IN 2019 Endorsed | 0% | 0 days | Mon 12/08/19 | Mon 12/08/19
1.8.3 | DP&AS IAC Circulation | 0% | 16 days | Tue 13/08/19 | Wed 04/09/19
1.8.3.1 | IN Documents sent to DP&AS | 0% | 1 day | Tue 13/08/19 | Tue 13/08/19
1.8.3.2 | DP&AS IAC Covering Letter | 0% | 2 days | Wed 14/08/19 | Thu 15/08/19
1.8.3.3 | I Note IAC Circulation (Out of Committee) | 0% | 10 days | Fri 16/08/19 | Fri 30/08/19
1.8.3.4 | DP&AS I Note Summary Feed Back to Morpheus Team | 0% | 3 days | Mon 02/09/19 | Wed 04/09/19
1.8.3.5 | I Note 2019 Approved | 0% | 0 days | Wed 04/09/19 | Wed 04/09/19
1.8.4 | Ministerial / Treasury Circulation | 0% | 20 days | Thu 05/09/19 | Wed 02/10/19
1.8.4.1 | Ministerial Review | 0% | 10 days | Thu 05/09/19 | Wed 18/09/19
1.8.4.2 | CST (Treasury Review) | 0% | 10 days | Thu 19/09/19 | Wed 02/10/19
1.8.4.3 | Ministerial Approval / Out letter - IN2019 | 0% | 0 days | Wed 02/10/19 | Wed 02/10/19
1.9 | Main Gate Business Case | 0% | 323 days | Tue 31/03/20 | Fri 16/07/21
1.9.1 | Evidence Generation | 0% | 230 days | Tue 31/03/20 | Wed 03/03/21
1.9.1.1 | IAAP | 0% | 141 days | Wed 01/04/20 | Wed 21/10/20
1.9.1.1.1 | Phase 2 IAAP Meeting | 0% | 1 day | Wed 01/04/20 | Wed 01/04/20
1.9.1.1.2 | Update existing IAAP | 0% | 60 days | Thu 02/04/20 | Tue 30/06/20
1.9.1.1.3 | Review updated IAAP | 0% | 20 days | Wed 01/07/20 | Tue 28/07/20
1.9.1.1.4 | Engagement Assurance / scrutiny | 0% | 40 days | Wed 29/07/20 | Wed 23/09/20
1.9.1.1.5 | Update Document post scrutiny engagement | 0% | 20 days | Thu 24/09/20 | Wed 21/10/20
1.9.1.1.6 | IAAP Version 2 released | 0% | 0 days | Wed 21/10/20 | Wed 21/10/20
1.9.1.2 | Cost model | 0% | 230 days | Tue 31/03/20 | Wed 03/03/21
1.9.1.2.1 | SRA Available | 0% | 0 days | Mon 13/07/20 | Mon 13/07/20
1.9.1.2.2 | 3OA's Available | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.9.1.2.3 | Accounting Treatments & FOREX confirmed with Defence Economics | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.9.1.2.4 | Support to developing Main Gate evidence | 0% | 60 days | Wed 01/04/20 | Mon 29/06/20
1.9.1.2.5 | Briefing (including compiling briefing packs) | 0% | 60 days | Wed 01/04/20 | Mon 29/06/20
1.9.1.2.6 | Update to Cost Model | 0% | 60 days | Wed 01/04/20 | Mon 29/06/20
1.9.1.2.7 | Finalise Cost Model for MGBC | 0% | 60 days | Tue 14/07/20 | Tue 06/10/20
1.9.1.2.8 | IA MDAL | 0% | 60 days | Wed 01/04/20 | Mon 29/06/20
1.9.1.2.9 | IA Risk Register | 0% | 60 days | Wed 01/04/20 | Mon 29/06/20
1.9.1.2.10 | Investment Appraisal | 0% | 40 days | Wed 07/10/20 | Tue 01/12/20
1.9.1.2.11 | Review Updated Cost Model with BATCIS TL and Update as required | 0% | 10 days | Wed 02/12/20 | Tue 15/12/20
1.9.1.2.12 | Raise CAAS Work Request Form DP122 | 0% | 1 day | Wed 01/04/20 | Wed 01/04/20
1.9.1.2.13 | PT Engagement With CAAS | 0% | 150 days | Thu 02/04/20 | Wed 04/11/20
1.9.1.2.14 | CAAS Verification | 0% | 15 days | Wed 16/12/20 | Wed 13/01/21
1.9.1.2.15 | CAAS Validation | 0% | 15 days | Thu 14/01/21 | Wed 03/02/21
1.9.1.2.16 | CAAS Independent Cost Estimate (ICE) | 0% | 150 days | Thu 02/04/20 | Wed 04/11/20
1.9.1.2.17 | CAAS Schedule Risk Analysis (SRA) | 0% | 20 days | Wed 16/12/20 | Wed 20/01/21
1.9.1.2.18 | CAAS 3rd Party Assurance | 0% | 150 days | Thu 02/04/20 | Wed 04/11/20
1.9.1.2.19 | CAAS Optimism Bias (OB) | 0% | 5 days | Wed 16/12/20 | Tue 22/12/20
1.9.1.2.20 | CAAS Approvals Team (CAT) Report | 0% | 20 days | Thu 04/02/21 | Wed 03/03/21
1.9.1.3 | Additional Evidence | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.9.1.3.1 | All MGBC Evidence Complete | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.9.2 | Main Gate Business Case Approval | 0% | 323 days | Wed 01/04/20 | Fri 16/07/21
1.9.2.1 | JROC | 0% | 12 days | Mon 04/01/21 | Tue 19/01/21
1.9.2.1.1 | Prepare for JROC | 0% | 5 days | Mon 04/01/21 | Fri 08/01/21
1.9.2.1.2 | Submit documents to JROC | 0% | 0 days | Fri 08/01/21 | Fri 08/01/21
1.9.2.1.3 | JROC Circulation | 0% | 5 days | Mon 11/01/21 | Fri 15/01/21
1.9.2.1.4 | JROC Meeting | 0% | 1 day | Mon 18/01/21 | Mon 18/01/21
1.9.2.1.5 | Rework following JROC | 0% | 1 day | Tue 19/01/21 | Tue 19/01/21
1.9.2.1.6 | JROC Complete | 0% | 0 days | Tue 19/01/21 | Tue 19/01/21
1.9.2.2 | MGBC | 0% | 214 days | Wed 01/04/20 | Tue 09/02/21
1.9.2.2.1 | LFE from RN4 Analysed | 0% | 10 days | Wed 01/04/20 | Thu 16/04/20
1.9.2.2.2 | RN4 LFE Report | 0% | 5 days | Fri 17/04/20 | Thu 23/04/20
1.9.2.2.3 | MGBC Approvals Workshop Prep | 0% | 20 days | Wed 01/04/20 | Thu 30/04/20
1.9.2.2.4 | MGBC Approvals Workshop | 0% | 2 days | Fri 01/05/20 | Tue 05/05/20
1.9.2.2.5 | MGBC outline Strategy | 0% | 5 days | Tue 26/05/20 | Mon 01/06/20
1.9.2.2.6 | MGBC Skeleton Drafting | 0% | 10 days | Tue 02/06/20 | Mon 15/06/20
1.9.2.2.7 | BATCIS Review MGBC Skeleton | 0% | 5 days | Tue 16/06/20 | Mon 22/06/20
1.9.2.2.8 | Update MGBC Skeleton | 0% | 5 days | Tue 23/06/20 | Mon 29/06/20
1.9.2.2.9 | CDIO Review of MGBC Skeleton | 0% | 5 days | Tue 30/06/20 | Mon 06/07/20
1.9.2.2.10 | MGBC Skeleton Endorsed | 0% | 0 days | Mon 06/07/20 | Mon 06/07/20
1.9.2.2.11 | BATCIS / MGBC Approval Plan | 0% | 5 days | Tue 07/07/20 | Mon 13/07/20
1.9.2.2.12 | MGBC drafting | 0% | 20 days | Tue 14/07/20 | Mon 10/08/20
1.9.2.2.13 | MGBC FAQ Drafting | 0% | 20 days | Tue 14/07/20 | Mon 10/08/20
1.9.2.2.14 | BATCIS Joint Review | 0% | 5 days | Tue 11/08/20 | Mon 17/08/20
1.9.2.2.15 | MGBC Update | 0% | 5 days | Tue 18/08/20 | Mon 24/08/20
1.9.2.2.16 | BATCIS Joint Review | 0% | 3 days | Tue 25/08/20 | Thu 27/08/20
1.9.2.2.17 | MGBC Update Including Complete Evidence | 0% | 5 days | Mon 04/01/21 | Fri 08/01/21
1.9.2.2.18 | Desk Level Review (Including JFC / Army / Scrutiny) | 0% | 5 days | Mon 11/01/21 | Fri 15/01/21
1.9.2.2.19 | MGBC Update | 0% | 3 days | Mon 18/01/21 | Wed 20/01/21
1.9.2.2.20 | MGBC Issued to 1Stars | 0% | 0 days | Wed 20/01/21 | Wed 20/01/21
1.9.2.2.21 | MGBC 1* Sign Off | 0% | 5 days | Thu 21/01/21 | Wed 27/01/21
1.9.2.2.22 | MGBC Post Sign Off Update | 0% | 2 days | Thu 28/01/21 | Fri 29/01/21
1.9.2.2.23 | MGBC Issued to CDIO / SRO | 0% | 0 days | Fri 29/01/21 | Fri 29/01/21
1.9.2.2.24 | MGBC CDIO / SRO Sign Off | 0% | 5 days | Mon 01/02/21 | Fri 05/02/21
1.9.2.2.25 | MGBC Update | 0% | 2 days | Mon 08/02/21 | Tue 09/02/21
1.9.2.2.26 | MGBC Endorsed | 0% | 0 days | Tue 09/02/21 | Tue 09/02/21
1.9.2.3 | ARB Assurance - To be aligned to Evidence Time lines | 0% | 109 days | Thu 08/10/20 | Wed 17/03/21
1.9.2.3.1 | Independent SME assurance reports | 0% | 69 days | Thu 08/10/20 | Wed 20/01/21
1.9.2.3.2 | Independent SME Assurance Reports Complete | 0% | 0 days | Wed 20/01/21 | Wed 20/01/21
1.9.2.3.3 | Financial Assurance | 0% | 69 days | Thu 08/10/20 | Wed 20/01/21
1.9.2.3.4 | Financial Assurance Complete | 0% | 0 days | Wed 20/01/21 | Wed 20/01/21
1.9.2.3.5 | Commercial Assurance | 0% | 69 days | Thu 08/10/20 | Wed 20/01/21
1.9.2.3.6 | Commercial Assurance Complete | 0% | 0 days | Wed 20/01/21 | Wed 20/01/21
1.9.2.3.7 | ISS Delivery Assurance (a-j) | 0% | 69 days | Thu 08/10/20 | Wed 20/01/21
1.9.2.3.8 | ISS Delivery Assurance (a-j) Complete | 0% | 0 days | Wed 20/01/21 | Wed 20/01/21
1.9.2.3.9 | ISS Self Assurance Report | 0% | 2 days | Thu 21/01/21 | Fri 22/01/21
1.9.2.3.10 | ISS Self Assurance Report Complete | 0% | 0 days | Fri 22/01/21 | Fri 22/01/21
1.9.2.3.11 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Tue 24/11/20 | Tue 24/11/20
1.9.2.3.12 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Wed 23/12/20 | Wed 23/12/20
1.9.2.3.13 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Fri 29/01/21 | Fri 29/01/21
1.9.2.3.14 | ARB Assurance Review Meeting (desk level) | 0% | 1 day | Mon 01/03/21 | Mon 01/03/21
1.9.2.3.15 | ISS ARB Circulation Prep & MGBC Update | 0% | 1 day | Tue 02/03/21 | Tue 02/03/21
1.9.2.3.16 | MGBC ARB Submission | 0% | 0 days | Tue 02/03/21 | Tue 02/03/21
1.9.2.3.17 | ISS ARB Circulation | 0% | 5 days | Wed 03/03/21 | Tue 09/03/21
1.9.2.3.18 | ISS ARB Meeting | 0% | 1 day | Wed 10/03/21 | Wed 10/03/21
1.9.2.3.19 | ISS ARB Complete | 0% | 0 days | Wed 10/03/21 | Wed 10/03/21
1.9.2.3.20 | MGBC Rework | 0% | 5 days | Thu 11/03/21 | Wed 17/03/21
1.9.2.3.21 | ISS ARB Endorsement | 0% | 0 days | Wed 17/03/21 | Wed 17/03/21
1.9.2.4 | DP&AS Draft-circulation | 0% | 20 days | Wed 17/03/21 | Fri 16/04/21
1.9.2.4.1 | Draft Scrutiny report | 0% | 0 days | Wed 17/03/21 | Wed 17/03/21
1.9.2.4.2 | Review and Address Scrutiny Report Comments | 0% | 18 days | Thu 18/03/21 | Wed 14/04/21
1.9.2.4.3 | MGBC Documents sent to DP&AS | 0% | 0 days | Wed 17/03/21 | Wed 17/03/21
1.9.2.4.4 | DP&AS Collate Draft Submission | 0% | 4 days | Thu 18/03/21 | Tue 23/03/21
1.9.2.4.5 | Draft Circulation (1 and 2 Star ) | 0% | 10 days | Wed 24/03/21 | Thu 08/04/21
1.9.2.4.6 | Draft Comments collated by DP&AS | 0% | 1 day | Fri 09/04/21 | Fri 09/04/21
1.9.2.4.7 | Rework of MGBC following comments | 0% | 5 days | Mon 12/04/21 | Fri 16/04/21
1.9.2.4.8 | Draft MGBC Circulation Complete | 0% | 0 days | Fri 16/04/21 | Fri 16/04/21
1.9.2.5 | JFC 2 Star Circulation & CDIO Decision Conference | 0% | 101 days | Thu 26/11/20 | Tue 27/04/21
1.9.2.5.1 | JFC MGBC Update Briefs (desk level) | 0% | 1 day | Thu 26/11/20 | Thu 26/11/20
1.9.2.5.2 | JFC MGBC Update Briefs (desk level) | 0% | 1 day | Mon 04/01/21 | Mon 04/01/21
1.9.2.5.3 | JFC MGBC Update Briefs (desk level) | 0% | 1 day | Tue 02/02/21 | Tue 02/02/21
1.9.2.5.4 | JFC MGBC Update Briefs (desk level) | 0% | 1 day | Wed 03/03/21 | Wed 03/03/21
1.9.2.5.5 | MGBC Documents sent to JFC 2 Stars | 0% | 0 days | Wed 03/03/21 | Wed 03/03/21
1.9.2.5.6 | JFC 2 Star & CDIO Circulation | 0% | 4 days | Mon 19/04/21 | Thu 22/04/21
1.9.2.5.7 | CDIO (JFC AHQ) Decision Conference | 0% | 1 day | Fri 23/04/21 | Fri 23/04/21
1.9.2.5.8 | MGBC Rework | 0% | 2 days | Mon 26/04/21 | Tue 27/04/21
1.9.2.5.9 | JFC 2 Star & CDIO Endorsement | 0% | 0 days | Tue 27/04/21 | Tue 27/04/21
1.9.2.6 | IAC | 0% | 15 days | Tue 27/04/21 | Wed 19/05/21
1.9.2.6.1 | Final Scrutiny Report | 0% | 0 days | Tue 27/04/21 | Tue 27/04/21
1.9.2.6.2 | Review and Address Scrutiny Report Comments | 0% | 10 days | Wed 28/04/21 | Wed 12/05/21
1.9.2.6.3 | MGBC Submitted to DPAS | 0% | 0 days | Tue 27/04/21 | Tue 27/04/21
1.9.2.6.4 | DP&AS Collate Final IAC Submission | 0% | 4 days | Wed 28/04/21 | Tue 04/05/21
1.9.2.6.5 | IAC Circulation | 0% | 10 days | Wed 05/05/21 | Tue 18/05/21
1.9.2.6.6 | IAC Meeting | 0% | 1 day | Wed 19/05/21 | Wed 19/05/21
1.9.2.6.7 | IAC Endorsement | 0% | 0 days | Wed 19/05/21 | Wed 19/05/21
1.9.2.7 | Ministerial / Treasury Circulation | 0% | 41 days | Thu 20/05/21 | Fri 16/07/21
1.9.2.7.1 | DP&AS Preparation | 0% | 3 days | Thu 20/05/21 | Mon 24/05/21
1.9.2.7.2 | Ministerial Review | 0% | 15 days | Tue 25/05/21 | Tue 15/06/21
1.9.2.7.3 | CST (Treasury Review) | 0% | 15 days | Wed 16/06/21 | Tue 06/07/21
1.9.2.7.4 | Cabinet Office Review | 0% | 5 days | Wed 07/07/21 | Tue 13/07/21
1.9.2.7.5 | DP&AS Out letter Preparation | 0% | 3 days | Wed 14/07/21 | Fri 16/07/21
1.9.2.7.6 | Ministerial Approval / Out letter - MGBC | 0% | 0 days | Fri 16/07/21 | Fri 16/07/21
1.1 | Temporary JPO Facility | 27% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.10.1 | Temporary JPO Facility | 31% | 863 days | Mon 06/03/17 | Fri 14/08/20
1.10.1.1 | JPO TP Temporary | 100% | 20 days | Mon 06/03/17 | Fri 31/03/17
1.10.1.2 | JPO TP Interim Operational | 100% | 0 days | Fri 31/03/17 | Fri 31/03/17
1.10.1.3 | JPO TP Interim | 100% | 125 days | Mon 03/04/17 | Fri 29/09/17
1.10.1.4 | JPO Facility (TP Final) Operational ** | 100% | 0 days | Fri 29/09/17 | Fri 29/09/17
1.10.1.5 | JPO TP Final | 17% | 718 days | Mon 02/10/17 | Fri 14/08/20
1.10.1.6 | End of GD Lease on JPO TP Final | 0% | 0 days | Fri 14/08/20 | Fri 14/08/20
1.10.2 | JPO - Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1 | TP Project Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.1 | JPO TP Management - BAU | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2 | Programme & Engineering | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.1 | JPO Project Controls | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.2 | JPO Management Reporting (Monthly) | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.3 | JPO Prepare for and Participate in the Integrated Baseline Review | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.4 | JPO Preparation for Assurance Reviews | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.5 | JPO Management of MOD Deliverables to GD | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.6 | JPO Management of GD Deliverables to MOD | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.7 | JPO GFX Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.8 | JPO TP Deliverable Management Process | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.9 | JPO MPPS Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.10 | JPO Conductor Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.11 | JPO Manage Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.12 | JPO EC3 (AJAX) Management | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.10.2.1.2.13 | JPO Enabling Business Transformation | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.11 | Enduring JPO Facility | 14% | 2173 days | Thu 16/03/17 | Thu 20/11/25
1.11.1 | Enduring JPO Facility Competition - DIO | 14% | 2173 days | Thu 16/03/17 | Thu 20/11/25
1.11.1.1 | Produce and Agree Statement of Need | 100% | 47 days | Thu 16/03/17 | Wed 24/05/17
1.11.1.2 | Produce Rough order of Costs | 72% | 297 days | Thu 25/05/17 | Tue 31/07/18
1.11.1.3 | SON and ROC Produced | 0% | 0 days | Tue 31/07/18 | Tue 31/07/18
1.11.1.4 | Produce JPO Letter of Intent and submit to DIO | 0% | 5 days | Wed 01/08/18 | Tue 07/08/18
1.11.1.5 | JPO Strategic Asset Planning Team (SAPT) Programme review | 0% | 40 days | Wed 08/08/18 | Wed 03/10/18
1.11.1.6 | DIO Endorse JPO SON | 0% | 20 days | Thu 04/10/18 | Wed 31/10/18
1.11.1.7 | JPO Capital Project Created | 0% | 0 days | Wed 31/10/18 | Wed 31/10/18
1.11.1.8 | Develop and Submit JPO URD | 100% | 64 days | Thu 25/05/17 | Wed 23/08/17
1.11.1.9 | JPO URD Submitted to DIO | 100% | 0 days | Wed 23/08/17 | Wed 23/08/17
1.11.1.10 | PPD JPO Produce Initial Planning Estimate (IPE) | 0% | 20 days | Thu 01/11/18 | Wed 28/11/18
1.11.1.11 | DIO SAPT Approve JPO IPE | 0% | 5 days | Thu 29/11/18 | Wed 05/12/18
1.11.1.12 | Approved JPO IPE | 0% | 0 days | Wed 05/12/18 | Wed 05/12/18
1.11.1.13 | BATCIS Transfer Funding for JPO Assessment Studies | 0% | 0 days | Wed 05/12/18 | Wed 05/12/18
1.11.1.14 | DIO Draft JPO Preliminary Business Case (PBC) | 0% | 60 days | Thu 06/12/18 | Thu 07/03/19
1.11.1.15 | JPO Preliminary Business Produced | 0% | 0 days | Thu 07/03/19 | Thu 07/03/19
1.11.1.16 | DIO Perform JPO Assessment Studies | 0% | 120 days | Fri 08/03/19 | Thu 29/08/19
1.11.1.17 | JPO Assessment Studies Completed | 0% | 0 days | Thu 29/08/19 | Thu 29/08/19
1.11.1.18 | Execute DIO JPO Initial Gate Business Case Process | 0% | 80 days | Fri 30/08/19 | Thu 19/12/19
1.11.1.19 | DIO JPO IGBC Approved | 0% | 0 days | Thu 19/12/19 | Thu 19/12/19
1.11.1.20 | BATCIS Secure and Transfer Funding for JPO Build Phase | 0% | 0 days | Thu 19/12/19 | Thu 19/12/19
1.11.1.21 | DIO Develop Preferred JPO Option | 0% | 100 days | Fri 20/12/19 | Wed 20/05/20
1.11.1.22 | DIO Prepare JPO Tender Documents | 0% | 20 days | Thu 21/05/20 | Thu 18/06/20
1.11.1.23 | JPO ITT Issued | 0% | 0 days | Thu 18/06/20 | Thu 18/06/20
1.11.1.24 | Tender Process up to JPO Contract Award | 0% | 120 days | Fri 19/06/20 | Fri 04/12/20
1.11.1.25 | EJPO Defence Cyber Protection Partnership (DCPP) Risk Assessment | 0% | 1 day | Mon 07/12/20 | Mon 07/12/20
1.11.1.26 | JPO Facility Contract Award | 0% | 0 days | Mon 07/12/20 | Mon 07/12/20
1.11.1.27 | Set Up JPO Facility | 0% | 238 days | Tue 08/12/20 | Fri 19/11/21
1.11.1.28 | eJPO Facility Ready | 0% | 0 days | Fri 19/11/21 | Fri 19/11/21
1.11.1.29 | eJPO Operational | 0% | 1000 days | Mon 22/11/21 | Thu 20/11/25
1.11.1.29.1 | Enduring JPO Operating | 0% | 1000 days | Mon 22/11/21 | Thu 20/11/25
1.12 | Interim MTRC | 47% | 963 days | Mon 06/03/17 | Tue 12/01/21
1.12.1 | Dependencies from GD to BATCIS | 0% | 861 days | Fri 16/06/17 | Thu 19/11/20
1.12.1.1 | GD Supply Initial version of MTRC LDD | 100% | 0 days | Fri 16/06/17 | Fri 16/06/17
1.12.1.2 | GD Supply Baseline version of MTRC LDD | 100% | 0 days | Thu 02/11/17 | Thu 02/11/17
1.12.1.3 | GD Supply first set of equipment (Mix of PPMs and QTMs) and functional software to iMTRC | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.12.1.4 | GD Supply additional 6 Platforms worth of kit (Mix of PPMs and QTMs) and functional software to iMTRC - Total now 7 | 0% | 0 days | Thu 25/04/19 | Thu 25/04/19
1.12.1.5 | Start Date for GD Supporting Installation of iMTRC Equipment | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.12.1.6 | GD Supply Operator and Maintainer Manuals for their Equipment | 0% | 0 days | Mon 29/10/18 | Mon 29/10/18
1.12.1.7 | GD Supply 30 QTMs of TMR 304s | 0% | 0 days | Thu 04/10/18 | Thu 04/10/18
1.12.1.8 | GD Supply 54 QTMs of TCS 300s | 0% | 0 days | Mon 14/01/19 | Mon 14/01/19
1.12.1.9 | GD Supply 9 QTMs of VPUs | 0% | 0 days | Mon 13/01/20 | Mon 13/01/20
1.12.1.10 | GD Supply 25 QTMs of TLAs | 0% | 0 days | Thu 13/06/19 | Thu 13/06/19
1.12.1.11 | GD Supply 9 QTMs of TMR 314s | 0% | 0 days | Tue 13/08/19 | Tue 13/08/19
1.12.1.12 | GD Supply 9 QTMs of SADD's | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.12.1.13 | GD Complete Delivery of final 10 Platforms worth of kit (QTMs) and functional software to iMTRC - 30 in total | 0% | 0 days | Thu 19/11/20 | Thu 19/11/20
1.12.1.14 | GD Supply Final version of MTRC LDD | 0% | 0 days | Thu 30/07/20 | Thu 30/07/20
1.12.2 | Dependencies from BATCIS to LSRC | 100% | 6 days | Thu 30/11/17 | Fri 08/12/17
1.12.2.1 | BATCIS Supply Finalised iMTRC Requirement to LSRC | 100% | 0 days | Thu 30/11/17 | Thu 30/11/17
1.12.2.2 | BATCIS Transfer iMTRC Payments to LSRC | 100% | 0 days | Fri 08/12/17 | Fri 08/12/17
1.12.3 | Dependencies from EnHCDR+ Provider to Conformance Engineers | 0% | 0 days | Tue 16/04/19 | Tue 16/04/19
1.12.3.1 | Completed EnHCDR received from EnHCDR Provider | 0% | 0 days | Tue 16/04/19 | Tue 16/04/19
1.12.4 | Dependencies from Conformance Engineers to GD | 0% | 0 days | Fri 17/05/19 | Fri 17/05/19
1.12.4.1 | Conformance Engineers Supply to GD Completed and Conformance Checked EnHCDR | 0% | 0 days | Fri 17/05/19 | Fri 17/05/19
1.12.5 | Logical Architecture Conformance Competition - FATS5 | 100% | 243 days | Thu 16/03/17 | Tue 06/03/18
1.12.5.1 | Review LFE from Similar Competitions | 100% | 1 day | Thu 16/03/17 | Thu 16/03/17
1.12.5.2 | Complete LAC ISS Front Door Process | 0% | 5 days | Fri 17/03/17 | Thu 23/03/17
1.12.5.3 | Refine LAC SOR | 100% | 10 days | Fri 17/03/17 | Thu 30/03/17
1.12.5.4 | Generate LAC Security Aspects Letter | 100% | 2 days | Fri 31/03/17 | Mon 03/04/17
1.12.5.5 | Produce LAC Procurement Strategy | 100% | 10 days | Tue 04/04/17 | Wed 19/04/17
1.12.5.6 | Produce LAC Commercial Strategy | 100% | 10 days | Tue 04/04/17 | Wed 19/04/17
1.12.5.7 | Produce and Approve LAC RCA | 100% | 50 days | Fri 05/05/17 | Fri 14/07/17
1.12.5.8 | Produce LAC Tasking Form & Evaluation Criteria | 100% | 70 days | Mon 17/07/17 | Mon 23/10/17
1.12.5.9 | Review & Approval of LAC By FATS G&G | 100% | 20 days | Tue 24/10/17 | Mon 20/11/17
1.12.5.10 | Issue LAC Pre Tasking Questionnaire | 0% | 1 day | Tue 21/11/17 | Tue 21/11/17
1.12.5.11 | LAC Pre Tasking Questionnaire Issued | 0% | 0 days | Tue 21/11/17 | Tue 21/11/17
1.12.5.12 | Industry Complete LAC Pre Tasking Questionnaire | 0% | 5 days | Wed 22/11/17 | Tue 28/11/17
1.12.5.13 | LAC Pre Tasking Questionnaire review | 0% | 1 day | Wed 29/11/17 | Wed 29/11/17
1.12.5.14 | Issue LAC ITT / Tasking Form | 100% | 10 days | Tue 21/11/17 | Mon 04/12/17
1.12.5.15 | LAC Defence Cyber Protection Partnership (DCPP) Risk Assessment | 100% | 1 day | Tue 05/12/17 | Tue 05/12/17
1.12.5.16 | LAC ITT/Tasking Form issued | 100% | 0 days | Tue 05/12/17 | Tue 05/12/17
1.12.5.17 | Industry Develop LAC Responses | 100% | 28 days | Wed 06/12/17 | Mon 22/01/18
1.12.5.18 | BATCIS Manage LAC CQs | 100% | 25 days | Wed 06/12/17 | Wed 17/01/18
1.12.5.19 | LAC Tender Responses received | 100% | 0 days | Mon 22/01/18 | Mon 22/01/18
1.12.5.20 | LAC Tenderer Evaluation | 100% | 8 days | Tue 23/01/18 | Thu 01/02/18
1.12.5.21 | Produce LAC Commitment Case / 2 SMS requests | 100% | 5 days | Fri 02/02/18 | Thu 08/02/18
1.12.5.22 | Hold LAC TAP | 100% | 1 day | Fri 09/02/18 | Fri 09/02/18
1.12.5.23 | Prepare & Provide LAC Feedback | 100% | 3 days | Mon 12/02/18 | Wed 14/02/18
1.12.5.24 | Award LAC Contract | 100% | 9 days | Thu 15/02/18 | Tue 27/02/18
1.12.5.25 | LAC Contract Awarded | 100% | 0 days | Tue 27/02/18 | Tue 27/02/18
1.12.5.26 | LAC Contract Mobilisation | 100% | 5 days | Wed 28/02/18 | Tue 06/03/18
1.12.5.27 | LAC Contract Start Date | 100% | 0 days | Tue 06/03/18 | Tue 06/03/18
1.12.6 | Physical Architecture Conformance Competition - FATS5 | 0% | 1 day? | Mon 06/03/17 | Mon 06/03/17
1.12.7 | System and Application Verification Testing Competition - FATS5 | 0% | 1 day | Mon 06/03/17 | Mon 06/03/17
1.12.8 | iMTRC Acquisition | 78% | 545 days | Mon 06/03/17 | Fri 10/05/19
1.12.8.1 | Produce Draft iMTRC Commissioning Plan | 100% | 20 days | Mon 06/03/17 | Fri 31/03/17
1.12.8.2 | Draft iMTRC Commissioning Plan Issued for Comment | 100% | 0 days | Fri 31/03/17 | Fri 31/03/17
1.12.8.3 | Receive Comments and Update Commissioning Plan | 100% | 15 days | Mon 03/04/17 | Tue 25/04/17
1.12.8.4 | iMTRC Commissioning Plan V1 Approved | 100% | 0 days | Tue 25/04/17 | Tue 25/04/17
1.12.8.5 | Maintain iMTRC Commissioning Plan | 100% | 167 days | Wed 26/04/17 | Tue 19/12/17
1.12.8.6 | iMTRC Commissioning and Requirements Plan V2 Approved | 100% | 0 days | Tue 19/12/17 | Tue 19/12/17
1.12.8.7 | iMTRC Infrastructure | 86% | 307 days | Thu 16/03/17 | Fri 08/06/18
1.12.8.7.1 | Ongoing Dialogue with LSRC on iMTRC Requirement | 100% | 80 days | Thu 16/03/17 | Tue 11/07/17
1.12.8.7.2 | Refine iMTRC Requirement | 100% | 60 days | Wed 12/07/17 | Wed 04/10/17
1.12.8.7.3 | Finalise iMTRC Requirement | 100% | 20 days | Fri 03/11/17 | Thu 30/11/17
1.12.8.7.4 | Detailed design and agree SLA with LSRC Facility Operator | 99% | 80 days | Fri 01/12/17 | Tue 03/04/18
1.12.8.7.5 | iMTRC Maintenance of Capability (MC) process with LSRC Underway | 100% | 0 days | Mon 08/01/18 | Mon 08/01/18
1.12.8.7.6 | Mobilise for iMTRC SLA Amendment | 100% | 5 days | Tue 09/01/18 | Mon 15/01/18
1.12.8.7.7 | iMTRC SLA Amendment Start Date | 100% | 0 days | Mon 15/01/18 | Mon 15/01/18
1.12.8.7.8 | Modify iMTRC LSRC Building including cabling etc | 53% | 100 days | Tue 16/01/18 | Fri 08/06/18
1.12.8.7.9 | iMTRC Infrastructure and Commission Plan Accepted and Ready * | 0% | 0 days | Fri 08/06/18 | Fri 08/06/18
1.12.8.8 | iMTRC Equipment - Test & Acceptance of 7 Platforms worth of kit | 47% | 376 days | Fri 03/11/17 | Fri 10/05/19
1.12.8.8.1 | Acquire new Equipment needed for iMTRC | 50% | 200 days | Fri 03/11/17 | Thu 23/08/18
1.12.8.8.2 | Acquire existing GFX Equipment needed for iMTRC | 50% | 200 days | Fri 03/11/17 | Thu 23/08/18
1.12.8.8.3 | Test and Accept first platforms worth of GD Supplied kit | 0% | 10 days | Tue 30/10/18 | Mon 12/11/18
1.12.8.8.4 | First set of GD Kit (One Platform) Accepted | 0% | 0 days | Mon 12/11/18 | Mon 12/11/18
1.12.8.8.5 | Test and Accept six platforms worth of GD Supplied kit | 0% | 10 days | Fri 26/04/19 | Fri 10/05/19
1.12.8.8.6 | Second set of GD Kit (Six Platforms) Accepted | 0% | 0 days | Fri 10/05/19 | Fri 10/05/19
1.12.8.9 | iMTRC Doctrine / Information | 57% | 328 days | Mon 24/07/17 | Fri 09/11/18
1.12.8.9.1 | Develop iMTRC Operating, Repair and Maintenance Procedures | 41% | 240 days | Fri 03/11/17 | Fri 19/10/18
1.12.8.9.2 | Finalise iMTRC Operating, Repair and Maintenance Procedures | 0% | 10 days | Mon 29/10/18 | Fri 09/11/18
1.12.8.9.3 | Develop and Agree Interoperability of iMTRC with other T&R facilities | 76% | 225 days | Mon 24/07/17 | Mon 18/06/18
1.12.8.9.4 | iMTRC Procedures Developed | 0% | 0 days | Fri 09/11/18 | Fri 09/11/18
1.12.8.10 | iMTRC Security Arrangements | 99% | 235 days | Wed 26/04/17 | Wed 04/04/18
1.12.8.10.1 | Develop and Agree Security Arrangements for iMTRC | 99% | 235 days | Wed 26/04/17 | Wed 04/04/18
1.12.8.10.2 | iMTRC Security Arrangements Agreed | 0% | 0 days | Wed 04/04/18 | Wed 04/04/18
1.12.8.11 | iMTRC Personnel | 100% | 220 days | Wed 26/04/17 | Mon 12/03/18
1.12.8.11.1 | Engage with Army HQ and ISS to determine personnel requirement needed for iMTRC | 100% | 220 days | Wed 26/04/17 | Mon 12/03/18
1.12.8.11.2 | Personnel needed for Logical Architecture Conformance Acquired | 100% | 0 days | Tue 06/03/18 | Tue 06/03/18
1.12.8.12 | iMTRC Personnel Supplied via PSS Contract | 0% | 0 days | Wed 27/06/18 | Wed 27/06/18
1.12.8.12.1 | Personnel needed for System Application Verification Testing Acquired | 0% | 0 days | Wed 27/06/18 | Wed 27/06/18
1.12.8.12.2 | Personnel needed for Physical Architecture Conformance Acquired | 0% | 0 days | Wed 27/06/18 | Wed 27/06/18
1.12.8.13 | iMTRC Organisation | 99% | 235 days | Wed 26/04/17 | Wed 04/04/18
1.12.8.13.1 | Develop Governance and Reporting Arrangements for iMTRC | 99% | 235 days | Wed 26/04/17 | Wed 04/04/18
1.12.8.13.2 | Governance and Reporting Arrangements for iMTRC Agreed | 0% | 0 days | Wed 04/04/18 | Wed 04/04/18
1.12.8.14 | iMTRC Training | 0% | 30 days | Mon 12/11/18 | Fri 21/12/18
1.12.8.14.1 | Develop Operator training material | 0% | 10 days | Mon 12/11/18 | Fri 23/11/18
1.12.8.14.2 | Training for LSRC Facility Operator on iMTRC Equipment, supported by GD | 0% | 20 days | Mon 26/11/18 | Fri 21/12/18
1.12.8.14.3 | Develop iMTRC Familiarisation Training Material | 0% | 10 days | Mon 12/11/18 | Fri 23/11/18
1.12.8.14.4 | Provide iMTRC Familiarisation Training | 0% | 5 days | Mon 26/11/18 | Fri 30/11/18
1.12.8.14.5 | iMTRC Staff Trained | 0% | 0 days | Fri 21/12/18 | Fri 21/12/18
1.12.8.15 | iMTRC Logistics | 99% | 235 days | Wed 26/04/17 | Wed 04/04/18
1.12.8.15.1 | Develop and Agree Approach to Logistics for iMTRC | 99% | 235 days | Wed 26/04/17 | Wed 04/04/18
1.12.8.15.2 | iMTRC Logistics Approach Agreed | 0% | 0 days | Wed 04/04/18 | Wed 04/04/18
1.12.9 | iMTRC Operation | 1% | 712 days | Wed 07/03/18 | Tue 12/01/21
1.12.9.1 | Perform Logical Conformance Testing - LAC Engineers | 8% | 204 days | Wed 07/03/18 | Mon 24/12/18
1.12.9.2 | Perform Logical Conformance Testing - LAC Engineers via the PSS Contract | 0% | 403 days | Wed 02/01/19 | Fri 07/08/20
1.12.9.3 | Prep for Physical Conformance Testing including Installation and Commissioning of 1 Platforms worth of kit | 0% | 100 days | Thu 28/06/18 | Thu 15/11/18
1.12.9.4 | 1 EVO Platform worth of Kit Accepted and Fully Operational | 0% | 0 days | Thu 15/11/18 | Thu 15/11/18
1.12.9.5 | Limited Physical Conformance Testing (1 Platform) | 0% | 20 days | Mon 03/12/18 | Mon 07/01/19
1.12.9.6 | Feedback Received on iMTRC Configuration | 0% | 0 days | Mon 07/01/19 | Mon 07/01/19
1.12.9.7 | Modify iMTRC to address feedback | 0% | 40 days | Tue 08/01/19 | Mon 04/03/19
1.12.9.8 | Continue Physical Conformance testing (1 Platform) | 0% | 65 days | Tue 05/03/19 | Fri 07/06/19
1.12.9.9 | Install and Commission additional GD Supplied Kit (6 Platforms) | 0% | 20 days | Mon 13/05/19 | Mon 10/06/19
1.12.9.10 | 7 EVO Platform Capability Accepted and fully Operational | 0% | 0 days | Mon 10/06/19 | Mon 10/06/19
1.12.9.11 | Perform Physical Conformance / Proving at 7 Platform capability level | 0% | 151 days | Tue 11/06/19 | Thu 16/01/20
1.12.9.12 | Test, Accept and Install further 13 Platforms worth of kit and perform testing | 0% | 10 days | Fri 24/01/20 | Thu 06/02/20
1.12.9.13 | 20 EVO Platform Capability Accepted and fully Operational | 0% | 0 days | Thu 06/02/20 | Thu 06/02/20
1.12.9.14 | Perform Physical Conformance / Proving at 20 Platform capability level | 0% | 210 days | Fri 07/02/20 | Thu 03/12/20
1.12.9.15 | Conformance Testing on completed EnHCDR | 0% | 20 days | Wed 17/04/19 | Fri 17/05/19
1.12.9.16 | Test, Accept and Install final 10 platforms worth of kit and perform testing | 0% | 10 days | Fri 20/11/20 | Thu 03/12/20
1.12.9.17 | 30 EVO Platform Capability Accepted and fully Operational | 0% | 0 days | Thu 03/12/20 | Thu 03/12/20
1.12.9.18 | Perform Physical Conformance / Proving at 30 Platform capability level | 0% | 15 days | Fri 04/12/20 | Thu 24/12/20
1.12.9.19 | TP - Related Physical Conformance Architecture Testing / Proving Completed | 0% | 0 days | Thu 24/12/20 | Thu 24/12/20
1.12.9.20 | System and Application Verification Testing observed by iMTRC Staff | 0% | 635 days | Thu 28/06/18 | Tue 12/01/21
1.13 | Enduring MTRC | 29% | 2206 days | Mon 06/03/17 | Fri 02/01/26
1.13.1 | Define Requirements | 100% | 189 days | Mon 06/03/17 | Thu 30/11/17
1.13.1.1 | Define Non Functional Requirements | 100% | 120 days | Mon 06/03/17 | Thu 24/08/17
1.13.1.2 | Define Functional Requirements | 100% | 120 days | Mon 06/03/17 | Thu 24/08/17
1.13.1.3 | Review Requirements | 100% | 42 days | Fri 25/08/17 | Tue 24/10/17
1.13.1.4 | Update and Endorse Requirements | 100% | 27 days | Wed 25/10/17 | Thu 30/11/17
1.13.1.5 | Requirements Agreed | 100% | 0 days | Thu 30/11/17 | Thu 30/11/17
1.13.2 | Analysis of Options v's non Functional Requirements | 72% | 171 days | Fri 01/12/17 | Fri 10/08/18
1.13.2.1 | Analyse Personnel Options | 72% | 110 days | Fri 01/12/17 | Wed 16/05/18
1.13.2.2 | Analyse Organisation / Governance Options | 72% | 110 days | Fri 01/12/17 | Wed 16/05/18
1.13.2.3 | Analyse Technical Options | 72% | 110 days | Fri 01/12/17 | Wed 16/05/18
1.13.2.4 | Analyse Information Options | 72% | 110 days | Fri 01/12/17 | Wed 16/05/18
1.13.2.5 | Analyse ILS Options | 72% | 110 days | Fri 01/12/17 | Wed 16/05/18
1.13.2.6 | Discuss and Agree Initial View on Preferred Option | 98% | 81 days | Fri 01/12/17 | Wed 04/04/18
1.13.2.7 | Initial Identification of Preferred Option | 0% | 0 days | Wed 16/05/18 | Wed 16/05/18
1.13.2.8 | Complete Analysis of Location Options (Informed by DIO Process) | 0% | 30 days | Mon 02/07/18 | Fri 10/08/18
1.13.3 | Agree Preferred Option | 0% | 20 days | Mon 15/10/18 | Fri 09/11/18
1.13.3.1 | Discuss and agree with all Stakeholders Preferred Option | 0% | 20 days | Mon 15/10/18 | Fri 09/11/18
1.13.3.2 | eMTRC Preferred Option Agreed | 0% | 0 days | Fri 09/11/18 | Fri 09/11/18
1.13.4 | eMTRC CAPITAL PROJECT | 5% | 1469 days | Fri 01/12/17 | Thu 19/10/23
1.13.4.1 | Stage 0. Strategy | 71% | 111 days | Fri 01/12/17 | Thu 17/05/18
1.13.4.1.1 | Analyse, Review, Develop, the URD | 100% | 40 days | Fri 01/12/17 | Fri 02/02/18
1.13.4.1.2 | Convene initial PAG | 98% | 40 days | Mon 05/02/18 | Tue 03/04/18
1.13.4.1.3 | Endorsed URD | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.13.4.1.4 | Confirmation of IPE Funding Required | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.13.4.1.5 | Deliver IPE | 0% | 10 days | Wed 04/04/18 | Tue 17/04/18
1.13.4.1.6 | Confirmation of Feasibility Study Funding Required | 0% | 0 days | Tue 17/04/18 | Tue 17/04/18
1.13.4.1.7 | Summary Sustainability Appraisal | 0% | 1 day | Wed 18/04/18 | Wed 18/04/18
1.13.4.1.8 | Develop FS Business Case | 0% | 10 days | Thu 19/04/18 | Wed 02/05/18
1.13.4.1.9 | Gateway Review 0 | 0% | 0 days | Wed 02/05/18 | Wed 02/05/18
1.13.4.1.10 | FS Business Case submitted | 0% | 0 days | Wed 02/05/18 | Wed 02/05/18
1.13.4.1.11 | FS Business Case scrutiny and approval | 0% | 10 days | Thu 03/05/18 | Thu 17/05/18
1.13.4.1.12 | FS Business Case approved | 0% | 0 days | Thu 17/05/18 | Thu 17/05/18
1.13.4.2 | Stage 1. Brief | 0% | 60 days | Fri 18/05/18 | Fri 10/08/18
1.13.4.2.1 | Finalise FS Tasking Instruction | 0% | 5 days | Fri 18/05/18 | Thu 24/05/18
1.13.4.2.2 | Develop FS Tasking Directive | 0% | 5 days | Fri 25/05/18 | Fri 01/06/18
1.13.4.2.3 | Raise RCA for PSP FS task | 0% | 2 days | Mon 04/06/18 | Tue 05/06/18
1.13.4.2.4 | Contract PSP for FS | 0% | 3 days | Wed 06/06/18 | Fri 08/06/18
1.13.4.2.5 | Deliver Feasibility Study | 0% | 15 days | Mon 11/06/18 | Fri 29/06/18
1.13.4.2.6 | Develop Preliminary Business Case (PBC) | 0% | 10 days | Mon 02/07/18 | Fri 13/07/18
1.13.4.2.7 | Confirmation of PBC Funding Required | 0% | 0 days | Fri 13/07/18 | Fri 13/07/18
1.13.4.2.8 | Convene post FS PAG | 0% | 10 days | Mon 16/07/18 | Fri 27/07/18
1.13.4.2.9 | Post FS PAG review concluded | 0% | 0 days | Fri 27/07/18 | Fri 27/07/18
1.13.4.2.10 | Gateway Review 1 | 0% | 0 days | Fri 27/07/18 | Fri 27/07/18
1.13.4.2.11 | PBC submitted | 0% | 0 days | Fri 27/07/18 | Fri 27/07/18
1.13.4.2.12 | PBC scrutiny and approval | 0% | 10 days | Mon 30/07/18 | Fri 10/08/18
1.13.4.2.13 | PBC approved | 0% | 0 days | Fri 10/08/18 | Fri 10/08/18
1.13.4.3 | Stage 2. Concept | 0% | 196 days | Mon 13/08/18 | Tue 28/05/19
1.13.4.3.1 | Finalise AS Tasking Instruction | 0% | 10 days | Mon 13/08/18 | Fri 24/08/18
1.13.4.3.2 | Develop AS Tasking Directive | 0% | 10 days | Tue 28/08/18 | Mon 10/09/18
1.13.4.3.3 | Raise RCA for PSP AS task | 0% | 2 days | Tue 11/09/18 | Wed 12/09/18
1.13.4.3.4 | Contract PSP ( including PSP Fee bid, submission and standstill period) | 0% | 3 days | Thu 13/09/18 | Mon 17/09/18
1.13.4.3.5 | Sustainability Appraisal and Report for Options | 0% | 1 day | Tue 18/09/18 | Tue 18/09/18
1.13.4.3.6 | Deliver Assessment Study | 0% | 90 days | Wed 19/09/18 | Wed 30/01/19
1.13.4.3.7 | Develop Initial Gate Business Case (IGBC) | 0% | 40 days | Thu 31/01/19 | Wed 27/03/19
1.13.4.3.8 | Confirmation of IGBC Funding Required | 0% | 0 days | Wed 27/03/19 | Wed 27/03/19
1.13.4.3.9 | Convene post AS PAG | 0% | 10 days | Thu 28/03/19 | Wed 10/04/19
1.13.4.3.10 | Post AS PAG review concluded | 0% | 0 days | Wed 10/04/19 | Wed 10/04/19
1.13.4.3.11 | Gateway Review 2 | 0% | 0 days | Wed 10/04/19 | Wed 10/04/19
1.13.4.3.12 | IGBC submitted | 0% | 0 days | Wed 10/04/19 | Wed 10/04/19
1.13.4.3.13 | IGBC & IAC scrutiny and approval | 0% | 30 days | Thu 11/04/19 | Tue 28/05/19
1.13.4.3.14 | IGBC IAC Forecast | 0% | 0 days | Tue 28/05/19 | Tue 28/05/19
1.13.4.3.15 | IGBC approved | 0% | 0 days | Tue 28/05/19 | Tue 28/05/19
1.13.4.4 | Stage 3. Definition to MGBC | 0% | 472 days | Wed 03/07/19 | Fri 21/05/21
1.13.4.4.1 | Definition and Development to eMTRC MGBC Approval | 0% | 472 days | Wed 03/07/19 | Fri 21/05/21
1.13.4.5 | Stage 4. Detailed Design and Contract Award | 0% | 70 days | Mon 24/05/21 | Tue 31/08/21
1.13.4.5.1 | Construction Contract notification and Design to Gateway 4 Review | 0% | 70 days | Mon 24/05/21 | Tue 31/08/21
1.13.4.6 | Stage 5. Build & Commission | 0% | 260 days | Wed 01/09/21 | Wed 14/09/22
1.13.4.6.1 | Construction and Build to Gateway 5 Review | 0% | 260 days | Wed 01/09/21 | Wed 14/09/22
1.13.4.7 | Stage 6. Handover and Close Out | 0% | 275 days | Thu 15/09/22 | Thu 19/10/23
1.13.4.7.1 | Post Construction fittings, Handover to Gateway 6 Review | 0% | 275 days | Thu 15/09/22 | Thu 19/10/23
1.13.5 | Implement Selected Option for eMTRC | 0% | 548 days | Thu 19/10/23 | Fri 02/01/26
1.13.5.1 | eMTRC Option Operational * | 0% | 0 days | Thu 19/10/23 | Thu 19/10/23
1.13.5.2 | System and Application Verification Testing in eMTRC | 0% | 548 days | Fri 20/10/23 | Fri 02/01/26
1.14 | Co-ordinating Design Organisation / TAF / OTP | 22% | 2112 days | Mon 06/03/17 | Thu 14/08/25
1.14.1 | GD Reviews | 0% | 688 days | Fri 30/06/17 | Tue 31/03/20
1.14.1.1 | PI01 Complete | 100% | 0 days | Fri 30/06/17 | Fri 30/06/17
1.14.1.2 | Assurance Review1 | 100% | 0 days | Thu 05/10/17 | Thu 05/10/17
1.14.1.3 | PI02 Complete | 100% | 0 days | Fri 22/09/17 | Fri 22/09/17
1.14.1.4 | PI03 Complete | 100% | 0 days | Fri 15/12/17 | Fri 15/12/17
1.14.1.5 | PI04 Complete | 100% | 0 days | Fri 23/03/18 | Fri 23/03/18
1.14.1.6 | Assurance Review2 | 0% | 0 days | Thu 19/04/18 | Thu 19/04/18
1.14.1.7 | PI05 Complete | 0% | 0 days | Fri 15/06/18 | Fri 15/06/18
1.14.1.8 | Assurance Review3 | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.14.1.9 | Assurance Review4 | 0% | 0 days | Tue 02/04/19 | Tue 02/04/19
1.14.1.10 | Assurance Review5 | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.14.1.11 | Assurance Review6 | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.14.2 | Dependencies from BATCIS to GD | 0% | 683 days | Fri 30/06/17 | Tue 24/03/20
1.14.2.1 | CDO ready for PI01 | 100% | 0 days | Fri 30/06/17 | Fri 30/06/17
1.14.2.2 | CDO ready for Assurance Review 1 | 100% | 0 days | Mon 02/10/17 | Mon 02/10/17
1.14.2.3 | CDO ready for PI02 | 100% | 0 days | Wed 20/09/17 | Wed 20/09/17
1.14.2.4 | CDO ready for PI03 | 100% | 0 days | Fri 15/12/17 | Fri 15/12/17
1.14.2.5 | CDO ready for PI04 | 100% | 0 days | Fri 23/03/18 | Fri 23/03/18
1.14.2.6 | CDO ready for Assurance Review 2 | 0% | 0 days | Fri 13/04/18 | Fri 13/04/18
1.14.2.7 | CDO ready for PI05 | 0% | 0 days | Fri 15/06/18 | Fri 15/06/18
1.14.2.8 | CDO ready for Assurance Review 3 | 0% | 0 days | Mon 24/09/18 | Mon 24/09/18
1.14.2.9 | CDO ready for Assurance Review 4 | 0% | 0 days | Tue 26/03/19 | Tue 26/03/19
1.14.2.10 | CDO ready for Assurance Review 5 | 0% | 0 days | Mon 23/09/19 | Mon 23/09/19
1.14.2.11 | CDO ready for Assurance Review 6 | 0% | 0 days | Tue 24/03/20 | Tue 24/03/20
1.14.3 | Dependencies from BATCIS to OTP | 0% | 120 days | Fri 06/10/17 | Wed 04/04/18
1.14.3.1 | Provide OTP with Info needed for Openness Assessment for PI03 Review | 100% | 0 days | Fri 06/10/17 | Fri 06/10/17
1.14.3.2 | Provide OTP with Info needed for Openness Assessment for PI04 Review | 100% | 0 days | Fri 12/01/18 | Fri 12/01/18
1.14.3.3 | Provide OTP with Info needed for Openness Assessment for PI05 Review | 0% | 0 days | Wed 04/04/18 | Wed 04/04/18
1.14.4 | Dependencies from BATCIS to TAF | 0% | 628 days | Mon 31/07/17 | Wed 05/02/20
1.14.4.1 | CDO Issue Assurance Review Artefacts to TAF Working Group wrt Assurance Review1 | 100% | 0 days | Mon 31/07/17 | Mon 31/07/17
1.14.4.2 | CDO Issue Assurance Review Artefacts to TAF Working Group wrt Assurance Review2 | 100% | 0 days | Tue 20/02/18 | Tue 20/02/18
1.14.4.3 | CDO Issue Assurance Review Artefacts to TAF Working Group wrt Assurance Review3 | 0% | 0 days | Mon 06/08/18 | Mon 06/08/18
1.14.4.4 | CDO Issue Assurance Review Artefacts to TAF Working Group wrt Assurance Review4 | 0% | 0 days | Wed 06/02/19 | Wed 06/02/19
1.14.4.5 | CDO Issue Assurance Review Artefacts to TAF Working Group wrt Assurance Review5 | 0% | 0 days | Mon 05/08/19 | Mon 05/08/19
1.14.4.6 | CDO Issue Assurance Review Artefacts to TAF Working Group wrt Assurance Review6 | 0% | 0 days | Wed 05/02/20 | Wed 05/02/20
1.14.5 | Engineering Management | 18% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.14.5.1 | Enduring Activities | 12% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.14.5.1.1 | Report on CDO (Monthly) | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.14.5.1.2 | Manage CDO ( Assumptions, Dependencies, PM Workbook, Panel meetings, Risks & Issues, LFE) | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.14.5.1.3 | Support to TP Agile Process | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.14.5.1.4 | Maintain and Update MEF | 0% | 688 days | Tue 03/04/18 | Thu 24/12/20
1.14.5.1.5 | Maintain and Update SEMS (Systems Engineering Management Strategy) | 0% | 628 days | Thu 28/06/18 | Thu 24/12/20
1.14.5.2 | Key Deliverables | 44% | 935 days | Mon 03/04/17 | Wed 23/12/20
1.14.5.2.1 | Systems Engineering Management Plan (SEMP) | 28% | 935 days | Mon 03/04/17 | Wed 23/12/20
1.14.5.2.1.1 | Produce Draft ENG SEMP V5 | 100% | 125 days | Mon 03/04/17 | Fri 29/09/17
1.14.5.2.1.2 | Draft ENG SEMP V5 Issued for Comment | 100% | 0 days | Fri 29/09/17 | Fri 29/09/17
1.14.5.2.1.3 | Review Draft ENG SEMP V5 | 100% | 10 days | Mon 02/10/17 | Fri 13/10/17
1.14.5.2.1.4 | Update Draft ENG SEMP V5 | 100% | 5 days | Mon 16/10/17 | Fri 20/10/17
1.14.5.2.1.5 | ENG SEMP V5 Approved | 100% | 0 days | Fri 20/10/17 | Fri 20/10/17
1.14.5.2.1.6 | Produce Draft ENG SEMP V6 | 100% | 93 days | Mon 23/10/17 | Thu 08/03/18
1.14.5.2.1.7 | Draft ENG SEMP V6 Issued for Comment | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.14.5.2.1.8 | Review Draft ENG SEMP V6 | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.14.5.2.1.9 | Update Draft ENG SEMP V6 | 100% | 5 days | Fri 23/03/18 | Thu 29/03/18
1.14.5.2.1.10 | ENG SEMP V6 Approved | 100% | 0 days | Thu 29/03/18 | Thu 29/03/18
1.14.5.2.1.11 | Produce Draft ENG SEMP V7 | 0% | 110 days | Thu 28/06/18 | Thu 29/11/18
1.14.5.2.1.12 | Draft ENG SEMP V7 Issued for Comment | 0% | 0 days | Thu 29/11/18 | Thu 29/11/18
1.14.5.2.1.13 | Review Draft ENG SEMP V7 | 0% | 10 days | Fri 30/11/18 | Thu 13/12/18
1.14.5.2.1.14 | Update Draft ENG SEMP V7 | 0% | 5 days | Fri 14/12/18 | Thu 20/12/18
1.14.5.2.1.15 | ENG SEMP V7 Approved | 0% | 0 days | Thu 20/12/18 | Thu 20/12/18
1.14.5.2.1.16 | Produce Draft ENG SEMP V8 | 0% | 109 days | Wed 02/01/19 | Fri 07/06/19
1.14.5.2.1.17 | Draft ENG SEMP V8 Issued for Comment | 0% | 0 days | Fri 07/06/19 | Fri 07/06/19
1.14.5.2.1.18 | Review Draft ENG SEMP V8 | 0% | 10 days | Mon 10/06/19 | Fri 21/06/19
1.14.5.2.1.19 | Update Draft ENG SEMP V8 | 0% | 5 days | Mon 24/06/19 | Fri 28/06/19
1.14.5.2.1.20 | ENG SEMP V8 Approved | 0% | 0 days | Fri 28/06/19 | Fri 28/06/19
1.14.5.2.1.21 | Produce Draft ENG SEMP V9 | 0% | 109 days | Mon 01/07/19 | Fri 29/11/19
1.14.5.2.1.22 | Draft ENG SEMP V9 Issued for Comment | 0% | 0 days | Fri 29/11/19 | Fri 29/11/19
1.14.5.2.1.23 | Review Draft ENG SEMP V9 | 0% | 10 days | Mon 02/12/19 | Fri 13/12/19
1.14.5.2.1.24 | Update Draft ENG SEMP V9 | 0% | 5 days | Mon 16/12/19 | Fri 20/12/19
1.14.5.2.1.25 | ENG SEMP V9 Approved | 0% | 0 days | Fri 20/12/19 | Fri 20/12/19
1.14.5.2.1.26 | Produce Draft ENG SEMP V10 | 0% | 112 days | Mon 23/12/19 | Tue 09/06/20
1.14.5.2.1.27 | Draft ENG SEMP V10 Issued for Comment | 0% | 0 days | Tue 09/06/20 | Tue 09/06/20
1.14.5.2.1.28 | Review Draft ENG SEMP V10 | 0% | 10 days | Wed 10/06/20 | Tue 23/06/20
1.14.5.2.1.29 | Update Draft ENG SEMP V10 | 0% | 5 days | Wed 24/06/20 | Tue 30/06/20
1.14.5.2.1.30 | ENG SEMP V10 Approved | 0% | 0 days | Tue 30/06/20 | Tue 30/06/20
1.14.5.2.1.31 | Produce Draft ENG SEMP V11 | 0% | 110 days | Wed 01/07/20 | Wed 02/12/20
1.14.5.2.1.32 | Draft ENG SEMP V11 Issued for Comment | 0% | 0 days | Wed 02/12/20 | Wed 02/12/20
1.14.5.2.1.33 | Review Draft ENG SEMP V11 | 0% | 10 days | Thu 03/12/20 | Wed 16/12/20
1.14.5.2.1.34 | Update Draft ENG SEMP V11 | 0% | 5 days | Thu 17/12/20 | Wed 23/12/20
1.14.5.2.1.35 | ENG SEMP V11 Approved | 0% | 0 days | Wed 23/12/20 | Wed 23/12/20
1.14.5.2.2 | MORPHEUS Enterprise Functions (MEF) | 100% | 248 days | Mon 03/04/17 | Thu 29/03/18
1.14.5.2.2.1 | Produce Draft MEF V7 | 100% | 125 days | Mon 03/04/17 | Fri 29/09/17
1.14.5.2.2.2 | Draft MEF V7 Issued for Comment | 100% | 0 days | Fri 29/09/17 | Fri 29/09/17
1.14.5.2.2.3 | Review Draft MEF V7 | 100% | 10 days | Mon 02/10/17 | Fri 13/10/17
1.14.5.2.2.4 | Update Draft MEF V7 | 100% | 5 days | Mon 16/10/17 | Fri 20/10/17
1.14.5.2.2.5 | MEF V7 Approved | 100% | 0 days | Fri 20/10/17 | Fri 20/10/17
1.14.5.2.2.6 | Produce Draft MEF V8 | 100% | 93 days | Mon 23/10/17 | Thu 08/03/18
1.14.5.2.2.7 | Draft MEF V8 Issued for Comment | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.14.5.2.2.8 | Review Draft MEF V8 | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.14.5.2.2.9 | Update Draft MEF V8 | 100% | 5 days | Fri 23/03/18 | Thu 29/03/18
1.14.5.2.2.10 | MEF V8 Approved | 100% | 0 days | Thu 29/03/18 | Thu 29/03/18
1.14.5.3 | Systems Engineering | 26% | 936 days | Mon 03/04/17 | Thu 24/12/20
1.14.5.3.1 | Enduring Activities | 26% | 936 days | Mon 03/04/17 | Thu 24/12/20
1.14.5.3.1.1 | Produce Quarterly Assurance Reports based on inputs from TAF & OTP | 26% | 936 days | Mon 03/04/17 | Thu 24/12/20
1.14.6 | Openness Testing Partner | 53% | 580 days | Mon 06/03/17 | Mon 01/07/19
1.14.6.1 | Openness Testing Partner Competition - FATS5 | 100% | 101 days | Mon 06/03/17 | Fri 28/07/17
1.14.6.1.1 | Mature OTP SOR Available | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.14.6.1.2 | Review LFE from Similar Competitions | 100% | 1 day | Thu 16/03/17 | Thu 16/03/17
1.14.6.1.3 | Complete OTP ISS Front Door Process | 0% | 5 days | Fri 17/03/17 | Thu 23/03/17
1.14.6.1.4 | Refine OTP SOR | 100% | 10 days | Fri 17/03/17 | Thu 30/03/17
1.14.6.1.5 | Generate OTP Security Aspects Letter | 100% | 2 days | Fri 31/03/17 | Mon 03/04/17
1.14.6.1.6 | Produce OTP Procurement Strategy | 100% | 1 day | Mon 06/03/17 | Tue 07/03/17
1.14.6.1.7 | Produce OTP Commercial Strategy | 100% | 1 day | Tue 07/03/17 | Wed 08/03/17
1.14.6.1.8 | Produce OTP Commitment Case / 2 SMS requests | 100% | 1 day | Thu 09/03/17 | Thu 09/03/17
1.14.6.1.9 | Produce and Approve OTP RCA | 100% | 1 day | Fri 10/03/17 | Fri 10/03/17
1.14.6.1.10 | Produce OTP Tasking Form & Evaluation Criteria | 100% | 16 days | Mon 13/03/17 | Mon 03/04/17
1.14.6.1.11 | OTP Review & Approval By FATS G&G | 100% | 40 days | Tue 04/04/17 | Fri 02/06/17
1.14.6.1.12 | Issue OTP Pre Tasking Questionnaire | 100% | 1 day | Mon 05/06/17 | Mon 05/06/17
1.14.6.1.13 | OTP Pre Tasking Questionnaire Issued | 100% | 0 days | Mon 05/06/17 | Mon 05/06/17
1.14.6.1.14 | Industry Complete OTP Pre Tasking Questionnaire | 100% | 5 days | Tue 06/06/17 | Mon 12/06/17
1.14.6.1.15 | OTP Pre Tasking Questionnaire review | 100% | 1 day | Tue 13/06/17 | Tue 13/06/17
1.14.6.1.16 | Issue OTP ITT / Tasking Form | 100% | 1 day | Wed 14/06/17 | Wed 14/06/17
1.14.6.1.17 | OTP ITT/Tasking Form issued | 100% | 0 days | Wed 14/06/17 | Wed 14/06/17
1.14.6.1.18 | Industry Develop OTP Responses | 100% | 10 days | Thu 15/06/17 | Wed 28/06/17
1.14.6.1.19 | BATCIS Manage OTP CQs | 100% | 14 days | Thu 15/06/17 | Tue 04/07/17
1.14.6.1.20 | OTP Tender Responses received | 100% | 0 days | Tue 04/07/17 | Tue 04/07/17
1.14.6.1.21 | OTP Tenderer Evaluation | 100% | 1 day | Wed 05/07/17 | Wed 05/07/17
1.14.6.1.22 | Hold OTP TAP | 100% | 1 day | Thu 06/07/17 | Thu 06/07/17
1.14.6.1.23 | Prepare & Provide OTP Feedback | 100% | 6 days | Fri 07/07/17 | Fri 14/07/17
1.14.6.1.24 | Award OTP Contract | 100% | 1 day | Fri 21/07/17 | Fri 21/07/17
1.14.6.1.25 | OTP Contract Awarded | 100% | 0 days | Fri 21/07/17 | Fri 21/07/17
1.14.6.1.26 | OTP Contract Mobilisation | 100% | 5 days | Mon 24/07/17 | Fri 28/07/17
1.14.6.1.27 | OTP Contract Start Date | 100% | 0 days | Fri 28/07/17 | Fri 28/07/17
1.14.6.2 | Openness Testing Partner on Contract | 42% | 544 days | Thu 27/04/17 | Mon 01/07/19
1.14.6.2.1 | CDO Assess Openness PI 1 | 100% | 30 days | Thu 27/04/17 | Fri 09/06/17
1.14.6.2.2 | CDO Produce Draft Architecture Openness Report & Draft Configuration Item Openness Report for Program Increment 1 | 100% | 10 days | Mon 12/06/17 | Fri 23/06/17
1.14.6.2.3 | CDO Planning for PI 2 | 100% | 5 days | Mon 26/06/17 | Fri 30/06/17
1.14.6.2.4 | CDO Produce Final Architecture Openness Report & Final Configuration Item Openness Report for Program Increment 1 | 100% | 10 days | Mon 03/07/17 | Fri 14/07/17
1.14.6.2.5 | Final Openness Reports produced for PI 1 by CDO | 100% | 0 days | Fri 14/07/17 | Fri 14/07/17
1.14.6.2.6 | CDO Assess Openness PI 2 | 100% | 34 days | Mon 17/07/17 | Fri 01/09/17
1.14.6.2.7 | CDO Produce Draft Architecture Openness Report & Draft Configuration Item Openness Report for Program Increment 2 | 100% | 9 days | Mon 04/09/17 | Thu 14/09/17
1.14.6.2.8 | CDO Planning for PI 3 and AR1 | 100% | 4 days | Fri 15/09/17 | Wed 20/09/17
1.14.6.2.9 | CDO Produce Final Architecture Openness Report & Final Configuration Item Openness Report for Program Increment 2 | 100% | 9 days | Fri 22/09/17 | Wed 04/10/17
1.14.6.2.10 | Final Openness Reports produced for PI 2 | 100% | 0 days | Wed 04/10/17 | Wed 04/10/17
1.14.6.2.11 | Assess Openness PI 3 | 100% | 31 days | Fri 06/10/17 | Fri 17/11/17
1.14.6.2.12 | Produce Draft Architecture Openness Report & Draft Configuration Item Openness Report for Program Increment 3 | 100% | 5 days | Mon 20/11/17 | Fri 24/11/17
1.14.6.2.13 | CDO Review and Comment on Draft Openness Report for PI 3 | 100% | 10 days | Mon 27/11/17 | Fri 08/12/17
1.14.6.2.14 | CDO & OTP Planning for PI 4 | 100% | 5 days | Mon 11/12/17 | Fri 15/12/17
1.14.6.2.15 | Produce Final Architecture Openness Report & Final Configuration Item Openness Report for Program Increment 3 | 100% | 10 days | Fri 15/12/17 | Fri 05/01/18
1.14.6.2.16 | CDO Review and Comment on Final Openness Report for PI 3 | 100% | 3 days | Mon 08/01/18 | Wed 10/01/18
1.14.6.2.17 | Final Openness Reports produced for PI 3 | 100% | 0 days | Wed 10/01/18 | Wed 10/01/18
1.14.6.2.18 | Assess Openness PI 4 | 100% | 31 days | Fri 12/01/18 | Fri 23/02/18
1.14.6.2.19 | Produce Draft Architecture Openness Report & Draft Configuration Item Openness Report for Program Increment 4 | 100% | 5 days | Mon 26/02/18 | Fri 02/03/18
1.14.6.2.20 | CDO Review and Comment on Draft Openness Report for PI 4 | 100% | 10 days | Mon 05/03/18 | Fri 16/03/18
1.14.6.2.21 | CDO &OTP Planning for PI 5 & AR2 | 100% | 5 days | Mon 19/03/18 | Fri 23/03/18
1.14.6.2.22 | Produce Final Architecture Openness Report & Final Configuration Item Openness Report for Program Increment 4 | 50% | 10 days | Fri 23/03/18 | Mon 09/04/18
1.14.6.2.23 | CDO Review and Comment on Final Openness Report for PI 4 | 0% | 3 days | Tue 10/04/18 | Thu 12/04/18
1.14.6.2.24 | Final Openness Reports produced for PI 4 | 0% | 0 days | Thu 12/04/18 | Thu 12/04/18
1.14.6.2.25 | Assess Openness PI 5 | 0% | 24 days | Fri 13/04/18 | Thu 17/05/18
1.14.6.2.26 | Produce Draft Architecture Openness Report & Draft Configuration Item Openness Report for Program Increment 5 | 0% | 5 days | Fri 18/05/18 | Thu 24/05/18
1.14.6.2.27 | CDO Review and Comment on Draft Openness Report for PI 5 | 0% | 10 days | Fri 25/05/18 | Fri 08/06/18
1.14.6.2.28 | CDO &OTP Planning for PI 6 | 0% | 5 days | Fri 08/06/18 | Fri 15/06/18
1.14.6.2.29 | Produce Final Architecture Openness Report & Final Configuration Item Openness Report for Program Increment 5 | 0% | 10 days | Fri 15/06/18 | Thu 28/06/18
1.14.6.2.30 | CDO Review and Comment on Final Openness Report for PI 5 | 0% | 3 days | Fri 29/06/18 | Tue 03/07/18
1.14.6.2.31 | Final Openness Reports produced for PI 5 | 0% | 0 days | Tue 03/07/18 | Tue 03/07/18
1.14.6.2.32 | Continue with Openness Testing (Extra Year Contract Option Exercised) | 0% | 248 days | Wed 04/07/18 | Mon 01/07/19
1.14.6.2.33 | End of Openness Testing Contract | 0% | 0 days | Mon 01/07/19 | Mon 01/07/19
1.14.7 | TAF | 25% | 2013 days | Mon 06/03/17 | Mon 24/03/25
1.14.7.1 | Enduring Activities | 54% | 500 days | Mon 06/03/17 | Tue 05/03/19
1.14.7.1.1 | Report on TAF Progress | 54% | 500 days | Mon 06/03/17 | Tue 05/03/19
1.14.7.2 | Key Deliverables | 30% | 900 days | Mon 03/04/17 | Wed 04/11/20
1.14.7.2.1 | TAF FAQ | 28% | 900 days | Mon 03/04/17 | Wed 04/11/20
1.14.7.2.1.1 | Produce Draft TAF FAQ | 100% | 18 days | Mon 03/04/17 | Fri 28/04/17
1.14.7.2.1.2 | Draft TAF FAQ Issued for Comment | 100% | 0 days | Fri 28/04/17 | Fri 28/04/17
1.14.7.2.1.3 | Review Draft TAF FAQ | 100% | 10 days | Tue 02/05/17 | Mon 15/05/17
1.14.7.2.1.4 | Update Draft TAF FAQ | 100% | 5 days | Tue 16/05/17 | Mon 22/05/17
1.14.7.2.1.5 | TAF FAQ V1 Approved | 100% | 0 days | Mon 22/05/17 | Mon 22/05/17
1.14.7.2.1.6 | Produce Draft TAF FAQ V2 | 83% | 258 days | Tue 23/05/17 | Mon 04/06/18
1.14.7.2.1.7 | Draft TAF FAQ V2 Issued for Comment | 0% | 0 days | Mon 04/06/18 | Mon 04/06/18
1.14.7.2.1.8 | Review Draft TAF FAQ V2 | 0% | 10 days | Tue 05/06/18 | Mon 18/06/18
1.14.7.2.1.9 | Update Draft TAF FAQ V2 | 0% | 5 days | Tue 19/06/18 | Mon 25/06/18
1.14.7.2.1.10 | TAF FAQ V2 Approved | 0% | 0 days | Mon 25/06/18 | Mon 25/06/18
1.14.7.2.1.11 | Produce Draft TAF FAQ V3 | 0% | 80 days | Tue 26/06/18 | Tue 16/10/18
1.14.7.2.1.12 | Draft TAF FAQ V3 Issued for Comment | 0% | 0 days | Tue 16/10/18 | Tue 16/10/18
1.14.7.2.1.13 | Review Draft TAF FAQ V3 | 0% | 10 days | Wed 17/10/18 | Tue 30/10/18
1.14.7.2.1.14 | Update Draft TAF FAQ V3 | 0% | 5 days | Wed 31/10/18 | Tue 06/11/18
1.14.7.2.1.15 | TAF FAQ V3 Approved | 0% | 0 days | Tue 06/11/18 | Tue 06/11/18
1.14.7.2.1.16 | Produce Draft TAF FAQ V4 | 0% | 108 days | Wed 07/11/18 | Mon 15/04/19
1.14.7.2.1.17 | Draft TAF FAQ V4 Issued for Comment | 0% | 0 days | Mon 15/04/19 | Mon 15/04/19
1.14.7.2.1.18 | Review Draft TAF FAQ V4 | 0% | 10 days | Tue 16/04/19 | Wed 01/05/19
1.14.7.2.1.19 | Update Draft TAF FAQ V4 | 0% | 5 days | Thu 02/05/19 | Thu 09/05/19
1.14.7.2.1.20 | TAF FAQ V4 Approved | 0% | 0 days | Thu 09/05/19 | Thu 09/05/19
1.14.7.2.1.21 | Produce Draft TAF FAQ V5 | 0% | 110 days | Fri 10/05/19 | Mon 14/10/19
1.14.7.2.1.22 | Draft TAF FAQ V5 Issued for Comment | 0% | 0 days | Mon 14/10/19 | Mon 14/10/19
1.14.7.2.1.23 | Review Draft TAF FAQ V5 | 0% | 10 days | Tue 15/10/19 | Mon 28/10/19
1.14.7.2.1.24 | Update Draft TAF FAQ V5 | 0% | 5 days | Tue 29/10/19 | Mon 04/11/19
1.14.7.2.1.25 | TAF FAQ V5 Approved | 0% | 0 days | Mon 04/11/19 | Mon 04/11/19
1.14.7.2.1.26 | Produce Draft TAF FAQ V6 | 0% | 108 days | Tue 05/11/19 | Tue 14/04/20
1.14.7.2.1.27 | Draft TAF FAQ V6 Issued for Comment | 0% | 0 days | Tue 14/04/20 | Tue 14/04/20
1.14.7.2.1.28 | Review Draft TAF FAQ V6 | 0% | 10 days | Wed 15/04/20 | Tue 28/04/20
1.14.7.2.1.29 | Update Draft TAF FAQ V6 | 0% | 5 days | Wed 29/04/20 | Wed 06/05/20
1.14.7.2.1.30 | TAF FAQ V6 Approved | 0% | 0 days | Wed 06/05/20 | Wed 06/05/20
1.14.7.2.1.31 | Produce Draft TAF FAQ V7 | 0% | 113 days | Thu 07/05/20 | Wed 14/10/20
1.14.7.2.1.32 | Draft TAF FAQ V7 Issued for Comment | 0% | 0 days | Wed 14/10/20 | Wed 14/10/20
1.14.7.2.1.33 | Review Draft TAF FAQ V7 | 0% | 10 days | Thu 15/10/20 | Wed 28/10/20
1.14.7.2.1.34 | Update Draft TAF FAQ V7 | 0% | 5 days | Thu 29/10/20 | Wed 04/11/20
1.14.7.2.1.35 | TAF FAQ V7 Approved | 0% | 0 days | Wed 04/11/20 | Wed 04/11/20
1.14.7.2.2 | TAF TOR | 31% | 794 days | Mon 03/04/17 | Mon 08/06/20
1.14.7.2.2.1 | Produce Draft TAF TOR | 100% | 61 days | Mon 03/04/17 | Fri 30/06/17
1.14.7.2.2.2 | Draft TAF TOR Issued for Comment | 100% | 0 days | Fri 30/06/17 | Fri 30/06/17
1.14.7.2.2.3 | Review Draft TAF TOR | 100% | 10 days | Mon 03/07/17 | Fri 14/07/17
1.14.7.2.2.4 | Update Draft TAF TOR | 100% | 5 days | Mon 17/07/17 | Fri 21/07/17
1.14.7.2.2.5 | TAF TOR V1 Approved | 100% | 0 days | Fri 21/07/17 | Fri 21/07/17
1.14.7.2.2.6 | Produce Draft TAF TOR V2 | 80% | 215 days | Mon 24/07/17 | Mon 04/06/18
1.14.7.2.2.7 | Draft TAF TOR V2 Issued for Comment | 0% | 0 days | Mon 04/06/18 | Mon 04/06/18
1.14.7.2.2.8 | Review Draft TAF TOR V2 | 0% | 10 days | Tue 05/06/18 | Mon 18/06/18
1.14.7.2.2.9 | Update Draft TAF TOR V2 | 0% | 5 days | Tue 19/06/18 | Mon 25/06/18
1.14.7.2.2.10 | TAF TOR V2 Approved | 0% | 0 days | Mon 25/06/18 | Mon 25/06/18
1.14.7.2.2.11 | Produce Draft TAF TOR V3 | 0% | 220 days | Tue 26/06/18 | Mon 13/05/19
1.14.7.2.2.12 | Draft TAF TOR V3 Issued for Comment | 0% | 0 days | Mon 13/05/19 | Mon 13/05/19
1.14.7.2.2.13 | Review Draft TAF TOR V3 | 0% | 10 days | Tue 14/05/19 | Tue 28/05/19
1.14.7.2.2.14 | Update Draft TAF TOR V3 | 0% | 5 days | Wed 29/05/19 | Tue 04/06/19
1.14.7.2.2.15 | TAF TOR V3 Approved | 0% | 0 days | Tue 04/06/19 | Tue 04/06/19
1.14.7.2.2.16 | Produce Draft TAF TOR V4 | 0% | 238 days | Wed 05/06/19 | Fri 15/05/20
1.14.7.2.2.17 | Draft TAF TOR V4 Issued for Comment | 0% | 0 days | Fri 15/05/20 | Fri 15/05/20
1.14.7.2.2.18 | Review Draft TAF TOR V4 | 0% | 10 days | Mon 18/05/20 | Mon 01/06/20
1.14.7.2.2.19 | Update Draft TAF TOR V4 | 0% | 5 days | Tue 02/06/20 | Mon 08/06/20
1.14.7.2.2.20 | TAF TOR V4 Approved | 0% | 0 days | Mon 08/06/20 | Mon 08/06/20
1.14.7.2.3 | TAF Strategy | 31% | 794 days | Mon 03/04/17 | Mon 08/06/20
1.14.7.2.3.1 | Produce Draft TAF Strategy | 100% | 61 days | Mon 03/04/17 | Fri 30/06/17
1.14.7.2.3.2 | Draft TAF Strategy Issued for Comment | 100% | 0 days | Fri 30/06/17 | Fri 30/06/17
1.14.7.2.3.3 | Review Draft TAF Strategy | 100% | 10 days | Mon 03/07/17 | Fri 14/07/17
1.14.7.2.3.4 | Update Draft TAF Strategy | 100% | 5 days | Mon 17/07/17 | Fri 21/07/17
1.14.7.2.3.5 | TAF Strategy V1 Approved | 100% | 0 days | Fri 21/07/17 | Fri 21/07/17
1.14.7.2.3.6 | Produce Draft TAF Strategy V2 | 80% | 215 days | Mon 24/07/17 | Mon 04/06/18
1.14.7.2.3.7 | Draft TAF Strategy V2 Issued for Comment | 0% | 0 days | Mon 04/06/18 | Mon 04/06/18
1.14.7.2.3.8 | Review Draft TAF Strategy V2 | 0% | 10 days | Tue 05/06/18 | Mon 18/06/18
1.14.7.2.3.9 | Update Draft TAF Strategy V2 | 0% | 5 days | Tue 19/06/18 | Mon 25/06/18
1.14.7.2.3.10 | TAF Strategy V2 Approved | 0% | 0 days | Mon 25/06/18 | Mon 25/06/18
1.14.7.2.3.11 | Produce Draft TAF Strategy V3 | 0% | 223 days | Tue 26/06/18 | Thu 16/05/19
1.14.7.2.3.12 | Draft TAF Strategy V3 Issued for Comment | 0% | 0 days | Thu 16/05/19 | Thu 16/05/19
1.14.7.2.3.13 | Review Draft TAF Strategy V3 | 0% | 10 days | Fri 17/05/19 | Fri 31/05/19
1.14.7.2.3.14 | Update Draft TAF Strategy V3 | 0% | 5 days | Mon 03/06/19 | Fri 07/06/19
1.14.7.2.3.15 | TAF Strategy V3 Approved | 0% | 0 days | Fri 07/06/19 | Fri 07/06/19
1.14.7.2.3.16 | Produce Draft TAF Strategy V4 | 0% | 235 days | Mon 10/06/19 | Fri 15/05/20
1.14.7.2.3.17 | Draft TAF Strategy V4 Issued for Comment | 0% | 0 days | Fri 15/05/20 | Fri 15/05/20
1.14.7.2.3.18 | Review Draft TAF Strategy V4 | 0% | 10 days | Mon 18/05/20 | Mon 01/06/20
1.14.7.2.3.19 | Update Draft TAF Strategy V4 | 0% | 5 days | Tue 02/06/20 | Mon 08/06/20
1.14.7.2.3.20 | TAF Strategy V4 Approved | 0% | 0 days | Mon 08/06/20 | Mon 08/06/20
1.14.7.3 | TAF Operation During TP Contract | 42% | 663 days | Mon 31/07/17 | Tue 24/03/20
1.14.7.3.1 | TAF input to Assurance Review 1 | 100% | 45 days | Mon 31/07/17 | Mon 02/10/17
1.14.7.3.1.1 | CDO Plans AR1 TAF Working Groups | 100% | 10 days | Mon 31/07/17 | Fri 11/08/17
1.14.7.3.1.2 | CDO Issues AR1 Artefacts to TAF Working Group Members | 100% | 0 days | Fri 11/08/17 | Fri 11/08/17
1.14.7.3.1.3 | TAF Working Group Members Review & Discuss AR1 Artefacts | 100% | 30 days | Mon 14/08/17 | Mon 25/09/17
1.14.7.3.1.4 | CDO Develops Report on Conclusions and Recommendations of TAF AR1 Working Groups | 100% | 5 days | Tue 26/09/17 | Mon 02/10/17
1.14.7.3.1.5 | CDO Ready for AR1 | 100% | 0 days | Mon 02/10/17 | Mon 02/10/17
1.14.7.3.2 | TAF Surgeries | 100% | 34 days | Tue 03/10/17 | Fri 17/11/17
1.14.7.3.2.1 | Preparation for TAF Surgeries | 100% | 9 days | Tue 03/10/17 | Fri 13/10/17
1.14.7.3.2.2 | Hold TAF Surgeries | 100% | 5 days | Mon 16/10/17 | Fri 20/10/17
1.14.7.3.2.3 | First Surgery Complete | 100% | 0 days | Fri 20/10/17 | Fri 20/10/17
1.14.7.3.2.4 | Preparation for TAF Surgeries | 100% | 15 days | Mon 23/10/17 | Fri 10/11/17
1.14.7.3.2.5 | Hold TAF Surgeries | 100% | 5 days | Mon 13/11/17 | Fri 17/11/17
1.14.7.3.2.6 | Second Surgery Complete | 100% | 0 days | Fri 17/11/17 | Fri 17/11/17
1.14.7.3.3 | TAF input to Assurance Review 2 | 76% | 37 days | Tue 20/02/18 | Fri 13/04/18
1.14.7.3.3.1 | CDO Plans AR 2TAF Working Groups | 100% | 12 days | Tue 20/02/18 | Wed 07/03/18
1.14.7.3.3.2 | CDO Issues AR2 Artefacts to TAF Working Group Members | 100% | 0 days | Wed 07/03/18 | Wed 07/03/18
1.14.7.3.3.3 | TAF Working Group Members Review & Discuss AR2 Artefacts | 80% | 20 days | Thu 08/03/18 | Fri 06/04/18
1.14.7.3.3.4 | CDO Develops Report on Conclusions and Recommendations of AR2 TAF Working Groups | 0% | 5 days | Mon 09/04/18 | Fri 13/04/18
1.14.7.3.3.5 | CDO Ready for AR2 | 0% | 0 days | Fri 13/04/18 | Fri 13/04/18
1.14.7.3.4 | TAF input to Assurance Review 3 | 0% | 35 days | Mon 06/08/18 | Mon 24/09/18
1.14.7.3.4.1 | CDO Plans AR3 TAF Working Groups | 0% | 10 days | Mon 06/08/18 | Fri 17/08/18
1.14.7.3.4.2 | CDO Issues AR3 Artefacts to TAF Working Group Members | 0% | 0 days | Fri 17/08/18 | Fri 17/08/18
1.14.7.3.4.3 | TAF Working Group Members Review & Discuss AR3 Artefacts | 0% | 20 days | Mon 20/08/18 | Mon 17/09/18
1.14.7.3.4.4 | CDO Develops Report on Conclusions and Recommendations of TAF AR3 Working Groups | 0% | 5 days | Tue 18/09/18 | Mon 24/09/18
1.14.7.3.4.5 | CDO Ready for AR3 | 0% | 0 days | Mon 24/09/18 | Mon 24/09/18
1.14.7.3.5 | TAF input to Assurance Review 4 | 0% | 35 days | Wed 06/02/19 | Tue 26/03/19
1.14.7.3.5.1 | CDO Plans AR4 TAF Working Groups | 0% | 10 days | Wed 06/02/19 | Tue 19/02/19
1.14.7.3.5.2 | CDO Issues AR4 Artefacts to TAF Working Group Members | 0% | 0 days | Tue 19/02/19 | Tue 19/02/19
1.14.7.3.5.3 | TAF Working Group Members Review & Discuss AR4 Artefacts | 0% | 20 days | Wed 20/02/19 | Tue 19/03/19
1.14.7.3.5.4 | CDO Develops Report on Conclusions and Recommendations of TAF AR4 Working Groups | 0% | 5 days | Wed 20/03/19 | Tue 26/03/19
1.14.7.3.5.5 | CDO Ready for AR4 | 0% | 0 days | Tue 26/03/19 | Tue 26/03/19
1.14.7.3.6 | TAF input to Assurance Review 5 | 0% | 35 days | Mon 05/08/19 | Mon 23/09/19
1.14.7.3.6.1 | CDO Plans AR5 TAF Working Groups | 0% | 10 days | Mon 05/08/19 | Fri 16/08/19
1.14.7.3.6.2 | CDO Issues AR5 Artefacts to TAF Working Group Members | 0% | 0 days | Fri 16/08/19 | Fri 16/08/19
1.14.7.3.6.3 | TAF Working Group Members Review & Discuss AR5 Artefacts | 0% | 20 days | Mon 19/08/19 | Mon 16/09/19
1.14.7.3.6.4 | CDI Develops Report on Conclusions and Recommendations of TAF AR5 Working Groups | 0% | 5 days | Tue 17/09/19 | Mon 23/09/19
1.14.7.3.6.5 | CDO Ready for AR5 | 0% | 0 days | Mon 23/09/19 | Mon 23/09/19
1.14.7.3.7 | TAF input to Assurance Review 6 | 0% | 35 days | Wed 05/02/20 | Tue 24/03/20
1.14.7.3.7.1 | CDO Plans AR6 TAF Working Groups | 0% | 10 days | Wed 05/02/20 | Tue 18/02/20
1.14.7.3.7.2 | CDO Issues AR6 Artefacts to TAF Working Group Members | 0% | 0 days | Tue 18/02/20 | Tue 18/02/20
1.14.7.3.7.3 | TAF Working Group Members Review & Discuss AR6 Artefacts | 0% | 20 days | Wed 19/02/20 | Tue 17/03/20
1.14.7.3.7.4 | CDO Develops Report on Conclusions and Recommendations of TAF AR6 Working Groups | 0% | 5 days | Wed 18/03/20 | Tue 24/03/20
1.14.7.3.7.5 | CDO Review Complete for AR6 | 0% | 0 days | Tue 24/03/20 | Tue 24/03/20
1.14.7.4 | TAF Operation Post AR6 | 0% | 1249 days | Wed 25/03/20 | Mon 24/03/25
1.14.7.4.1 | Ongoing Industry Engagement | 0% | 1249 days | Wed 25/03/20 | Mon 24/03/25
1.14.8 | Architecture | 33% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.14.8.1 | Enduring Activities | 29% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.14.8.1.1 | Architecture Report on Progress (Monthly) | 28% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.14.8.1.2 | Conduct Architecture Assurance Reviews for TP Artefacts | 28% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.14.8.1.3 | Maintain MORPHEUS Service Architecture Plan | 55% | 38 days | Thu 01/03/18 | Wed 25/04/18
1.14.8.2 | Key Deliverables | 40% | 935 days | Mon 03/04/17 | Wed 23/12/20
1.14.8.2.1 | Architecture Management Plan | 27% | 935 days | Mon 03/04/17 | Wed 23/12/20
1.14.8.2.1.1 | Produce Draft AMP V2 | 100% | 140 days | Mon 03/04/17 | Fri 20/10/17
1.14.8.2.1.2 | Draft AMP V2 Issued for Comment | 100% | 0 days | Fri 20/10/17 | Fri 20/10/17
1.14.8.2.1.3 | Review Draft AMP V2 | 100% | 10 days | Mon 23/10/17 | Fri 03/11/17
1.14.8.2.1.4 | Update Draft AMP V2 | 100% | 5 days | Mon 06/11/17 | Fri 10/11/17
1.14.8.2.1.5 | AMP V2 Approved | 100% | 0 days | Fri 10/11/17 | Fri 10/11/17
1.14.8.2.1.6 | Produce Initial MORPHEUS Service Architecture Repository V4 | 100% | 78 days | Mon 13/11/17 | Thu 08/03/18
1.14.8.2.1.7 | Initial MORPHEUS Service Architecture Repository V4 Issued for Comment | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.14.8.2.1.8 | Review Initial MORPHEUS Service Architecture Repository V4 | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.14.8.2.1.9 | Update Initial MORPHEUS Service Architecture Repository V4 | 33% | 15 days | Fri 23/03/18 | Mon 16/04/18
1.14.8.2.1.10 | Initial MORPHEUS Service Architecture Repository V4 Approved | 0% | 0 days | Mon 16/04/18 | Mon 16/04/18
1.14.8.2.1.11 | Produce MORPHEUS Service Architecture Repository V5 | 0% | 35 days | Tue 17/04/18 | Wed 06/06/18
1.14.8.2.1.12 | MORPHEUS Service Architecture Repository V5 Issued for Comment | 0% | 0 days | Wed 06/06/18 | Wed 06/06/18
1.14.8.2.1.13 | Review MORPHEUS Service Architecture Repository V5 | 0% | 10 days | Thu 07/06/18 | Wed 20/06/18
1.14.8.2.1.14 | Update MORPHEUS Service Architecture Repository V5 | 0% | 5 days | Thu 21/06/18 | Wed 27/06/18
1.14.8.2.1.15 | MORPHEUS Service Architecture Repository V5 Approved | 0% | 0 days | Wed 27/06/18 | Wed 27/06/18
1.14.8.2.1.16 | Produce MORPHEUS Service Architecture Repository V6 | 0% | 136 days | Thu 28/06/18 | Mon 14/01/19
1.14.8.2.1.17 | MORPHEUS Service Architecture Repository V6 Issued for Comment | 0% | 0 days | Mon 14/01/19 | Mon 14/01/19
1.14.8.2.1.18 | Review MORPHEUS Service Architecture Repository V6 | 0% | 10 days | Tue 15/01/19 | Mon 28/01/19
1.14.8.2.1.19 | Update MORPHEUS Service Architecture Repository V6 | 0% | 5 days | Tue 29/01/19 | Mon 04/02/19
1.14.8.2.1.20 | MORPHEUS Service Architecture Repository V6 Approved | 0% | 0 days | Mon 04/02/19 | Mon 04/02/19
1.14.8.2.1.21 | Produce MORPHEUS Service Architecture Repository V7 | 0% | 108 days | Tue 05/02/19 | Wed 10/07/19
1.14.8.2.1.22 | MORPHEUS Service Architecture Repository V7 Issued for Comment | 0% | 0 days | Wed 10/07/19 | Wed 10/07/19
1.14.8.2.1.23 | Review MORPHEUS Service Architecture Repository V7 | 0% | 10 days | Thu 11/07/19 | Wed 24/07/19
1.14.8.2.1.24 | Update MORPHEUS Service Architecture Repository V7 | 0% | 5 days | Thu 25/07/19 | Wed 31/07/19
1.14.8.2.1.25 | MORPHEUS Service Architecture Repository V7 Approved | 0% | 0 days | Wed 31/07/19 | Wed 31/07/19
1.14.8.2.1.26 | Produce MORPHEUS Service Architecture Repository V8 | 0% | 108 days | Thu 01/08/19 | Wed 08/01/20
1.14.8.2.1.27 | MORPHEUS Service Architecture Repository V8 Issued for Comment | 0% | 0 days | Wed 08/01/20 | Wed 08/01/20
1.14.8.2.1.28 | Review MORPHEUS Service Architecture Repository V8 | 0% | 10 days | Thu 09/01/20 | Wed 22/01/20
1.14.8.2.1.29 | Update MORPHEUS Service Architecture Repository V8 | 0% | 5 days | Thu 23/01/20 | Wed 29/01/20
1.14.8.2.1.30 | MORPHEUS Service Architecture Repository V8 Approved | 0% | 0 days | Wed 29/01/20 | Wed 29/01/20
1.14.8.2.1.31 | Produce MORPHEUS Service Architecture Repository V9 | 0% | 111 days | Thu 30/01/20 | Wed 08/07/20
1.14.8.2.1.32 | MORPHEUS Service Architecture Repository V9 Issued for Comment | 0% | 0 days | Wed 08/07/20 | Wed 08/07/20
1.14.8.2.1.33 | Review MORPHEUS Service Architecture Repository V9 | 0% | 10 days | Thu 09/07/20 | Wed 22/07/20
1.14.8.2.1.34 | Update MORPHEUS Service Architecture Repository V9 | 0% | 5 days | Thu 23/07/20 | Wed 29/07/20
1.14.8.2.1.35 | MORPHEUS Service Architecture Repository V9 Approved | 0% | 0 days | Wed 29/07/20 | Wed 29/07/20
1.14.8.2.1.36 | Produce MORPHEUS Service Architecture Repository V10 | 0% | 89 days | Thu 30/07/20 | Wed 02/12/20
1.14.8.2.1.37 | MORPHEUS Service Architecture Repository V10 Issued for Comment | 0% | 0 days | Wed 02/12/20 | Wed 02/12/20
1.14.8.2.1.38 | Review MORPHEUS Service Architecture Repository V10 | 0% | 10 days | Thu 03/12/20 | Wed 16/12/20
1.14.8.2.1.39 | Update MORPHEUS Service Architecture Repository V10 | 0% | 5 days | Thu 17/12/20 | Wed 23/12/20
1.14.8.2.1.40 | MORPHEUS Service Architecture Repository V10 Approved | 0% | 0 days | Wed 23/12/20 | Wed 23/12/20
1.14.8.2.2 | MORPHEUS Service Architecture | 100% | 227 days | Mon 03/04/17 | Wed 28/02/18
1.14.8.2.2.1 | Produce Draft MSA V3 | 100% | 87 days | Mon 03/04/17 | Mon 07/08/17
1.14.8.2.2.2 | Draft MSA V3 Issued for Comment | 100% | 0 days | Mon 07/08/17 | Mon 07/08/17
1.14.8.2.2.3 | Review Draft MSA V3 | 100% | 10 days | Tue 08/08/17 | Mon 21/08/17
1.14.8.2.2.4 | Update Draft MSA V3 | 100% | 5 days | Tue 22/08/17 | Tue 29/08/17
1.14.8.2.2.5 | MSA V3 Approved | 100% | 0 days | Tue 29/08/17 | Tue 29/08/17
1.14.8.2.2.6 | Produce Draft MSA V4 | 100% | 100 days | Wed 30/08/17 | Wed 24/01/18
1.14.8.2.2.7 | Draft Architecture Management Plan Issued for Comment | 100% | 0 days | Wed 24/01/18 | Wed 24/01/18
1.14.8.2.2.8 | Review Draft Architecture Management Plan | 100% | 10 days | Thu 25/01/18 | Wed 07/02/18
1.14.8.2.2.9 | Update Draft Architecture Management Plan | 100% | 5 days | Thu 08/02/18 | Wed 14/02/18
1.14.8.2.2.10 | Architecture Management Plan Approved | 100% | 0 days | Wed 28/02/18 | Wed 28/02/18
1.14.9 | Safety and Environmental Management | 32% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.14.9.1 | Enduring Activities | 24% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.14.9.1.1 | Report on Progress for Safety & Environmental activities | 100% | 268 days | Mon 06/03/17 | Thu 29/03/18
1.14.9.1.2 | Support Management and Execution of TP Contract with respect to Safety and Environmental, Safety Strategy and Safety Framework | 28% | 953 days | Mon 06/03/17 | Mon 21/12/20
1.14.9.1.3 | Maintain the HIA | 4% | 714 days | Thu 22/02/18 | Thu 24/12/20
1.14.9.1.4 | Maintain the EISS Report | 18% | 839 days | Tue 22/08/17 | Thu 24/12/20
1.14.9.1.5 | Maintain the EIS Report | 18% | 839 days | Tue 22/08/17 | Thu 24/12/20
1.14.9.2 | Key Deliverables | 53% | 933 days | Mon 03/04/17 | Mon 21/12/20
1.14.9.2.1 | Safety & Environmental Committee TORs | 100% | 54 days | Mon 03/04/17 | Wed 21/06/17
1.14.9.2.1.1 | Produce Draft Safety & Environmental Committee TORs | 100% | 39 days | Mon 03/04/17 | Wed 31/05/17
1.14.9.2.1.2 | Draft Safety & Environmental Committee TORs Issued for Comment | 100% | 0 days | Wed 31/05/17 | Wed 31/05/17
1.14.9.2.1.3 | Review Draft Safety & Environmental Committee TORs | 100% | 10 days | Thu 01/06/17 | Wed 14/06/17
1.14.9.2.1.4 | Update Draft Safety & Environmental Committee TORs | 100% | 5 days | Thu 15/06/17 | Wed 21/06/17
1.14.9.2.1.5 | Safety & Environmental Committee TORs Approved | 100% | 0 days | Wed 21/06/17 | Wed 21/06/17
1.14.9.2.2 | Safety Strategy & Safety Framework | 100% | 54 days | Mon 03/04/17 | Wed 21/06/17
1.14.9.2.2.1 | Produce Draft Safety Strategy & Safety Framework | 100% | 39 days | Mon 03/04/17 | Wed 31/05/17
1.14.9.2.2.2 | Draft Safety Strategy & Safety Framework Issued for Comment | 100% | 0 days | Wed 31/05/17 | Wed 31/05/17
1.14.9.2.2.3 | Review Draft Safety Strategy & Safety Framework | 100% | 10 days | Thu 01/06/17 | Wed 14/06/17
1.14.9.2.2.4 | Update Draft Safety Strategy & Safety Framework | 100% | 5 days | Thu 15/06/17 | Wed 21/06/17
1.14.9.2.2.5 | Safety Strategy & Safety Framework Approved | 100% | 0 days | Wed 21/06/17 | Wed 21/06/17
1.14.9.2.3 | Safety and Environmental Management System | 0% | 54 days | Mon 03/04/17 | Wed 21/06/17
1.14.9.2.3.1 | Produce Draft SEMS | 0% | 39 days | Mon 03/04/17 | Wed 31/05/17
1.14.9.2.3.2 | Draft SEMS Issued for Comment | 0% | 0 days | Wed 31/05/17 | Wed 31/05/17
1.14.9.2.3.3 | Review Draft SEMS | 0% | 10 days | Thu 01/06/17 | Wed 14/06/17
1.14.9.2.3.4 | Update Draft SEMS | 0% | 5 days | Thu 15/06/17 | Wed 21/06/17
1.14.9.2.3.5 | SEMS Approved | 0% | 0 days | Wed 21/06/17 | Wed 21/06/17
1.14.9.2.4 | Safety and Environmental Management Plan (S&EMP) | 27% | 933 days | Mon 03/04/17 | Mon 21/12/20
1.14.9.2.4.1 | Produce Draft S&EMP V1 | 100% | 77 days | Mon 03/04/17 | Mon 24/07/17
1.14.9.2.4.2 | Draft S&EMP V1 Issued for Comment | 100% | 0 days | Mon 24/07/17 | Mon 24/07/17
1.14.9.2.4.3 | Review Draft S&EMP V1 | 100% | 10 days | Tue 25/07/17 | Mon 07/08/17
1.14.9.2.4.4 | Update Draft S&EMP V1 | 100% | 5 days | Tue 08/08/17 | Mon 14/08/17
1.14.9.2.4.5 | S&EMP V1 Approved | 100% | 0 days | Mon 14/08/17 | Mon 14/08/17
1.14.9.2.4.6 | Produce Draft S&EMP V2 | 100% | 73 days | Tue 15/08/17 | Fri 24/11/17
1.14.9.2.4.7 | Draft S&EMP V2 Issued for Comment | 100% | 0 days | Fri 24/11/17 | Fri 24/11/17
1.14.9.2.4.8 | Review Draft S&EMP V2 | 100% | 10 days | Mon 27/11/17 | Fri 08/12/17
1.14.9.2.4.9 | Update Draft S&EMP V2 | 100% | 4 days | Mon 11/12/17 | Thu 14/12/17
1.14.9.2.4.10 | S&EMP V2 Approved | 100% | 0 days | Fri 15/12/17 | Fri 15/12/17
1.14.9.2.4.11 | Produce Draft S&EMP V3 | 100% | 54 days | Fri 15/12/17 | Thu 08/03/18
1.14.9.2.4.12 | Draft S&EMP V3 Issued for Comment | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.14.9.2.4.13 | Review Draft S&EMP V3 | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.14.9.2.4.14 | Update Draft S&EMP V3 | 20% | 25 days | Fri 23/03/18 | Mon 30/04/18
1.14.9.2.4.15 | S&EMP V3 Approved | 0% | 0 days | Mon 30/04/18 | Mon 30/04/18
1.14.9.2.4.16 | Produce Draft S&EMP V4 | 0% | 15 days | Tue 01/05/18 | Tue 22/05/18
1.14.9.2.4.17 | Draft S&EMP V4 Issued for Comment | 0% | 0 days | Tue 22/05/18 | Tue 22/05/18
1.14.9.2.4.18 | Review Draft S&EMP V4 | 0% | 10 days | Wed 23/05/18 | Wed 06/06/18
1.14.9.2.4.19 | Update Draft S&EMP V4 | 0% | 5 days | Thu 07/06/18 | Wed 13/06/18
1.14.9.2.4.20 | S&EMP V4 Approved | 0% | 0 days | Wed 13/06/18 | Wed 13/06/18
1.14.9.2.4.21 | Produce Draft S&EMP V5 | 0% | 115 days | Thu 14/06/18 | Thu 22/11/18
1.14.9.2.4.22 | Draft S&EMP V5 Issued for Comment | 0% | 0 days | Thu 22/11/18 | Thu 22/11/18
1.14.9.2.4.23 | Review Draft S&EMP V5 | 0% | 10 days | Fri 23/11/18 | Thu 06/12/18
1.14.9.2.4.24 | Update Draft S&EMP V5 | 0% | 5 days | Fri 07/12/18 | Thu 13/12/18
1.14.9.2.4.25 | S&EMP V5 Approved | 0% | 0 days | Thu 13/12/18 | Thu 13/12/18
1.14.9.2.4.26 | Produce Draft S&EMP V6 | 0% | 115 days | Fri 14/12/18 | Thu 06/06/19
1.14.9.2.4.27 | Draft S&EMP V6 Issued for Comment | 0% | 0 days | Thu 06/06/19 | Thu 06/06/19
1.14.9.2.4.28 | Review Draft S&EMP V6 | 0% | 10 days | Fri 07/06/19 | Thu 20/06/19
1.14.9.2.4.29 | Update Draft S&EMP V6 | 0% | 5 days | Fri 21/06/19 | Thu 27/06/19
1.14.9.2.4.30 | S&EMP V6 Approved | 0% | 0 days | Thu 27/06/19 | Thu 27/06/19
1.14.9.2.4.31 | Produce Draft S&EMP V7 | 0% | 110 days | Fri 28/06/19 | Fri 29/11/19
1.14.9.2.4.32 | Draft S&EMP V7 Issued for Comment | 0% | 0 days | Fri 29/11/19 | Fri 29/11/19
1.14.9.2.4.33 | Review Draft S&EMP V7 | 0% | 10 days | Mon 02/12/19 | Fri 13/12/19
1.14.9.2.4.34 | Update Draft S&EMP V7 | 0% | 5 days | Mon 16/12/19 | Fri 20/12/19
1.14.9.2.4.35 | S&EMP V7 Approved | 0% | 0 days | Fri 20/12/19 | Fri 20/12/19
1.14.9.2.4.36 | Produce Draft S&EMP V8 | 0% | 110 days | Mon 23/12/19 | Fri 05/06/20
1.14.9.2.4.37 | Draft S&EMP V8 Issued for Comment | 0% | 0 days | Fri 05/06/20 | Fri 05/06/20
1.14.9.2.4.38 | Review Draft S&EMP V8 | 0% | 10 days | Mon 08/06/20 | Fri 19/06/20
1.14.9.2.4.39 | Update Draft S&EMP V8 | 0% | 5 days | Mon 22/06/20 | Fri 26/06/20
1.14.9.2.4.40 | S&EMP V8 Approved | 0% | 0 days | Fri 26/06/20 | Fri 26/06/20
1.14.9.2.4.41 | Produce Draft S&EMP V9 | 0% | 110 days | Mon 29/06/20 | Mon 30/11/20
1.14.9.2.4.42 | Draft S&EMP V9Issued for Comment | 0% | 0 days | Mon 30/11/20 | Mon 30/11/20
1.14.9.2.4.43 | Review Draft S&EMP V9 | 0% | 10 days | Tue 01/12/20 | Mon 14/12/20
1.14.9.2.4.44 | Update Draft S&EMP V9 | 0% | 5 days | Tue 15/12/20 | Mon 21/12/20
1.14.9.2.4.45 | S&EMP V9 Approved | 0% | 0 days | Mon 21/12/20 | Mon 21/12/20
1.14.9.2.5 | Hazard Identification and Analysis | 100% | 222 days | Mon 03/04/17 | Wed 21/02/18
1.14.9.2.5.1 | Produce Preliminary HIA | 100% | 207 days | Mon 03/04/17 | Wed 31/01/18
1.14.9.2.5.2 | Draft Preliminary HIA Issued for Comment | 100% | 0 days | Wed 31/01/18 | Wed 31/01/18
1.14.9.2.5.3 | Review Preliminary HIA | 100% | 10 days | Thu 01/02/18 | Wed 14/02/18
1.14.9.2.5.4 | Update Preliminary HIA | 100% | 5 days | Thu 15/02/18 | Wed 21/02/18
1.14.9.2.5.5 | Preliminary HIA Approved | 100% | 0 days | Wed 21/02/18 | Wed 21/02/18
1.14.9.2.6 | Environmental Screening and Scoping Exercise | 100% | 97 days | Mon 03/04/17 | Mon 21/08/17
1.14.9.2.6.1 | Produce Draft EISS Report | 100% | 82 days | Mon 03/04/17 | Mon 31/07/17
1.14.9.2.6.2 | Draft EISS Report Issues for Comment | 100% | 0 days | Mon 31/07/17 | Mon 31/07/17
1.14.9.2.6.3 | Review Draft EISS Report | 100% | 10 days | Tue 01/08/17 | Mon 14/08/17
1.14.9.2.6.4 | Update Draft EISS Report | 100% | 5 days | Tue 15/08/17 | Mon 21/08/17
1.14.9.2.6.5 | EISS Report Approved | 100% | 0 days | Mon 21/08/17 | Mon 21/08/17
1.14.9.2.7 | Environmental Statement | 100% | 97 days | Mon 03/04/17 | Mon 21/08/17
1.14.9.2.7.1 | Produce Draft EIS Report | 100% | 82 days | Mon 03/04/17 | Mon 31/07/17
1.14.9.2.7.2 | Draft EIS Report Issues for Comment | 100% | 0 days | Mon 31/07/17 | Mon 31/07/17
1.14.9.2.7.3 | Review Draft EIS Report | 100% | 10 days | Tue 01/08/17 | Mon 14/08/17
1.14.9.2.7.4 | Update Draft EIS Report | 100% | 5 days | Tue 15/08/17 | Mon 21/08/17
1.14.9.2.7.5 | EIS Report Approved | 100% | 0 days | Mon 21/08/17 | Mon 21/08/17
1.14.10 | Security | 14% | 2112 days | Mon 06/03/17 | Thu 14/08/25
1.14.10.1 | Enduring Activities | 13% | 2112 days | Mon 06/03/17 | Thu 14/08/25
1.14.10.1.1 | Report on Progress for Security activities (Monthly) | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.14.10.1.2 | Support Management and Execution of TP Contract with respect to Security | 27% | 940 days | Mon 27/03/17 | Wed 23/12/20
1.14.10.1.3 | Ongoing Security Working Groups | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.14.10.1.4 | Continue to update RMADS as Required | 23% | 896 days | Fri 02/06/17 | Thu 24/12/20
1.14.10.1.5 | Continue to review Security Management Plan as Required | 10% | 2050 days | Thu 25/05/17 | Tue 05/08/25
1.14.10.1.6 | Continue to review SADD as Required | 4% | 1924 days | Thu 30/11/17 | Thu 14/08/25
1.14.10.2 | Key Deliverables | 28% | 870 days | Mon 27/03/17 | Wed 16/09/20
1.14.10.2.1 | Security Management Plan | 100% | 40 days | Mon 27/03/17 | Wed 24/05/17
1.14.10.2.1.1 | Review first draft of the GD Security Management Plan | 100% | 10 days | Mon 27/03/17 | Fri 07/04/17
1.14.10.2.1.2 | GD Security Management Plan Review & update as required | 100% | 20 days | Mon 10/04/17 | Wed 10/05/17
1.14.10.2.1.3 | Security Management Plan Accepted | 100% | 10 days | Thu 11/05/17 | Wed 24/05/17
1.14.10.2.1.4 | Security Management Plan Initial Version Signed Off | 100% | 0 days | Wed 24/05/17 | Wed 24/05/17
1.14.10.2.2 | RMADS (Risk Management and Accreditation Document Set ) | 100% | 45 days | Mon 27/03/17 | Thu 01/06/17
1.14.10.2.2.1 | Produce RMADS first draft | 100% | 20 days | Mon 27/03/17 | Tue 25/04/17
1.14.10.2.2.2 | RMADS Review first draft and update as required | 100% | 10 days | Wed 26/04/17 | Wed 10/05/17
1.14.10.2.2.3 | RMADS Updated by DIAS | 100% | 15 days | Thu 11/05/17 | Thu 01/06/17
1.14.10.2.2.4 | RMADS Initial Version Signed Off by DIAS | 100% | 0 days | Thu 01/06/17 | Thu 01/06/17
1.14.10.2.3 | Security Risk and Vulnerability Register | 16% | 737 days | Thu 05/10/17 | Wed 16/09/20
1.14.10.2.3.1 | GD Set up the Security Risk and Vulnerability Register | 100% | 20 days | Thu 05/10/17 | Wed 01/11/17
1.14.10.2.3.2 | GD Maintain and Update the Security Risk and Vulnerability Register | 23% | 440 days | Thu 02/11/17 | Thu 08/08/19
1.14.10.2.3.3 | Security Risk and Vulnerability Register Set up & Passed to MOD | 0% | 0 days | Thu 08/08/19 | Thu 08/08/19
1.14.10.2.3.4 | Continue to review Security Risk and Vulnerability Register as Required | 0% | 277 days | Fri 09/08/19 | Wed 16/09/20
1.14.10.2.4 | Security Aspects Design Document | 100% | 40 days | Thu 05/10/17 | Wed 29/11/17
1.14.10.2.4.1 | Review first draft of the GD SADD | 100% | 10 days | Thu 05/10/17 | Wed 18/10/17
1.14.10.2.4.2 | GD SADD Review & updated as required | 100% | 20 days | Thu 19/10/17 | Wed 15/11/17
1.14.10.2.4.3 | SADD Accepted | 100% | 10 days | Thu 16/11/17 | Wed 29/11/17
1.14.10.2.4.4 | SADD Signed Off | 100% | 0 days | Wed 29/11/17 | Wed 29/11/17
1.14.11 | E3M | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.14.11.1 | Enduring Activities | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.14.11.1.1 | Report on Progress for E3M activities | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.14.11.1.2 | Support Management and Execution of TP Contract with respect to E3M | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.15 | Private Sector Support | 32% | 2303 days | Mon 06/03/17 | Fri 22/05/26
1.15.1 | CF AP2 Contract | 14% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.15.1.1 | Agree CF AP2 Contract | 100% | 20 days | Mon 06/03/17 | Fri 31/03/17
1.15.1.2 | PSS Management Support | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.15.1.3 | CF AP2 Contract Award | 100% | 0 days | Fri 31/03/17 | Fri 31/03/17
1.15.1.4 | End of CF AP2 Contract | 0% | 0 days | Tue 31/07/18 | Tue 31/07/18
1.15.2 | Competition for Private Sector Support - ITN | 89% | 328 days | Mon 06/03/17 | Wed 27/06/18
1.15.2.1 | Draft PSS SOR Available | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.15.2.2 | Review LFE from similar Competitions | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.15.2.3 | Complete PSS ISS Front Door Process | 100% | 5 days | Tue 07/03/17 | Mon 13/03/17
1.15.2.4 | Refine existing PSS SOR | 100% | 30 days | Tue 07/03/17 | Wed 19/04/17
1.15.2.5 | Obtain PSS Security Exemptions (If needed) | 100% | 15 days | Thu 20/04/17 | Thu 11/05/17
1.15.2.6 | Draft PSS PIN | 100% | 1 day | Mon 06/03/17 | Tue 07/03/17
1.15.2.7 | Commercial Approval of PSS PIN | 100% | 1 day | Wed 05/04/17 | Wed 05/04/17
1.15.2.8 | Issue PSS PIN | 100% | 1 day | Thu 06/04/17 | Thu 06/04/17
1.15.2.9 | PSS PIN Issued | 100% | 0 days | Thu 06/04/17 | Thu 06/04/17
1.15.2.10 | Draft PSS Procurement Strategy - Start | 100% | 2 days | Mon 06/03/17 | Tue 07/03/17
1.15.2.11 | Draft PSS Procurement Strategy - Completion | 100% | 2 days | Mon 06/03/17 | Tue 07/03/17
1.15.2.12 | Draft PSS Commercial Strategy | 100% | 5 days | Fri 07/04/17 | Thu 13/04/17
1.15.2.13 | Approve Draft PSS Procurement Strategy | 100% | 57 days | Wed 08/03/17 | Wed 31/05/17
1.15.2.14 | Approve Draft PSS Commercial Strategy | 100% | 18 days | Tue 18/04/17 | Fri 12/05/17
1.15.2.15 | PSS Procurement & Commercial Strategies Agreed | 100% | 0 days | Wed 31/05/17 | Wed 31/05/17
1.15.2.16 | Produce Draft PSS Commitment Case / 1 SMS Request | 100% | 30 days | Fri 21/04/17 | Mon 05/06/17
1.15.2.17 | Mature Draft PSS SOR | 100% | 17 days | Mon 15/05/17 | Wed 07/06/17
1.15.2.18 | Raise PSS RCA | 100% | 2 days | Tue 06/06/17 | Wed 07/06/17
1.15.2.19 | Approve PSS RCA | 100% | 1 day | Thu 08/06/17 | Thu 08/06/17
1.15.2.20 | Submit PSS RCA to Commercial | 100% | 1 day | Fri 09/06/17 | Fri 09/06/17
1.15.2.21 | PSS Requirement Sufficiently Mature to run Competition | 100% | 0 days | Fri 09/06/17 | Fri 09/06/17
1.15.2.22 | Draft & Approve PSS Contract Notice | 100% | 7 days | Mon 12/06/17 | Tue 20/06/17
1.15.2.23 | Produce PSS DPQQ Part 1 - Commercial | 100% | 15 days | Mon 12/06/17 | Fri 30/06/17
1.15.2.24 | Produce PSS DPQQ Part 2 - Technical | 100% | 15 days | Mon 12/06/17 | Fri 30/06/17
1.15.2.25 | Develop PSS Evaluation Criteria | 100% | 15 days | Wed 21/06/17 | Tue 11/07/17
1.15.2.26 | Issue PSS DPQQ to Tenderers | 100% | 1 day | Wed 12/07/17 | Wed 12/07/17
1.15.2.27 | PSS DPQQ Issued | 100% | 0 days | Wed 12/07/17 | Wed 12/07/17
1.15.2.28 | Tenderers Produce PSS DPQQ Responses | 100% | 22 days | Thu 13/07/17 | Fri 11/08/17
1.15.2.29 | BATCIS Manage PSS CQs | 100% | 17 days | Thu 13/07/17 | Fri 04/08/17
1.15.2.30 | PSS DPQQ Responses Received | 100% | 0 days | Fri 11/08/17 | Fri 11/08/17
1.15.2.31 | Evaluate & Moderation of PSS DPQQ Responses | 100% | 23 days | Mon 14/08/17 | Thu 14/09/17
1.15.2.32 | Notify PSS Down selected Tenderers | 100% | 1 day | Fri 22/09/17 | Fri 22/09/17
1.15.2.33 | Notify PSS Unsuccessful Tenderers | 100% | 1 day | Fri 22/09/17 | Fri 22/09/17
1.15.2.34 | Hold PSS Debrief Sessions | 0% | 3 days | Mon 25/09/17 | Wed 27/09/17
1.15.2.35 | Produce PSS ITN -Includes SOR Final Version | 100% | 103 days | Mon 12/06/17 | Thu 02/11/17
1.15.2.36 | Produce PSS Draft Contract | 100% | 103 days | Mon 12/06/17 | Thu 02/11/17
1.15.2.37 | Produce PSS Contract Management Plan | 100% | 103 days | Mon 12/06/17 | Thu 02/11/17
1.15.2.38 | PSS Defence Cyber Protection Partnership (DCPP) Risk Assessment | 100% | 1 day | Fri 03/11/17 | Fri 03/11/17
1.15.2.39 | Issue PSS ITN to Tenderers | 100% | 1 day | Mon 06/11/17 | Mon 06/11/17
1.15.2.40 | PSS ITN Issued | 100% | 0 days | Mon 06/11/17 | Mon 06/11/17
1.15.2.41 | Produce and Issue PSS Contract Bidders Notice | 100% | 1 day | Tue 07/11/17 | Tue 07/11/17
1.15.2.42 | Hold PSS Bidders Conference | 100% | 1 day | Wed 22/11/17 | Wed 22/11/17
1.15.2.43 | Hold Bidders One to Ones | 100% | 2 days | Mon 11/12/17 | Tue 12/12/17
1.15.2.44 | Tenderers Produces PSS ITN Response | 100% | 40 days | Tue 07/11/17 | Tue 09/01/18
1.15.2.45 | BATCIS Manage PSS CQs | 100% | 38 days | Tue 07/11/17 | Fri 05/01/18
1.15.2.46 | PSS ITN Responses Received | 100% | 0 days | Tue 09/01/18 | Tue 09/01/18
1.15.2.47 | Tender Board Process PSS Responses | 100% | 3 days | Wed 10/01/18 | Fri 12/01/18
1.15.2.48 | Tender Board Release PSS Responses to BATCIS Commercial | 100% | 0 days | Fri 12/01/18 | Fri 12/01/18
1.15.2.49 | Evaluation of PSS Affordability | 100% | 20 days | Mon 15/01/18 | Fri 09/02/18
1.15.2.50 | Evaluation of PSS T&Cs | 100% | 20 days | Mon 15/01/18 | Fri 09/02/18
1.15.2.51 | Individual Assessor Evaluation of PSS Technical & PM Aspects | 100% | 15 days | Mon 15/01/18 | Fri 02/02/18
1.15.2.52 | Achieve Consensus Evaluation of PSS Technical & PM Aspects | 100% | 10 days | Mon 05/02/18 | Fri 16/02/18
1.15.2.53 | Moderate results of PSS Evaluation | 100% | 5 days | Mon 19/02/18 | Fri 23/02/18
1.15.2.54 | Hold PSS TEP 2 | 100% | 5 days | Mon 26/02/18 | Fri 02/03/18
1.15.2.55 | PSS TEP 2 Held | 100% | 0 days | Fri 02/03/18 | Fri 02/03/18
1.15.2.56 | Prepare for PSS Negotiation | 100% | 12 days | Mon 05/03/18 | Tue 20/03/18
1.15.2.57 | Provide Draft Commitment Case and SMS Case for JFC & ARMY HQ | 0% | 0 days | Thu 05/04/18 | Thu 05/04/18
1.15.2.58 | Negotiate with PSS | 32% | 22 days | Wed 21/03/18 | Mon 23/04/18
1.15.2.59 | Industry Prepare and Submit PSS BAFO | 0% | 9 days | Tue 24/04/18 | Fri 04/05/18
1.15.2.60 | PSS BAFO Received | 0% | 0 days | Fri 04/05/18 | Fri 04/05/18
1.15.2.61 | Individual Assessor Evaluation of PSS BAFO Technical & PM Aspects | 0% | 9 days | Tue 08/05/18 | Fri 18/05/18
1.15.2.62 | Achieve Consensus Evaluation of PSS BAFO Technical & PM Aspects | 0% | 9 days | Tue 08/05/18 | Fri 18/05/18
1.15.2.63 | Evaluation of PSS BAFO Affordability | 0% | 9 days | Tue 08/05/18 | Fri 18/05/18
1.15.2.64 | Moderate & Agree Results of PSS BAFO Technical & PM Evaluation | 0% | 5 days | Mon 21/05/18 | Fri 25/05/18
1.15.2.65 | Hold Post PSS BAFO TEP 3A | 0% | 1 day | Tue 29/05/18 | Tue 29/05/18
1.15.2.66 | Interview Led Assessment | 0% | 1 day | Tue 05/06/18 | Tue 05/06/18
1.15.2.67 | Hold Post PSS ILA P TEP 3B | 0% | 1 day | Wed 06/06/18 | Wed 06/06/18
1.15.2.68 | Notify PSS Tenderers of Result of Competition | 0% | 1 day | Thu 07/06/18 | Thu 07/06/18
1.15.2.69 | Finalise PSS Contract | 0% | 8 days | Fri 08/06/18 | Tue 19/06/18
1.15.2.70 | Debrief Unsuccessful PSS Tenderers | 0% | 8 days | Fri 08/06/18 | Tue 19/06/18
1.15.2.71 | PSS Contract Standstill Period | 0% | 8 days | Fri 08/06/18 | Tue 19/06/18
1.15.2.72 | Send Final SMS Case to JFC & ARMY HQ for Sign Off | 0% | 8 days | Fri 08/06/18 | Tue 19/06/18
1.15.2.73 | Award PSS Contract | 0% | 1 day | Wed 20/06/18 | Wed 20/06/18
1.15.2.74 | PSS Contract Awarded | 0% | 0 days | Wed 20/06/18 | Wed 20/06/18
1.15.2.75 | PSS Contract Mobilisation | 0% | 5 days | Thu 21/06/18 | Wed 27/06/18
1.15.3 | PSS Contract | 0% | 1246 days | Wed 27/06/18 | Thu 22/06/23
1.15.3.1 | PSS (Re-Competed) Contract Start Date | 0% | 0 days | Wed 27/06/18 | Wed 27/06/18
1.15.3.2 | PSS Handover Completed | 0% | 0 days | Tue 31/07/18 | Tue 31/07/18
1.15.3.3 | End of PSS Three Years of Support | 0% | 0 days | Thu 24/06/21 | Thu 24/06/21
1.15.3.4 | End of PSS Fourth Year of Support | 0% | 0 days | Thu 23/06/22 | Thu 23/06/22
1.15.3.5 | End of PSS Fifth year of Support | 0% | 0 days | Thu 22/06/23 | Thu 22/06/23
1.15.4 | Private Sector Support Re-Compete | 0% | 339 days | Mon 17/01/22 | Thu 25/05/23
1.15.4.1 | Start Prep for PSS Re-Compete Competition | 0% | 0 days | Mon 17/01/22 | Mon 17/01/22
1.15.4.2 | Develop SOR | 0% | 8 days | Tue 18/01/22 | Thu 27/01/22
1.15.4.3 | Run ITN Competition | 0% | 331 days | Fri 28/01/22 | Thu 25/05/23
1.15.5 | New PSS Contract | 0% | 748 days | Thu 25/05/23 | Fri 22/05/26
1.15.5.1 | New PSS Contract Start Date | 0% | 0 days | Thu 25/05/23 | Thu 25/05/23
1.15.5.2 | End of Three years of New PSS Support | 0% | 0 days | Fri 22/05/26 | Fri 22/05/26
1.16 | System Integration | 0% | 1770 days | Fri 08/06/18 | Mon 07/07/25
1.16.1 | System Integration Competition - ITN | 0% | 474 days | Fri 08/06/18 | Wed 29/04/20
1.16.1.1 | Produce SI Competition Data Pack | 0% | 140 days | Fri 08/06/18 | Fri 21/12/18
1.16.1.2 | Mature SI Data Pack Available | 0% | 0 days | Fri 21/12/18 | Fri 21/12/18
1.16.1.3 | Start SI Competition | 0% | 0 days | Fri 28/09/18 | Fri 28/09/18
1.16.1.4 | Review LFE from similar Competitions | 0% | 1 day | Mon 01/10/18 | Mon 01/10/18
1.16.1.5 | Complete SI ISS Front Door Process | 0% | 5 days | Tue 02/10/18 | Mon 08/10/18
1.16.1.6 | Refine existing SI SOR | 0% | 10 days | Mon 24/12/18 | Mon 14/01/19
1.16.1.7 | Obtain SI Security Exemptions and Security Aspects Letter (If needed) | 0% | 15 days | Tue 15/01/19 | Mon 04/02/19
1.16.1.8 | Draft SI PIN | 0% | 3 days | Tue 05/02/19 | Thu 07/02/19
1.16.1.9 | Commercial Approval of SI PIN | 0% | 1 day | Fri 08/02/19 | Fri 08/02/19
1.16.1.10 | Issue SI PIN | 0% | 1 day | Mon 11/02/19 | Mon 11/02/19
1.16.1.11 | PIN IS Issued | 0% | 0 days | Mon 11/02/19 | Mon 11/02/19
1.16.1.12 | Draft SI Procurement Strategy - Start | 0% | 5 days | Tue 12/02/19 | Mon 18/02/19
1.16.1.13 | Draft SI Procurement Strategy - Completion | 0% | 10 days | Tue 19/02/19 | Mon 04/03/19
1.16.1.14 | Draft SI Commercial Strategy | 0% | 15 days | Tue 19/02/19 | Mon 11/03/19
1.16.1.15 | Approve SI Procurement Strategy | 0% | 5 days | Tue 05/03/19 | Mon 11/03/19
1.16.1.16 | Approve SI Commercial Strategy | 0% | 5 days | Tue 12/03/19 | Mon 18/03/19
1.16.1.17 | SI Procurement & Commercial Strategies Agreed | 0% | 0 days | Mon 18/03/19 | Mon 18/03/19
1.16.1.18 | Raise SI RCA | 0% | 1 day | Tue 19/03/19 | Tue 19/03/19
1.16.1.19 | Approve SI RCA | 0% | 1 day | Wed 20/03/19 | Wed 20/03/19
1.16.1.20 | Submit SI RCA to Commercial | 0% | 1 day | Thu 21/03/19 | Thu 21/03/19
1.16.1.21 | SI Requirement Sufficiently Mature to run Competition | 0% | 0 days | Thu 21/03/19 | Thu 21/03/19
1.16.1.22 | Draft SI & Approve Contract Notice | 0% | 1 day | Fri 22/03/19 | Fri 22/03/19
1.16.1.23 | Produce SI DPQQ Part 1 - Commercial | 0% | 22 days | Mon 25/03/19 | Thu 25/04/19
1.16.1.24 | Produce SI DPQQ Part 2 - Technical | 0% | 22 days | Mon 25/03/19 | Thu 25/04/19
1.16.1.25 | Develop SI Evaluation Criteria | 0% | 15 days | Mon 25/03/19 | Fri 12/04/19
1.16.1.26 | Issue SI DPQQ to Tenderers | 0% | 1 day | Fri 26/04/19 | Fri 26/04/19
1.16.1.27 | SI DPQQ Issued | 0% | 0 days | Fri 26/04/19 | Fri 26/04/19
1.16.1.28 | Tenderers Produce SI DPQQ Responses | 0% | 22 days | Mon 29/04/19 | Thu 30/05/19
1.16.1.29 | BATCIS Manage SI CQs | 0% | 17 days | Mon 29/04/19 | Wed 22/05/19
1.16.1.30 | SI DPQQ Responses Received | 0% | 0 days | Thu 30/05/19 | Thu 30/05/19
1.16.1.31 | Evaluate SI DPQQ Responses | 0% | 15 days | Fri 31/05/19 | Thu 20/06/19
1.16.1.32 | Notify Down selected SI Tenderers | 0% | 5 days | Fri 21/06/19 | Thu 27/06/19
1.16.1.33 | Notify Unsuccessful SI Tenderers | 0% | 1 day | Fri 28/06/19 | Fri 28/06/19
1.16.1.34 | Hold SI Debrief Sessions | 0% | 6 days | Mon 01/07/19 | Mon 08/07/19
1.16.1.35 | Produce SI ITN | 0% | 50 days | Fri 22/03/19 | Wed 05/06/19
1.16.1.36 | Produce Draft SI Contract | 0% | 50 days | Fri 22/03/19 | Wed 05/06/19
1.16.1.37 | Produce SI Contract Management Plan | 0% | 50 days | Fri 22/03/19 | Wed 05/06/19
1.16.1.38 | SI Defence Cyber Protection Partnership (DCPP) Risk Assessment | 0% | 1 day | Thu 06/06/19 | Thu 06/06/19
1.16.1.39 | Issue SI ITN to Tenderers | 0% | 1 day | Tue 09/07/19 | Tue 09/07/19
1.16.1.40 | SI ITN Issued | 0% | 0 days | Tue 09/07/19 | Tue 09/07/19
1.16.1.41 | Produce and Issue SI Contract Bidders Notice | 0% | 1 day | Wed 10/07/19 | Wed 10/07/19
1.16.1.42 | Hold SI Bidders Conference | 0% | 1 day | Thu 11/07/19 | Thu 11/07/19
1.16.1.43 | Tenderers Produce SI ITN Response | 0% | 40 days | Wed 10/07/19 | Wed 04/09/19
1.16.1.44 | BATCIS Manage SI CQs | 0% | 30 days | Wed 10/07/19 | Tue 20/08/19
1.16.1.45 | SI ITN Responses Received | 0% | 0 days | Wed 04/09/19 | Wed 04/09/19
1.16.1.46 | Hold Evaluators Briefing | 0% | 1 day | Thu 05/09/19 | Thu 05/09/19
1.16.1.47 | Tender Board Process SI Responses | 0% | 4 days | Fri 06/09/19 | Wed 11/09/19
1.16.1.48 | Tender Board Release SI Responses to BATCIS Commercial | 0% | 0 days | Wed 11/09/19 | Wed 11/09/19
1.16.1.49 | Evaluation of SI Affordability | 0% | 20 days | Thu 12/09/19 | Wed 09/10/19
1.16.1.50 | Evaluation of SI T&Cs | 0% | 20 days | Thu 12/09/19 | Wed 09/10/19
1.16.1.51 | Individual Assessor Evaluation of SI Technical & PM Aspects | 0% | 15 days | Thu 12/09/19 | Wed 02/10/19
1.16.1.52 | Achieve Consensus Evaluation of SI Technical & PM Aspects | 0% | 10 days | Thu 03/10/19 | Wed 16/10/19
1.16.1.53 | Moderate results of SI Evaluation | 0% | 5 days | Thu 17/10/19 | Wed 23/10/19
1.16.1.54 | Hold SI TEP | 0% | 1 day | Thu 24/10/19 | Thu 24/10/19
1.16.1.55 | SI TEP Held | 0% | 0 days | Thu 24/10/19 | Thu 24/10/19
1.16.1.56 | Prepare for SI Negotiation | 0% | 20 days | Fri 25/10/19 | Thu 21/11/19
1.16.1.57 | Negotiate with SI | 0% | 25 days | Fri 22/11/19 | Fri 03/01/20
1.16.1.58 | Industry Prepare and Submit SI BAFO | 0% | 10 days | Mon 06/01/20 | Fri 17/01/20
1.16.1.59 | SI BAFO Received | 0% | 0 days | Fri 17/01/20 | Fri 17/01/20
1.16.1.60 | Individual Assessor Evaluation of SI BAFO Technical & PM Aspects | 0% | 5 days | Mon 20/01/20 | Fri 24/01/20
1.16.1.61 | Achieve Consensus Evaluation of SI BAFO Technical & PM Aspects | 0% | 5 days | Mon 27/01/20 | Fri 31/01/20
1.16.1.62 | Evaluation of SI BAFO Affordability | 0% | 10 days | Mon 20/01/20 | Fri 31/01/20
1.16.1.63 | Moderate & Agree Results of SI BAFO Technical & PM Evaluation | 0% | 5 days | Mon 03/02/20 | Fri 07/02/20
1.16.1.64 | Hold Post SI BAFO TEP | 0% | 1 day | Mon 10/02/20 | Mon 10/02/20
1.16.1.65 | Produce SI Commitment Case / 2 SMS Requests | 0% | 25 days | Tue 11/02/20 | Mon 16/03/20
1.16.1.66 | Notify Tenderers of Result of SI Competition | 0% | 1 day | Tue 17/03/20 | Tue 17/03/20
1.16.1.67 | Finalise SI Contract | 0% | 10 days | Wed 18/03/20 | Tue 31/03/20
1.16.1.68 | Debrief Unsuccessful SI Tenderers | 0% | 15 days | Wed 18/03/20 | Tue 07/04/20
1.16.1.69 | SI Contract Standstill Period | 0% | 8 days | Wed 08/04/20 | Tue 21/04/20
1.16.1.70 | Award SI Contract | 0% | 1 day | Wed 22/04/20 | Wed 22/04/20
1.16.1.71 | SI Contract Awarded * | 0% | 0 days | Wed 22/04/20 | Wed 22/04/20
1.16.1.72 | SI Contract Mobilisation | 0% | 5 days | Thu 23/04/20 | Wed 29/04/20
1.16.1.73 | SI Contract Start Date | 0% | 0 days | Wed 29/04/20 | Wed 29/04/20
1.16.2 | System Integrator Contract | 0% | 1296 days | Thu 30/04/20 | Mon 07/07/25
1.16.2.1 | Handover period with GD | 0% | 125 days | Thu 30/04/20 | Mon 26/10/20
1.16.2.2 | New System Integrator Fully Operational (Years 1 to 3) | 0% | 627 days | Mon 04/01/21 | Wed 05/07/23
1.16.2.3 | Fourth Year of New SI Integrator | 0% | 251 days | Thu 06/07/23 | Fri 05/07/24
1.16.2.4 | Fifth Year of New SI Integrator | 0% | 250 days | Mon 08/07/24 | Mon 07/07/25
1.16.2.5 | End Of Competed SI Contract | 0% | 0 days | Mon 07/07/25 | Mon 07/07/25
1.17 | Platform Integrator | 30% | 931 days | Mon 06/03/17 | Thu 19/11/20
1.17.1 | Dependencies from GD to BATCIS | 0% | 654 days | Thu 29/06/17 | Mon 10/02/20
1.17.1.1 | GD Supply Platform Installation Guidelines Document (Draft) | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.17.1.2 | GD Supply System BOM (Draft) | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.17.1.3 | GD Supply Generic Complex Fit PSD (Draft) | 100% | 0 days | Thu 29/06/17 | Thu 29/06/17
1.17.1.4 | GD Supply Platform Installation Guidelines Document (Baselined) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.5 | GD Supply System BOM (Baselined) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.6 | GD Supply Generic EvO Fit PSD, inc. Complex Fit with VIP Panel (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.7 | GD Supply Remaining PSDs for EvO Fits (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.8 | GD Supply Remaining BOMs (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.9 | GD Supply Cable Specification Document (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.10 | GD Supply IKEE Cables and best available MPPS Space Models | 0% | 0 days | Thu 03/05/18 | Thu 03/05/18
1.17.1.11 | GD Supply Cable ICDs (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.12 | GD Supply Product EMC Information (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.13 | GD Supply Product Tempest Information (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.14 | GD Supply CAT Testing Procedures (Draft) | 0% | 0 days | Tue 03/04/18 | Tue 03/04/18
1.17.1.15 | GD Supply PPM or Final Space Models for Two Platforms (1 legacy, 1 Future) | 0% | 0 days | Tue 29/01/19 | Tue 29/01/19
1.17.1.16 | GD Supply Product Safety Cases (Mature Hazard log and ALARP) | 0% | 0 days | Wed 03/04/19 | Wed 03/04/19
1.17.1.17 | GD Supply QTMs for 3 Platforms (2 Legacy, 1 Future) | 0% | 0 days | Mon 09/12/19 | Mon 09/12/19
1.17.1.18 | GD Supply QTMs for the remaining 7 Platforms - 10 in Total | 0% | 0 days | Fri 31/01/20 | Fri 31/01/20
1.17.1.19 | GD Supply CAT Testing Procedures (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.1.20 | GD Supply Equipment Maintenance Procedures (Latest Version available at Feb 2020) | 0% | 0 days | Mon 10/02/20 | Mon 10/02/20
1.17.1.21 | GD Supply Generic Complex Fit PSD (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.1.22 | GD Supply Remaining PSDs for EvO Fits (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.1.23 | GD Supply Remaining BOMs (Latest version as at Feb 2020) | 0% | 0 days | Mon 10/02/20 | Mon 10/02/20
1.17.1.24 | GD Supply Cable Specification Document (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.1.25 | GD Supply Cable ICDs (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.1.26 | GD Supply Product EMC Information (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.1.27 | GD Supply Product Tempest Information (Final) | 0% | 0 days | Mon 30/09/19 | Mon 30/09/19
1.17.2 | Dependencies from BATCIS to GD | 0% | 921 days | Fri 17/03/17 | Thu 19/11/20
1.17.2.1 | MOD Supply GD with Platform Survey Report | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.17.2.2 | FOT Field Test Readiness Review Complete * | 0% | 0 days | Wed 14/10/20 | Wed 14/10/20
1.17.2.3 | FOT Field Tests Completed * | 0% | 0 days | Thu 19/11/20 | Thu 19/11/20
1.17.3 | Surveys and Use Case | 86% | 306 days | Mon 06/03/17 | Fri 25/05/18
1.17.3.1 | Produce Report on all PI Platform Surveys | 100% | 10 days | Mon 06/03/17 | Fri 17/03/17
1.17.3.2 | PI Platform Survey Report Issued | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.17.3.3 | BATCIS/Army Decide PI FOT Platform Types | 100% | 60 days | Mon 20/03/17 | Thu 15/06/17
1.17.3.4 | Produce PI FOT Use Case | 81% | 200 days | Mon 07/08/17 | Fri 25/05/18
1.17.3.5 | PI FOT Use Case Produced | 0% | 0 days | Fri 25/05/18 | Fri 25/05/18
1.17.4 | MIDAC Competition -ITN | 82% | 384 days | Mon 06/03/17 | Fri 14/09/18
1.17.4.1 | Mature MIDAC SOR Available | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.17.4.2 | Review LFE from similar MIDAC Competitions | 100% | 3 days | Thu 16/03/17 | Mon 20/03/17
1.17.4.3 | Complete MIDAC ISS Front Door Process | 0% | 5 days | Tue 21/03/17 | Mon 27/03/17
1.17.4.4 | Refine existing MIDAC SOR | 100% | 8 days | Wed 08/03/17 | Fri 17/03/17
1.17.4.5 | Obtain Security Exemptions (If needed) | 100% | 20 days | Tue 21/03/17 | Wed 19/04/17
1.17.4.6 | Draft MIDAC PIN | 100% | 1 day | Thu 20/04/17 | Thu 20/04/17
1.17.4.7 | Commercial Approval of MIDAC PIN | 100% | 1 day | Fri 21/04/17 | Fri 21/04/17
1.17.4.8 | Issue MIDAC PIN | 100% | 1 day | Mon 24/04/17 | Mon 24/04/17
1.17.4.9 | MIDAC PIN Issued | 100% | 0 days | Mon 24/04/17 | Mon 24/04/17
1.17.4.10 | Draft MIDAC Procurement Strategy - Start | 100% | 7 days | Tue 25/04/17 | Thu 04/05/17
1.17.4.11 | Draft MIDAC Procurement Strategy - Completion | 100% | 15 days | Fri 05/05/17 | Thu 25/05/17
1.17.4.12 | Draft MIDAC Commercial Strategy | 100% | 15 days | Fri 05/05/17 | Thu 25/05/17
1.17.4.13 | Approve MIDAC Procurement Strategy | 100% | 4 days | Thu 25/05/17 | Thu 01/06/17
1.17.4.14 | Approve MIDAC Commercial Strategy | 100% | 4 days | Fri 26/05/17 | Thu 01/06/17
1.17.4.15 | MIDAC Procurement & Commercial Strategies Agreed | 100% | 0 days | Thu 01/06/17 | Thu 01/06/17
1.17.4.16 | Raise MIDAC RCA | 100% | 19 days | Fri 02/06/17 | Wed 28/06/17
1.17.4.17 | Approve MIDAC RCA | 100% | 1 day | Thu 29/06/17 | Thu 29/06/17
1.17.4.18 | Submit MIDAC RCA to Commercial | 100% | 10 days | Fri 30/06/17 | Thu 13/07/17
1.17.4.19 | MIDAC Requirement Sufficiently Mature to run Competition | 100% | 0 days | Thu 13/07/17 | Thu 13/07/17
1.17.4.20 | Draft & Approve MIDAC Contract Notice | 100% | 3 days | Fri 30/06/17 | Tue 04/07/17
1.17.4.21 | Produce MIDAC DPQQ Part 1 - Commercial | 100% | 22 days | Tue 04/07/17 | Wed 02/08/17
1.17.4.22 | Produce MIDAC DPQQ Part 2 - Technical | 100% | 22 days | Tue 04/07/17 | Wed 02/08/17
1.17.4.23 | Develop MIDAC Evaluation Criteria | 100% | 15 days | Tue 04/07/17 | Mon 24/07/17
1.17.4.24 | Issue MIDAC DPQQ to Tenderers | 100% | 2 days | Thu 03/08/17 | Fri 04/08/17
1.17.4.25 | MIDAC DPQQ Issued | 100% | 0 days | Fri 04/08/17 | Fri 04/08/17
1.17.4.26 | Tenderers Produce MIDAC DPQQ Responses | 100% | 21 days | Mon 07/08/17 | Tue 05/09/17
1.17.4.27 | BATCIS Manage MIDAC CQs | 100% | 16 days | Mon 07/08/17 | Tue 29/08/17
1.17.4.28 | MIDAC DPQQ Responses Received | 100% | 0 days | Tue 05/09/17 | Tue 05/09/17
1.17.4.29 | Evaluate and Moderation of MIDAC DPQQ Responses | 100% | 12 days | Wed 06/09/17 | Thu 21/09/17
1.17.4.30 | Notify Down selected MIDAC Tenderers | 100% | 9 days | Fri 29/09/17 | Wed 11/10/17
1.17.4.31 | Notify Unsuccessful MIDAC Tenderers | 100% | 1 day | Thu 12/10/17 | Thu 12/10/17
1.17.4.32 | Hold MIDAC Debrief Sessions | 100% | 6 days | Fri 13/10/17 | Fri 20/10/17
1.17.4.33 | Produce MIDAC ITN | 100% | 99 days | Fri 14/07/17 | Thu 30/11/17
1.17.4.34 | Produce Draft MIDAC Contract | 100% | 97 days | Fri 14/07/17 | Tue 28/11/17
1.17.4.35 | Produce MIDAC Contract Management Plan | 100% | 97 days | Fri 14/07/17 | Tue 28/11/17
1.17.4.36 | MIDAC Defence Cyber Protection Partnership (DCPP) Risk Assessment | 100% | 1 day | Wed 29/11/17 | Wed 29/11/17
1.17.4.37 | Issue MIDAC ITN to Tenderers | 100% | 1 day | Fri 01/12/17 | Fri 01/12/17
1.17.4.38 | MIDAC ITN Issued | 100% | 0 days | Fri 01/12/17 | Fri 01/12/17
1.17.4.39 | Produce and Issue MIDAC Contract Bidders Notice | 100% | 1 day | Mon 04/12/17 | Mon 04/12/17
1.17.4.40 | Hold MIDAC Bidders Conference | 100% | 1 day | Tue 12/12/17 | Wed 13/12/17
1.17.4.41 | Tenderers Produces MIDAC ITN Response | 100% | 30 days | Mon 04/12/17 | Mon 22/01/18
1.17.4.42 | BATCIS Manage MIDAC CQs | 100% | 30 days | Mon 04/12/17 | Mon 22/01/18
1.17.4.43 | MIDAC ITN Responses Received | 100% | 0 days | Mon 22/01/18 | Mon 22/01/18
1.17.4.44 | Tender Board Process MIDAC Responses | 100% | 36 days | Tue 23/01/18 | Tue 13/03/18
1.17.4.45 | Revised Tender Board Process MIDAC Responses | 100% | 1 day | Wed 14/03/18 | Wed 14/03/18
1.17.4.46 | Revised Tender Board Release MIDAC Responses to BATCIS Commercial | 100% | 0 days | Wed 14/03/18 | Wed 14/03/18
1.17.4.47 | Evaluation of MIDAC Affordability | 61% | 18 days | Thu 15/03/18 | Wed 11/04/18
1.17.4.48 | Evaluation of MIDAC T&Cs | 61% | 18 days | Thu 15/03/18 | Wed 11/04/18
1.17.4.49 | Individual Assessor Evaluation of MIDAC Technical & PM Aspects | 100% | 10 days | Thu 15/03/18 | Wed 28/03/18
1.17.4.50 | Achieve Consensus Evaluation of MIDAC Technical & PM Aspects | 20% | 5 days | Thu 29/03/18 | Fri 06/04/18
1.17.4.51 | Moderate results of MIDAC Evaluation | 0% | 2 days | Thu 12/04/18 | Fri 13/04/18
1.17.4.52 | Hold MIDAC TEP | 0% | 1 day | Mon 16/04/18 | Mon 16/04/18
1.17.4.53 | MIDAC TEP Held | 0% | 0 days | Mon 16/04/18 | Mon 16/04/18
1.17.4.54 | Prepare for MIDAC Negotiation | 0% | 15 days | Tue 17/04/18 | Tue 08/05/18
1.17.4.55 | Negotiate with MIDAC | 0% | 20 days | Wed 09/05/18 | Wed 06/06/18
1.17.4.56 | MIDAC Prepare and Submit BAFO | 0% | 10 days | Thu 07/06/18 | Wed 20/06/18
1.17.4.57 | MIDAC BAFO Received | 0% | 0 days | Wed 20/06/18 | Wed 20/06/18
1.17.4.58 | Individual Assessor Evaluation of MIDAC BAFO Technical & PM Aspects | 0% | 7 days | Thu 21/06/18 | Fri 29/06/18
1.17.4.59 | Achieve Consensus Evaluation of MIDAC BAFO Technical & PM Aspects | 0% | 3 days | Mon 02/07/18 | Wed 04/07/18
1.17.4.60 | Evaluation of MIDAC BAFO Affordability | 0% | 10 days | Thu 21/06/18 | Wed 04/07/18
1.17.4.61 | Moderate & Agree Results of MIDAC BAFO Technical & PM Evaluation | 0% | 5 days | Thu 05/07/18 | Wed 11/07/18
1.17.4.62 | Hold Post MIDAC BAFO TEP | 0% | 1 day | Thu 12/07/18 | Thu 12/07/18
1.17.4.63 | Produce MIDAC Commitment Case / 2 SMS Requests | 0% | 15 days | Fri 13/07/18 | Thu 02/08/18
1.17.4.64 | Notify Tenderers of Result of MIDAC Competition | 0% | 1 day | Fri 03/08/18 | Fri 03/08/18
1.17.4.65 | Finalise MIDAC Contract | 0% | 10 days | Mon 06/08/18 | Fri 17/08/18
1.17.4.66 | Debrief Unsuccessful MIDAC Tenderers | 0% | 15 days | Mon 06/08/18 | Fri 24/08/18
1.17.4.67 | MIDAC Contract Standstill Period | 0% | 8 days | Tue 28/08/18 | Thu 06/09/18
1.17.4.68 | Award MIDAC Contract | 0% | 1 day | Fri 07/09/18 | Fri 07/09/18
1.17.4.69 | MIDAC Contract Awarded * | 0% | 0 days | Fri 07/09/18 | Fri 07/09/18
1.17.4.70 | MIDAC Contract Mobilisation | 0% | 5 days | Mon 10/09/18 | Fri 14/09/18
1.17.4.71 | MIDAC Contract Start Date | 0% | 0 days | Fri 14/09/18 | Fri 14/09/18
1.17.5 | MIDAC Project | 6% | 801 days | Mon 11/09/17 | Thu 19/11/20
1.17.5.1 | Collate BCIP 5.6 Design Lines | 0% | 5 days | Mon 17/09/18 | Fri 21/09/18
1.17.5.2 | Organise Design Line Workshop | 0% | 5 days | Mon 17/09/18 | Fri 21/09/18
1.17.5.3 | MOR Design Line Rationalisation Workshop | 0% | 5 days | Mon 24/09/18 | Fri 28/09/18
1.17.5.4 | Rationalise MOR Design Lines | 0% | 5 days | Mon 01/10/18 | Fri 05/10/18
1.17.5.5 | Organise Design Line Scope Review | 0% | 5 days | Mon 01/10/18 | Fri 05/10/18
1.17.5.6 | Design Line Scope Review | 0% | 1 day | Mon 08/10/18 | Mon 08/10/18
1.17.5.7 | Finalise MOR Design Lines | 0% | 10 days | Tue 09/10/18 | Mon 22/10/18
1.17.5.8 | Develop FOT Mother/Father Fits | 0% | 30 days | Tue 23/10/18 | Mon 03/12/18
1.17.5.9 | Develop Generic Mother/Father Fits | 0% | 53 days | Tue 23/10/18 | Fri 11/01/19
1.17.5.10 | Organise PSSRA | 0% | 5 days | Tue 27/11/18 | Mon 03/12/18
1.17.5.11 | Platform Subsystem Requirements Analysis (PSSRA) | 0% | 2 days | Tue 04/12/18 | Wed 05/12/18
1.17.5.12 | Set up V&V and E3 Working Group (Enduring through IDR) | 0% | 239 days | Thu 06/12/18 | Wed 20/11/19
1.17.5.13 | Produce FOT Technical Data Packs (TDPs) | 0% | 39 days | Thu 06/12/18 | Wed 06/02/19
1.17.5.14 | Produce Non-FOT TDPs | 0% | 100 days | Thu 06/12/18 | Tue 07/05/19
1.17.5.15 | MOD Secure Platforms for MIDAC Survey | 69% | 201 days | Mon 11/09/17 | Mon 02/07/18
1.17.5.16 | Installation Design Survey of Platform Types | 0% | 30 days | Fri 04/05/18 | Mon 18/06/18
1.17.5.17 | Perform Installation Concept Design | 0% | 66 days | Thu 07/02/19 | Tue 14/05/19
1.17.5.18 | Organise Concept Design Review | 0% | 5 days | Wed 08/05/19 | Tue 14/05/19
1.17.5.19 | Concept Design Review | 0% | 1 day | Wed 15/05/19 | Wed 15/05/19
1.17.5.20 | Perform Further Non-FOT Installation Design | 0% | 132 days | Thu 16/05/19 | Tue 19/11/19
1.17.5.21 | Perform Installation Analysis (Non-FOT) | 0% | 132 days | Thu 16/05/19 | Tue 19/11/19
1.17.5.22 | Perform Installation Modelling (Non-FOT) | 0% | 132 days | Thu 16/05/19 | Tue 19/11/19
1.17.5.23 | Compile Non-FOT Safety Cases | 0% | 132 days | Thu 16/05/19 | Tue 19/11/19
1.17.5.24 | Perform Installation Modelling (FOT) | 0% | 45 days | Thu 16/05/19 | Thu 18/07/19
1.17.5.25 | Perform Installation Analysis (FOT) | 0% | 45 days | Thu 16/05/19 | Thu 18/07/19
1.17.5.26 | Perform Further FOT Installation Design | 0% | 45 days | Thu 16/05/19 | Thu 18/07/19
1.17.5.27 | Compile FOT Safety Cases | 0% | 45 days | Thu 16/05/19 | Thu 18/07/19
1.17.5.28 | Installation Safety Review (ISR) | 0% | 5 days | Fri 19/07/19 | Thu 25/07/19
1.17.5.29 | Produce Safety Documentation | 0% | 120 days | Fri 26/07/19 | Mon 20/01/20
1.17.5.30 | FOT Installation Design Review (IDR) | 0% | 5 days | Fri 26/07/19 | Thu 01/08/19
1.17.5.31 | Perform Final Installation Design | 0% | 45 days | Fri 02/08/19 | Fri 04/10/19
1.17.5.32 | Finalise AKEE Designs | 0% | 20 days | Mon 09/09/19 | Fri 04/10/19
1.17.5.33 | Deliver Final ICDs, PSDs, BOM & Software Req Spec for FOT Vehicles | 0% | 0 days | Fri 04/10/19 | Fri 04/10/19
1.17.5.34 | Non-FOT Installation Design Review (IDR) | 0% | 5 days | Thu 21/11/19 | Wed 27/11/19
1.17.5.35 | Produce ICDs, PSDs,BOM & Software Req Spec for Non-FOT Vehicles | 0% | 40 days | Thu 28/11/19 | Thu 30/01/20
1.17.5.36 | Deliver ICDs, PSDs, BOM & Software Req Spec for Non-FOT Vehicles / End of Non-FOT activities | 0% | 0 days | Thu 30/01/20 | Thu 30/01/20
1.17.5.37 | Manufacture AKEE/IKEE/Cabling (as required) | 0% | 60 days | Mon 07/10/19 | Mon 06/01/20
1.17.5.38 | MOD Secure FOT Platforms for Conversion | 0% | 240 days | Tue 19/06/18 | Tue 04/06/19
1.17.5.39 | FOT Platforms available for MIDAC | 0% | 0 days | Tue 04/06/19 | Tue 04/06/19
1.17.5.40 | Start Platform Conversion/Installation | 0% | 32 days | Tue 07/01/20 | Wed 19/02/20
1.17.5.41 | Complete Platform Conversion/Installation | 0% | 3 days | Thu 20/02/20 | Mon 24/02/20
1.17.5.42 | Organise PIDR1 | 0% | 5 days | Tue 18/02/20 | Mon 24/02/20
1.17.5.43 | Prototype Installation Design Review (PIDR1) for each FOT Vehicle - TRR | 0% | 10 days | Tue 25/02/20 | Mon 09/03/20
1.17.5.44 | Certification Testing - To include ECM & Tempest | 0% | 80 days | Tue 10/03/20 | Fri 03/07/20
1.17.5.45 | Production Installation Design Review (PIDR2) for each FOT Vehicle | 0% | 137 days | Tue 24/03/20 | Wed 07/10/20
1.17.5.46 | Ready for FOT Test Readiness Review (TRR) | 0% | 5 days | Thu 08/10/20 | Wed 14/10/20
1.17.5.47 | FOT Field Test Readiness Review Complete | 0% | 0 days | Wed 14/10/20 | Wed 14/10/20
1.17.5.48 | Perform FOT Field Tests | 0% | 26 days | Thu 15/10/20 | Thu 19/11/20
1.17.5.49 | FOT Field Tests Completed | 0% | 0 days | Thu 19/11/20 | Thu 19/11/20
1.18 | BMA | 27% | 1152 days | Mon 06/03/17 | Mon 11/10/21
1.18.1 | Dependencies from GD to MoD | 0% | 290 days | Thu 03/08/17 | Mon 01/10/18
1.18.1.1 | GD Supply Information for BMA Competition (ID22) | 100% | 0 days | Thu 03/08/17 | Thu 03/08/17
1.18.1.2 | GD Supply BMA Mature Draft Technical Specification (ID29) | 100% | 0 days | Thu 22/03/18 | Thu 22/03/18
1.18.1.3 | GD Supply BMA Final Technical Specification (IDs 32 & 33) | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.18.1.4 | GD Supply EvO Computing Platforms | 0% | 0 days | Thu 15/03/18 | Thu 15/03/18
1.18.1.5 | GD Supply EvO Reference Model / Access to System Integration Lab Agreed | 100% | 0 days | Thu 15/03/18 | Thu 15/03/18
1.18.2 | Dependencies from MoD to GD | 0% | 377 days | Tue 06/11/18 | Thu 14/05/20
1.18.2.1 | MoD Supply GD with BMA Technical Proposals, Compliance Statements & Other GFI | 0% | 0 days | Tue 06/11/18 | Tue 06/11/18
1.18.2.2 | MoD Supply GD with Initial Drop of BMA * | 0% | 0 days | Fri 22/02/19 | Fri 22/02/19
1.18.2.3 | MoD Supply GD with Common Services Drop of BMA * | 0% | 0 days | Thu 15/08/19 | Thu 15/08/19
1.18.2.4 | MoD Supply GD with BMA Openness Test Results | 0% | 0 days | Mon 17/02/20 | Mon 17/02/20
1.18.2.5 | MoD Supply GD with Full Functionality Drop of BMA * | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.2.6 | MoD Supply GD with Documentation on BMA Software | 0% | 0 days | Mon 17/02/20 | Mon 17/02/20
1.18.2.7 | MoD Supply GD with BMA Product Qualification Document | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.2.8 | MoD Supply GD with BMA Product Certificate of Conformance | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.2.9 | MoD Supply GD with EvO Baseline Drop of BMA | 0% | 0 days | Thu 14/05/20 | Thu 14/05/20
1.18.3 | Dependencies from BMA to MoD | 0% | 461 days | Tue 06/11/18 | Fri 11/09/20
1.18.3.1 | BMA Supplier Supply Final Technical Proposal | 0% | 0 days | Tue 06/11/18 | Tue 06/11/18
1.18.3.2 | BMA Supplier Supply Initial Drop of BMA | 0% | 0 days | Fri 22/02/19 | Fri 22/02/19
1.18.3.3 | BMA Supplier Supply Common Services Drop of BMA | 0% | 0 days | Thu 15/08/19 | Thu 15/08/19
1.18.3.4 | BMA Supplier Supply Openness Test Results | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.3.5 | BMA Supplier Supply Full Functional Drop of BMA | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.3.6 | BMA Supplier Supply BMA Software Documentation | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.3.7 | BMA Supplier Supply BMA Certificate of Conformance | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.3.8 | BMA Supplier Supply BMA Qualification Documentation | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.3.9 | BMA Supplier Supply BMA TNA Report | 0% | 0 days | Mon 18/11/19 | Mon 18/11/19
1.18.3.10 | BMA Supplier Supply EvO Baseline Drop of BMA | 0% | 0 days | Thu 14/05/20 | Thu 14/05/20
1.18.3.11 | BMA Supplier Supply Training Material | 0% | 0 days | Fri 11/09/20 | Fri 11/09/20
1.18.4 | Dependencies from MoD to BMA Supplier | 0% | 138 days | Thu 15/03/18 | Mon 01/10/18
1.18.4.1 | MoD Supply BMA Supplier with EvO Computing Platforms | 0% | 0 days | Thu 15/03/18 | Thu 15/03/18
1.18.4.2 | GD Supply EvO Reference Model / Access to System Integration Lab Agreed | 100% | 0 days | Thu 15/03/18 | Thu 15/03/18
1.18.4.3 | MoD Supply BMA Supplier with GD BMA Mature Draft Technical Specification | 0% | 0 days | Thu 19/04/18 | Thu 19/04/18
1.18.4.4 | MoD Supply BMA Supplier with GD BMA Final Technical Specification | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.18.4.5 | MoD Supply BMA with Collective Training Requirement | 0% | 0 days | Fri 28/09/18 | Fri 28/09/18
1.18.5 | Dependencies from MoD to Training Provider | 0% | 203 days | Mon 18/11/19 | Fri 11/09/20
1.18.5.1 | MoD Supply Training Provider with BMA TNA | 0% | 0 days | Mon 18/11/19 | Mon 18/11/19
1.18.5.2 | MoD Supply Training Provider with Training Material | 0% | 0 days | Fri 11/09/20 | Fri 11/09/20
1.18.6 | BMA Competition - ITN | 81% | 381 days | Mon 06/03/17 | Tue 11/09/18
1.18.6.1 | Strategy | 100% | 159 days | Mon 06/03/17 | Thu 19/10/17
1.18.6.1.1 | Mature BMA SOR and Obligations Dependencies Matrix Available | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.18.6.1.2 | Review LFE from similar BMA Competitions | 100% | 1 day | Wed 15/03/17 | Thu 16/03/17
1.18.6.1.3 | Refine existing BMA SOR | 100% | 8 days | Thu 16/03/17 | Tue 28/03/17
1.18.6.1.4 | Obtain Security Exemptions for BMA | 100% | 31 days | Tue 28/03/17 | Mon 15/05/17
1.18.6.1.5 | Draft BMA PIN | 100% | 35 days | Mon 06/03/17 | Tue 25/04/17
1.18.6.1.6 | Commercial Approval of BMA PIN | 100% | 5 days | Tue 25/04/17 | Wed 03/05/17
1.18.6.1.7 | Issue BMA PIN | 100% | 1 day | Wed 03/05/17 | Thu 04/05/17
1.18.6.1.8 | BMA PIN Issued | 100% | 0 days | Thu 04/05/17 | Thu 04/05/17
1.18.6.1.9 | Draft BMA Procurement Strategy - Start | 100% | 3 days | Thu 04/05/17 | Tue 09/05/17
1.18.6.1.10 | Draft BMA Procurement Strategy - Completion | 100% | 46 days | Tue 09/05/17 | Thu 13/07/17
1.18.6.1.11 | Draft BMA Commercial Strategy | 100% | 110 days | Wed 10/05/17 | Thu 12/10/17
1.18.6.1.12 | Approve BMA Procurement Strategy | 100% | 5 days | Fri 14/07/17 | Thu 20/07/17
1.18.6.1.13 | Approve BMA Commercial Strategy | 100% | 5 days | Fri 13/10/17 | Thu 19/10/17
1.18.6.1.14 | BMA Procurement & Commercial Strategies Agreed | 100% | 0 days | Thu 19/10/17 | Thu 19/10/17
1.18.6.1.15 | Raise BMA RCA | 100% | 1 day | Thu 04/05/17 | Fri 05/05/17
1.18.6.1.16 | Approve BMA RCA | 100% | 1 day | Fri 05/05/17 | Mon 08/05/17
1.18.6.1.17 | Submit BMA RCA to Commercial | 100% | 1 day | Mon 08/05/17 | Tue 09/05/17
1.18.6.2 | Maturing SOR | 100% | 94 days | Mon 06/03/17 | Wed 19/07/17
1.18.6.2.1 | Obtain Training SORs | 100% | 0 days | Wed 21/06/17 | Wed 21/06/17
1.18.6.2.2 | Finalise SOR 60% | 100% | 10 days | Wed 21/06/17 | Wed 05/07/17
1.18.6.2.3 | BMA Requirement Sufficiently Mature to run DPQQ | 100% | 0 days | Wed 05/07/17 | Wed 05/07/17
1.18.6.2.4 | Obtain DRAFT ILS SORs | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.18.6.2.5 | Finalise SOR 95% | 100% | 10 days | Thu 06/07/17 | Wed 19/07/17
1.18.6.2.6 | BMA Requirement Sufficiently Mature to Start Competition | 100% | 0 days | Wed 19/07/17 | Wed 19/07/17
1.18.6.3 | DPQQ | 100% | 83 days | Thu 06/07/17 | Tue 31/10/17
1.18.6.3.1 | Draft & Approve BMA Contract Notice | 100% | 1 day | Thu 06/07/17 | Thu 06/07/17
1.18.6.3.2 | Produce BMA DPQQ Part 1 - Commercial | 100% | 10 days | Thu 06/07/17 | Thu 20/07/17
1.18.6.3.3 | Produce BMA DPQQ Part 2 - Technical | 100% | 27 days | Fri 07/07/17 | Mon 14/08/17
1.18.6.3.4 | Develop BMA Evaluation Criteria | 100% | 29 days | Fri 07/07/17 | Wed 16/08/17
1.18.6.3.5 | Issue BMA DPQQ to Tenderers | 100% | 2 days | Thu 17/08/17 | Fri 18/08/17
1.18.6.3.6 | BMA DPQQ Issued | 100% | 0 days | Fri 18/08/17 | Fri 18/08/17
1.18.6.3.7 | Tenderers Produce BMA DPQQ Responses | 100% | 20 days | Mon 21/08/17 | Mon 18/09/17
1.18.6.3.8 | BATCIS Manage BMA CQs | 100% | 20 days | Mon 21/08/17 | Mon 18/09/17
1.18.6.3.9 | BMA DPQQ Responses Received | 100% | 0 days | Mon 18/09/17 | Mon 18/09/17
1.18.6.3.10 | Evaluate BMA DPQQ Responses | 100% | 23 days | Tue 19/09/17 | Thu 19/10/17
1.18.6.3.11 | BMA DPQQ Results Notification | 100% | 8 days | Fri 20/10/17 | Tue 31/10/17
1.18.6.4 | ITN | 97% | 276 days | Mon 06/03/17 | Thu 12/04/18
1.18.6.4.1 | Start Production of BMA ITN | 100% | 30 days | Wed 05/07/17 | Wed 16/08/17
1.18.6.4.2 | Produce and Issue BMA Contract Bidders Notice | 100% | 1 day | Mon 06/03/17 | Mon 06/03/17
1.18.6.4.3 | Complete Production of BMA ITN inc GD Data (SOR 100%) | 100% | 57 days | Thu 17/08/17 | Mon 06/11/17
1.18.6.4.4 | Produce Draft BMA Contract | 100% | 77 days | Thu 20/07/17 | Mon 06/11/17
1.18.6.4.5 | Produce BMA Contract Management Plan | 100% | 77 days | Thu 20/07/17 | Mon 06/11/17
1.18.6.4.6 | BMA Defence Cyber Protection Partnership (DCPP) Risk Assessment | 100% | 1 day | Tue 07/11/17 | Tue 07/11/17
1.18.6.4.7 | Issue BMA ITN to Tenderers | 100% | 1 day | Wed 08/11/17 | Wed 08/11/17
1.18.6.4.8 | BMA ITN Issued | 100% | 0 days | Wed 08/11/17 | Wed 08/11/17
1.18.6.4.9 | Hold BMA Bidders Conference | 100% | 1 day | Tue 05/12/17 | Wed 06/12/17
1.18.6.4.10 | BATCIS Manage BMA CQs | 100% | 51 days | Thu 09/11/17 | Fri 26/01/18
1.18.6.4.11 | Tenderers Produces BMA Proposal | 100% | 58 days | Thu 09/11/17 | Tue 06/02/18
1.18.6.4.12 | BMA ITN Proposals Received | 100% | 0 days | Tue 06/02/18 | Tue 06/02/18
1.18.6.4.13 | Tender Board Process BMA Proposals | 100% | 2 days | Wed 07/02/18 | Thu 08/02/18
1.18.6.4.14 | Tender Board Release BMA Responses to BATCIS Commercial | 100% | 0 days | Thu 08/02/18 | Thu 08/02/18
1.18.6.4.15 | Initial Compliance Check of BMA Proposals | 100% | 1 day | Fri 09/02/18 | Fri 09/02/18
1.18.6.4.16 | Hold BMA TEP 1 | 0% | 1 day | Mon 12/02/18 | Mon 12/02/18
1.18.6.4.17 | BMA TEP 1 Held | 0% | 0 days | Mon 12/02/18 | Mon 12/02/18
1.18.6.4.18 | Evaluation of BMA Financial and CQs | 89% | 38 days | Mon 12/02/18 | Fri 06/04/18
1.18.6.4.19 | Evaluation of BMA Commercial and CQs | 100% | 28 days | Mon 12/02/18 | Wed 21/03/18
1.18.6.4.20 | Evaluation of BMA Technical and CQs | 100% | 33 days | Mon 12/02/18 | Wed 28/03/18
1.18.6.4.21 | Moderate results of BMA Commercial & Technical Evaluation | 20% | 5 days | Thu 29/03/18 | Fri 06/04/18
1.18.6.4.22 | Collate BMA Results | 0% | 3 days | Mon 09/04/18 | Wed 11/04/18
1.18.6.4.23 | Hold BMA TEP 2 | 0% | 1 day | Thu 12/04/18 | Thu 12/04/18
1.18.6.4.24 | BMA TEP 2 Held | 0% | 0 days | Thu 12/04/18 | Thu 12/04/18
1.18.6.5 | Negotiation, BAFO & Down select | 0% | 109 days | Mon 09/04/18 | Tue 11/09/18
1.18.6.5.1 | Conduct Preparation for BMA Negotiation | 0% | 25 days | Mon 09/04/18 | Mon 14/05/18
1.18.6.5.2 | Notify BMA Tenderers of Results | 0% | 2 days | Fri 13/04/18 | Mon 16/04/18
1.18.6.5.3 | Tenderers Review Updated Contract | 0% | 5 days | Tue 17/04/18 | Mon 23/04/18
1.18.6.5.4 | Tenderers Agree Contract / Notify Negotiation Areas | 0% | 1 day | Mon 23/04/18 | Mon 23/04/18
1.18.6.5.5 | Tenderers Prepare for Negotiation | 0% | 9 days | Tue 17/04/18 | Fri 27/04/18
1.18.6.5.6 | Negotiate with BMA Tenderers | 0% | 23 days | Mon 30/04/18 | Fri 01/06/18
1.18.6.5.7 | BMA Tenderers Produce BAFO | 0% | 13 days | Mon 04/06/18 | Wed 20/06/18
1.18.6.5.8 | BMA Tenderers Submit BAFO | 0% | 1 day | Thu 21/06/18 | Thu 21/06/18
1.18.6.5.9 | Tender Board Process BMA BAFOs | 0% | 1 day | Fri 22/06/18 | Fri 22/06/18
1.18.6.5.10 | BMA BAFO Received | 0% | 0 days | Fri 22/06/18 | Fri 22/06/18
1.18.6.5.11 | Evaluate BAFO Delta's | 0% | 15 days | Mon 25/06/18 | Fri 13/07/18
1.18.6.5.12 | Moderate & Agree Results of BMA BAFO | 0% | 10 days | Mon 16/07/18 | Fri 27/07/18
1.18.6.5.13 | Hold BMA TEP 3a | 0% | 1 day | Mon 30/07/18 | Mon 30/07/18
1.18.6.5.14 | Tenderers Deliver Presentations | 0% | 1 day | Tue 31/07/18 | Tue 31/07/18
1.18.6.5.15 | Evaluate Presentations | 0% | 1 day | Tue 31/07/18 | Tue 31/07/18
1.18.6.5.16 | Create Composite BAFO & Presentation Results | 0% | 2 days | Tue 31/07/18 | Thu 02/08/18
1.18.6.5.17 | Hold BMA TEP 3b | 0% | 1 day | Thu 02/08/18 | Fri 03/08/18
1.18.6.5.18 | CASDD & Cabinet Office Conduct Due Diligence on BMA Contract | 0% | 30 days | Tue 19/06/18 | Mon 30/07/18
1.18.6.5.19 | Produce & Submit BMA Commitment Case / 2 x SMS Requests | 0% | 10 days | Tue 17/07/18 | Mon 30/07/18
1.18.6.5.20 | BMA Commitment Case Approved | 0% | 0 days | Mon 30/07/18 | Mon 30/07/18
1.18.6.5.21 | BMA SMS (x2) Cases Approved | 0% | 0 days | Mon 30/07/18 | Mon 30/07/18
1.18.6.5.22 | Preparation for BMA Debrief | 0% | 5 days | Mon 06/08/18 | Fri 10/08/18
1.18.6.5.23 | Notify Tenderers of Result of BMA Competition | 0% | 3 days | Mon 13/08/18 | Wed 15/08/18
1.18.6.5.24 | BMA Contract Standstill Period | 0% | 8 days | Mon 13/08/18 | Wed 22/08/18
1.18.6.5.25 | Debrief Unsuccessful BMA Tenderers | 0% | 3 days | Mon 13/08/18 | Wed 15/08/18
1.18.6.5.26 | Update and Finalise BMA Documentation | 0% | 5 days | Thu 16/08/18 | Wed 22/08/18
1.18.6.5.27 | Final Review of BMA Documents & Initial Pages before Signature | 0% | 2 days | Thu 23/08/18 | Fri 24/08/18
1.18.6.5.28 | Award BMA Contract | 0% | 1 day | Tue 28/08/18 | Tue 28/08/18
1.18.6.5.29 | BMA Contract Awarded ** | 0% | 0 days | Tue 28/08/18 | Tue 28/08/18
1.18.6.5.30 | BMA Contract Mobilisation | 0% | 10 days | Wed 29/08/18 | Tue 11/09/18
1.18.6.5.31 | BMA Contract Start Date | 0% | 0 days | Tue 11/09/18 | Tue 11/09/18
1.18.7 | BMA Contract | 0% | 771 days | Wed 12/09/18 | Mon 11/10/21
1.18.7.1 | BMA Development | 0% | 501 days | Wed 12/09/18 | Fri 11/09/20
1.18.7.1.1 | Start Development of Initial Drop of BMA | 0% | 40 days | Wed 12/09/18 | Tue 06/11/18
1.18.7.1.2 | BMA Deliver Final Technical Proposal | 0% | 0 days | Tue 06/11/18 | Tue 06/11/18
1.18.7.1.3 | CDO Endorses the Final BMA Technical Proposal | 0% | 0 days | Tue 06/11/18 | Tue 06/11/18
1.18.7.1.4 | Continue with Development of Initial Drop of BMA | 0% | 42 days | Wed 07/11/18 | Fri 11/01/19
1.18.7.1.5 | Complete Development of Initial Drop of BMA | 0% | 30 days | Mon 14/01/19 | Fri 22/02/19
1.18.7.1.6 | Deliver Initial Drop of BMA to MoD | 0% | 0 days | Fri 22/02/19 | Fri 22/02/19
1.18.7.1.7 | Develop Common Services Drop of BMA | 0% | 120 days | Mon 25/02/19 | Thu 15/08/19
1.18.7.1.8 | Deliver Common Services Drop of BMA to MoD | 0% | 0 days | Thu 15/08/19 | Thu 15/08/19
1.18.7.1.9 | Conduct BMA Training Needs Analysis | 0% | 80 days | Mon 01/10/18 | Mon 28/01/19
1.18.7.1.10 | Development Full Functionality Drop of BMA | 0% | 185 days | Mon 25/02/19 | Fri 15/11/19
1.18.7.1.11 | Deliver the BMA TNA Report | 0% | 1 day | Mon 18/11/19 | Mon 18/11/19
1.18.7.1.12 | Final Development of Full Functionality Drop of BMA | 0% | 50 days | Mon 18/11/19 | Mon 03/02/20
1.18.7.1.13 | Deliver Full Functionality Drop of BMA to MoD | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.7.1.14 | Deliver Product Qualification Documentation to MoD | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.7.1.15 | Deliver Certificate of Conformance to MoD | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.7.1.16 | Deliver Openness Test Results to MoD | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.7.1.17 | CDO Review BMA Openness Test Results | 0% | 10 days | Tue 04/02/20 | Mon 17/02/20
1.18.7.1.18 | CDO Endorse BMA Openness Test Results | 0% | 0 days | Mon 17/02/20 | Mon 17/02/20
1.18.7.1.19 | Deliver BMA Software Documentation to MoD | 0% | 0 days | Mon 03/02/20 | Mon 03/02/20
1.18.7.1.20 | CDO Review BMA Software Documentation | 0% | 10 days | Tue 04/02/20 | Mon 17/02/20
1.18.7.1.21 | CDO Endorse BMA Software Documentation | 0% | 0 days | Mon 17/02/20 | Mon 17/02/20
1.18.7.1.22 | Develop EvO Baseline Drop of BMA | 0% | 70 days | Tue 04/02/20 | Thu 14/05/20
1.18.7.1.23 | Deliver EvO Baseline Drop of BMA to MoD | 0% | 0 days | Thu 14/05/20 | Thu 14/05/20
1.18.7.1.24 | Develop Training Material | 0% | 203 days | Tue 19/11/19 | Fri 11/09/20
1.18.7.1.25 | Deliver BMA Training Material to Training | 0% | 0 days | Fri 11/09/20 | Fri 11/09/20
1.18.7.2 | BMA Support | 0% | 556 days | Mon 25/02/19 | Mon 17/05/21
1.18.7.2.1 | BMA Support-Integration | 0% | 456 days | Mon 25/02/19 | Tue 15/12/20
1.18.7.2.2 | BMA Support-Post Integration | 0% | 100 days | Wed 16/12/20 | Mon 17/05/21
1.18.7.3 | ARMY Support | 0% | 771 days | Wed 12/09/18 | Mon 11/10/21
1.18.7.3.1 | Support ARMY Apps Strategy and Help Deliver it | 0% | 771 days | Wed 12/09/18 | Mon 11/10/21
1.19 | EnHCDR | 26% | 1194 days | Mon 06/03/17 | Thu 09/12/21
1.19.1 | Dependencies from GD to BATCIS | 0% | 179 days | Wed 17/01/18 | Mon 01/10/18
1.19.1.1 | GD Supply Draft Spec for Contract Award | 100% | 0 days | Wed 17/01/18 | Wed 17/01/18
1.19.1.2 | GD Supply HRS/SRS for EnHCDR | 0% | 0 days | Mon 01/10/18 | Mon 01/10/18
1.19.2 | Dependencies from EnHCDR Provider to Conformance Engineers | 0% | 0 days | Tue 16/04/19 | Tue 16/04/19
1.19.2.1 | EnHCDR Provider Supplies Single Drop of EnHCDR to Conformance Engineers (For MACA24) | 0% | 0 days | Tue 16/04/19 | Tue 16/04/19
1.19.3 | Dependencies from MOD to GD | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.3.1 | MOD Supply GD with EnHCDR Technical Proposals, Compliance Statements & Other GFI | 0% | 0 days | Wed 28/03/18 | Wed 28/03/18
1.19.3.2 | MOD Supply Results of Openness Tests for EnHCDR MACA36(D7-3b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.3.3 | MOD Supply Documentation for EnHCDR Software MACA 36 (D7-4b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.3.4 | MOD Supply EnHCDR Product Qualification Document MACA36 (D7-1b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.3.5 | MOD Supply EnHCDR Product Certificate of Conformance & Certification / Verification Test Results MACA36 (D7-2b & D7 -5b) | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.4 | EnHCDR Procurement- Single Source | 70% | 349 days | Mon 06/03/17 | Fri 27/07/18
1.19.4.1 | Develop EnHCDR SOR - Continued from AP2 Schedule | 75% | 12 days | Thu 16/03/17 | Fri 31/03/17
1.19.4.2 | Mature EnHCDR SOR Available | 100% | 0 days | Fri 31/03/17 | Fri 31/03/17
1.19.4.3 | Review LFE from similar EnHCDR Competitions | 100% | 1 day | Thu 16/03/17 | Thu 16/03/17
1.19.4.4 | Complete ISS Front Door Process for EnHCDR | 0% | 5 days | Fri 17/03/17 | Thu 23/03/17
1.19.4.5 | Refine existing EnHCDR SOR | 100% | 4 days | Mon 03/04/17 | Thu 06/04/17
1.19.4.6 | Obtain Security Exemptions for EnHCDR (If needed) | 100% | 0 days | Mon 06/03/17 | Mon 06/03/17
1.19.4.7 | Draft EnHCDR Procurement Strategy - Start | 0% | 5 days | Mon 06/03/17 | Mon 13/03/17
1.19.4.8 | Draft EnHCDR Procurement Strategy - Completion | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.19.4.9 | Draft EnHCDR Commercial Strategy | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.19.4.10 | Approve EnHCDR Procurement Strategy | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.19.4.11 | Approve EnHCDR Commercial Strategy | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.19.4.12 | EnHCDR Procurement & Commercial Strategies Agreed | 100% | 0 days | Fri 17/03/17 | Fri 17/03/17
1.19.4.13 | Technical Requirements Evaluation | 100% | 189 days | Fri 26/05/17 | Mon 26/02/18
1.19.4.13.1 | Raise Tech Requirements RCA | 100% | 10 days | Fri 26/05/17 | Fri 09/06/17
1.19.4.13.2 | Raise Commitment Case | 100% | 1 day | Mon 12/06/17 | Mon 12/06/17
1.19.4.13.3 | Approval of Commitment Case | 100% | 5 days | Tue 13/06/17 | Mon 19/06/17
1.19.4.13.4 | Commitment Case Approved | 100% | 0 days | Mon 19/06/17 | Mon 19/06/17
1.19.4.13.5 | Raise TRA SMS to JFC | 100% | 5 days | Tue 20/06/17 | Mon 26/06/17
1.19.4.13.6 | TRA SMS Approval From JFC | 100% | 14 days | Tue 27/06/17 | Fri 14/07/17
1.19.4.13.7 | TRA SMS Approved | 100% | 0 days | Fri 14/07/17 | Fri 14/07/17
1.19.4.13.8 | Draft Contract for Tech Evaluation | 100% | 9 days | Mon 17/07/17 | Thu 27/07/17
1.19.4.13.9 | SoR Tech Requirements Scoping Workshop (at Harris) | 100% | 47 days | Mon 17/07/17 | Wed 20/09/17
1.19.4.13.10 | Harris Price Effort for Tech Requirements Validation | 100% | 17 days | Thu 21/09/17 | Fri 13/10/17
1.19.4.13.11 | Approve TRA Contract & Issue | 100% | 17 days | Mon 16/10/17 | Tue 07/11/17
1.19.4.13.12 | Contract Issued (Technical Requirements Evaluation) | 100% | 0 days | Tue 07/11/17 | Tue 07/11/17
1.19.4.13.13 | Refine Technical Requirements (Lab Testing) | 100% | 42 days | Wed 08/11/17 | Fri 12/01/18
1.19.4.13.14 | Agree Technical Requirements (final) | 100% | 9 days | Mon 15/01/18 | Thu 25/01/18
1.19.4.13.15 | Final Technical Requirements Report Produced | 100% | 0 days | Thu 25/01/18 | Thu 25/01/18
1.19.4.13.16 | Amend TRA SoR | 100% | 2 days | Fri 26/01/18 | Mon 29/01/18
1.19.4.13.17 | Final Approval of TRA SoR | 100% | 20 days | Tue 30/01/18 | Mon 26/02/18
1.19.4.13.18 | TRA SoR Approved | 100% | 0 days | Mon 26/02/18 | Mon 26/02/18
1.19.4.14 | EnHCDR Procurement | 60% | 340 days | Mon 20/03/17 | Fri 27/07/18
1.19.4.14.1 | Produce EnHCDR Commitment Case / 2 SMS Requests | 100% | 220 days | Wed 05/04/17 | Wed 21/02/18
1.19.4.14.2 | Raise EnHCDR RCA for 250 units | 100% | 45 days | Mon 20/03/17 | Wed 24/05/17
1.19.4.14.3 | Submit EnHCDR RCA to Commercial | 100% | 1 day | Thu 25/05/17 | Thu 25/05/17
1.19.4.14.4 | EnHCDR Requirements Sufficiently mature to run Procurement | 100% | 0 days | Thu 25/05/17 | Thu 25/05/17
1.19.4.14.5 | Draft & Approve Voluntary Transparency Notice for EnHCDR | 100% | 11 days | Mon 20/03/17 | Mon 03/04/17
1.19.4.14.6 | Issue EnHCDR VTN to OJEU / DCB | 100% | 1 day | Tue 04/04/17 | Tue 04/04/17
1.19.4.14.7 | EnHCDR VTN Stand Still Period | 100% | 8 days | Wed 05/04/17 | Tue 18/04/17
1.19.4.14.8 | Produce EnHCDR ITN | 100% | 11 days | Fri 26/05/17 | Mon 12/06/17
1.19.4.14.9 | Produce Draft EnHCDR Contract | 100% | 11 days | Tue 13/06/17 | Tue 27/06/17
1.19.4.14.10 | Produce EnHCDR Contract Management Plan | 100% | 11 days | Wed 28/06/17 | Wed 12/07/17
1.19.4.14.11 | EnHCDR Defence Cyber Protection Partnership (DCPP) Risk Assessment | 80% | 10 days | Wed 13/12/17 | Wed 03/01/18
1.19.4.14.12 | Issue EnHCDR ITN to Tenderer | 0% | 1 day | Thu 04/01/18 | Thu 04/01/18
1.19.4.14.13 | EnHCDR ITN Issued | 0% | 0 days | Thu 04/01/18 | Thu 04/01/18
1.19.4.14.14 | Tenderer Produces EnHCDR ITN Response | 0% | 32 days | Fri 05/01/18 | Mon 19/02/18
1.19.4.14.15 | BATCIS Manage EnHCDR CQs | 0% | 32 days | Fri 05/01/18 | Mon 19/02/18
1.19.4.14.16 | EnHCDR ITN Response Received | 0% | 0 days | Mon 19/02/18 | Mon 19/02/18
1.19.4.14.17 | Evaluation of EnHCDR Affordability | 0% | 20 days | Tue 20/02/18 | Mon 19/03/18
1.19.4.14.18 | Evaluation of T&Cs for EnHCDR Contract | 0% | 20 days | Tue 20/02/18 | Mon 19/03/18
1.19.4.14.19 | Individual Assessor Evaluation of EnHCDR Technical & PM Aspects | 0% | 20 days | Tue 20/02/18 | Mon 19/03/18
1.19.4.14.20 | Achieve Consensus Evaluation of EnHCDR Technical & PM Aspects | 0% | 2 days | Tue 20/03/18 | Wed 21/03/18
1.19.4.14.21 | Moderate results of EnHCDR Evaluation | 0% | 5 days | Thu 22/03/18 | Wed 28/03/18
1.19.4.14.22 | Hold EnHCDR TEP | 0% | 1 day | Thu 29/03/18 | Thu 29/03/18
1.19.4.14.23 | EnHCDR TEP Held | 0% | 0 days | Thu 29/03/18 | Thu 29/03/18
1.19.4.14.24 | Prepare for EnHCDR Negotiations | 0% | 15 days | Tue 03/04/18 | Mon 23/04/18
1.19.4.14.25 | Negotiate EnHCDR Contract | 0% | 25 days | Tue 24/04/18 | Wed 30/05/18
1.19.4.14.26 | Tenderer Prepares and Submits EnHCDR BAFO | 0% | 10 days | Thu 31/05/18 | Wed 13/06/18
1.19.4.14.27 | EnHCDR BAFO Received | 0% | 0 days | Wed 13/06/18 | Wed 13/06/18
1.19.4.14.28 | Technical & PM Evaluation of EnHCDR BAFO | 0% | 4 days | Thu 14/06/18 | Tue 19/06/18
1.19.4.14.29 | Affordability Evaluation of EnHCDR BAFO | 0% | 4 days | Thu 14/06/18 | Tue 19/06/18
1.19.4.14.30 | Hold Post-BAFO TEP for EnHCDR | 0% | 1 day | Wed 20/06/18 | Wed 20/06/18
1.19.4.14.31 | Finalise EnHCDR Contract | 0% | 11 days | Thu 21/06/18 | Thu 05/07/18
1.19.4.14.32 | Contract & VTN No2 Standstill Period for EnHCDR | 0% | 10 days | Fri 06/07/18 | Thu 19/07/18
1.19.4.14.33 | Award EnHCDR Contract | 0% | 1 day | Fri 20/07/18 | Fri 20/07/18
1.19.4.14.34 | EnHCDR Contract Awarded * | 0% | 0 days | Fri 20/07/18 | Fri 20/07/18
1.19.4.14.35 | EnHCDR Contract Mobilisation | 0% | 5 days | Mon 23/07/18 | Fri 27/07/18
1.19.4.14.36 | EnHCDR Contract Start Date | 0% | 0 days | Fri 27/07/18 | Fri 27/07/18
1.19.5 | EnHCDR Contract | 0% | 845 days | Mon 30/07/18 | Thu 09/12/21
1.19.5.1 | EnHCDR Development | 0% | 430 days | Mon 30/07/18 | Fri 17/04/20
1.19.5.1.1 | Develop EnHCDR - Part1a (Without Final Spec from GD) | 0% | 100 days | Mon 30/07/18 | Mon 17/12/18
1.19.5.1.2 | Develop EnHCDR - Part1b (Final Spec Received from GD ) | 0% | 80 days | Tue 18/12/18 | Tue 16/04/19
1.19.5.1.3 | Completed EnHCDR Issued to Conformance Engineers * | 0% | 0 days | Tue 16/04/19 | Tue 16/04/19
1.19.5.1.4 | Develop EnHCDR - Part 2 | 0% | 250 days | Wed 17/04/19 | Fri 17/04/20
1.19.5.1.5 | EnHCDR Openness Test Results Endorsed by CDO | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.5.1.6 | MOD Supply GD with EnHCDR Software Documentation Endorsed by CDO | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.5.1.7 | MOD Supply GD with EnHCDR Product Qualification Document & Certificate of Conformance | 0% | 0 days | Fri 17/04/20 | Fri 17/04/20
1.19.5.2 | EnHCDR Support | 0% | 845 days | Mon 30/07/18 | Thu 09/12/21
1.19.5.2.1 | Support GD on EnHCDR Integration and Test Activities | 0% | 735 days | Mon 30/07/18 | Wed 07/07/21
1.19.5.2.2 | Support MOD on EnHCDR after end of TP Contract | 0% | 110 days | Thu 08/07/21 | Thu 09/12/21
1.2 | ILS | 16% | 2108 days | Mon 06/03/17 | Fri 08/08/25
1.20.1 | Enduring Activities | 8% | 2108 days | Mon 06/03/17 | Fri 08/08/25
1.20.1.1 | ILS Report on Progress (Monthly) | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.20.1.2 | Support Management and Execution of TP Contract with respect to ILS | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.20.1.3 | ILS Support / Advice to Interim Support Solution Team | 28% | 956 days | Mon 06/03/17 | Thu 24/12/20
1.20.1.4 | Maintain and Update Use study | 0% | 678 days | Tue 17/04/18 | Thu 24/12/20
1.20.1.5 | Maintain and Update ILS Plan | 0% | 683 days | Tue 10/04/18 | Thu 24/12/20
1.20.1.6 | Update and maintain the Support Solution Development Tool (SSDT) | 0% | 688 days | Tue 03/04/18 | Thu 24/12/20
1.20.1.7 | Update and maintain the BATCIS ILS Strategy | 0% | 1780 days | Thu 28/06/18 | Fri 08/08/25
1.20.1.8 | Update and maintain the BATCIS Supportability Analysis Strategy | 0% | 1780 days | Thu 28/06/18 | Fri 08/08/25
1.20.2 | Key Deliverables | 97% | 278 days | Mon 06/03/17 | Mon 16/04/18
1.20.2.1 | ILS Plan (GFX) | 98% | 273 days | Mon 06/03/17 | Mon 09/04/18
1.20.2.1.1 | 1st Draft | 100% | 17 days | Mon 06/03/17 | Tue 28/03/17
1.20.2.1.1.1 | Draft Outline ILS Element Plans | 100% | 12 days | Mon 06/03/17 | Tue 21/03/17
1.20.2.1.1.2 | Sign Off of ILS Plan | 100% | 5 days | Wed 22/03/17 | Tue 28/03/17
1.20.2.1.1.3 | Draft ILS Plan Approved | 100% | 0 days | Tue 28/03/17 | Tue 28/03/17
1.20.2.1.2 | Version 1 | 100% | 54 days | Mon 03/04/17 | Wed 21/06/17
1.20.2.1.2.1 | Review and Update ILS Plan V1 Main Body | 100% | 29 days | Mon 03/04/17 | Tue 16/05/17
1.20.2.1.2.2 | Review and Update ILS Element Plans V1 | 100% | 10 days | Wed 17/05/17 | Wed 31/05/17
1.20.2.1.2.3 | Draft ILS Plan V1 Issued for Comment | 100% | 0 days | Wed 31/05/17 | Wed 31/05/17
1.20.2.1.2.4 | Circulate ILS Plan V1 for Stakeholder Comment and Endorsement | 100% | 10 days | Thu 01/06/17 | Wed 14/06/17
1.20.2.1.2.5 | Update and Approve ILS Plan V1 | 100% | 5 days | Thu 15/06/17 | Wed 21/06/17
1.20.2.1.2.6 | ILS Plan V1 Approved (Input to BMA) | 100% | 0 days | Wed 21/06/17 | Wed 21/06/17
1.20.2.1.3 | Version 2 | 100% | 88 days | Thu 22/06/17 | Tue 24/10/17
1.20.2.1.3.1 | Review and Update ILS Plan V2 Main Body | 100% | 68 days | Thu 22/06/17 | Tue 26/09/17
1.20.2.1.3.2 | Review and Update ILS Element Plans V2 | 100% | 10 days | Wed 27/09/17 | Tue 10/10/17
1.20.2.1.3.3 | Draft ILS Plan V2 Issued for Comment | 100% | 0 days | Tue 10/10/17 | Tue 10/10/17
1.20.2.1.3.4 | Circulate ILS Plan V2 for Stakeholder Comment and Endorsement | 100% | 9 days | Wed 11/10/17 | Mon 23/10/17
1.20.2.1.3.5 | Update and Approve ILS Plan V2 | 100% | 1 day | Tue 24/10/17 | Tue 24/10/17
1.20.2.1.3.6 | ILS Plan V2 Approved | 100% | 0 days | Tue 24/10/17 | Tue 24/10/17
1.20.2.1.4 | Version 3 | 95% | 111 days | Wed 25/10/17 | Mon 09/04/18
1.20.2.1.4.1 | Review and Update ILS Plan V3 Main Body | 100% | 81 days | Wed 25/10/17 | Thu 22/02/18
1.20.2.1.4.2 | Review and Update ILS Element Plans V3 | 100% | 10 days | Fri 23/02/18 | Thu 08/03/18
1.20.2.1.4.3 | Draft ILS Plan V3 Issued for Comment | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.20.2.1.4.4 | Circulate ILS Plan V3 for Stakeholder Comment and Endorsement | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.20.2.1.4.5 | Update and Approve ILS Plan V3 | 50% | 10 days | Fri 23/03/18 | Mon 09/04/18
1.20.2.1.4.6 | ILS Plan V3 Approved | 0% | 0 days | Mon 09/04/18 | Mon 09/04/18
1.20.2.2 | Use Study (GFX) | 96% | 258 days | Mon 03/04/17 | Mon 16/04/18
1.20.2.2.1 | 1st Draft | 100% | 78 days | Mon 03/04/17 | Tue 25/07/17
1.20.2.2.1.1 | Draft Use Study Main Body | 100% | 71 days | Mon 03/04/17 | Fri 14/07/17
1.20.2.2.1.2 | Draft Use Study Issued for Comment | 100% | 0 days | Fri 14/07/17 | Fri 14/07/17
1.20.2.2.1.3 | Circulate Draft Use Study for Stakeholder Comment | 100% | 5 days | Mon 17/07/17 | Fri 21/07/17
1.20.2.2.1.4 | Update and Approve Draft Use Study | 100% | 2 days | Mon 24/07/17 | Tue 25/07/17
1.20.2.2.1.5 | Draft Use Study Approved | 100% | 0 days | Tue 25/07/17 | Tue 25/07/17
1.20.2.2.2 | Version 1 | 100% | 88 days | Wed 26/07/17 | Mon 27/11/17
1.20.2.2.2.1 | Review and Update Use Study V1 | 100% | 73 days | Wed 26/07/17 | Mon 06/11/17
1.20.2.2.2.2 | Use Study V1 Issued for Comment | 100% | 0 days | Mon 06/11/17 | Mon 06/11/17
1.20.2.2.2.3 | Circulate Use Study V1 for Stakeholder Comment | 100% | 10 days | Tue 07/11/17 | Mon 20/11/17
1.20.2.2.2.4 | Update and Approve Use Study V1 | 100% | 2 days | Tue 21/11/17 | Wed 22/11/17
1.20.2.2.2.5 | Use Study V1 Approved | 100% | 0 days | Mon 27/11/17 | Mon 27/11/17
1.20.2.2.3 | Version 2 | 89% | 92 days | Tue 28/11/17 | Mon 16/04/18
1.20.2.2.3.1 | Review and Update Use Study V2 | 100% | 77 days | Tue 28/11/17 | Thu 22/03/18
1.20.2.2.3.2 | Use Study V2 Issued for Comment | 100% | 0 days | Thu 22/03/18 | Thu 22/03/18
1.20.2.2.3.3 | Circulate Use Study V2 for Stakeholder Comment | 50% | 10 days | Fri 23/03/18 | Mon 09/04/18
1.20.2.2.3.4 | Update and Approve Use Study V | 0% | 5 days | Tue 10/04/18 | Mon 16/04/18
1.20.2.2.3.5 | Use Study V2 Approved | 0% | 0 days | Mon 16/04/18 | Mon 16/04/18
1.20.3 | Future Support Strategy | 62% | 403 days | Mon 03/04/17 | Thu 08/11/18
1.20.3.1 | Version 6 | 100% | 105 days | Mon 03/04/17 | Fri 01/09/17
1.20.3.1.1 | Produce Future Support Strategy V6 Draft | 100% | 95 days | Mon 03/04/17 | Thu 17/08/17
1.20.3.1.2 | Draft Future Support Strategy V6 Issued for Comment | 100% | 0 days | Thu 17/08/17 | Thu 17/08/17
1.20.3.1.3 | Circulate Future Support Strategy V6 for Stakeholder Comment | 100% | 5 days | Fri 18/08/17 | Thu 24/08/17
1.20.3.1.4 | Update and Approve Future Support Strategy V6 | 100% | 5 days | Fri 25/08/17 | Fri 01/09/17
1.20.3.1.5 | Future Support Strategy V6 Approved | 100% | 0 days | Fri 01/09/17 | Fri 01/09/17
1.20.3.2 | Version 7 | 93% | 153 days | Mon 04/09/17 | Mon 16/04/18
1.20.3.2.1 | Produce Future Support Strategy V7 Draft | 100% | 113 days | Mon 04/09/17 | Thu 15/02/18
1.20.3.2.2 | Draft Future Support Strategy V7 Issued for Comment | 100% | 0 days | Thu 15/02/18 | Thu 15/02/18
1.20.3.2.3 | Circulate Future Support Strategy V7 for Stakeholder Comment | 100% | 20 days | Fri 16/02/18 | Thu 15/03/18
1.20.3.2.4 | Update and Approve Future Support Strategy V7 | 50% | 20 days | Fri 16/03/18 | Mon 16/04/18
1.20.3.2.5 | Future Support Strategy V7 Approved | 0% | 0 days | Mon 16/04/18 | Mon 16/04/18
1.20.3.3 | Version 8 | 0% | 145 days | Tue 17/04/18 | Thu 08/11/18
1.20.3.3.1 | Produce Future Support Strategy V8 Draft | 0% | 130 days | Tue 17/04/18 | Thu 18/10/18
1.20.3.3.2 | Draft Future Support Strategy V8 Issued for Comment | 0% | 0 days | Thu 18/10/18 | Thu 18/10/18
1.20.3.3.3 | Circulate Future Support Strategy V8 for Stakeholder Comment | 0% | 10 days | Fri 19/10/18 | Thu 01/11/18
1.20.3.3.4 | Update and Approve Future Support Strategy V8 | 0% | 5 days | Fri 02/11/18 | Thu 08/11/18
1.20.3.3.5 | Future Support Strategy V8 Approved | 0% | 0 days | Thu 08/11/18 | Thu 08/11/18
1.20.4 | Enduring Support Solution | 55% | 342 days | Mon 03/07/17 | Thu 08/11/18
1.20.4.1 | Produce Enduring Support Solution Outline Structure of Options Analysis Paper | 100% | 5 days | Mon 03/07/17 | Fri 07/07/17
1.20.4.2 | Write Enduring Support Solution Options Analysis Paper | 97% | 187 days | Mon 10/07/17 | Mon 09/04/18
1.20.4.3 | Draft Enduring Support Solution Options Analysis Paper Issued for Comment | 0% | 0 days | Mon 09/04/18 | Mon 09/04/18
1.20.4.4 | Enduring Support Solution Stakeholder Review | 0% | 10 days | Tue 10/04/18 | Mon 23/04/18
1.20.4.5 | Update and Approve Enduring Support Solution Options Analysis Paper | 0% | 5 days | Tue 24/04/18 | Mon 30/04/18
1.20.4.6 | Enduring Support Solution Options Analysis Paper Approved for RN4 | 0% | 0 days | Mon 30/04/18 | Mon 30/04/18
1.20.4.7 | Update Enduring Support Solution Options Analysis Paper | 0% | 120 days | Tue 01/05/18 | Thu 18/10/18
1.20.4.8 | Draft Enduring Support Solution Options Analysis Paper Issued for Comment | 0% | 0 days | Thu 18/10/18 | Thu 18/10/18
1.20.4.9 | Enduring Support Solution Stakeholder Review | 0% | 10 days | Fri 19/10/18 | Thu 01/11/18
1.20.4.10 | Update and Approve Enduring Support Solution Options Analysis Paper | 0% | 5 days | Fri 02/11/18 | Thu 08/11/18
1.20.4.11 | Enduring Support Solution Options Analysis Paper Approved for RN5 | 0% | 0 days | Thu 08/11/18 | Thu 08/11/18
1.21 | Requirements | 19% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.21.1 | Enduring Activities | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.21.1.1 | Support and Review CONEMP, CONOP and CONUSE | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.21.1.2 | Engage with GD in relation to TP Contract | 27% | 941 days | Mon 27/03/17 | Thu 24/12/20
1.21.1.3 | Maintain ITEAP for TP Contract (Annex A) | 100% | 61 days | Mon 03/04/17 | Fri 30/06/17
1.21.1.4 | Maintain MORPHEUS ITEAP | 9% | 2024 days | Mon 03/07/17 | Tue 05/08/25
1.21.1.5 | Maintain and Update URD | 0% | 520 days | Tue 03/04/18 | Wed 29/04/20
1.21.1.6 | Maintain and Update SRD (EvO) | 0% | 604 days | Tue 03/04/18 | Thu 27/08/20
1.21.1.7 | Maintain and Update EvO Capability Use Cases | 17% | 829 days | Wed 06/09/17 | Thu 24/12/20
1.21.1.8 | Support to Spiral Development | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.21.1.9 | Support to Requirements Working Groups | 13% | 2105 days | Mon 06/03/17 | Tue 05/08/25
1.21.2 | EvO Capability Use Cases | 100% | 127 days | Mon 06/03/17 | Tue 05/09/17
1.21.2.1 | Develop Capability Use Cases | 100% | 102 days | Mon 06/03/17 | Mon 31/07/17
1.21.2.2 | Draft Capability Use Cases Issued | 100% | 0 days | Mon 31/07/17 | Mon 31/07/17
1.21.2.3 | Review Capability Use Cases | 100% | 10 days | Tue 01/08/17 | Mon 14/08/17
1.21.2.4 | Update Capability Use Cases | 100% | 5 days | Tue 15/08/17 | Mon 21/08/17
1.21.2.5 | Capability Use Cases Approved | 100% | 10 days | Mon 21/08/17 | Tue 05/09/17
1.21.3 | ITEAP for TP Contract | 100% | 20 days | Mon 06/03/17 | Fri 31/03/17
1.21.3.1 | Update ITEAP for TP Contract | 100% | 20 days | Mon 06/03/17 | Fri 31/03/17
1.21.4 | Requirements Reports | 100% | 181 days | Mon 06/03/17 | Mon 20/11/17
1.21.4.1 | Produce Draft Interim Requirements Report | 100% | 58 days | Mon 06/03/17 | Tue 30/05/17
1.21.4.2 | Draft Interim Requirements Report Issued | 100% | 0 days | Tue 30/05/17 | Tue 30/05/17
1.21.4.3 | Review Draft Interim Requirements Report | 100% | 10 days | Wed 31/05/17 | Tue 13/06/17
1.21.4.4 | Update Draft Interim Requirements Report | 100% | 5 days | Wed 14/06/17 | Tue 20/06/17
1.21.4.5 | Interim Requirements Report Approved | 100% | 0 days | Mon 19/06/17 | Mon 19/06/17
1.21.4.6 | Produce Draft Final Interim Requirements Report | 100% | 94 days | Tue 20/06/17 | Mon 30/10/17
1.21.4.7 | Draft Final Requirements Report Issued | 100% | 0 days | Mon 30/10/17 | Mon 30/10/17
1.21.4.8 | Review Draft Final Requirements Report | 100% | 10 days | Tue 31/10/17 | Mon 13/11/17
1.21.4.9 | Update Draft Final Requirements Report | 100% | 5 days | Tue 14/11/17 | Mon 20/11/17
1.21.4.10 | Final Requirements Report Approved | 100% | 0 days | Mon 20/11/17 | Mon 20/11/17
1.21.5 | Maintain URD | 100% | 268 days | Mon 06/03/17 | Thu 29/03/18
1.21.5.1 | Update URD | 100% | 253 days | Mon 06/03/17 | Thu 08/03/18
1.21.5.2 | Issue Updated URD | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.21.5.3 | Review Updated URD | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.21.5.4 | Finalise Updated URD | 100% | 5 days | Fri 23/03/18 | Thu 29/03/18
1.21.5.5 | Updated URD Approved | 100% | 0 days | Thu 29/03/18 | Thu 29/03/18
1.21.6 | Maintain SRD | 100% | 268 days | Mon 06/03/17 | Thu 29/03/18
1.21.6.1 | Update SRD | 100% | 253 days | Mon 06/03/17 | Thu 08/03/18
1.21.6.2 | Issue Updated SRD | 100% | 0 days | Thu 08/03/18 | Thu 08/03/18
1.21.6.3 | Review Updated SRD | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.21.6.4 | Finalise Updated SRD | 100% | 5 days | Fri 23/03/18 | Thu 29/03/18
1.21.6.5 | Updated SRD Approved | 100% | 0 days | Thu 29/03/18 | Thu 29/03/18
1.22 | Training | 8% | 2232 days | Mon 03/04/17 | Mon 09/03/26
1.22.1 | Dependencies from GD to BATCIS | 0% | 674 days | Tue 06/02/18 | Thu 15/10/20
1.22.1.1 | Training Scoping Report | 100% | 0 days | Tue 06/02/18 | Tue 06/02/18
1.22.1.2 | TNA Report Delivery for TRA Acceptance available at AR6 (Consolidated) | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.22.1.3 | Delivery of DFF Training Courses | 0% | 0 days | Tue 31/03/20 | Tue 31/03/20
1.22.1.4 | Final Delivery of TNA Report and Training material | 0% | 0 days | Thu 15/10/20 | Thu 15/10/20
1.22.2 | Dependencies from Field Army to Training Provider | 0% | 0 days | Fri 28/09/18 | Fri 28/09/18
1.22.2.1 | Field Army provide BMA Collective Training Requirements to Training | 0% | 0 days | Fri 28/09/18 | Fri 28/09/18
1.22.3 | Dependencies from Training Provider to BMA Provider | 0% | 0 days | Fri 28/09/18 | Fri 28/09/18
1.22.3.1 | Training provide BMA Collective Training Requirements to BMA Provider | 0% | 0 days | Fri 28/09/18 | Fri 28/09/18
1.22.4 | Dependencies from Training Provider to GD | 0% | 0 days | Mon 02/12/19 | Mon 02/12/19
1.22.4.1 | BMA TNA | 0% | 0 days | Mon 02/12/19 | Mon 02/12/19
1.22.5 | Dependencies from BMA to Training Provider | 0% | 203 days | Mon 18/11/19 | Fri 11/09/20
1.22.5.1 | BMA TNA | 0% | 0 days | Mon 18/11/19 | Mon 18/11/19
1.22.5.2 | BMA Deliver Training Material | 0% | 0 days | Fri 11/09/20 | Fri 11/09/20
1.22.6 | Training Management | 13% | 2185 days | Mon 03/04/17 | Wed 24/12/25
1.22.6.1 | Training Management FY17/18 (Includes Monthly Report) | 100% | 248 days | Mon 03/04/17 | Thu 29/03/18
1.22.6.2 | Review of Training Documents in Prep for IBR | 100% | 4 days | Tue 18/04/17 | Fri 21/04/17
1.22.6.3 | Review of Training Documents in Prep for P1 | 100% | 10 days | Mon 19/06/17 | Fri 30/06/17
1.22.6.4 | Review of Training Documents in Prep for AR1 & PI2 | 100% | 10 days | Thu 21/09/17 | Wed 04/10/17
1.22.6.5 | Review of Training Documents in Prep for PI3 | 100% | 10 days | Fri 01/12/17 | Thu 14/12/17
1.22.6.6 | Review of Training Documents in Prep for PI4 | 100% | 10 days | Fri 09/03/18 | Thu 22/03/18
1.22.6.7 | Training Management FY18 /19 Onwards (Includes Monthly Report) | 0% | 1937 days | Tue 03/04/18 | Wed 24/12/25
1.22.6.8 | TRA Endorsement of TNA Scoping Study | 100% | 37 days | Wed 07/02/18 | Thu 29/03/18
1.22.6.9 | TNA Scoping Study Accepted | 100% | 0 days | Thu 29/03/18 | Thu 29/03/18
1.22.6.10 | Training Options Analysis Review Period | 2% | 220 days | Fri 23/03/18 | Fri 08/02/19
1.22.6.11 | Training Options Analysis Endorsed | 0% | 0 days | Fri 08/02/19 | Fri 08/02/19
1.22.6.12 | BMA TNA Review | 0% | 10 days | Tue 19/11/19 | Mon 02/12/19
1.22.6.13 | BMA TNA Accepted | 0% | 0 days | Mon 02/12/19 | Mon 02/12/19
1.22.6.14 | BMA Training Material Review | 0% | 10 days | Mon 14/09/20 | Fri 25/09/20
1.22.6.15 | BMA Training Material Accepted | 0% | 0 days | Fri 25/09/20 | Fri 25/09/20
1.22.6.16 | Consolidated TNA Review | 0% | 10 days | Wed 01/04/20 | Thu 16/04/20
1.22.6.17 | Consolidated TNA Accepted | 0% | 0 days | Thu 16/04/20 | Thu 16/04/20
1.22.6.18 | Final Delivery of TNA Report and Training material Review | 0% | 10 days | Thu 15/10/20 | Wed 28/10/20
1.22.6.19 | Final TNA Report and Training material (GD) Accepted | 0% | 0 days | Wed 28/10/20 | Wed 28/10/20
1.22.7 | Key Authority Training Products | 100% | 54 days | Mon 03/04/17 | Wed 21/06/17
1.22.7.1 | Training SORs for BMA | 100% | 54 days | Mon 03/04/17 | Wed 21/06/17
1.22.7.1.1 | Produce Draft BMA SOR | 100% | 39 days | Mon 03/04/17 | Wed 31/05/17
1.22.7.1.2 | Draft Training BMA SOR Issued for Review | 100% | 0 days | Wed 31/05/17 | Wed 31/05/17
1.22.7.1.3 | Review Draft BMA SOR | 100% | 10 days | Thu 01/06/17 | Wed 14/06/17
1.22.7.1.4 | Update Draft BMA SOR | 100% | 5 days | Thu 15/06/17 | Wed 21/06/17
1.22.7.1.5 | Training BMA SOR Approved | 100% | 0 days | Wed 21/06/17 | Wed 21/06/17
1.22.8 | PSS Training Design & Courseware Development | 0% | 808 days | Tue 24/12/19 | Wed 22/03/23
1.22.8.1 | Designers Familiarisation with EvO Kit | 0% | 60 days | Tue 24/12/19 | Tue 24/03/20
1.22.8.2 | Start to Design OFT & Conversion Training Courses | 0% | 146 days | Wed 25/03/20 | Wed 21/10/20
1.22.8.3 | Start to Design OFT & Conversion Courseware | 0% | 40 days | Thu 29/10/20 | Wed 23/12/20
1.22.8.4 | Complete the Design of OFT & Conversion Training & Development of Courseware | 0% | 117 days | Thu 24/12/20 | Fri 18/06/21
1.22.8.5 | Maintain Conversion Courseware | 0% | 440 days | Mon 21/06/21 | Wed 22/03/23
1.22.9 | Deliver OFT & Conversion Training to Military Users | 0% | 1769 days | Fri 08/02/19 | Mon 09/03/26
1.22.9.1 | Training Delivery Method Agreed | 0% | 0 days | Fri 08/02/19 | Fri 08/02/19
1.22.9.2 | Prepare for OFT & Conversion Training Delivery | 0% | 117 days | Thu 24/12/20 | Fri 18/06/21
1.22.9.3 | Acquire Kit and Run OFT Training Pilot Course | 0% | 20 days | Mon 21/06/21 | Fri 16/07/21
1.22.9.4 | Deliver OFT Training | 0% | 480 days | Mon 19/07/21 | Tue 20/06/23
1.22.9.5 | OFT Training Delivered | 0% | 0 days | Tue 20/06/23 | Tue 20/06/23
1.22.9.6 | Deliver Conversion Training | 0% | 680 days | Wed 21/06/23 | Mon 09/03/26
1.22.9.7 | Conversion Training Delivered | 0% | 0 days | Mon 09/03/26 | Mon 09/03/26
1.23 | Fielding and Conversion Competition | 0% | 345 days | Fri 29/11/19 | Thu 22/04/21
1.23.1 | Dependencies from other Parties to BATCIS | 0% | 0 days | Fri 29/11/19 | Fri 29/11/19
1.23.1.1 | Fielding Strategy & Plan - (ARMY to provide) | 0% | 0 days | Fri 29/11/19 | Fri 29/11/19
1.23.2 | Fielding and Conversion Competition -ITN | 0% | 335 days | Fri 13/12/19 | Thu 22/04/21
1.23.2.1 | Mature F&C SOR Available | 0% | 0 days | Fri 13/12/19 | Fri 13/12/19
1.23.2.2 | Review LFE from similar F&C Competitions | 0% | 1 day | Mon 16/12/19 | Mon 16/12/19
1.23.2.3 | Complete F&C ISS Front Door Process | 0% | 5 days | Tue 17/12/19 | Mon 23/12/19
1.23.2.4 | Refine existing F&C SOR | 0% | 10 days | Tue 17/12/19 | Tue 07/01/20
1.23.2.5 | Obtain Security Exemptions and Security Aspects Letter (If needed) | 0% | 15 days | Wed 08/01/20 | Tue 28/01/20
1.23.2.6 | Draft F&C PIN | 0% | 3 days | Wed 29/01/20 | Fri 31/01/20
1.23.2.7 | Commercial Approval of F&C PIN | 0% | 1 day | Mon 03/02/20 | Mon 03/02/20
1.23.2.8 | Issue F&C PIN | 0% | 1 day | Tue 04/02/20 | Tue 04/02/20
1.23.2.9 | F&C PIN Issued | 0% | 0 days | Tue 04/02/20 | Tue 04/02/20
1.23.2.10 | Draft F&C Procurement Strategy - Start | 0% | 5 days | Wed 05/02/20 | Tue 11/02/20
1.23.2.11 | Draft F&C Procurement Strategy - Completion | 0% | 10 days | Wed 12/02/20 | Tue 25/02/20
1.23.2.12 | Draft F&C Commercial Strategy | 0% | 15 days | Wed 12/02/20 | Tue 03/03/20
1.23.2.13 | Approve F&C Procurement Strategy | 0% | 5 days | Wed 26/02/20 | Tue 03/03/20
1.23.2.14 | Approve F&C Commercial Strategy | 0% | 5 days | Wed 04/03/20 | Tue 10/03/20
1.23.2.15 | F&C Procurement & Commercial Strategies Agreed | 0% | 0 days | Tue 10/03/20 | Tue 10/03/20
1.23.2.16 | Raise F&C RCA | 0% | 1 day | Wed 11/03/20 | Wed 11/03/20
1.23.2.17 | Approve F&C RCA | 0% | 1 day | Thu 12/03/20 | Thu 12/03/20
1.23.2.18 | Submit F&C RCA to Commercial | 0% | 1 day | Fri 13/03/20 | Fri 13/03/20
1.23.2.19 | F&C Requirement Sufficiently Mature to run Competition | 0% | 0 days | Fri 13/03/20 | Fri 13/03/20
1.23.2.20 | Draft & Approve F&C Contract Notice | 0% | 1 day | Mon 16/03/20 | Mon 16/03/20
1.23.2.21 | Produce F&C DPQQ Part 1 - Commercial | 0% | 22 days | Tue 17/03/20 | Fri 17/04/20
1.23.2.22 | Produce F&C DPQQ Part 2 - Technical | 0% | 22 days | Tue 17/03/20 | Fri 17/04/20
1.23.2.23 | Develop F&C Evaluation Criteria | 0% | 15 days | Tue 17/03/20 | Mon 06/04/20
1.23.2.24 | Issue F&C DPQQ to Tenderers | 0% | 1 day | Mon 20/04/20 | Mon 20/04/20
1.23.2.25 | F&C DPQQ Issued | 0% | 0 days | Mon 20/04/20 | Mon 20/04/20
1.23.2.26 | Tenderers Produce F&C DPQQ Responses | 0% | 22 days | Tue 21/04/20 | Thu 21/05/20
1.23.2.27 | BATCIS Manage F&C CQs | 0% | 17 days | Tue 21/04/20 | Thu 14/05/20
1.23.2.28 | F&C DPQQ Responses Received | 0% | 0 days | Thu 21/05/20 | Thu 21/05/20
1.23.2.29 | Evaluate F&C DPQQ Responses | 0% | 15 days | Fri 22/05/20 | Fri 12/06/20
1.23.2.30 | Notify Down selected F&C Tenderers | 0% | 5 days | Mon 15/06/20 | Fri 19/06/20
1.23.2.31 | Notify Unsuccessful F&C Tenderers | 0% | 1 day | Mon 22/06/20 | Mon 22/06/20
1.23.2.32 | Hold F&C Debrief Sessions | 0% | 6 days | Tue 23/06/20 | Tue 30/06/20
1.23.2.33 | Produce F&C ITN | 0% | 55 days | Mon 16/03/20 | Thu 04/06/20
1.23.2.34 | Produce Draft F&C Contract | 0% | 50 days | Mon 16/03/20 | Thu 28/05/20
1.23.2.35 | Produce F&C Contract Management Plan | 0% | 50 days | Mon 16/03/20 | Thu 28/05/20
1.23.2.36 | F&C Defence Cyber Protection Partnership (DCPP) Risk Assessment | 0% | 1 day | Fri 29/05/20 | Fri 29/05/20
1.23.2.37 | Issue F&C ITN to Tenderers | 0% | 1 day | Wed 01/07/20 | Wed 01/07/20
1.23.2.38 | F&C ITN Issued | 0% | 0 days | Wed 01/07/20 | Wed 01/07/20
1.23.2.39 | Produce and Issue F&C Contract Bidders Notice | 0% | 1 day | Thu 02/07/20 | Thu 02/07/20
1.23.2.40 | Hold F&C Bidders Conference | 0% | 1 day | Fri 03/07/20 | Fri 03/07/20
1.23.2.41 | Tenderers Produces F&C ITN Response | 0% | 40 days | Thu 02/07/20 | Wed 26/08/20
1.23.2.42 | BATCIS Manage F&C CQs | 0% | 30 days | Thu 02/07/20 | Wed 12/08/20
1.23.2.43 | F&C ITN Responses Received | 0% | 0 days | Wed 26/08/20 | Wed 26/08/20
1.23.2.44 | Hold Evaluators Briefing | 0% | 1 day | Thu 27/08/20 | Thu 27/08/20
1.23.2.45 | Tender Board Process F&C Responses | 0% | 4 days | Fri 28/08/20 | Thu 03/09/20
1.23.2.46 | Tender Board Release F&C Responses to BATCIS Commercial | 0% | 0 days | Thu 03/09/20 | Thu 03/09/20
1.23.2.47 | Evaluation of F&C Affordability | 0% | 20 days | Fri 04/09/20 | Thu 01/10/20
1.23.2.48 | Evaluation of F&C T&Cs | 0% | 20 days | Fri 04/09/20 | Thu 01/10/20
1.23.2.49 | Individual Assessor Evaluation of F&C Technical & PM Aspects | 0% | 15 days | Fri 04/09/20 | Thu 24/09/20
1.23.2.50 | Achieve Consensus Evaluation of F&C Technical & PM Aspects | 0% | 10 days | Fri 25/09/20 | Thu 08/10/20
1.23.2.51 | Moderate results of F&C Evaluation | 0% | 5 days | Fri 09/10/20 | Thu 15/10/20
1.23.2.52 | Hold F&C TEP | 0% | 1 day | Fri 16/10/20 | Fri 16/10/20
1.23.2.53 | F&C TEP Held | 0% | 0 days | Fri 16/10/20 | Fri 16/10/20
1.23.2.54 | Prepare for F&C Negotiation | 0% | 20 days | Mon 19/10/20 | Fri 13/11/20
1.23.2.55 | Negotiate with F&C | 0% | 25 days | Mon 16/11/20 | Fri 18/12/20
1.23.2.56 | F&C Prepare and Submit BAFO | 0% | 10 days | Mon 21/12/20 | Mon 11/01/21
1.23.2.57 | F&C BAFO Received | 0% | 0 days | Mon 11/01/21 | Mon 11/01/21
1.23.2.58 | Individual Assessor Evaluation of F&C BAFO Technical & PM Aspects | 0% | 5 days | Tue 12/01/21 | Mon 18/01/21
1.23.2.59 | Achieve Consensus Evaluation of F&C BAFO Technical & PM Aspects | 0% | 5 days | Tue 19/01/21 | Mon 25/01/21
1.23.2.60 | Evaluation of F&C BAFO Affordability | 0% | 10 days | Tue 12/01/21 | Mon 25/01/21
1.23.2.61 | Moderate & Agree Results of F&C BAFO Technical & PM Evaluation | 0% | 5 days | Tue 26/01/21 | Mon 01/02/21
1.23.2.62 | Hold Post F&C BAFO TEP | 0% | 1 day | Tue 02/02/21 | Tue 02/02/21
1.23.2.63 | Produce F&C Commitment Case / 2 SMS Requests | 0% | 25 days | Wed 03/02/21 | Tue 09/03/21
1.23.2.64 | Notify Tenderers of Result of F&C Competition | 0% | 1 day | Wed 10/03/21 | Wed 10/03/21
1.23.2.65 | Finalise F&C Contract | 0% | 10 days | Thu 11/03/21 | Wed 24/03/21
1.23.2.66 | Debrief Unsuccessful F&C Tenderers | 0% | 15 days | Thu 11/03/21 | Wed 31/03/21
1.23.2.67 | F&C Contract Standstill Period | 0% | 8 days | Thu 01/04/21 | Wed 14/04/21
1.23.2.68 | Award F&C Contract | 0% | 1 day | Thu 15/04/21 | Thu 15/04/21
1.23.2.69 | F&C Contract Awarded | 0% | 0 days | Thu 15/04/21 | Thu 15/04/21
1.23.2.70 | F&C Contract Mobilisation | 0% | 5 days | Fri 16/04/21 | Thu 22/04/21
1.24 | OFT and Conversion | 0% | 1506 days | Fri 28/02/20 | Mon 09/03/26
1.24.1 | Dependencies from Army to BATCIS | 0% | 0 days | Fri 16/07/21 | Fri 16/07/21
1.24.1.1 | Vehicles to be converted for OFT available - (ARMY to provide) | 0% | 0 days | Fri 16/07/21 | Fri 16/07/21
1.24.2 | Fielding and Conversion Contract | 0% | 0 days | Thu 22/04/21 | Thu 22/04/21
1.24.2.1 | Fielding Partner Contract Start Date | 0% | 0 days | Thu 22/04/21 | Thu 22/04/21
1.24.3 | MPPS Manufacture | 0% | 1306 days | Fri 28/02/20 | Wed 21/05/25
1.24.3.1 | Long lead Items (Firm Price Agreed) | 0% | 130 days | Fri 28/02/20 | Thu 03/09/20
1.24.3.2 | Order Long lead Items | 0% | 80 days | Fri 04/09/20 | Thu 24/12/20
1.24.3.3 | Low Rate Manufacture of MPPS Units for OFT * | 0% | 240 days | Mon 19/07/21 | Mon 04/07/22
1.24.3.4 | High Rate Manufacture of MPPS Units for Fleet Conversion | 0% | 720 days | Tue 05/07/22 | Wed 21/05/25
1.24.4 | Prep for OFT & Conversion | 0% | 282 days | Fri 20/11/20 | Wed 12/01/22
1.24.4.1 | Perform Safety and Certification work needed for start of OFT | 0% | 120 days | Fri 20/11/20 | Wed 19/05/21
1.24.4.2 | Handover between PI Contractor F&C Contractor | 0% | 60 days | Fri 23/04/21 | Mon 19/07/21
1.24.4.3 | Perform any remaining Safety and Certification work needed for OFT and Fleet conversion | 0% | 120 days | Tue 20/07/21 | Wed 12/01/22
1.24.5 | Conversion and Training | 0% | 1160 days | Mon 19/07/21 | Mon 09/03/26
1.24.5.1 | Convert and Train 20 Vehicles of Brigade XXX * | 0% | 40 days | Mon 19/07/21 | Mon 13/09/21
1.24.5.2 | Convert and Train 2 Battle Groups of Brigade XXX * | 0% | 240 days | Tue 14/09/21 | Tue 30/08/22
1.24.5.3 | Convert and Train remaining elements of Brigade XXX * | 0% | 40 days | Thu 23/02/23 | Fri 21/04/23
1.24.5.4 | Convert and Train Rest of the Fleet * | 0% | 720 days | Mon 24/04/23 | Mon 09/03/26
1.24.6 | Testing at Scale | 0% | 1120 days | Tue 14/09/21 | Mon 09/03/26
1.24.6.1 | Testing at Scale | 0% | 240 days | Tue 14/09/21 | Tue 30/08/22
1.24.6.2 | Battle Group Exercise * | 0% | 60 days | Wed 31/08/22 | Tue 22/11/22
1.24.6.3 | Rework | 0% | 60 days | Wed 23/11/22 | Wed 22/02/23
1.24.6.4 | EvO IOC * | 0% | 0 days | Fri 21/04/23 | Fri 21/04/23
1.24.6.5 | EvO FOC | 0% | 0 days | Mon 09/03/26 | Mon 09/03/26
1.25 | MSP's | 0% | 1825 days | Thu 27/02/20 | Fri 18/06/27
1.25.1 | MSP Applications Competition - ITN | 0% | 625 days | Thu 27/02/20 | Fri 26/08/22
1.25.1.1 | RN5 outletter | 0% | 0 days | Thu 27/02/20 | Thu 27/02/20
1.25.1.2 | Produce MSP Applications Competition Data Pack | 0% | 100 days | Fri 28/02/20 | Wed 22/07/20
1.25.1.3 | Mature MSP Applications Data Pack Available | 0% | 0 days | Wed 22/07/20 | Wed 22/07/20
1.25.1.4 | Start MSP Applications Competition | 0% | 0 days | Thu 27/02/20 | Thu 27/02/20
1.25.1.5 | Review LFE from Similar Competitions | 0% | 1 day | Fri 28/02/20 | Fri 28/02/20
1.25.1.6 | Refine existing MSP Applications SOR | 0% | 10 days | Thu 23/07/20 | Wed 05/08/20
1.25.1.7 | Obtain Security Exemptions and Security Aspects Letter (If needed) | 0% | 15 days | Thu 06/08/20 | Wed 26/08/20
1.25.1.8 | Draft MSP Applications PIN | 0% | 3 days | Thu 27/08/20 | Tue 01/09/20
1.25.1.9 | Commercial Approval of MSP Applications PIN | 0% | 1 day | Wed 02/09/20 | Wed 02/09/20
1.25.1.10 | Issue MSP Applications PIN | 0% | 1 day | Thu 03/09/20 | Thu 03/09/20
1.25.1.11 | MSP Applications PIN Issued | 0% | 0 days | Thu 03/09/20 | Thu 03/09/20
1.25.1.12 | Draft MSP Applications Procurement Strategy - Start | 0% | 5 days | Fri 04/09/20 | Thu 10/09/20
1.25.1.13 | Draft MSP Applications Procurement Strategy - Completion | 0% | 10 days | Fri 11/09/20 | Thu 24/09/20
1.25.1.14 | Draft MSP Applications Commercial Strategy | 0% | 15 days | Fri 11/09/20 | Thu 01/10/20
1.25.1.15 | Approve MSP Applications Procurement Strategy | 0% | 5 days | Fri 25/09/20 | Thu 01/10/20
1.25.1.16 | Approve MSP Applications Commercial Strategy | 0% | 5 days | Fri 02/10/20 | Thu 08/10/20
1.25.1.17 | MSP Applications Procurement & Commercial Strategies Agreed | 0% | 0 days | Thu 08/10/20 | Thu 08/10/20
1.25.1.18 | Raise MSP Applications RCA | 0% | 1 day | Fri 09/10/20 | Fri 09/10/20
1.25.1.19 | Approve MSP Applications RCA | 0% | 1 day | Mon 12/10/20 | Mon 12/10/20
1.25.1.20 | Submit MSP Applications RCA to Commercial | 0% | 1 day | Tue 13/10/20 | Tue 13/10/20
1.25.1.21 | MSP Applications Requirement Sufficiently Mature to run Competition | 0% | 0 days | Tue 13/10/20 | Tue 13/10/20
1.25.1.22 | Draft MSP Applications & Approve Contract Notice | 0% | 1 day | Wed 14/10/20 | Wed 14/10/20
1.25.1.23 | Produce MSP Applications DPQQ Part 1 - Commercial | 0% | 22 days | Thu 15/10/20 | Fri 13/11/20
1.25.1.24 | Produce MSP Applications DPQQ Part 2 - Technical | 0% | 22 days | Thu 15/10/20 | Fri 13/11/20
1.25.1.25 | Develop MSP Applications Evaluation Criteria | 0% | 15 days | Thu 15/10/20 | Wed 04/11/20
1.25.1.26 | Issue MSP Applications DPQQ to Tenderers | 0% | 1 day | Mon 16/11/20 | Mon 16/11/20
1.25.1.27 | MSP Applications DPQQ Issued | 0% | 0 days | Mon 16/11/20 | Mon 16/11/20
1.25.1.28 | Tenderers Produce MSP Applications DPQQ Responses | 0% | 22 days | Tue 17/11/20 | Wed 16/12/20
1.25.1.29 | BATCIS Manage MSP Applications CQs | 0% | 17 days | Tue 17/11/20 | Wed 09/12/20
1.25.1.30 | MSP Applications DPQQ Responses Received | 0% | 0 days | Wed 16/12/20 | Wed 16/12/20
1.25.1.31 | Evaluate & Moderation of MSP Applications DPQQ Responses | 0% | 20 days | Thu 17/12/20 | Thu 21/01/21
1.25.1.32 | Notify Down selected MSP Applications Tenderers | 0% | 5 days | Fri 22/01/21 | Thu 28/01/21
1.25.1.33 | Notify Unsuccessful MSP Applications Tenderers | 0% | 1 day | Fri 29/01/21 | Fri 29/01/21
1.25.1.34 | Hold MSP Applications Debrief Sessions | 0% | 6 days | Mon 01/02/21 | Mon 08/02/21
1.25.1.35 | Produce MSP Applications ITN | 0% | 50 days | Fri 23/04/21 | Mon 05/07/21
1.25.1.36 | Evaluation Criteria Review with Defence Economics & CASDD | 0% | 15 days | Tue 06/07/21 | Mon 26/07/21
1.25.1.37 | Produce Draft MSP Applications Contract | 0% | 50 days | Wed 14/10/20 | Tue 22/12/20
1.25.1.38 | Produce MSP Applications Contract Management Plan | 0% | 50 days | Wed 14/10/20 | Tue 22/12/20
1.25.1.39 | MSP Defence Cyber Protection Partnership (DCPP) Risk Assessment | 0% | 1 day | Wed 23/12/20 | Wed 23/12/20
1.25.1.40 | Issue MSP Applications ITN to Tenderers | 0% | 1 day | Tue 27/07/21 | Tue 27/07/21
1.25.1.41 | MSP Applications ITN Issued | 0% | 0 days | Tue 27/07/21 | Tue 27/07/21
1.25.1.42 | Produce and Issue MSP Applications Contract Bidders Notice | 0% | 1 day | Wed 28/07/21 | Wed 28/07/21
1.25.1.43 | Hold MSP Applications Bidders Conference | 0% | 1 day | Thu 29/07/21 | Thu 29/07/21
1.25.1.44 | Tenderers Produce MSP Applications ITN Response | 0% | 40 days | Wed 28/07/21 | Wed 22/09/21
1.25.1.45 | BATCIS Manage MSP Applications CQs | 0% | 30 days | Wed 28/07/21 | Wed 08/09/21
1.25.1.46 | MSP Applications ITN Responses Received | 0% | 0 days | Wed 22/09/21 | Wed 22/09/21
1.25.1.47 | Tender Board Process MSP Applications Responses | 0% | 5 days | Thu 23/09/21 | Wed 29/09/21
1.25.1.48 | Tender Board Release MSP Applications Responses to BATCIS Commercial | 0% | 0 days | Wed 29/09/21 | Wed 29/09/21
1.25.1.49 | Evaluation of MSP Applications Affordability | 0% | 20 days | Thu 30/09/21 | Wed 27/10/21
1.25.1.50 | Evaluation of MSP Applications T&Cs | 0% | 20 days | Thu 30/09/21 | Wed 27/10/21
1.25.1.51 | Individual Assessor Evaluation of MSP Applications Technical & PM Aspects | 0% | 15 days | Thu 30/09/21 | Wed 20/10/21
1.25.1.52 | Achieve Consensus Evaluation of MSP Applications Technical & PM Aspects | 0% | 10 days | Thu 21/10/21 | Wed 03/11/21
1.25.1.53 | Moderate results of MSP Applications Evaluation | 0% | 5 days | Thu 04/11/21 | Wed 10/11/21
1.25.1.54 | Hold MSP Applications TEP | 0% | 1 day | Thu 11/11/21 | Thu 11/11/21
1.25.1.55 | MSP Applications TEP Held | 0% | 0 days | Thu 11/11/21 | Thu 11/11/21
1.25.1.56 | Prepare for MSP Applications Negotiation | 0% | 20 days | Fri 12/11/21 | Thu 09/12/21
1.25.1.57 | Negotiate with MSP Applications ( Assumed three companies, not allowed 1 company, direction from central legal) | 0% | 35 days | Fri 10/12/21 | Fri 04/02/22
1.25.1.58 | Industry Prepare and Submit MSP Applications BAFO | 0% | 10 days | Mon 07/02/22 | Fri 18/02/22
1.25.1.59 | MSP Applications BAFO Received | 0% | 0 days | Fri 18/02/22 | Fri 18/02/22
1.25.1.60 | Individual Assessor Evaluation of MSP Applications BAFO Technical & PM Aspects | 0% | 15 days | Mon 21/02/22 | Fri 11/03/22
1.25.1.61 | Achieve Consensus Evaluation of MSP Applications BAFO Technical & PM Aspects | 0% | 15 days | Mon 14/03/22 | Fri 01/04/22
1.25.1.62 | Evaluation of MSP Applications BAFO Affordability | 0% | 30 days | Mon 21/02/22 | Fri 01/04/22
1.25.1.63 | Moderate & Agree Results of MSP Applications BAFO Technical & PM Evaluation | 0% | 15 days | Mon 04/04/22 | Tue 26/04/22
1.25.1.64 | Hold Post MSP Applications BAFO TEP | 0% | 1 day | Wed 27/04/22 | Wed 27/04/22
1.25.1.65 | Produce MSP Applications Commitment Case / 2 SMS Requests | 0% | 25 days | Thu 28/04/22 | Fri 03/06/22
1.25.1.66 | Notify Tenderers of Result of MSP Applications Competition | 0% | 1 day | Mon 06/06/22 | Mon 06/06/22
1.25.1.67 | Finalise MSP Applications Contract | 0% | 10 days | Tue 07/06/22 | Mon 20/06/22
1.25.1.68 | Debrief Unsuccessful MSP Applications Tenderers | 0% | 15 days | Tue 07/06/22 | Mon 27/06/22
1.25.1.69 | CASDD Pre-Contract Award Review (Due Diligence) | 0% | 30 days | Tue 28/06/22 | Mon 08/08/22
1.25.1.70 | MSP Applications Contract Standstill Period | 0% | 8 days | Tue 09/08/22 | Thu 18/08/22
1.25.1.71 | Award MSP Applications Contract | 0% | 1 day | Fri 19/08/22 | Fri 19/08/22
1.25.1.72 | MSP Applications Contract Awarded | 0% | 0 days | Fri 19/08/22 | Fri 19/08/22
1.25.1.73 | MSP Applications Contract Mobilisation | 0% | 5 days | Mon 22/08/22 | Fri 26/08/22
1.25.1.74 | MSP Applications Contract Start Date | 0% | 0 days | Fri 26/08/22 | Fri 26/08/22
1.25.2 | MSP Applications Contract | 0% | 1200 days | Tue 30/08/22 | Fri 18/06/27
1.25.2.1 | MSP Applications Operational | 0% | 1200 days | Tue 30/08/22 | Fri 18/06/27
1.25.3 | MSP Infrastructure / Networks Competition - ITN | 0% | 625 days | Thu 27/02/20 | Fri 26/08/22
1.25.3.1 | RN5 outletter | 0% | 0 days | Thu 27/02/20 | Thu 27/02/20
1.25.3.2 | Produce MSP Infrastructure / Networks Competition Data Pack | 0% | 100 days | Fri 28/02/20 | Wed 22/07/20
1.25.3.3 | Mature MSP Infrastructure / Networks Data Pack Available | 0% | 0 days | Wed 22/07/20 | Wed 22/07/20
1.25.3.4 | Start MSP Infrastructure / Networks Competition | 0% | 0 days | Thu 27/02/20 | Thu 27/02/20
1.25.3.5 | Review LFE from Similar Competitions | 0% | 1 day | Fri 28/02/20 | Fri 28/02/20
1.25.3.6 | Refine existing MSP Infrastructure / Networks SOR | 0% | 10 days | Thu 23/07/20 | Wed 05/08/20
1.25.3.7 | Obtain Security Exemptions and Security Aspects Letter (If needed) | 0% | 15 days | Thu 06/08/20 | Wed 26/08/20
1.25.3.8 | Draft MSP Infrastructure / Networks PIN | 0% | 3 days | Thu 27/08/20 | Tue 01/09/20
1.25.3.9 | Commercial Approval of MSP Infrastructure / Networks PIN | 0% | 1 day | Wed 02/09/20 | Wed 02/09/20
1.25.3.10 | Issue MSP Infrastructure / Networks PIN | 0% | 1 day | Thu 03/09/20 | Thu 03/09/20
1.25.3.11 | MSP Infrastructure / Networks PIN Issued | 0% | 0 days | Thu 03/09/20 | Thu 03/09/20
1.25.3.12 | Draft MSP Infrastructure / Networks Procurement Strategy - Start | 0% | 5 days | Fri 04/09/20 | Thu 10/09/20
1.25.3.13 | Draft MSP Infrastructure / Networks Procurement Strategy - Completion | 0% | 10 days | Fri 11/09/20 | Thu 24/09/20
1.25.3.14 | Draft MSP Infrastructure / Networks Commercial Strategy | 0% | 15 days | Fri 11/09/20 | Thu 01/10/20
1.25.3.15 | Approve MSP Infrastructure / Networks Procurement Strategy | 0% | 5 days | Fri 25/09/20 | Thu 01/10/20
1.25.3.16 | Approve MSP Infrastructure / Networks Commercial Strategy | 0% | 5 days | Fri 02/10/20 | Thu 08/10/20
1.25.3.17 | MSP Infrastructure / Networks Procurement & Commercial Strategies Agreed | 0% | 0 days | Thu 08/10/20 | Thu 08/10/20
1.25.3.18 | Raise MSP Infrastructure / Networks RCA | 0% | 1 day | Fri 09/10/20 | Fri 09/10/20
1.25.3.19 | Approve MSP Infrastructure / Networks RCA | 0% | 1 day | Mon 12/10/20 | Mon 12/10/20
1.25.3.20 | Submit MSP Infrastructure / Networks RCA to Commercial | 0% | 1 day | Tue 13/10/20 | Tue 13/10/20
1.25.3.21 | MSP Infrastructure / Networks Requirement Sufficiently Mature to run Competition | 0% | 0 days | Tue 13/10/20 | Tue 13/10/20
1.25.3.22 | Draft MSP Infrastructure / Networks & Approve Contract Notice | 0% | 1 day | Wed 14/10/20 | Wed 14/10/20
1.25.3.23 | Produce MSP Infrastructure / Networks DPQQ Part 1 - Commercial | 0% | 22 days | Thu 15/10/20 | Fri 13/11/20
1.25.3.24 | Produce MSP Infrastructure / Networks DPQQ Part 2 - Technical | 0% | 22 days | Thu 15/10/20 | Fri 13/11/20
1.25.3.25 | Develop MSP Infrastructure / Networks Evaluation Criteria | 0% | 15 days | Thu 15/10/20 | Wed 04/11/20
1.25.3.26 | Issue MSP Infrastructure / Networks DPQQ to Tenderers | 0% | 1 day | Mon 16/11/20 | Mon 16/11/20
1.25.3.27 | MSP Infrastructure / Networks DPQQ Issued | 0% | 0 days | Mon 16/11/20 | Mon 16/11/20
1.25.3.28 | Tenderers Produce MSP Infrastructure / Networks DPQQ Responses | 0% | 22 days | Tue 17/11/20 | Wed 16/12/20
1.25.3.29 | BATCIS Manage MSP Infrastructure / Networks CQs | 0% | 17 days | Tue 17/11/20 | Wed 09/12/20
1.25.3.30 | MSP Infrastructure / Networks DPQQ Responses Received | 0% | 0 days | Wed 16/12/20 | Wed 16/12/20
1.25.3.31 | Evaluate & Moderation of MSP Infrastructure / Networks DPQQ Responses | 0% | 20 days | Thu 17/12/20 | Thu 21/01/21
1.25.3.32 | Notify Down selected MSP Infrastructure / Networks Tenderers | 0% | 5 days | Fri 22/01/21 | Thu 28/01/21
1.25.3.33 | Notify Unsuccessful MSP Infrastructure / Networks Tenderers | 0% | 1 day | Fri 29/01/21 | Fri 29/01/21
1.25.3.34 | Hold MSP Infrastructure / Networks Debrief Sessions | 0% | 6 days | Mon 01/02/21 | Mon 08/02/21
1.25.3.35 | Produce MSP Infrastructure / Networks ITN | 0% | 50 days | Fri 23/04/21 | Mon 05/07/21
1.25.3.36 | Evaluation Criteria Review with Defence Economics & CASDD | 0% | 15 days | Tue 06/07/21 | Mon 26/07/21
1.25.3.37 | Produce Draft MSP Infrastructure / Networks Contract | 0% | 50 days | Wed 14/10/20 | Tue 22/12/20
1.25.3.38 | Produce MSP Infrastructure / Networks Contract Management Plan | 0% | 50 days | Wed 14/10/20 | Tue 22/12/20
1.25.3.39 | MSP Defence Cyber Protection Partnership (DCPP) Risk Assessment | 0% | 1 day | Wed 23/12/20 | Wed 23/12/20
1.25.3.40 | Issue MSP Infrastructure / Networks ITN to Tenderers | 0% | 1 day | Tue 27/07/21 | Tue 27/07/21
1.25.3.41 | MSP Infrastructure / Networks ITN Issued | 0% | 0 days | Tue 27/07/21 | Tue 27/07/21
1.25.3.42 | Produce and Issue MSP Infrastructure / Networks Contract Bidders Notice | 0% | 1 day | Wed 28/07/21 | Wed 28/07/21
1.25.3.43 | Hold MSP Infrastructure / Networks Bidders Conference | 0% | 1 day | Thu 29/07/21 | Thu 29/07/21
1.25.3.44 | Tenderers Produce MSP Infrastructure / Networks ITN Response | 0% | 40 days | Wed 28/07/21 | Wed 22/09/21
1.25.3.45 | BATCIS Manage MSP Infrastructure / Networks CQs | 0% | 30 days | Wed 28/07/21 | Wed 08/09/21
1.25.3.46 | MSP Infrastructure / Networks ITN Responses Received | 0% | 0 days | Wed 22/09/21 | Wed 22/09/21
1.25.3.47 | Tender Board Process MSP Infrastructure / Networks Responses | 0% | 5 days | Thu 23/09/21 | Wed 29/09/21
1.25.3.48 | Tender Board Release MSP Infrastructure / Networks Responses to BATCIS Commercial | 0% | 0 days | Wed 29/09/21 | Wed 29/09/21
1.25.3.49 | Evaluation of MSP Infrastructure / Networks Affordability | 0% | 20 days | Thu 30/09/21 | Wed 27/10/21
1.25.3.50 | Evaluation of MSP Infrastructure / Networks T&Cs | 0% | 20 days | Thu 30/09/21 | Wed 27/10/21
1.25.3.51 | Individual Assessor Evaluation of MSP Infrastructure / Networks Technical & PM Aspects | 0% | 15 days | Thu 30/09/21 | Wed 20/10/21
1.25.3.52 | Achieve Consensus Evaluation of MSP Infrastructure / Networks Technical & PM Aspects | 0% | 10 days | Thu 21/10/21 | Wed 03/11/21
1.25.3.53 | Moderate results of MSP Infrastructure / Networks Evaluation | 0% | 5 days | Thu 04/11/21 | Wed 10/11/21
1.25.3.54 | Hold MSP Infrastructure / Networks TEP | 0% | 1 day | Thu 11/11/21 | Thu 11/11/21
1.25.3.55 | MSP Infrastructure / Networks TEP Held | 0% | 0 days | Thu 11/11/21 | Thu 11/11/21
1.25.3.56 | Prepare for MSP Infrastructure / Networks Negotiation | 0% | 20 days | Fri 12/11/21 | Thu 09/12/21
1.25.3.57 | Negotiate with MSP Infrastructure / Networks ( Assumed three companies, not allowed 1 company, direction from central legal) | 0% | 35 days | Fri 10/12/21 | Fri 04/02/22
1.25.3.58 | Industry Prepare and Submit MSP Infrastructure / Networks BAFO | 0% | 10 days | Mon 07/02/22 | Fri 18/02/22
1.25.3.59 | MSP Infrastructure / Networks BAFO Received | 0% | 0 days | Fri 18/02/22 | Fri 18/02/22
1.25.3.60 | Individual Assessor Evaluation of MSP Infrastructure / Networks BAFO Technical & PM Aspects | 0% | 15 days | Mon 21/02/22 | Fri 11/03/22
1.25.3.61 | Achieve Consensus Evaluation of MSP Infrastructure / Networks BAFO Technical & PM Aspects | 0% | 15 days | Mon 14/03/22 | Fri 01/04/22
1.25.3.62 | Evaluation of MSP Infrastructure / Networks BAFO Affordability | 0% | 30 days | Mon 21/02/22 | Fri 01/04/22
1.25.3.63 | Moderate & Agree Results of MSP Infrastructure / Networks BAFO Technical & PM Evaluation | 0% | 15 days | Mon 04/04/22 | Tue 26/04/22
1.25.3.64 | Hold Post MSP Infrastructure / Networks BAFO TEP | 0% | 1 day | Wed 27/04/22 | Wed 27/04/22
1.25.3.65 | Produce MSP Infrastructure / Networks Commitment Case / 2 SMS Requests | 0% | 25 days | Thu 28/04/22 | Fri 03/06/22
1.25.3.66 | Notify Tenderers of Result of MSP Infrastructure / Networks Competition | 0% | 1 day | Mon 06/06/22 | Mon 06/06/22
1.25.3.67 | Finalise MSP Infrastructure / Networks Contract | 0% | 10 days | Tue 07/06/22 | Mon 20/06/22
1.25.3.68 | Debrief Unsuccessful MSP Infrastructure / Networks Tenderers | 0% | 15 days | Tue 07/06/22 | Mon 27/06/22
1.25.3.69 | CASDD Pre-Contract Award Review (Due Diligence) | 0% | 30 days | Tue 28/06/22 | Mon 08/08/22
1.25.3.70 | MSP Infrastructure / Networks Contract Standstill Period | 0% | 8 days | Tue 09/08/22 | Thu 18/08/22
1.25.3.71 | Award MSP Infrastructure / Networks Contract | 0% | 1 day | Fri 19/08/22 | Fri 19/08/22
1.25.3.72 | MSP Infrastructure / Networks Contract Awarded | 0% | 0 days | Fri 19/08/22 | Fri 19/08/22
1.25.3.73 | MSP Infrastructure / Networks Contract Mobilisation | 0% | 5 days | Mon 22/08/22 | Fri 26/08/22
1.25.3.74 | MSP Infrastructure / Networks Contract Start Date | 0% | 0 days | Fri 26/08/22 | Fri 26/08/22
1.25.4 | MSP Infrastructure / Networks Contract | 0% | 1200 days | Tue 30/08/22 | Fri 18/06/27
1.25.4.1 | MSP Infrastructure / Networks Operational | 0% | 1200 days | Tue 30/08/22 | Fri 18/06/27
1.25.5 | MSP Bearers Competition - ITN | 0% | 625 days | Thu 27/02/20 | Fri 26/08/22
1.25.5.1 | RN5 outletter | 0% | 0 days | Thu 27/02/20 | Thu 27/02/20
1.25.5.2 | Produce MSP Bearers Competition Data Pack | 0% | 100 days | Fri 28/02/20 | Wed 22/07/20
1.25.5.3 | Mature MSP Bearers Data Pack Available | 0% | 0 days | Wed 22/07/20 | Wed 22/07/20
1.25.5.4 | Start MSP Bearers Competition | 0% | 0 days | Thu 27/02/20 | Thu 27/02/20
1.25.5.5 | Review LFE from Similar Competitions | 0% | 1 day | Fri 28/02/20 | Fri 28/02/20
1.25.5.6 | Refine existing MSP Bearers SOR | 0% | 10 days | Thu 23/07/20 | Wed 05/08/20
1.25.5.7 | Obtain Security Exemptions and Security Aspects Letter (If needed) | 0% | 15 days | Thu 06/08/20 | Wed 26/08/20
1.25.5.8 | Draft MSP Bearers PIN | 0% | 3 days | Thu 27/08/20 | Tue 01/09/20
1.25.5.9 | Commercial Approval of MSP Bearers PIN | 0% | 1 day | Wed 02/09/20 | Wed 02/09/20
1.25.5.10 | Issue MSP Bearers PIN | 0% | 1 day | Thu 03/09/20 | Thu 03/09/20
1.25.5.11 | MSP Bearers PIN Issued | 0% | 0 days | Thu 03/09/20 | Thu 03/09/20
1.25.5.12 | Draft MSP Bearers Procurement Strategy - Start | 0% | 5 days | Fri 04/09/20 | Thu 10/09/20
1.25.5.13 | Draft MSP Bearers Procurement Strategy - Completion | 0% | 10 days | Fri 11/09/20 | Thu 24/09/20
1.25.5.14 | Draft MSP Bearers Commercial Strategy | 0% | 15 days | Fri 11/09/20 | Thu 01/10/20
1.25.5.15 | Approve MSP Bearers Procurement Strategy | 0% | 5 days | Fri 25/09/20 | Thu 01/10/20
1.25.5.16 | Approve MSP Bearers Commercial Strategy | 0% | 5 days | Fri 02/10/20 | Thu 08/10/20
1.25.5.17 | MSP Bearers Procurement & Commercial Strategies Agreed | 0% | 0 days | Thu 08/10/20 | Thu 08/10/20
1.25.5.18 | Raise MSP Bearers RCA | 0% | 1 day | Fri 09/10/20 | Fri 09/10/20
1.25.5.19 | Approve MSP Bearers RCA | 0% | 1 day | Mon 12/10/20 | Mon 12/10/20
1.25.5.20 | Submit MSP Bearers RCA to Commercial | 0% | 1 day | Tue 13/10/20 | Tue 13/10/20
1.25.5.21 | MSP Bearers Requirement Sufficiently Mature to run Competition | 0% | 0 days | Tue 13/10/20 | Tue 13/10/20
1.25.5.22 | Draft MSP Bearers & Approve Contract Notice | 0% | 1 day | Wed 14/10/20 | Wed 14/10/20
1.25.5.23 | Produce MSP Bearers DPQQ Part 1 - Commercial | 0% | 22 days | Thu 15/10/20 | Fri 13/11/20
1.25.5.24 | Produce MSP Bearers DPQQ Part 2 - Technical | 0% | 22 days | Thu 15/10/20 | Fri 13/11/20
1.25.5.25 | Develop MSP Bearers Evaluation Criteria | 0% | 15 days | Thu 15/10/20 | Wed 04/11/20
1.25.5.26 | Issue MSP Bearers DPQQ to Tenderers | 0% | 1 day | Mon 16/11/20 | Mon 16/11/20
1.25.5.27 | MSP Bearers DPQQ Issued | 0% | 0 days | Mon 16/11/20 | Mon 16/11/20
1.25.5.28 | Tenderers Produce MSP Bearers DPQQ Responses | 0% | 22 days | Tue 17/11/20 | Wed 16/12/20
1.25.5.29 | BATCIS Manage MSP Bearers CQs | 0% | 17 days | Tue 17/11/20 | Wed 09/12/20
1.25.5.30 | MSP Bearers DPQQ Responses Received | 0% | 0 days | Wed 16/12/20 | Wed 16/12/20
1.25.5.31 | Evaluate & Moderation of MSP Bearers DPQQ Responses | 0% | 20 days | Thu 17/12/20 | Thu 21/01/21
1.25.5.32 | Notify Down selected MSP Bearers Tenderers | 0% | 5 days | Fri 22/01/21 | Thu 28/01/21
1.25.5.33 | Notify Unsuccessful MSP Bearers Tenderers | 0% | 1 day | Fri 29/01/21 | Fri 29/01/21
1.25.5.34 | Hold MSP Bearers Debrief Sessions | 0% | 6 days | Mon 01/02/21 | Mon 08/02/21
1.25.5.35 | Produce MSP Bearers ITN | 0% | 50 days | Fri 23/04/21 | Mon 05/07/21
1.25.5.36 | Evaluation Criteria Review with Defence Economics & CASDD | 0% | 15 days | Tue 06/07/21 | Mon 26/07/21
1.25.5.37 | Produce Draft MSP Bearers Contract | 0% | 50 days | Wed 14/10/20 | Tue 22/12/20
1.25.5.38 | Produce MSP Bearers Contract Management Plan | 0% | 50 days | Wed 14/10/20 | Tue 22/12/20
1.25.5.39 | MSP Defence Cyber Protection Partnership (DCPP) Risk Assessment | 0% | 1 day | Wed 23/12/20 | Wed 23/12/20
1.25.5.40 | Issue MSP Bearers ITN to Tenderers | 0% | 1 day | Tue 27/07/21 | Tue 27/07/21
1.25.5.41 | MSP Bearers ITN Issued | 0% | 0 days | Tue 27/07/21 | Tue 27/07/21
1.25.5.42 | Produce and Issue MSP Bearers Contract Bidders Notice | 0% | 1 day | Wed 28/07/21 | Wed 28/07/21
1.25.5.43 | Hold MSP Bearers Bidders Conference | 0% | 1 day | Thu 29/07/21 | Thu 29/07/21
1.25.5.44 | Tenderers Produce MSP Bearers ITN Response | 0% | 40 days | Wed 28/07/21 | Wed 22/09/21
1.25.5.45 | BATCIS Manage MSP Bearers CQs | 0% | 30 days | Wed 28/07/21 | Wed 08/09/21
1.25.5.46 | MSP Bearers ITN Responses Received | 0% | 0 days | Wed 22/09/21 | Wed 22/09/21
1.25.5.47 | Tender Board Process MSP Bearers Responses | 0% | 5 days | Thu 23/09/21 | Wed 29/09/21
1.25.5.48 | Tender Board Release MSP Bearers Responses to BATCIS Commercial | 0% | 0 days | Wed 29/09/21 | Wed 29/09/21
1.25.5.49 | Evaluation of MSP Bearers Affordability | 0% | 20 days | Thu 30/09/21 | Wed 27/10/21
1.25.5.50 | Evaluation of MSP Bearers T&Cs | 0% | 20 days | Thu 30/09/21 | Wed 27/10/21
1.25.5.51 | Individual Assessor Evaluation of MSP Bearers Technical & PM Aspects | 0% | 15 days | Thu 30/09/21 | Wed 20/10/21
1.25.5.52 | Achieve Consensus Evaluation of MSP Bearers Technical & PM Aspects | 0% | 10 days | Thu 21/10/21 | Wed 03/11/21
1.25.5.53 | Moderate results of MSP Bearers Evaluation | 0% | 5 days | Thu 04/11/21 | Wed 10/11/21
1.25.5.54 | Hold MSP Bearers TEP | 0% | 1 day | Thu 11/11/21 | Thu 11/11/21
1.25.5.55 | MSP Bearers TEP Held | 0% | 0 days | Thu 11/11/21 | Thu 11/11/21
1.25.5.56 | Prepare for MSP Bearers Negotiation | 0% | 20 days | Fri 12/11/21 | Thu 09/12/21
1.25.5.57 | Negotiate with MSP Bearers ( Assumed three companies, not allowed 1 company, direction from central legal) | 0% | 35 days | Fri 10/12/21 | Fri 04/02/22
1.25.5.58 | Industry Prepare and Submit MSP Bearers BAFO | 0% | 10 days | Mon 07/02/22 | Fri 18/02/22
1.25.5.59 | MSP Bearers BAFO Received | 0% | 0 days | Fri 18/02/22 | Fri 18/02/22
1.25.5.60 | Individual Assessor Evaluation of MSP Bearers BAFO Technical & PM Aspects | 0% | 15 days | Mon 21/02/22 | Fri 11/03/22
1.25.5.61 | Achieve Consensus Evaluation of MSP Bearers BAFO Technical & PM Aspects | 0% | 15 days | Mon 14/03/22 | Fri 01/04/22
1.25.5.62 | Evaluation of MSP Bearers BAFO Affordability | 0% | 30 days | Mon 21/02/22 | Fri 01/04/22
1.25.5.63 | Moderate & Agree Results of MSP Bearers BAFO Technical & PM Evaluation | 0% | 15 days | Mon 04/04/22 | Tue 26/04/22
1.25.5.64 | Hold Post MSP Bearers BAFO TEP | 0% | 1 day | Wed 27/04/22 | Wed 27/04/22
1.25.5.65 | Produce MSP Bearers Commitment Case / 2 SMS Requests | 0% | 25 days | Thu 28/04/22 | Fri 03/06/22
1.25.5.66 | Notify Tenderers of Result of MSP Bearers Competition | 0% | 1 day | Mon 06/06/22 | Mon 06/06/22
1.25.5.67 | Finalise MSP Bearers Contract | 0% | 10 days | Tue 07/06/22 | Mon 20/06/22
1.25.5.68 | Debrief Unsuccessful MSP Bearers Tenderers | 0% | 15 days | Tue 07/06/22 | Mon 27/06/22
1.25.5.69 | CASDD Pre-Contract Award Review (Due Diligence) | 0% | 30 days | Tue 28/06/22 | Mon 08/08/22
1.25.5.70 | MSP Bearers Contract Standstill Period | 0% | 8 days | Tue 09/08/22 | Thu 18/08/22
1.25.5.71 | Award MSP Bearers Contract | 0% | 1 day | Fri 19/08/22 | Fri 19/08/22
1.25.5.72 | MSP Bearers Contract Awarded | 0% | 0 days | Fri 19/08/22 | Fri 19/08/22
1.25.5.73 | MSP Bearers Contract Mobilisation | 0% | 5 days | Mon 22/08/22 | Fri 26/08/22
1.25.5.74 | MSP Bearers Contract Start Date | 0% | 0 days | Fri 26/08/22 | Fri 26/08/22
1.25.6 | MSP Bearers Contract | 0% | 1200 days | Tue 30/08/22 | Fri 18/06/27
1.25.6.1 | MSP Bearers Operational | 0% | 1200 days | Tue 30/08/22 | Fri 18/06/27
1.26 | MORPHEUS Schedule End Point | 0% | 0 days | Fri 18/06/27 | Fri 18/06/27