## Sheet1
CLARIFICATION LOG
Tender: | Design Tender - Roof Repair Works (MEND) - Royal Institution of Cornwall
Tender Reference: | 10/2023_(03)
Published Date: | 2023-10-12
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | Are the site visits on the same day / time for all suppliers. | Yes. We have updated the Volume 1 - Timetable to afford the opportunity for Site Visits but these will be on set days / times – 13/10/2023 at 10:30 or 18/10/2023 at 13:00 Please contact Authorised Representative to arrange. | 2023-10-06
2 | How is the project being funded? | Funded by the Arts Council and Cornwall Council. | 2023-10-12
3 | Has a Principal Designer already been appointed up to RIBA Stage 3 and if so, will the information prepared to date be provided? | No. Scott& Co (details on drawings) were appointed to submit the Planning applications not to progress any project. There was no prior Principal Designer appointment. | 2023-10-12
4 | The Developed Design (RIBA Stage 3) already carried out, may introduce potential design liability issues. Any new designer would need to review the design undertaken to date. Is the client prepared to accept a design review and changes in design proposals to mitigate design liabilities, including potential delays in programme which may result? | It is understood that a design review will need to be undertaken. However, it is hoped that as planning has been approved, then there won't be many, if any, changes in the design proposals as time and budget are both restricted due to funding requirements. | 2023-10-12
5 | Are you requesting a Design Team to Complete Design, Tender and Contract Administration Task RIBA 4-6 inclusive or are you seeking a Design + Build Team to complete the design and implement the construction works? | Please see Appendices 1 and 5 which outline the duties that are required. We will require a PM to run the tender process, supervise the works to ensure compliance with their design and to advise the client. They will also be required to attend the site weekly and to maintain quality checks and raise defects as required. | 2023-10-12
6 | The requirement of minimum £10m Public Liability Insurance, is that required to be provided by the design team or could this be provided as a consortium Design + Build Team? | Just the design team. | 2023-10-12
7 | Do you expect there to be any input needed from a structural engineer as part of the works? | We do not believe that there is a need for a structural engineer. The project is for replacement roof coverings, no increased loadings are anticipated. | 2023-10-12
8 | Can you confirm the scope of the tender return please: - Do you require further information on top of the tender forms, and method statement? - Do you require CVs for the proposed team? - Do you require relevant case studies of similar completed work? | As detailed in Volume 2: Please provide CV and / or organisation biographies detailing all key members of your core team, either individuals or companies and the role which they would play in the delivery of the project. Where roles are not yet determined at time of tender then details should be provided around how you would select and appoint, to take into account assurances on high end quality outcomes, detail how you propose to meet that condition e.g. appoint another individual or organisation under your supervision with the specific experience, skill or knowledge required to meet the condition. Provide the name and contact details of sub contractors. To support your response, we would be seeking suitable case studies and references sites which Royal Institution of Cornwall may seek to contact as part of due diligence around evaluation. Your proposals should provide clear reference on how the experience you have would be utilised on this project to deliver meaningful quality outcomes. | 2023-10-12
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: