### THE OFFICE FOR NUCLEAR REGULATION

STATEMENT OF SERVICE REQUIREMENT FOR THE PROVISION OF SUPPORT ON INTERNAL HAZARDS SAFETY ASSESSMENT FOR STEP 3 OF GDA OF THE UK ABWR

BACKGROUND TO THE PROJECT

- In January 2014 ONR formally started Step 2 of the Generic Design Assessment (GDA) of Hitachi General Electric’s (Hitachi-GE) UK Advanced Boiling Water Reactor (UK ABWR). Hitachi-GE is the Requesting Party for the UK ABWR GDA (referred to as “the RP” in this specification).

- Step 2 of GDA is an overview of the acceptability, in accordance with the regulatory regime of Great Britain, of the design fundamentals, including review of key nuclear safety and nuclear security claims with the aim of identifying any fundamental safety or security shortfalls that could prevent the issue of a Design Acceptance Confirmation (DAC) (see http://www.onr.org.uk/new-reactors/ngn03.pdf).

- During Step 2, ONR has reviewed the key safety claims put forward by RP in the area of internal hazards Preliminary Safety Report (PSR). ONR completed Step 2 at the end of August 2014. ONR’s technical assessment reports covering the assessment work undertaken during Step 2 and key conclusions were also published in August 2014.

- During Step 3, ONR will assess the “safety arguments” of the internal hazards safety case submissions which supports the safety claims made.

- For internal hazards “safety argument” is interpreted as the structured robust justification to underpin the claims made (see also scope of the services required). The safety arguments should be coherent, sufficient and commensurate with the potential risks. It should provide the entry points and clear links to the safety case documentation as a whole.

- ONR’s Step 3 assessment plan in the area of internal hazards acknowledged that the key claims on internal hazards by the RP during Step 2 were incomplete.  As a result, ONR’s Step 3 assessment will also consider whether the key claims relating to internal hazards that underpin the safety of the UK ABWR are complete and reasonable.

- For Internal hazards “safety claims” are interpreted as specific statements about the design features which prevent, limit the severity and limit the consequences of the internal hazards on Structures, Systems and Components (SSCs) important in the delivery of the fundamental safety functions, which when implemented will demonstrate that the threats from Internal Hazards are either removed, withstood or minimised.

- ONR commenced its Step 3 assessment of GDA on 1st September 2014 and expects to be completed at the end of August 2015.

- During Step 4, ONR will assess the evidence by conducting in-depth assessment, on a sampling basis, of the internal hazards safety case submissions to confirm that the claims and arguments are underpinned by robust evidence. ONR expects to start Step 4 of GDA on 1st September 2015 and complete it at the end of 2017.

- A key part of Step 2 was for ONR inspectors responsible for assessing the ABWR design to identify areas where timely input from Technical Support Contactors (TSCs) is required to enable GDA to progress to programme, and to ultimately inform ONR’s regulatory decision on the acceptability of the ABWR design, or otherwise, for construction in the UK. ONR have identified that independent technical support in the area of internal hazards is one such area.

- ONR anticipate initiating engagement with the TSC during the early stage of Step 3, with technical support being provided throughout the Step 3.

SCOPE OF THE SERVICES REQUIRED

- The TSC is required to provide technical support to ONR, during Steps 3 of GDA, to independently assess the UK ABWR internal hazards Pre-Commencement Safety Report (PCSR) submissions.

- The scope of services required during Step 3 includes:

- Familiarisation with ONR’s Step 2 assessment report findings, recommendations, and existing Regulatory Queries (RQ) and Regulatory Observations (RO);

- Undertake an independent detailed technical review of the Step 3 internal hazards submissions (see Appendix 1) in line with ONR’s regulatory expectations and modern standards. The review should confirm:

- The suitability and sufficiency of the internal hazards methodologies (Revision 1);

- The adequacy of the Topic Reports on each internal hazards (Revision 0 and Revision 1) covering the following aspects:

  - The identification and screening of internal hazards initiating events including simultaneous effects and combined consequential events, specific to UK ABWR, have been thorough and complete;

  - All identified initiating events have been considered in the internal hazards analysis, as appropriate;

  - Appropriate safety claims  and arguments have been presented for all relevant buildings;

  - Defence in depth arguments have been presented; and

  - The risk has been reduced As Low As Reasonably Practicable (ALARP).

Note: Revision 0 covers methodology, hazard sources and combined hazard identification whereas Revision 1 covers design approach, hazard/ fault schedule and other topics. The RP is yet to confirm what will be fully covered in each revision.

- The adequacy of the supporting Topic Reports for the ROs on Emergency Diesel Generators (EDGs) in the Reactor Building, Single Doors on Class1 safety barriers and on the Main Steam Tunnel;

- The adequacy of other supporting documents including the Topic Report on cross cutting issues, barriers identification and room data sheets;

- The adequacy of the Overall Topic Report on Internal Hazards (Revision 0 and Revision 1); and

- The adequacy of the PCSR Revision A.

- To be able to deliver the various parts of this work package, the scope of the work should also include, where appropriate:

- The identification of any necessary UK ABWR information required from the RP. ONR will formally submit these to RP as Regulatory Queries, but the contractor is expected to identify the information required;

- Review of part, or all of, any responses provided by the RP in answer to any queries raised in conjunction with completing the work package; and

- Support to ONR during technical meetings with the RP. This might include, for example, discussions on information required to undertake the review. ONR would expect the TSC to be present when the final results of the work are discussed with the RP. This may involve attending video/teleconferences or face-to-face meetings in the UK (Liverpool).

- Develop a forward work programme, with planned tasks, deliverables, milestones, timeframes and project costs;

- Obtain ONR acceptance to the technical review scope, supporting programme and project costs;

- Deliver the defined scope as set out in the programme and to the project cost;

- Routinely review the programme scope, deliverables, milestones, timeframes, project costs and indicative invoice forecast;

- Regular brief progress meeting will be required during the course of the contract, mainly via teleconference or at the TSCs office. These should be no more frequent than bimonthly; and

- The contractor should report the overall results of this work in two reports to ONR: a report on the review of the internal hazards methodologies and Revision 0 of the Overall Topic Report on internal hazards topics; and a report on the review of the remaining Topic Reports (for each internal hazard, in response to ROs, exception to segregation, combined hazards, hazards not considered in detail and other cross cutting issues) and supporting documents (barrier substantiation report rev. 1, room data sheet rev. 1). The reports should contain full details of the work undertaken, discussion of the review, summary, conclusions and a full reference list.

CONSTRAINTS

- Constraints related to regulatory judgement: Whilst the contractor will undertake the detailed technical reviews, it will be done under direction and management of ONR.  Regulatory judgement on the adequacy of the internal hazards safety case for the UK ABWR shall be made exclusively by ONR.

- Constraints on guidance to be used by the TSC for the review of the UK ABWR Internal hazards:

- ONR’s Safety Assessment Principles (SAP).

(http://www.onr.org.uk/saps/saps2006.pdf).

- ONR’s Technical Assessment Guide (TAG) on Internal Hazards.

(www.onr.gov.uk/operational/tech_asst_guides/index.htm.

- IAEA’s Safety Standards Series:

- Safety of Nuclear Power Plants: Design. Specific Safety Requirements.  International Atomic Energy Agency (IAEA). Safety Standards Series No. SSR-2/1.  IAEA. Vienna. 2012;

- Protection Against Internal Fires and Explosions in the Design of Nuclear Power Plants. Safety Guide. International Atomic Energy Agency (IAEA) Safety Standards Series No. NS-G-1.7. IAEA. Vienna. 2004; and

- Protection against Internal Hazards other than Fires and Explosions in the Design of Nuclear Power Plants. Safety Guide. International Atomic Energy Agency (IAEA) Safety Standards Series No. NS-G-1.11. IAEA, Vienna 2004.

- WENRA References Levels:

- Reactor Safety Reference Levels (January 2008);

- Safety Objectives for New Power Reactors (December 2009) and Statement on Safety Objectives for New Nuclear Power Plants (November 2010);

- Statement on Safety Objectives for New Nuclear Power Plants (March 2013) and Safety of New NPP Designs (March 2013; and

- Any additional relevant national and international standards and authoritative guidance as identified by the TSC, in agreement with ONR.

- Constraints related to the TSC’s technical capabilities:

- The TSC should put forward a team with knowledge in the ABWR technology; and

- The TSC should put forward a team with expert knowledge in internal hazards safety assessment and with good knowledge of the UK regulatory expectations on internal hazards.

- Scheduling constraints – meetings with the RP: ONR anticipates that a number of meetings with the RP will require participation of TSC’s staff; for example:

- A number of monthly meetings and Technical Workshops in the UK (6 in Liverpool) and Japan (3 in Hitachi City) between ONR and the RP during Step 3 has been outlined. The meetings are expected to last between 3-5 days. The TSC is not expected to attend the meetings in Japan; and

- A number of video/teleconferences meetings in the UK (Liverpool) may also needed (2 hours maximum each).

- A pragmatic and flexible approach will need to be adopted by the TSC to deal with the project needs in terms of meeting dates, attendance and attendees.

- Timing constraints: A start date of November 2014 is initially proposed. The work package is assumed to be approximately 9 months in duration. This will be agreed and fixed when the contract is awarded, as will key project milestones and delivery dates for the various reports:

- Start of Step 3: 1st September 2014;

- Proposal received: November 2014;

- TSC selection and approvals process: November 2014 – T0;

- Contract awarded (subject to the necessary approvals): T0;

- Kick-off meeting between ONR and TSC: within 10 working days of T0;

- TSC’s Step 3 draft report is required before end of May 2015 (this is for the purpose of ONR’s Step 3 reporting – it is understood that the report will not cover the review of the totality of information submitted by the RP during Step 3 (see Appendix 1); and

- End of the Step 3: August 2015.

- Security constraints:

- Much of the RP’s PSA material and, as a consequence, the TSC’s review reports will include information of a sensitive nature and attract the UK protective marking OFFICIAL – SENSITIVE. The received and produced data will therefore need to be handled appropriately; and

- Work cannot commence until the required security clearances of individuals working on the project have been established and the TSC’s IT systems have been demonstrated to be suitable for the protective marking applied to the information.

- Conflict of interest constraints: The TSC should not have previously supported the RP (directly or indirectly), in developing or reviewing the UK or Japanese ABWR internal hazards safety case.

- Constraints related to the performance of the TSC: At the end of Step 3 a review will be conducted of the quality and timeliness of the TSC’s work and interactions with ONR and the RP to inform a decision of whether the contract should proceed to the next phase of the project (Step 4).

- Other constraints – distribution of the TSC’s reports and usage of the TSC’s information included in the UK ABWR review reports:

- It is ONR’s intention to provide the TSC’s reports to the RP for confirmation of factual accuracy; and

- Interim outcomes of the TSC’s review will be used by ONR, if appropriate, to inform the preparation of Regulatory Observations (and / or Regulatory Issues if serious shortfalls are identified which could prevent provision of a design acceptance confirmation, DAC) requesting the RP to make improvements to the UK ABWR internal hazards safety case during GDA. The final outcome of the TSC’s review will be used by ONR to raise, if appropriate, GDA Issues and / or GDA Findings at the end of Step 3. In addition, ONR will report on the progress and outcome of this work in its ABWR GDA Step 3 summary report (overview of status of assessment at the end of Step 3) and, as appropriate, in the GDA quarterly reports, all expected to be published.

OBJECTIVES

- In summary, the overall objective of this work is to provide technical support to ONR, during Steps 3 of GDA, to review the UK ABWR internal hazards PCSR submissions. This will be done via:

- Review of the RP’s internal hazards submissions (methodologies, topic reports and supporting documents as given in Appendix 1), against ONR’s SAPs, ONR’s TAG on internal hazards and international guidance and good practice;

- Support ONR (including any required preparation) during teleconferences, videoconferences and / or face-to-face meetings (in the UK) with the RP to discuss progress of the assessment of the various internal hazards tasks, findings from the reviews, emerging issues, etc, and / or to request additional information and / or analysis from the RP;

- Draft queries and / or observations to request additional information and / or analysis from the RP (to be formally submitted by ONR) and advise ONR on the adequacy of the RP’s responses;

- Report to ONR any shortfalls identified during the review of the UK ABWR internal hazards safety case submissions and comment on their significance;

- Evaluate the importance of the assessment findings and their potential impact on the internal hazards PCSR aspects;

- Document the work done and the findings. The TSC will be required to produce  approved Step 3 technical review reports;

- Project management – report monthly progress (short summary of progress and expenditure per task and team member) and coordination between the different technical disciplines, within the TSC’s team, involved in the review of the UK ABWR internal hazards safety case; and

- Deliver the work in accordance with the agreed scope, programme timescales and project costs.

TENDER SUBMISSIONS

- Procurement Unit (PU) will provide TSCs with:

- details of “how” to submit tenders and the timeframe for doing so;

- Any proposal in response to this specification should:

- Clearly address all aspects of the specification (including objectives, scope and constraints);

- Details of the project team members, including grades and rates and short curriculum vitae (CV) summarising relevant experience;

- Details regarding the experience of the project team on safety analysis for the BWR technology (indicate if the project team has specific experience on the ABWR design);

- Explain how the aims and scope of the work are to be addressed, and the proposed approach. This should include:

- Identification of the required tasks with the number of days required for each task and timescales, including details of who will undertake each of the tasks; and

- Experience of the project team relevant to each of the tasks. This should include a brief description of examples of the work undertaken by the individual that provides evidence of adequate experience to undertake the assigned task.

- Identify the anticipated engagement with ONR, including any progress meetings;

- Include a project plan and timetable covering each of the proposed tasks;

- Provide a detailed breakdown of all proposed costs associated with this work;

- Total costs should be presented per financial year (ONR financial year starts in April); and

- Provide a schedule of invoices and forecast of invoice values.

CONTRACT MANAGEMENT

- The ONR Project Officer:

Office for Nuclear Regulation

Redgrave Court
Merton Road, Bootle
L20 7HS

EVALUATION

- Evaluation criteria; Quality:

- How well did the tender address all aspects of the specification? (Weighting: Critical);

- How suitable is the proposed approach, including tasks, number of days required and timescales?  (Weighting: Critical);

- How suitable is the experience of the project team regarding BWR technology and internal hazards safety assessment (Weighting: Critical);

- How suitable is the experience of the project team to undertake the tasks assigned to them (Weighting: Critical). This will be evaluated considering the experience of each member of the team. Evidence needs to be provided per task allocated to each individual. The following will be considered when scoring each task:

- Experience of individuals in Internal Hazards safety case assessment;

- Experience of individuals in ABWR; and

- Experience of individual in UK regulatory regime.

- How suitable is the anticipated engagement with ONR? (Weighting: Important).

- Evaluation criteria; Financial:

- Are the costings clear and do they represent value for money? (Y/N).

PROPOSED TIMETABLE

PU will provide TSCs with an indication of the overall timetable for the procurement exercise.

| Invitation to Tender (ITT) issued |  |
| --- | --- |
| Deadline for Tender Questions |  |
| Publication of Questions and Answers |  |
| Deadline for Receipt of Tenders |  |
| Identify Preferred Bidder |  |
| Award of Contract |  |

ENQUIRIES

To ensure that all TSCs are provided with the same information regarding the service requirement, PU will handle all initial enquires from the TSCs.  Where appropriate PU will liaise with ONR to determine the answer and circulate the response to all TSCs who are involved.  Unless advised to the contrary PU will approach whoever in ONR will be responsible for managing the required work.

Appendix 1: RP’s Internal HAZARDS DELIVERY PROGRAMME

- The RP’s current expected delivery programme for the Step 3 internal hazards PCSR is summarised below:

| Submission Identity | Title | Date |
| --- | --- | --- |
| Step 3 Submission - Level 1 | - PCSR – Internal Hazards Chapter 7, Rev A | - 23/8/14 |
| Step 3 Submission - Level 1 | - PCSR – Internal Hazards Chapter 7, Rev B | - 21/08/15 |
| Step 3 Submission Level 2 | - Overall Topic Report on Internal Hazards, Rev 0 - (document map, IH safety case, general principles of protection, summary of Lv. 3 TRs rev 0) | - 20/12/14 |
| Step 3 Submission Level 2 | - Overall Topic Report on Internal Hazards, Rev 1 (exceptions of the general principles, scope of IH assessment, summary of Lv. 3 TRs rev 1) | - 30/06/15 |
| Step 3 Submission Level 3 | - Topic Report on Identification and Screening, Rev 0 | - 20/10/14 |
| Step 3 Submission Level 3 | - Topic Report on Identification and Screening, Rev 1 | - 1/12/14 |
| Step 3 Submission Level 3 | - Topic Report on Internal Fire, Rev 0 | - 1/12/14 |
| Step 3 Submission Level 3 | - Topic Report on Internal Fire, Rev 1 | - 25/04/15 |
| Step 3 Submission Level 3 | - Topic Report on Internal Flooding, Rev 0 | - 1/12/14 |
| Step 3 Submission Level 3 | - Topic Report on Internal Flooding, Rev 1 | - 25/04/15 |
| Step 3 Submission Level 3 | - Topic Report on Pipe Whip / Jet Impact, Rev 0 | - 1/12/14 |
| Step 3 Submission Level 3 | - Topic Report on Pipe Whip / Jet Impact, Rev 1 | - 25/04/15 |
| Step 3 Submission Level 3 | - Topic Report on Dropped Load and Collapse Loads, Rev 0 | - 1/12/14 |
| Step 3 Submission Level 3 | - Topic Report on Dropped Load and Collapse Loads, Rev 1 | - 25/04/15 |
| Step 3 Submission - Level 3 | - Topic Report on Internal Missile, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 3 | - Topic Report on Internal Missile, Rev 1 | - 25/04/15 |
| Step 3 Submission - Level 3 | - Topic Report on Internal Explosion, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 3 | - Topic Report on Internal Explosion, Rev 1 | - 25/04/15 |
| Step 3 Submission Level 3 | - Topic Report EMI, Rev 0 | - 1/12/14 |
| Step 3 Submission Level 3 | - Topic Report on EMI, Rev 1 | - 25/04/15 |
| Step 3 Submission - Level 3 | - Topic Report on Combined Hazards, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 3 | - Topic Report on Combined Hazards, Rev 1 | - 30/05/15 |
| Step 3 Submission - Level 3 | - Topic Report of Hazards not to be Considered in Detail | - 1/12/14 |
| Step 3 Submission - Level 3 | - Topic Report of Hazards not to be Considered in Detail, Rev 1 | - 25/04/15 |
| Step 3 Submission - Level 3 | - Topic Report on Exceptions to Segregation, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 3 | - Topic Report on Exceptions to Segregation, Rev 1 | - 25/04/15 |
| Step 3 Submission - Level 4 | - Barrier Substantiation Report, Rev 0 | - 7/02/15 |
| Step 3 Submission - Level 4 | - Barrier Substantiation Report, Rev 1 | - 30/05/15 |
| Step 3 Submission - Level 4 | - Barrier Substantiation Report, Rev 2 | - 31/08/15 |
| Step 3 Submission - Level 4 | - Room Data Sheet, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Room Data Sheet, Rev 1 | - 7/02/15 |
| Step 3 Submission - Level 4 | - Room Data Sheet, Rev 2 | - 31/08/15 |
| Step 3 Submission - Level 4 | - Topic Report on Doors on Class 1 Barrier, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Topic Report on Doors on Class 1 Barrier, Rev 1 | - 27/02/15 |
| Step 3 Submission - Level 4 | - Topic Report on EDGs Location, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Topic Report on EDGs Location, Rev 1 | - 27/02/15 |
| Step 3 Submission - Level 4 | - Topic Report on MS Tunnel Room Layout, Rev 0 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Topic Report on MS Tunnel Room Layout, Rev 1 | - 27/02/15 |
| Step 3 Submission - Level 4 | - Topic Report on Other Cross Cutting Issues, Rev 0 | - 30/05/15 |
| Step 3 Submission - Level 4 | - Methodology for Internal Fire, Rev 0 | - 29/09/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Fire, Rev 1 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Flood, Rev 0 | - 29/09/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Flood, Rev 1 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Methodology for Pipe Whip / Jet Impact, Rev 0 | - 3/10/14 |
| Step 3 Submission - Level 4 | - Methodology for Pipe Whip / Jet Impact, Rev 1 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Methodology for Dropped Load and Collapse Loads, Rev 0 | - 3/10/14 |
| Step 3 Submission - Level 4 | - Methodology for Dropped Load and Collapse Loads, Rev 1 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Missile, Rev 0 | - 3/10/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Missile, Rev 1 | - 1/12/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Explosion, Rev 0 | - 3/10/14 |
| Step 3 Submission - Level 4 | - Methodology for Internal Explosion, Rev 1 | - 1/12/14 |
| Step 3 Submission Level 4 | - RO on Emergency Diesel Generators in Reactor Building | - TBC |
| Step 3 Submission Level 4 | - RO on Single doors on safety class 1 barrier in Reactor Building | - TBC |
| Step 3 Submission Level 4 | - RO on Main Steam Tunnel | - TBC |