Warrant for the commission of work under Framework Agreement 1.11.4.2266 for the Provision of Technical Support Services to

The Office for Nuclear Regulation (ONR)

| Consultant | GRS |
| --- | --- |
| Project Title | The Provision of Technical Support on Internal Hazards Safety Assessment for Step 3 of GDA of the UK ABWR |
| ONR Project No. | ONR237 |

1	PROGRAMME OF WORK

1.1	Whereas the Contractor was successful as a result of a competitive tendering exercise under tender reference ONR/T2603 to deliver the above services under Lot 1 of the Framework Agreement.

1.2	The Programme of Work to be carried out will comprise the complete schedule of 	services, as described in the Contractor’s proposal detailed at Annex 1.

2	DURATION

2.1	The Services shall commence on 26 January 2015 and shall be completed by 28 August 2015.

3	CONTRACT MANAGEMENT

3.1	The ONR Contract Manager who will be responsible for liaison and certifying completion of the provision and overall management of the Services.

3.2	The Technical Support Contract Manager who will be responsible for liaison and certifying completion of the provision and overall management of the Services.

4	REPORTING REQUIREMENTS

4.1	The reporting requirements applicable relating to the delivery of the Services are described in Annex 2.

4.2	Draft and Final Reports should be submitted by e-mail to onr.research@onr.gsi.gov.uk

5	MAXIMUM COST

  - 5.1	The total cost for providing the service will be £109,900 exclusive of VAT. Any additional costs will be agreed in advance and in writing with the ONR Contract Manager and subject to a Variation to Agreement.

6	INVOICING

6.1	Invoices shall be submitted to ONR in accordance with the following Invoice 	Schedule:

Date of Invoice                     	Amount to be invoiced

| By end of April 2015 | £30,500 |
| --- | --- |
| By end of August 2015 | £79,400 |

6.2	Any variation to the Invoice Schedule shall be agreed with the ONR Project 	Manager and a revised Invoice Schedule provided.

6.3	An original, electronic invoice accompanied by any appropriate Progress Reports, in the format detailed in Annex 2 should be submitted by e-mail to :

onr.research@onr.gsi.gov.uk

6.4	Payment will be made subject to Clause C2.2 of Schedule B, Terms & Conditions of the Framework Agreement.

6.5	 Failure to provide a progress report may result in a delay to the payment, or rejection of the invoice.

SIGNATORIES

In Witness Whereof this WARRANT TO THE FRAMEWORK AGREEMENT has been agreed :

| Signature |  |
| --- | --- |
| Name in Capitals |  |
| Position |  |
| Date |  |

Duly authorised to sign on behalf of GRS

Boltmannstraße 14, 85748 Garching, Germany

| Signature |  |
| --- | --- |
| Name in Capitals |  |
| Position |  |
| Date |  |

Duly authorised to sign on behalf of the OFFICE FOR NUCLEAR REGULATION

Building 4, Redgrave Court, Merton Road, Bootle, Merseyside L20 7HS

Annex 1

PROGRAMME OF WORK

The Contractor shall undertake the Programme of Work titled Provision of Technical Support on Internal Hazards Safety Assessment for Step 3 of GDA of the UK ABWR, dated 03 Decmber 2014, Rev 2 and referenced by GRS as AG-3589, AB-333011.

Annex 2

PROJECT PROGRESS REPORT

Within the Project Progress Report, Contractors should seek to provide HSE with an assurance about the status of the project in terms of progress towards delivering the required work to the agreed quality, within agreed timescales and cost.

Where you cannot provide this assurance, you should clearly detail the corrective action you are taking to address any shortcomings.

Progress Reports should be submitted in the format detailed overleaf.  You must complete all boxes. Where appropriate, you may provide additional information (Gantt charts, etc.).

Please note that invoices submitted without a properly completed Progress Report will be rejected.

TECHNICAL SUPPORT FRAMEWORK

PROJECT PROGRESS REPORT

ONR Project No.		XXX			Contractor			XXX

Progress Report No. 	XXX			Report Date:			XXX

Project Title:		XXX

TSC Project Manager:		XXX

1 	PROGRESS REPORT

List the Deliverables, Key Events, Achieved in this Period

List any Problem Areas & Your Remedial Actions

List the Planned Activities for the next Reporting Period

Insert any Notes / Comments

List and Supporting Attachments

2	COSTS (exc VAT)

Agreed Monthly Cost Profile

Invoiced Costs Against Agreed Cost Profile (Include this month’s invoiced cost)

Cumulative Cost to Date (include this month’s invoiced cost)

Invoiced Cost to Date as a Percentage of Permissible Maximum Expenditure

3	EFFORT

Percentage of Work Completed to Date

4	SIGNATORY

| Signature |  |
| --- | --- |
| Name in Capitals |  |
| Position |  |
| Date |  |