SCHEDULE 2.6

CALL OFF TEMPLATE

THIS Call Off is issued on 21/03/2024 (the “**Services Commencement Date**"), by the Authority to **Teligent Limited** (the “**Supplier**”), a company incorporated under the laws of England and Wales and whose registered office is located at 2 Kings Hill Avenue, Kings Hill, West Malling, Kent. ME19 4AQ pursuant to the ADB Services Agreement (relating to the provision of ADB Services to extend the Shared Rural Network to the Extended Area Service) dated as of   
29 October 2021 (as amended and supplemented from time to time, the “**MFA**”), to which both the Authority and Supplier are a “Party” as are they also referred to in this Call Off individually as a “Party” and collectively as the “Parties”.

The Authority and the Supplier both desire to enter into this Call Off pursuant to clause 5 of the MFA under which the Supplier will provide the scope of Services requested in respect of the EAS Sites identified by the Authority within this Call Off;

The Parties hereby agree as follows:

1. Incorporation of MFA. Except as otherwise provided herein, the terms of the MFA are incorporated into this Call Off by this reference as if such terms were stated in full herein and as if references therein to the “Agreement” were references to this Call Off. Capitalized terms used in this Call Off without definition that are defined in the MFA shall have the meanings set out in the MFA.
2. To the extent that there is any conflict or inconsistency between the provisions of this Call Off and the terms of the MFA, the terms of this Call Off shall govern but only with respect to the provision and receipt of relevant Services under this Call Off. To the extent there are matters which by their nature are to be performed under the MFA or another Call Off such matters shall be performed under the MFA or such other Call Off.

# TERM AND TERMINATION

* 1. The term of this Call Off shall commence on the date first written above and expire on the later of the expiry of the MFA or the date upon which the last EAS Site is completed under this Call Off, unless terminated earlier in accordance with Section 3.2 below or extended by the Parties’ mutual agreement as expressed in writing. In the event the MFA expires prior to the expiry of this Call Off, the terms of the MFA will continue to govern the Call Off until the expiry or termination of the Call Off.
  2. Termination. This Call Off may be terminated by the Authority to the extent the Authority may terminate the MFA as if this Call Off were the MFA. Except as otherwise provided in the MFA, any such termination of this Call Off or any other Call Off under the MFA shall not in and of itself give rise to a termination of the MFA or any other Call Off.

# SERVICES

## Set out in Appendix 1 is the list of EAS Sites in respect of which the Supplier is to provide Services. Within Appendix 1 EAS Sites are identified as being either EAS Site in needs of an Upgrade (EAS Upgrade Sites) or EAS Sites in need of a New Build (EAS New Build Sites). The Authority shall include where applicable any Transmission Hop Sites within the list of EAS New Build Sites and the Authority shall further identify within Appendix 1 any such Transmission Hop Sites.

## It is acknowledged that in the delivery of the Services the Supplier shall follow the methodology and protocol it has set out for delivering the Services in Schedule 4.

# Implementation Services

## For each EAS Upgrade Site the Supplier shall produce a Minor Schedule of Works in accordance with the provisions of the MFA and more specifically in a form that shall follow the structure set out in Appendix 2.

## For each EAS New Build Site the Supplier shall produce a Major Schedule of Works in accordance with the provisions of the MFA and more specifically in a form that shall follow the structure set out in Appendix 3.

# Operational Services

## For each EAS Site identified within Appendix 1 the Supplier shall deliver the Operational Services as described and set out in Schedule 2.1 to the MFA and as further particularised in the Minor Schedule of Works or Major Schedule of Works for that EAS Site as applicable

# Service DELIVERY

## All Services carried out under this Call Off shall be subject to the operation of the following Schedules of the MFA as applicable.

## The Supplier shall as part of the delivery of the Implementation Services in respect of each EAS Site identified in Appendix 1 generate and provide to the Authority as part of the Implementation Services the Minor Schedule of Works for each EAS Upgrade Site and the Major Schedule of Works for each EAS New Build Site, as applicable.

# Applicablity of construction act

## For all Services and work carried out either in the delivery of the Implementation Services or in the delivery of the Operational Services it is acknowledged that all such work shall be governed by the Construction Act 1998 (As amended).

# Charges and Reimbursements

## The Authority shall for each Call Off issue as at the Call Off Commencement Date a Purchase Order for the Implementation Services to be delivered in relation to each Batch.

## Thereafter in relation to each individual EAS Site as the Implementation Services are completed then upon the ATP Milestone being Achieved the Authority shall issue a Purchase Order for the delivery of the Operational Services.

## All Charges payable for work carried out by the Supplier under this Call Off shall be paid on a monthly basis in accordance with the provisions of Schedule 7.1 (Charges) of the MFA.

# Governance

## This Call Off shall be governed by the centralised governance process described in Schedule 8.1 (Governance) of the MFA.

# INSURANCE

## For this Call Off, Contractors “All Risks” Insurance as specified in Schedule 2.5 is required

|  |  |
| --- | --- |
| SIGNED for and on behalf of ) Teligent Telecoms Limited by a director: )  )  ) | Signature:  Name (block  capitals):  Position: |

|  |  |
| --- | --- |
| SIGNED for and on behalf of ) the Secretary of State for the Home Department )  )  ) | Signature:  Name (block  capitals):  Position: |

Appendix 1

EAS Sites in scope:

1. List of EAS Sites requiring New Builds under this instruction, referred to as Batch 32b:

|  |
| --- |
| * 1. EAS0528   2. EAS0529 |

Appendix 2

EAS Sites Major Schedule of Works

(to be submitted by Supplier for each EAS Site)

**1) EAS SITE NAME AND UNIQUE REFERENCE ID:** EAS0528 **[Supplier Ref]**

Implementation Services

* 1. Acquisition Services
  2. Planning Services
  3. Design Service

**2) EAS SITE NAME AND UNIQUE REFERENCE ID:** EAS0529 **[Supplier Ref]**

Implementation Services

1. Acquisition Services
2. Planning Services
3. Design Service
4. Milestones for the New Build EAS Sites

| ID | Description | Minimum Outputs required to claim | Responsible | MILESTONE DATE (Milestone + X Working Days) |
| --- | --- | --- | --- | --- |
| MS1 | * SSR (Site Search Report) Submitted * A physical survey has been carried out to identify potential Sites that may provide the coverage defined in the SARF and where the Site provider has indicated that they would support the development and the surveyor believes obtaining planning consent for the required development will be achievable. The milestone is claimed when the SSR has been submitted to the radio planning team. | Site Search Report | Authority - Radio Planner |  |
| MS2 | * Transmission Supplier Instructed * The Transmission Supplier has been provided with a formal instruction to proceed. A PO has been raised. | Formal instruction and PO | Authority |  |
| MS3 | * Select preferred candidate site * The SSR has been reviewed by the Radio and Transmission Planning team. The proposed Site options have been reviewed and the preferred candidate Site selected. The Radio Planner issues Initial Engineering Approval. | Preferred Candidate Selected  Initial Engineering Approval | Authority - Radio Planner |  |
| MS4 | * ADB Instructed * The ADB Supplier has been provided with a formal instruction to proceed. A PO has been raised. The instruction is fully defined within an ADB Polygon Pack. | ADB Polygon Pack | Authority |  |
| MS5 | * Multi Skilled Visit Completed * Cross stakeholder agreement for the development and configuration of the Site has been obtained and key inputs into the Site design and baseline project plan provided. The on-Site MSV has been completed. | Site development plan & design input document (Initial Build Document)  Updated NGR  Existing Site Share: Approved Offer letter | Supplier | MS4 + 20 |
| MS6 | * General Arrangements/Planning Drawings Approved * The baseline project plan, GA and planning drawings have submitted and formally approved. An estimate of future build costs have been provided ready for Authority ‘Gate Approval’ | Baseline Project Time Plan  Estimated build costs  Approved GA/Planning drawings | Authority | MS5 + 25 |
| MS7 | * Structure/Ground Survey Completed * A GEO Tec survey and/or GDC has been carried out and a formal report submitted. The report provides positive confirmation that the Site can technically proceed (this does not confirm commercial acceptability). | GEO Tec Survey Report  DGC Report | Supplier | MS5 + 40 |
| MS8 | * Detailed Design Drawings/Build Costs Approved * The Detailed Design drawings have been submitted and formally approved. Build costs have been provided for Authority ‘Gate Approval’ and approved. | Approved Detailed Design drawings  Approved Build Costs | Authority |  |
| MS9 | * Local Planning Authority Consultation Complete * The LPA has been consulted and any potential restrictions on Site development understood and fed into the Site design process. The LPA consultation process has been completed. | Site specific restriction identified | Supplier |  |
| MS10 | * Submit Planning * A planning application for the proposed Site development has been formally submitted to the LPA, the planning application fee made, and receipt confirmed. | Site Planning Submission Pack | Supplier | MS5 + 40 |
| MS11 | * Planning Approved * The planning application for the proposed Site development has been approved. Any approval conditions (e.g., additional landscaping) are fully understood. | LPA formal confirmation of planning approval | Supplier |  |
| MS12 | * Heads of Terms Agreed * Heads of Terms have been agreed with the Site Provider. HoTs have been provided for Authority ‘Gate Approval’ and approved. | Agreed HoTs | Supplier |  |
| MS13 | * Legals Completed * A lease/licence is in place granting the Authority legal access to Site. The lease/license has been approved by the Authority Land Development Manager and Sealed by the Authority as appropriate. | Legal Access Agreement  Early Access Agreement | Supplier |  |
| MS14 | * Power Quote Received * A quotation with delivery timescales for the required power solution has been received and provided for Authority ‘Gate Approval’. This may include quotes for both permanent and tactical power solutions. | Power quote and delivery timescales | Supplier | MS5 + 45 |
| MS15 | * Transmission Quote Received * A quotation with delivery timescales for the required transmission solution has been received and provided for Authority ‘Gate Approval’. This may include quotes for both permanent and tactical transmission solutions. | Transmission quote and delivery timescales | Authority |  |
| MS16 | * Site Accessed * A summation of MS11 (Planning Approved) and MS13 (Legals Completed). | MS11 – Planning Approved  MS13 – Legals Completed | Authority |  |
| MS17 | * Site Ready for Build * The Site meets the following conditions:  1. Detailed Design and build costs approved (MS8) 2. Site is Accessed (MS16) 3. The Site has a valid and approved power solution (permanent or tactical). 4. The Site has a valid and approved transmission solution (permanent or tactical). 5. The above milestones should also be completed for the a-end Site  * The above has been provided for Authority ‘Gate Approval’ and approved. | MS8 – Detailed Design and Build Costs Approved  MS16 – Site Accessed  Power quote received (MS14) and Approved  Transmission quote received (MS15) and Approved  A-end Site dependencies at MS15  Approved Site Share station schedule  Authority ‘Gate Approval’ | Supplier |  |
| MS18 | * Acquisition Hand Over Pack Approved * The Acquisition HOP has been submitted to and approved by the Authority. | Approved Acquisition HOP | Authority | MS17 + 10 |

Appendix 3

List of Authority Documents Published on SharePoint

* As-Builts