# Annex A

| Title of Project | COR0924 Survey DNA Analysis |
| --- | --- |
| Date and Time for Return of Bids | Thursday 3rd October 2024 @16:00 hours UK |
| Contract Reference Number | C24-0810-1948 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO Kayleigh Thomas, Anamika Poyil, or Fionnuala McBreen OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Unique Onyewueke Joint Nature Conservation Committee Email: unique.onyewuekee@jncc.gov.uk Telephone: +441224 083515 |
| Contact for Queries Regarding the Procurement Procedure | Unique Onyewueke Joint Nature Conservation Committee Email: unique.onyewueke@jncc.gov.uk Telephone: +441224 083515 |
| Proposed Start Date | 14 October 2024 |
| Proposed End Date | 28 February 2025 |

COR0924 Survey DNA Analysis

Contents

1.	Joint Nature Conservation Committee	3

2.	Contract Summary	3

3.	Project Background and Aims	3

4.	Project Methods	4

5.	Contract Objectives	5

6.	Detailed Tasks	6

7.	Outputs	7

8.	Product Specification	7

9.	Dissemination	7

10.	Timescale	8

11.	Health and Safety	8

12.	Data Protection	8

13.	Project Management	8

14.	Instructions for Bid Submission	9

15.	Evaluation Criteria	10

16.	Payment	11

17.	Additional Requirements	11

18.  Procurement Timetable (which may be subject to change)	11

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Contract Summary

JNCC wishes to commission a contract to undertake analysis of benthic DNA samples that will be collected during the COR0924 survey to a region offshore of St Kilda in Autumn 2024.

Bidders are invited to provide a quote to include:

- Cost of analysis per sample for up to 80 DNA samples;

- Cost of reporting; and

- Cost of storing actual samples for one year in case of future analyses dependent on funding.

The contract, with any remedial actions following JNCC’s quality checks, will need to be fully completed by March 2025.

## Project Background and Aims

Metaprobes have been increasingly used in recent years to passively collect DNA from marine habitats. They have the potential to provide a relatively cheap and minimal extra effort method of sampling DNA in marine ecosystems, complementing existing traditional survey methods. Metaprobes have been deployed in inshore waters but there is limited understanding of their use in offshore waters. JNCC aim to address this research gap by asking the overarching question: Can we detect benthic species offshore using eDNA collected with metaprobes?

JNCC will be collaborating with Agri-Food and Bioscience Institute (AFBI) to undertake an offshore survey aboard the RV Corystes to a region offshore of St Kilda (survey code COR0924). The survey will depart Belfast Harbour on 26th September 2024 and return to the same port on 11th October 2024. During the survey, 36 sledge camera tows (Figure 1) will be conducted, providing an ideal opportunity to test collecting eDNA using metaprobes in the offshore benthic environment and to compare findings with benthic imagery.

There is a risk that metaprobes may become clogged with sediment, impacting the ability to passively filter water and collect eDNA. This will be investigated through the study’s experimental design by placing mesh around half of the metaprobes deployed.

From outputs of the DNA analysis and camera sledge tows, JNCC aim to answer the following questions:

- Does the species richness of benthic organisms detected vary between eDNA and imagery?

- Does community composition of benthic organisms detected vary between eDNA and imagery?

- Does species richness differ between metaprobes deployed with mesh and no mesh?

- How many metaprobes are required to achieve a complete dataset?

Figure 1 - Map showing the potential stations where DNA samples will be collected aboard the COR0924 survey to offshore St Kilda.

## Project Methods

To address questions 1 – 3, JNCC will attach two metaprobes to the camera sledge (one metaprobe with fine mesh wrapped around it and the other without) at the same position on the sledge for 20 camera sledge tows. Each metaprobe will have one piece of gauze to collect DNA, with each piece of gauze representing a sample. For this part of the study, there will be 40 DNA samples in total.

To address question 4, JNCC will attach 10 metaprobes with mesh wrapped around each metaprobe to the camera sledge for one tow, and JNCC with attach an additional 10 metaprobes without mesh to the camera sledge for another tow. For this part of the study, there will be 20 DNA samples in total.

An Acoustic Doppler Current Profiler (ADCP) will also be deployed on the camera sledge to enable JNCC to understand the flow of water passing over the metaprobe and allow correction for this.

One control will be taken from the processing lab each day that metaprobes are deployed. The controls will consist of one piece of gauze prepared in the same way as the other metaprobes, with up to 20 controls in total. For the whole project, there will therefore be up to 80 DNA samples. However, the number of samples will depend on various factors, such as weather and success of camera sledge deployments.

Each DNA sample will be preserved in a 50ml tube of ethanol and will be stored in a -20 freezer on the vessel, then samples will be transported to the lab in a cool box with ice packs. For the DNA analysis JNCC would like to test for the presence of invertebrates and vertebrates including fish. Once the DNA and camera sledge imagery have been analysed, JNCC will statistically analyse the data to answer the research questions. This includes conducting one-way ANOVAs and PERMANOVAs to address questions 1 – 4, and plotting species data into a species accumulation curve to ascertain how many metaprobes are required to reach a species richness asymptote. JNCC plan to publish findings as a research paper in a peer-reviewed journal.

Please note the following documents can be supplied to the successful contractor:

Sampling protocol

Survey plan

Associated metadata

Draft cruise report (timing tbc)

Proforma for DNA analysis data

## Contract Objectives

To meet the overall aims of this project (Section 2), the objectives of this contract are to use open access primers to analyse each DNA sample for the following:

- Benthic invertebrates

- Vertebrates

- Fishes

## Detailed Tasks

The successful contractor should provide:

1.  A Microsoft Excel spreadsheet listing the species identified (Latin and common names), the fragment of DNA extracted as part of the study identified as that species, and the reference library and sequence ID used to identify the species.

2. All raw sequence data generated in the FASTQ format.

3.  A final report (in JNCC style – refer to Product Specification) describing the objectives of the DNA analysis, the methods, results and conclusions of the work.

The methods section of the report should share sufficient detail for the study to be repeated. It should cover:

- Clear field protocol detailing eDNA sampling and storage for method comparison and validation.

- DNA extraction methods – including the names of kits if used. State how the DNA was quantified and discuss the quality of DNA extracted.

- PCR amplification – specify the primers, PCR cycle conditions and reagents used.

- Sequencing – detail how the DNA products were prepared for sequencing including reagents, primers and conditions. State how the DNA was quantified, and the model of the sequencing machine used. In addition, the methods should allow the reader to understand the confidence in the sequences obtained.

- Bio-informatic processing: State in detail how the bio-informatic processing was completed, by specifying the steps taken. State any programs that were used.

- State any reference libraries used, and if a custom database was created the rules used.

- Where sequences are being used for taxonomic assignment, please explain the methods used to assign a species and why any reads may have been discarded.

The results and discussion sections of the report should include the following in sufficient detail:

- Detailed description of fish/benthic communities.

- Detailed results tables on species of interest, including UK BAP Priority Species, OSPAR Threatened and/or Declining Species, Annex II species, Species listed as Features of Conservation Interest (FOCI), and invasive non-native species.

- the efficiency of DNA extraction and correct amplification of expected PCR products at each stage.

- A discussion of any problems and how they were resolved, such as issues with PCR leading to a change of reagents or amplification conditions.

- A detailed discussion explaining the results and confidence levels of the bioinformatic processing.

## Outputs

Any products or outputs submitted to JNCC should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

| Output/Deliverable | Format |
| --- | --- |
| Analysis of DNA samples | MS Excel spreadsheet in proforma provided by JNCC |
| Raw sequence data | FASTQ |
| Final report | MS Word Doc and Adobe PDF |

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible. This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style and be produced using a JNCC template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

## Dissemination

The products/outputs produced under this contract will be a JNCC and Defra product and shall not be published or disseminated without the written permission of JNCC and Defra. All material supplied as part of this contract shall remain copyright of JNCC and Defra. It is envisioned that outputs from this contract will feed into a research paper in a peer-reviewed journal. Prior to publication of the research paper, findings from this contract will be made available to staff within JNCC and Defra and may be published on the JNCC or Defra website.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (if required) | 14th – 18th October |
| Receipt of samples | 14th – 18th October |
| Completion of analysis and reporting, provision of draft deliverables to JNCC | By 31st January 2025 |
| Completion of JNCC QC checks and remedial action (if necessary) | By 28th February 2025 |

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Data Protection

JNCC and the successful contractor will agree and acknowledge that they are each independent Data Controllers in relation to Personal Data. Each Party will be individually responsible with complying with data protection legislation.

Any Shared Personal Data must be shared and processed by the Data Owner and the Data Recipients in accordance with the Data Protection Legislation.

Any Shared Personal Data shall only be used for purposes to be agreed by both Parties and shall not be used for any other purpose that is incompatible with this Agreement unless agreed in writing by the respective Data Protection Officers.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

Name: Kayleigh Thomas

Email:  Kayleigh.Thomas@jncc.gov.uk

Telephone: +441733 866813

Name: Anamika Poyil

Email: Anamika.Poyil@jncc.gov.uk

Telephone: +441224 083561

Name: Fionnuala McBreen

Email: Fionnuala.McBreen@jncc.gov.uk

Telephone: +441733 866954

## Instructions for Bid Submission

The bid submission should include the following:

- A brief summary of the bidder’s experience in relation to the requirements of this contract;

- A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 15);

- A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

- A draft Table of Contents for the final report;

- Details of Quality Control procedures to be followed.

- Details of the bidder’s own internal Quality Management System;

- Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

- Availability of the Project Team for an online start-up meeting.

- Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

- The following documentation (to submit in a zip folder separate from the proposal):

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments;

  - Copies of your company's modern slavery and or safeguarding statement or policy and;

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 15.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff and staff members from Natural England.  Unless otherwise stated in your bid submission, bids will be forwarded to these agencies for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (60% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 15 |  |
|  | Understanding of, and relevance to, the requirements in particular the understanding of outputs | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 13 |  |
|  | Risks if important team members drop out | 7 |  |
|  | Sub Total | 20 |  |
| 3. Cost (20% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager, payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## 18.  Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice |  |
| Last date for receipt of clarification questions |  |
| Final submission date for bids |  |
| Evaluation of bids |  |
| Post-tender negotiation/clarification and or presentation if required |  |
| Successful/unsuccessful bidders notified |  |
| Contract award |  |
| Start of project |  |