Sensitive - Commercial

Version: 28 May 2020

Instructions to Tenderers - Extract

Timeline

The target timeline is set out below:

| Documents uploaded to Contract Finder | 5 Mar 20 |
| --- | --- |
| Site Visits for Bidders | TBC# |
| Last date for receipt of tenders | 10 Jun 20 |
| Tender evaluation completed | 24 Jun 20 |
| Preferred bidder notified | 25 Jun 20 |
| Preferred bidder’s site investigation period | 25 Jun 20 to 7 Aug 20 |
| Preferred bidder’s design development period | 25 Jun 20 to 21 Aug 20 |
| Contract awarded | 1 Sept 20 |
| Works completed on site (long-stop date) | 11 Mar 21 |

The intention of LS185 is to adopt the following procurement sequence:

- Publish the tender, and seek bids

- Provide a site visit for each bidder that wants it (recommended)

- Receive the tender returns (Design to RIBA Stage 3)

- Evaluate the tender returns

- Select a preferred bidder

- Allow that bidder to undertake physical surveys

- Work with that bidder to develop their design to RIBA Stage 4, and in particular to take account of any new survey data

- Award the contract

# = Date dependant on government advice. Subsequent dates in the table will be amended to suit.