## Version
M&R Service Plan Template Amendments Page
Amend. No. | Revision No. | Amendments | Initials | Date
0 | 0 | Tender Issue | TT | 2016-08-01
1 | 1 | In Section 1 (Cyclic items) insert new line item 4.3.1.2 Gully clean covers and clear obstructions | SOS | 2016-10-12
2 | 1 | At end of Section 1 and Section 2 insert new row with note stating '(insert additional rows as required for any activity not covered by the above)' | SOS | 2016-10-12
3 | 1 | Column B of template - Service Information References updated to reference specific paragraphs instead of sections of the Service Information | SOS | 2016-10-12
4 | 1 | Section 2 heading amended from reactive items to repair items | SOS | 2016-10-12
5 | 2 | Guidance notes - additional text added to para 2.2 with respect to requirements in Annex 20 | SOS | 2016-10-12

## Guidance Note
Service Plan- Guidance Note
1. Introduction
1.1. | The purpose of this document is to provide guidance to producing contract compliant Service Plan aligned to the expectations of Highways England and fulfilling the requirements of the M&R contract.
1.2. | The quantity/interventions, location and resources stated for each activity/item should reflect the works anticipated to be undertaken during that month.
2. Guidance
2.1 | Section 1 - Deliver Maintenance Solutions (Cyclic Items) – The Contractor should state the activities intended to be completed in each month and on how many assets within the Affected Property. Each activity should be accompanied by a location of where the activity will take place. The resource that the Contractor proposes to use to undertake that work should be stated.
2.2 | Section 1 - Deliver Maintenance Solutions (Cyclic Items) – There should be clear differentiation between the activities being undertaken which are 'low', 'medium' and 'high' level of service in accordance with the CRMDP. Where activity is defined in Annex 20 (either above that required in CRMDP or a bespoke item), it should be referenced as Annex 20 in the Level of Service Column. For example, a section of network might have a 'high' level of service and require 6 activities within the year - the 'low' level must be shown to be undertaken first, then the other activities shown separately over and above this. The total quantity against the 'low', 'medium' and 'high' levels of service for each sub asset type must equal the total interventions stated in the Price List Schedule A.
2.3 | Sections 2 to 6 - The Contractor must use available information to forecast the expected level of work for these activities (which should be stated as the quantity). The resource that the Contractor proposes to use to undertake that work should be stated.

## Template
Maintenance and Response Contract Service Plan | Pricing List Schedule A Reference Number (if applicable) | Asset Type | Sub Asset Type | Item | Level of Service | April 20XX | [5 empty] | May 20XX | [5 empty] | June 20XX | [5 empty] | July 20XX | [5 empty] | August 20XX | [5 empty] | September 20XX | [5 empty] | October 20XX | [5 empty] | November 20XX | [5 empty] | December 20XX | [5 empty] | January 20XX | [5 empty] | February 20XX | [5 empty] | March 20XX
[6 empty] | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE |  |  | Quantity | Unit | Location | Resource FTE
[9 empty] | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour |  |  |  | Staff (Office) | Staff (Site) | Labour
Section 1 - Deliver Maintenance Solutions (Cyclic Items)
SI 16.1 | 4.1.1 |  | Stock maintenance |  | -
SI 16.4.1 | 4.2.1 | 400 - Road Restraint System and pedestrian Barriers | Vehicle restraint system, and all barrier systems (excluding concrete barriers) | Check all Road Restraint System (Vehicle Restraint System(VRS) and Pedestrian Restraint System) | -
SI 16.4.1 | 4.2.2.1 | 400 - Road Restraint System and pedestrian Barriers | Vehicle restraint system, and all barrier systems (excluding concrete barriers) | VRS - Tensioned Corrugated Beam (includes barrier length, transitions and Terminals) | -
SI 16.4.1 | 4.2.2.2 | 400 - Road Restraint System and pedestrian Barriers | Vehicle restraint system, and all barrier systems (excluding concrete barriers) | VRS - Wire Rope Safety Barrier (includes barrier length, transitions and Terminals) | -
SI 16.5.1 | 4.3.1.1 | 500 - Drainage and Service Ducts | Gullies | Gully Emptying, clean covers and clear obstructions | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.1.2 | 500 - Drainage and Service Ducts | Gullies | Clean covers and clear obstructions | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.2.1 | 500 - Drainage and Service Ducts | Linear drainage systems | Cleaning, rodding, jetting and proving Combined Kerb & Drainage System | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.2.2 | 500 - Drainage and Service Ducts | Linear drainage systems | Cleaning, rodding, jetting and proving Linear Drainage Channel | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.2.3 | 500 - Drainage and Service Ducts | Linear drainage systems | Cleaning, rodding, jetting and proving combined Channel and Pipe Systems | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.3.1 | 500 - Drainage and Service Ducts | Grips and counterfort drains | Clear Weed/vegetation growth, clean, recut drainage Grip inlet and non piped drainage Grip | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.3.2 | 500 - Drainage and Service Ducts | Grips and counterfort drains | Clear Weed/vegetation growth cleaning, rodding, jetting and proving of drainage Grip inlet and piped drainage Grip | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.3.3 | 500 - Drainage and Service Ducts | Grips and counterfort drains | Clear Weed/vegetation growth, clean, recut Counterfort drains | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.4 | 500 - Drainage and Service Ducts | Catch Pits | Clear Weed/vegetation growth, around frames, Clean, empty catch pits | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.5 | 500 - Drainage and Service Ducts | Ditches | Clean ditches by removing all material that could impair operation (overgrown vegetation, silt, debris/rubbish, or eroded banks where present impede flow and impair operation) | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.6 | 500 - Drainage and Service Ducts | Outfalls, including infiltration tanks/stilling basins and/or settlement ponds | Clean outfalls by removing all material that could impair operation (Headwalls, Pipe outfall) | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.7 | 500 - Drainage and Service Ducts | Interceptors | Clear Weed/vegetation growth, around frames, Clean, empty Interceptors | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.8 | 500 - Drainage and Service Ducts | Manholes | Clear Weed/vegetation growth, around frames, Clean, empty Manholes | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.9 | 500 - Drainage and Service Ducts | Culvert | Clean remove any blockage(silt, overgrown vegetation / weed, debris/rubbish, eroded bank material) restricting the free flow of water through the culvert | Low
Medium
High
(Insert additional rows as required)
SI 16.5.1 | 4.3.10 | 500 - Drainage and Service Ducts | Filter drains | Edge Scrap, clear vegetation/weed cut back to remove build up from edge of carriage way through to filter material in (Filter Drain and Combined carrier and Filter drain) that could impair operation | Low
Medium
High
(Insert additional rows as required)
SI 16.8.1 | 4.4.1.1 | 1200 - Traffic Signs and Road Markings | Traffic Signs | Clean all traffic sign faces and reference numbers areas less than 5m2 | Low
Medium
High
(Insert additional rows as required)
SI 16.8.1 | 4.4.1.2 | 1200 - Traffic Signs and Road Markings | Traffic Signs | Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | Low
Medium
High
(Insert additional rows as required)
SI 16.8.1 | 4.4.1.3 | 1200 - Traffic Signs and Road Markings | Traffic Signs | Clean all traffic sign faces and reference numbers of all Gantry Signs | Low
Medium
High
(Insert additional rows as required)
SI 16.8.1 | 4.3.2 | 1200 - Traffic Signs and Road Markings | Bollards | Clean all illuminated and non illuminated(retroflective) bollards | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.1 | 1300 - Lighting | SWITCHED Lamps (TLD, PL-L, PL-S, SOX) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.2 | 1300 - Lighting | Switched Lamps (TLDHF) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.3 | 1300 - Lighting | Switched Lamps (CDM-T, CDO, SON/T) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.4 | 1300 - Lighting | Switched lamps (GLS) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.5 | 1300 - Lighting | UNSWITCHED Lamps (TLD, PL-L, PL-S, SOX) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.6 | 1300 - Lighting | Unswitched lamps(TLDHF) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.7 | 1300 - Lighting | Unswitched Lamps (CDM-T, CDO, SON/T) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.8 | 1300 - Lighting | Unswitched lamps (GLS) | Bulk lamp clean and change | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.9 | 1300 - Lighting | Lamps (LED) for Road Lighting | Bulk Clean | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.10 | 1300 - Lighting | Lamps (LED) for Illuminated Signs and Bollards | Bulk Clean optics and translucent surfaces | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.11 | 1300 - Lighting | Network cabling and electrical components | Electrical testing including structural testing of columns (<20m in height) | Low
Medium
High
(Insert additional rows as required)
SI 16.9.1 | 4.5.12 | 1300 - Lighting | Feeder pillars | Good condition of feeder pillars to be maintained | Low
Medium
High
(Insert additional rows as required)
SI 16.12.1 | 4.6.1 | 3000 Ecology and Biodiverse Habitats | Injurious Weeds | Maintain Affected Property to control the spread or increase of instances of Injurious Weeds. | Low
Medium
High
(Insert additional rows as required)
SI 16.12.1 | 4.6.2 | 3000 Ecology and Biodiverse Habitats | Invasive Plant Species | Maintain Affected Property to control the spread or increase of instances of Invasive Plant Species. | Low
Medium
High
(Insert additional rows as required)
SI 16.12.1 | 4.6.3 | 3000 Ecology and Biodiverse Habitats | Grassland | Maintain habitat integrity, including removal of scrub encroachment | Low
Medium
High
(Insert additional rows as required)
SI 16.12.1 | 4.6.4 | 3000 Ecology and Biodiverse Habitats | Wetlands | Pond maintenance, clear vegetation and maintain open water | Low
Medium
High
(Insert additional rows as required)
SI 16.12.1 | 4.6.5 | 3000 Ecology and Biodiverse Habitats | Wildlife structures and tunnels | Remove all material that could impair operation | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.1 | 3100 - Soft Estate Landscape | Shrubs/ trees | Hedgerow trimming | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.2 | 3100 - Soft Estate Landscape | Woodland | Thin/ coppice | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.3 | 3100 - Soft Estate Landscape | Wildflower grassland | Cut and remove arising | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.4 | 3100 - Soft Estate Landscape | Grass and vegetation | Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve. | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.5 | 3100 - Soft Estate Landscape | Grass and vegetation | Preserve CCTV camera operational visibility splays | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.6 | 3100 - Soft Estate Landscape | Grass and vegetation | Maintain and preserve road users’ visibility of road traffic signs and signals. | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.7 | 3100 - Soft Estate Landscape | Grass and vegetation | Ensure illumination / lumination from lighting is not obscured. | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.8 | 3100 - Soft Estate Landscape | Grass and vegetation | Removing obstructions that prevent safe access, inspection and maintenance of technology equipment. | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.9 | 3100 - Soft Estate Landscape | Grass and vegetation | Facilitate safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas. | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.10 | 3100 - Soft Estate Landscape | Grass and vegetation | Undertake 2m wide amenity cut of amenity grass areas, including gates way features, village verges and special landscape features | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.11 | 3100 - Soft Estate Landscape | Grass and vegetation | Undertake 2m wide amenity cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year (in addition to visibility splay maintenance) | Low
Medium
High
(Insert additional rows as required)
SI 16.13.1 | 4.7.12 | 3100 - Soft Estate Landscape | Grass and vegetation | Grass cut from road edge to face of barrier on the central reserve Spray selective Herbicide to control weeds and broad leaf species, spray grass growth retarder after first cut of season | Low
Medium
High
(Insert additional rows as required)
SI 16.14.1 | 4.8.1 |  | Running lanes | Full sweep | Low
Medium
High
(Insert additional rows as required)
SI 16.14.1 | 4.8.2 |  | Paved non-running areas | Full sweep | Low
Medium
High
(Insert additional rows as required)
SI 16.14.1 | 4.8.3 |  | Carriageway, paved verges and paved central reservations of motorways and APTRs | Litter picking to maintain to grade A | Low
Medium
High
(Insert additional rows as required)
SI 16.14.1 | 4.8.4 |  | Motorway and APTR roundabouts and lay-bys, approach and slip roads | Litter picking to maintain to grade A | Low
Medium
High
(Insert additional rows as required)
SI 16.14.1 | 4.8.5 |  | All other parts of the Affected Property (non-paved, excluding amenity areas) | Litter pick to maintain to grade B | Low
Medium
High
(Insert additional rows as required)
SI 16.14.1 | 4.8.6 |  | Amenity areas | Litter picking to maintain to grade A | Low
Medium
High
(Insert additional rows as required)
(insert additional rows as required for any activity not covered by the above) |  |  |  |  | (Insert additional rows as required)
Section 2 - Deliver Maintenance Solutions (Repair Items)
SI 16.15.1 to 16.15.4 | - | 100 - Traffic Management | - | Traffic management | -
SI 16.3.14 | - | 300 - Fencing | - | Replacement of damaged fencing | -
SI 16.4.2 | - | 400 - Road Restraint Systems | - | Replacement of damaged safety barrier | -
|  |  | - | Not used | -
SI 16.5.3 | - | 500 - Drainage | - | Gully emptier including operator and driver | -
|  |  | - | Vactor unit including operator and driver | -
|  |  | - | CCTV unit including operator | -
|  |  | - | Disposal of Waste | -
SI 16.7.1 | - | 700 - Pavements | - | Patching in carriageway | -
SI 16.8.2 | - | 1200 - Traffic Signs and Road Marking | - | Replace regulatory traffic sign face | -
|  |  | - | Replace regulatory traffic lit sign face | -
|  |  | - | Replace damaged marker posts | -
SI 16.12.2 and SI 16.13.2 | - | 3000 - Landscaping and Ecology 3100 - Soft Estate Landscape | - | Grass cutter including driver and operators | -
|  |  | - | Disposal of waste | -
SI 16.14.2 | - | 4000 - Sweeping and Cleaning | - | Full sweep | -
|  |  | - | Litter picking to maintain to grade A | -
|  |  | - | Litter picking to maintain to grade B | -
|  |  | - | Pickup and 2 operatives | -
|  |  | - | Disposal of waste | -
(insert additional rows as required activity not covered by the above) |  |  |  |  | -
Section 3 - Deliver Severe Weather Plan
SI 17 | 2.1.1 | 7800 - Winter Maintenance | - | Take delivery of salt | -
| 2.1.2 |  | - | Salt management | -
| 2.1.3 |  | - | Drivers on standby | -
| 2.1.4 |  | - | Maintain winter fleet | -
| 2.1.5 |  | - | Winter fleet insurance | -
| 2.1.6 |  | - | Manage brine | -
| 2.1.7 |  | - | Maintain saturator | -
| 2.1.8 |  | - | Reporting | -
| 2.1.9 |  | - | Other Severe Water Duties | -
| - |  | - | Preparation for precautionary salting | -
| - |  | - | Precautionary salting | -
Section 4 - Deliver Incident Response
SI 18 | 3.1.1 | - | - | Incident response (attend, 3rd party reporting and advise repair) | -
Section 5 - Restore Asset Condition After Incident
SI 19 |  | 300 - Fencing |  |  | -
|  | 400 - Road Restraint Systems |  |  | -
|  | 500 - Drainage |  |  | -
|  | 600 - Geotechnical assets |  |  | -
|  | 700 - Pavements |  |  | -
|  | 1200 - Traffic Signs and Road Marking |  |  | -
|  | 1300 - Lighting |  |  | -
|  | 1700 - structures |  |  | -
|  | 3000 - Landscaping and Ecology |  |  | -
|  | 3100 - Soft Estate Landscape |  |  | -
Section 6 - Deliver Premises Management
SI 9 | 5.1.1 | Employer's Premises | - | General | -
|  |  |  | Asset and property management services | -
|  |  |  | Car parking | -
|  |  |  | Cleaning services | -
|  |  |  | Health, safety and environmental management in premises | -
|  |  |  | Estates services | -
|  |  |  | Grounds | -
|  |  |  | Helpdesk services | -
|  |  |  | materials management services | -
|  |  |  | Office equipment | -
|  |  |  | Pest control services | -
|  |  |  | Security services | -
|  |  |  | Utilities management | -
|  |  |  | Waste management services | -
|  |  |  | Safe checking of vehicles | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -