# Annex A

| Title of Project | Ocean Country Partnership Programme: Maldives Scoping user needs for an environmental data management system in the Maldives |
| --- | --- |
| Date and Time for Return of Bids | Monday 14 October 2024 at 16:00 (BST) |
| Contract Reference Number | C24-0604-1945 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO DAISY LEADBEATER, HANNAH HOOD OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: +44 1733 866988 |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Proposed Start Date | 28 October 2024 |
| Proposed End Date | 14 March 2025 |

Ocean Country Partnership Programme: Maldives

Scoping user needs for an environmental data management system in the Maldives

Contents

1.	Project Background	3

2.	Project Aims & Objectives	3

3.	Project Objectives: Detailed Tasks	4

4.	Product specification	6

5.	Project management	7

6.	Timescale	7

7.	Potential Follow-On Work	8

8.	Dissemination	8

9.	Health and Safety	8

10.	Instructions for Bid Submission	8

11.	Evaluation Criteria	9

12.	Payment	11

13.	Additional Requirements	11

14.	Procurement Timetable (which may be subject to change)	11

# Project Background

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

JNCC co-leads the Biodiversity theme of the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Fund which includes three UK government agencies: JNCC, Cefas and the MMO. OCPP has been supporting Maldives Environment Protection Agency (EPA) with priority areas, such as marine pollution emergency response, Marine Protected Areas (MPA) management and Environmental Impact Assessment (EIA).

The OCPP supports countries to:

- strengthen marine science expertise

- develop science-based policy and management tools

create educational resources for coastal communities

Throughout this document, we refer to JNCC as the organisation delivering the contract. However, we wish to clarify that this is part of JNCC’s work under the OCPP and so any reference to OCPP staff members refers to staff from JNCC, Cefas or the MMO working under the OCPP.

This contract is being delivered by JNCC on behalf of the Maldives Environmental Protection Agency (EPA). The EPA have requested support to develop a data management system to facilitate storage and access to data across the divisions within the department.

The EPA receives vast amounts of data under various regulations, including EIA reports, monitoring reports, inspection findings, research findings and annual reports submitted by all permit holders under the Environmental Act (4/93). This means that raw data are not readily accessible to review and reuse by EPA or other government departments.

The need for an effective data management system has been identified as a key priority for EPA as there is a need to consolidate and organise the diverse data collected for EIA and monitoring purposes.

Not only will the data management system help with the storage and organisation of environmental data collected in the Maldives, but it will also extend to enabling public access to the data for researchers, academics and local councils. This will promote collaboration and transparency in industry led environmental data collection and promote the reuse of environmental data to enable the EPA to understand environmental changes occurring throughout the country.

This project will focus on collecting information about user wants and needs for a data management system within the Maldives. This stage is fundamental for the development of a database as the output of this stage will shape the objectives of the database itself based on information provided by potential users.

# Project Aims & Objectives

This project aims to support the EPA by undertaking a scoping exercise to build understanding around the need for a data management system for use across Government departments and by stakeholders throughout the Maldives. The project will do this by collecting information about what potential users want, need and how they would use the database. The outcomes of this scoping would feed into the specification for the development of a future database.

The EPA have clear priorities for the database and want this to be used by many different stakeholder groups throughout the country, therefore, this project will focus on understanding stakeholder needs for an environmental database and how and why they might interact with the database. The successful bidder will receive a list of stakeholders from EPA who they anticipate using the database and who the contractor should contact.

This project is the initiation phase of the design and development of the data management system. The project objectives are to:

Understand how data are collected, prepared, stored, analysed, and distributed by the EPA.

Further understand, the EPA’s wants and needs for a new database system (for example, does there need to be a geographic visualisation component), understand the EPA’s preference for the maintenance of the database (for example, will it be maintained in-house or externally) and determine their capacity (resource and financial) to maintain this database.

Understand the stakeholders who are likely to use the database and collect information about their requirements for a database, and how to encourage engagement with the product. This includes understanding any technological limitations (such as hardware or internet limitations) that may make a database inaccessible. The successful contractor should therefore propose a set of minimum requirements for the database to ensure accessibility for the target stakeholder groups.

Collate the outputs from objectives 1-3 into a report which provides a detailed concept for the database. This report should give a thorough summary of all user research undertaken and should include a set of recommendations for the data management system based on the findings of the user research. This report will be used as a concept note for the next phase of the works which will be the development of the database itself.

# Project Objectives: Detailed Tasks

To achieve the aim and objectives, we anticipate the following tasks need to be completed. Contract bidders are welcome to advise on different or additional tasks they anticipate would increase the success of the project. We welcome the expertise of contractors with specific user research knowledge or those who have carried out similar projects within the Maldives. The contractor should have the ability to conduct stakeholder engagement in both Dhivehi and English.

Specific tasks

Carry out targeted interviews with EPA staff members who undertake data collection, preparation, storage, analysis and distribution. These targeted interviews should aim to understand how interviewees work with data, any limitations they currently experience and how interviewees anticipate a database could improve working with data. Targeted interviews should also aim to understand the EPA’s preference for the maintenance of the database (for example, will it be maintained in-house or externally) and determine their capacity (resource and financial) to maintain this database.

Develop a list of potential stakeholders, with help from OCPP and EPA staff, who may use the database and endeavour to contact a representative proportion of these stakeholder groups. This is to ensure that we have identified appropriate stakeholders, and we understand who might have an interest in the database. By contacting a representative proportion of stakeholders, the contractor will also ensure we thoroughly capture and understand user needs for a database.

Develop and conduct user story interviews and/or workshops with these stakeholders to understand the needs for a database. These interviews and/or workshops will focus on understanding how the stakeholder currently works with data, any limitations they currently experience and how interviewees anticipate a database could improve working with data. The interviewers should also aim to understand any technological limitations (both hardware and internet availability) that the interviewees may experience that may impact their accessibility to use the database.

The successful bidder will design a strategy for carrying out user research that maximises accessibility and efficiently collects information on the needs of users. For example, an in-person workshop in Male targeting many stakeholders, will efficiently collect vast amounts of data. However, it should be anticipated that stakeholders will not live in Male and so travel and/or online interviews may be necessary to collect all relevant information. The strategy for collecting user story interviews and/or workshops should cover logistics related to interviews and workshops, such as anticipated venue hire and travel needs, whilst ensuring that online platforms are utilised wherever practicable to ensure funding for the project is maximised as much as possible.

Produce a final report describing all work undertaken during the project and summarising the findings of the research. This should include a detailed needs assessment based on information collected from questionnaires, workshops and user story interviews. The conclusions of the report should include recommendations for the database based on the user research collected and provide clear minimum technological requirements for the database to ensure it is accessible to all target users. The report should also give a clear list of maintenance requirements for the database as well as the EPA’s capacity to maintain the database, highlighting any anticipated resource or financial limitations.

Maintain effective communication with OCPP and EPA throughout the project, ensuring we are able to input to specific deliverables and can provide technical assistance where needed.

Outputs would include

Interview and questionnaire scripts and written plans for workshops. JNCC and EPA will review these scripts and plans ahead of any interviews or workshops.

Interview transcripts and/or raw notes from interviews and workshops.

A final summary report which we anticipate including the following topics/sections:

Background to the project, including a summary of the current processes within the EPA for data collection, preparation, storage, analysis and distribution;

Rationale for the project, including any specific needs or resource gaps which the database will resolve;

Methodology of the study, including a summary of meetings held between the contractor and JNCC and EPA, a list of stakeholders identified and why, and a summary of all interviews and workshops carried out;

Summary of the task outputs;

Recommendations for a database based on these outputs including minimum technological requirements; and

Maintenance plan for the database.

JNCC and EPA would like the opportunity to review draft versions of this report so changes can be suggested. We anticipate this report will be used by the database developer to prioritise features, ensure accessibility and maximise engagement with the database.

# Product specification

Any final reports and supporting appendices should be accessible to those with a non-technical background and should be in English language. OCPP and EPA will help with providing guidance on the level of detail that should be included within the report in order for it to be shared and used with a wider audience.

Any recommendations for the data management system must include the requirement for the development to use openly accessible software with an established maintenance plan (including cost estimate plan) in place to ensure the system is used sustainably.

JNCC is committed to making its resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

impaired vision

motor difficulties

cognitive impairments or learning disabilities

deafness or impaired hearing

The contractor will not publish any information, by any means of publication, resulting from this contract without written consent from JNCC and the EPA.

Collection of personal data to meet the outputs of this contract should be handled in line with JNCC’s OCPP Privacy Notice.

# Project management

The contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main point of contact for JNCC.

JNCC’s main contact points will be:

Name: Daisy Leadbeater

Email:  Daisy.Leadbeater@jncc.gov.uk

Telephone: +44 1224 083534

Name: Hannah Hood

Email: Hannah.Hood@jncc.gov.uk

Telephone: +44 1224083520

It is anticipated that all contact between JNCC and the contractor will take place remotely online.

# Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | 28 October 2024 |
| Proposed workplan provided by contractor | 4 November 2024 |
| Interviews and workshops | November 2024, December 2024, January 2025 |
| Report drafting by contractor and reviewed by OCPP and EPA (maximum of two drafts to be reviewed) | January 2025 / February 2025 |
| Draft final report for review by OCPP and EPA | 28 February 2025 |
| Final report delivered | 14 March 2025 |

Please note the period of three months to conduct interviews and workshops is precautionary and to allow flexibility in being able to contact an appropriate sample size of stakeholders.

If contractors think they will be able to deliver work packages in less time than that specified above, they should give adequate justification within their bid documents.

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26. Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance.

# Potential Follow-On Work

For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

# Dissemination

The final report will be shared with the developer selected to develop the database and any raw data or information gathered in this contract, such as interview and workshop information, should also be made available to share if required.

The final report will also be made available to all staff of EPA and any members of the public who may have an interest in using the database.

Please note that any work carried out will be subject to JNCC’s data protection policy. For more information, please visit https://jncc.gov.uk/about-jncc/corporate-information/data-protection/. JNCC will discuss data protection matters with the successful contractor ahead of works commencing.

# Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding.

For further information, please visit https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/. To be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

Any incidents occurring within the contract period should be immediately reported to JNCC.

# Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 11), potentially including suggestions for suitable software or approaches as appropriate;

Details of Quality Control procedures to be followed see EQA Policy Appendix 1 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion);

Details of the bidder’s own internal Quality Management System;

Any identified risks associated the potential project and mitigations against them;

A project plan and an estimate of time required to achieve each objective;

Details of the Project Team including their roles and experience;

Overall quote for the contract (in GBP or USD) should include:

  - Daily rates for all members of the Project Team

  - Rates for attending virtual start-up, interim and final meetings with JNCC project team

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation (to submit in a zip folder separate from the proposal):

  - If your company includes more than 5 employees, please provide copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

# Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by JNCC staff and staff from the Maldives EPA. For transparency, JNCC will check with the Maldives EPA for their approval before award of contract.

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid |  |  |  |
| 1 | Clarity of proposal particularly work programme and deliverables | 7 |  |
| 2 | Understanding of technical requirements needed | 5 |  |
| 3 | Soundness and logicality of methods | 5 |  |
| 4 | Identification and proposed solutions to potential risks/issues | 5 |  |
| 5 | Serious weaknesses which threaten success | 5 |  |
|  | Sub Total | 27 |  |
| 2. Details of Contractor |  |  |  |
| 6 | Expertise and previous experience of conducting user research. | 13 |  |
| 7 | Experience of conducting in-person and online workshops and interviews. | 7 |  |
| 8 | Relevant expertise working in Maldives or regionally and ability to easily work within the Maldives | 13 |  |
| 9 | Understanding of data management systems, their utility and requirements | 10 |  |
| 10 | Knowledge of the Environment Protection Agency (EPA) in the Maldives | 5 |  |
| 11 | Ability of contractor to be able to deliver workshops and written products in English and Dhivehi | 5 |  |
|  | Sub Total | 53 |  |
| 3. Cost |  |  |  |
| 7 | Transparency and correctness of presentation | 10 |  |
| 8 | Fairness/reasonableness for the level of work and expertise required | 10 |  |
|  | Sub Total | 20 |  |
| Total Score |  | 100 |  |

# Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£) or US Dollars ($).

Payment will be made on completion of the objectives, or at interim milestones on agreement with the contractor, following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer. Payment schedule will be agreed between the contractor and project managers during the project inception.

# Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

# Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 16 September 2024 |
| Last date for receipt of clarification questions | 7 October 2024 |
| Final submission date for bids | 14 October 2024 |
| Evaluation of bids | w/c 14 October 2024 |
| Post-tender negotiation/clarification and or presentation if required | w/e 18 October 2024 |
| Successful Bidder Notified & Contract award | w/c 21 October 2024 |
| Unsuccessful bidders notified | w/e 25 October 2024 |
| Start of project | w/c 28 October 2024 |