## Sheet1
CLARIFICATION LOG
Tender: | Solar Energy System and Battery Storage
Tender Reference: | NZ739
Published Date: | 2024-03-22
Version number: | 0.4
Number | Clarification | Response | Reply date
1 | Are we limited to using a hybrid inverter? It would be far more practical and cost efficient to use one or two larger "main" inverters connected to AC battery chargers. | No - not limited. If you believe that you have a better solution - please detail this and explain why and clearly indicate the cost. | 2024-03-26
2 | Are we able to cover skylights? | No | 2024-03-26
3 | Is it the building circled? | Yes | 2024-03-26
4 | Would you be open to higher power panels? 560/580W panels? | The specification states MINIMUM requirement - so yes. | 2024-03-26
5 | Please confirm where the plant room/point of connection is located. | Within 20ft of the incoming power supply. Separate shed will be built for the batteries. | 2024-03-28
6 | I’m assuming the shed is going to be build by a third party for the BESS storage? | Yes | 2024-04-02
7 | Also, can you please highlight where this is due to go as the cabling and trenching can be costly and we are conscious of the fixed budget on this one. | 15m from where the power comes into the building. | 2024-04-02
8 | Do we only need to install the panels on the roof which is lined in red? Because if we install the panels on north-east facing roof, generation will be less. But south-west facing roof is OK. | Yes. 170-180kw output is required. | 2024-04-02
9 | Do you have power outs? | Yes. Please ensure your system accounts for this. | 2024-04-02
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk