## Front Sheet P003
DRAFT
organisatonal information requirements
The Shared Estates Service (SES) Cluster: Project Control Framework
STD/BIM/P003 BIM Plain Language Questions
SES Cluster Full List of Project, Design and Asset Requirements expressed in plain language
>Template Version 1.0 (for review with BIM2AIM SIG)

## MoJ PLQs
Stage | MoJ Plain Language Questions (To assist early project concept stage conversations - primarily by Client and Supply Chain filtered by RIBA Stage) | Cross Ref (Where Repeated)
Stage 00 - Strategy | Is the built asset sensitive, in whole or in part? | Pt5 Sec
Stage 00 - Strategy | Have considered whether the built asset may be of interest to a threat agent for hostile, malicious, fraudulent and/or criminal behaviours or activities. | Pt5 Sec
Stage 00 - Strategy | Are any neighbouring built assets sensitive? | Pt5 Sec
Stage 00 - Strategy | Have consulted with the owner/occupier/operator of any neighbouring built asset(s) to establish whether any measures need to be applied to information which will be shared, but which is not publicly available. | Pt5 Sec
Stage 00 - Strategy | Is there a need for a security-minded approach? | Pt5 Sec
Stage 00 - Strategy | Have undertaken the Security Triage process and determined whether a security-minded approach is required or, where business benefits may be derived, desirable. | Pt5 Sec
Stage 00 - Strategy | Is a Built Asset Security Manager in place? | Pt5 Sec
Stage 00 - Strategy | A suitably qualified and experienced individual has been appointed to fulfil the role of Built Asset Security Manager. | Pt5 Sec
Stage 00 - Strategy | Is an approved Built Asset Risk Management Strategy is place? | Pt5 Sec
Stage 00 - Strategy | A Built Asset Risk Management Strategy comprising risk assessment, risk mitigation and review processes is in place and it conforms with the requirements of PAS 1192-5:2015. | Pt5 Sec
Stage 00 - Strategy | Is an approved Built Asset Security Strategy (BASS) in place? | Pt5 Sec
Stage 00 - Strategy | A BASS which conforms with the requirements of PAS 1192-5:2015 is in place. | Pt5 Sec
Stage 00 - Strategy | Is an approved Built Asset Security Management Plan (BASMP) in place? | Pt5 Sec
Stage 00 - Strategy | A BASMP which conforms with the requirements of PAS 1192-5:2015 is in place. | Pt5 Sec
Stage 00 - Strategy | Is an approved Security Breach/Incident Management Plan (SB/IMP) in place? | Pt5 Sec
Stage 00 - Strategy | SB/IMP which conforms with the requirements of PAS 1192-5:2015 is in place. | Pt5 Sec
Stage 00 - Strategy | Is an approved Built Asset Security Information Requirements (BASIR) in place? | Pt5 Sec
Stage 00 - Strategy | A BASIR which conforms with the requirements of PAS 1192-5:2015 is in place. | Pt5 Sec
Stage 00 - Strategy | Are security-minded measures in place in relation to access given to information outside formal contracts, for example, in pre-contract dealings? | Pt5 Sec
Stage 00 - Strategy | There is separation and suitable protection of sensitive information and data. | Pt5 Sec
Stage 00 - Strategy | How will the security requirements as defined by the Built Asset Security Management Plan (BASMP) and Built Asset Security Information Requirements (BASIR) be met post-contract award? | Pt5 Sec
Stage 00 - Strategy | Evidence of how the security requirements defined in the Employer’s Information Requirements (EIR) will be met is included in submitted tender documentation. | Pt5 Sec
Stage 01 - Brief | What data and/or information needs to be excluded from exchanges with third parties (e.g. planning authorities and other statutory authorities)? | Pt5 Sec
Stage 01 - Brief | There is separation and suitable protection of sensitive information and data. | Pt5 Sec
Stage 01 - Brief | Appropriate measures are in place for redaction of information and use of other protective measures. | Pt5 Sec
Stage 01 - Brief | Special handling arrangements have been discussed and agreed with the planning authority. | Pt5 Sec
Stage 01 - Brief | Are there measures in place for the handling, processing and storage of existing built asset information and survey data, including data or information relating to neighbouring built assets? | Pt5 Sec
Stage 01 - Brief | Appropriate and proportionate measures are in place to protect the data and/or information, and where appropriate, are consistent with the requirements of the neighbouring asset’s owner/occupier/operator. | Pt5 Sec
Stage 01 - Brief | Are there suitable measures in place for the protection of personal and commercial data and/or information? | Pt5 Sec
Stage 01 - Brief | Confidentiality and non-disclosure agreements are contained in contractual documentation and access to and/or use of sensitive data is on a need-to-know basis. | Pt5 Sec
Stage 01 - Brief | Are there suitable measures in place for the protection of stakeholder data and/or information, for example property ownership along the route of an infrastructure project, environmental information etc. | Pt5 Sec
Stage 01 - Brief | Access to and/or use of data is on a need-to-know basis. | Pt5 Sec
Stage 01 - Brief | Is there appropriate management of information detailing: the security protection level or classification level of a project; security risk; and potential mitigation measures? | Pt5 Sec
Stage 01 - Brief | Information is handled on a strict need-to-know basis with security measures implemented in accordance with agreed risk management strategy. | Pt5 Sec
Stage 01 - Brief | Have high risk positions been identified within the project team and appropriate measures taken with regard to these positions? | Pt5 Sec
Stage 01 - Brief | High risk positions are identified, appropriate screening and vetting is in place and appropriate security-minded training is provided where necessary. | Pt5 Sec
Stage 01 - Brief | Has the use and nature of purpose-specific and/or volume-specific Construction Operations Building Information Exchange (COBie) files been agreed? | Pt5 Sec
Stage 01 - Brief | Where appropriate, information pertaining to sensitive assets and systems will be contained in separate files. | Pt5 Sec
Stage 02A - Concept (Outbound) | What is the Space Planning Design? | N/A
Stage 02A - Concept (Outbound) | Does the design’s performance meet the brief’s requirements? | 2a,2b
Stage 02A - Concept (Outbound) | What is the high level strategy for structural design? | N/A
Stage 02A - Concept (Outbound) | What are the high level strategy from services systems? | N/A
Stage 02A - Concept (Outbound) | Can the services and structure be combined within the Concept Design within the 3D volumes available? | 2a,2b
Stage 02A - Concept (Outbound) | Can the Client’s BREEAM objectives be met? | 2a,2b
Stage 02A - Concept (Outbound) | Has the concept been designed for efficient manufacture and assembly? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | How easy is it to assemble / build? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | What is the preliminary cost estimate? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | How shall the facility be procured? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | How will the outline proposals be communicated to the client? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | How will any Client specific performance needs be met? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | How will special presentation needs be met (EG to stakeholders and approvers)? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | Is the cost plan and cash flow forecast reliable and the risk allowance reasonable? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | Has the delivery schedule been validated? | 2a, 2b, 3
Stage 02A - Concept (Outbound) | Are there any deviations from the brief or proposals to improve it e.g with respect to the use of client standard BIM objects? | 2a,2b
Stage 02A - Concept (Outbound) | Is there appropriate management of information detailing: the security protection level or classification level of a project; security risk; and potential mitigation measures? | Pt5 Sec
Stage 02A - Concept (Outbound) | Information is handled on a strict need-to-know basis with security measures implemented in accordance with agreed risk management strategy. | Pt5 Sec
Stage 02A - Concept (Outbound) | Do the models and accompanying data and information meet the requirements of the BASIR? | Pt5 Sec
Stage 02A - Concept (Outbound) | Models, data and information are consistent with the requirements of the BASIR. | Pt5 Sec
Stage 02A - Concept (Outbound) | Can the designers show that the project can be delivered in a security-minded way? | Pt5 Sec
Stage 02A - Concept (Outbound) | It can be shown that the delivery of the project can meet the requirements of the BASS and BASMP. | Pt5 Sec
Stage 02A - Concept (Outbound) | Have the BASS, BASMP and/or BASIR been reviewed in light of the additional information generated during the Concept stage? | Pt5 Sec
Stage 02A - Concept (Outbound) | Documents have been reviewed and updated, including review of changes in risk environment or changes in operational requirements. | Pt5 Sec
Stage 02B - Concept (Inbound Response) | What is the Concept Design? | N/A
Stage 02B - Concept (Inbound Response) | Does the design’s performance meet the brief’s requirements? | 2a,2b
Stage 02B - Concept (Inbound Response) | What is the outline proposal for structural design? | N/A
Stage 02B - Concept (Inbound Response) | What are the output requirements from services systems? | N/A
Stage 02B - Concept (Inbound Response) | Can the services and structure be combined within the Concept Design within the 3D volumes available? | 2a,2b
Stage 02B - Concept (Inbound Response) | Can Building Regulations Part L and Energy Performance Certificate Requirements be met? | N/A
Stage 02B - Concept (Inbound Response) | Can the Client’s BREEAM objectives be met? | 2a,2b
Stage 02B - Concept (Inbound Response) | Has the concept been designed for efficient manufacture and assembly? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | How easy is it to assemble / build? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | What is the preliminary cost estimate? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | How shall the facility be procured? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | How will the outline proposals be communicated to the client? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | How will any Client specific performance needs be met? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | How will special presentation needs be met (e.g to stakeholders and approvers)? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | Is the cost plan and cash flow forecast reliable and the risk allowance reasonable? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | Has the delivery schedule been validated? | 2a, 2b, 3
Stage 02B - Concept (Inbound Response) | Are there any deviations from the brief or proposals to improve it e.g with respect to the use of client standard BIM objects? | 2a,2b
Stage 03 - Definition / Developed Design | Does the design’s performance meet the; schedule of accommodation, GIFA, and volumetric requirements? | N/A
Stage 03 - Definition / Developed Design | Are the proposals for the structural design integrated? | N/A
Stage 03 - Definition / Developed Design | Are the proposals or output requirements for the services systems integrated? | N/A
Stage 03 - Definition / Developed Design | Are the services and structure combined within the concept design and are the designed volumes available? | N/A
Stage 03 - Definition / Developed Design | Have the Building Regulations Part L and Energy Performance calculations been run and do they meet the requirements? | N/A
Stage 03 - Definition / Developed Design | Has the concept been designed for efficient manufacture and assembly? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | How easy is it to assemble / build? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | What is the preliminary cost estimate? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | How shall the facility be procured? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | How will the outline proposals be communicated to the client? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | How will any Client specific performance needs be met? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | How will special presentation needs be met (EG to stakeholders and approvers)? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | Is the cost plan and cash flow forecast reliable and the risk allowance reasonable? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | Has the delivery schedule been validated? | 2a, 2b, 3
Stage 03 - Definition / Developed Design | Are there any deviations from the brief or proposals to improve it? eg. with respect to the use of client standard BIM objects? | N/A
Stage 03 - Definition / Developed Design | Is there appropriate management of information detailing: naming, category and functionality of areas, zones and assets; built asset usage (in whole or in part); and sensitive performance criteria? | Pt5 Sec
Stage 03 - Definition / Developed Design | Information is handled on a strict need-to-know basis with security measures implemented in accordance with agreed risk management strategy and at the level of detail consistent with the BASIR. | Pt5 Sec
Stage 03 - Definition / Developed Design | Where appropriate, have specialist sub-contractors have been utilised to provide information and guidance pertaining to the requirements and logistics of sensitive assets and systems? | Pt5 Sec
Stage 03 - Definition / Developed Design | Appropriate information is available to relevant members of the design team to assure correct specification of supporting infrastructure and planning for deployment of sensitive assets and systems. | Pt5 Sec
Stage 03 - Definition / Developed Design | Do the models and accompanying data and information meet the requirements of the BASIR? | Pt5 Sec
Stage 03 - Definition / Developed Design | Models, data and information are consistent with the requirements of the BASIR. | Pt5 Sec
Stage 03 - Definition / Developed Design | Have the BASS, BASMP and/or BASIR been reviewed in light of the additional information generated during the Definition stage? | Pt5 Sec
Stage 03 - Definition / Developed Design | Documents have been reviewed and updated, including review of changes in risk environment or changes in operational requirements. | Pt5 Sec
Stage 04 - Design/Technical Design | Is there appropriate management of information detailing sensitive asset and system selection (including name, manufacturer, model number, performance and description) and connectivity? | Pt5 Sec
Stage 04 - Design/Technical Design | Information is handled on a strict need-to-know basis with security measures implemented in accordance with agreed risk management strategy and at a level of detail consistent with the BASIR. | Pt5 Sec
Stage 04 - Design/Technical Design | Is there appropriate management of data and information prepared by specialist sub-contractors in relation to sensitive assets and systems? | Pt5 Sec
Stage 04 - Design/Technical Design | Information is handled on a strict need-to-know basis with security measures implemented in accordance with agreed risk management strategy and at a level of detail consistent with the BASIR. | Pt5 Sec
Stage 04 - Design/Technical Design | (For most sensitive assets) Is the appropriate protection of information relating to the handling of emergency situations including evacuation procedures and contingency measures in place? | Pt5 Sec
Stage 04 - Design/Technical Design | Information is handled on a strict need-to-know basis outside the employer’s organisation and embedded third parties. | Pt5 Sec
Stage 04 - Design/Technical Design | (For most sensitive assets) Is the appropriate protection of information relating to maintenance and facilities management of the asset in place? | Pt5 Sec
Stage 04 - Design/Technical Design | Information is handled on a strict need-to-know basis outside the employer’s organisation and embedded third parties. | Pt5 Sec
Stage 04 - Design/Technical Design | Do the models and accompanying data and information meet the requirements of the BASIR? | Pt5 Sec
Stage 04 - Design/Technical Design | Models, data and information are consistent with the requirements of the BASIR. | Pt5 Sec
Stage 04 - Design/Technical Design | Have the BASS, BASMP and/or BASIR been reviewed in light of the additional information generated during the Design stage? | Pt5 Sec
Stage 04 - Design/Technical Design | Documents have been reviewed and updated, including review of changes in risk environment or changes in operational requirements. | Pt5 Sec
Stage 05 - Build / Construction | Does the facility meet the brief? | 5, 6
Stage 05 - Build / Construction | What has been built? | 5, 6
Stage 05 - Build / Construction | Do the systems work correctly? | 5, 6
Stage 05 - Build / Construction | How does a specific product / element perform? | 5, 6
Stage 05 - Build / Construction | How will the facility be operated? | 5,6
Stage 05 - Build / Construction | How is the facility to be maintained? | 5, 6
Stage 05 - Build / Construction | What is the relevant Health and Safety information? | 5, 6
Stage 05 - Build / Construction | How will the construction site be managed securely? | Pt5 Sec
Stage 05 - Build / Construction | Arrangements at the construction site are in accordance with the policies, processes and procedures set out in the BASMP and include measures to limit, or disrupt the success of, physical hostile reconnaissance. | Pt5 Sec
Stage 05 - Build / Construction | Do the models and accompanying data and information meet the requirements of the BASIR? | Pt5 Sec
Stage 05 - Build / Construction | Models, data and information are consistent with the requirements of the BASIR. | Pt5 Sec
Stage 05 - Build / Construction | Have the BASS, BASMP and/or BASIR been reviewed in light of the additional information generated during the Build stage? | Pt5 Sec
Stage 05 - Build / Construction | Documents have been reviewed and updated, including review of changes in risk environment or changes in operational requirements. | Pt5 Sec
Stage 05 - Build / Construction | Is the installation of sensitive assets and systems scheduled so as to prevent unauthorised access and limit the potential for damage or compromise? | Pt5 Sec
Stage 05 - Build / Construction | Installation of sensitive assets, and the fitting-out of sensitive areas is programmed for a time where access to those assets or areas can be limited to a number of specialist contractors, and where, for logistical reasons, this is not possible, appropriate and proportionate security measures are in place. | Pt5 Sec
Stage 06 - Handover & Closeout | Does the facility meet the brief? | 5, 6
Stage 06 - Handover & Closeout | What changes have been incorporated? | N/A
Stage 06 - Handover & Closeout | What has been built? | 5, 6
Stage 06 - Handover & Closeout | Do the systems work correctly? | 5, 6
Stage 06 - Handover & Closeout | What is the basis for a valuation? | N/A
Stage 06 - Handover & Closeout | How does a specific product / element perform? | 5, 6
Stage 06 - Handover & Closeout | How will the facility be operated? | 5,6
Stage 06 - Handover & Closeout | How is the facility to be maintained? | 5, 6
Stage 06 - Handover & Closeout | What is the relevant Health and Safety information? | 5, 6
Stage 06 - Handover & Closeout | Do the models and accompanying data and information meet the requirements of the BASIR? | Pt5 Sec
Stage 06 - Handover & Closeout | Models, data and information including information provided for operation and maintenance are consistent with the requirements of the BASIR. | Pt5 Sec
Stage 06 - Handover & Closeout | Are measures being applied for the secure return, storage or destruction of asset information? | Pt5 Sec
Stage 06 - Handover & Closeout | Procedures for post-contract management of information have been implemented. | Pt5 Sec
Stage 06 - Handover & Closeout | Does the transfer of asset information to the Asset Information Model and the arrangements for access meet the requirements of the BASIR? | Pt5 Sec
Stage 06 - Handover & Closeout | Models, data and information are consistent with the requirements of the BASIR. Access arrangements are in accordance with the BASMP. | Pt5 Sec
Stage 06 - Handover & Closeout | Have the BASS, BASMP and/or BASIR been reviewed in light of the additional information generated during the Handover stage? | Pt5 Sec
Stage 06 - Handover & Closeout | Documents have been reviewed and updated, including review of changes in risk environment or changes in operational requirements. | Pt5 Sec
Stage 07 - Operation & End of Life | What security measures are required in the event that the built asset is significantly modified or decommissioned, or there is a change of ownership, occupancy or use? | Pt5 Sec
Stage 07 - Operation & End of Life | Appropriate measures are in place to protect valuable, attractive and sensitive items, including all physical or information assets. | Pt5 Sec