## Greenworks & Maintance Spec
What | Where | Work | More Details | How often | When | Notes
S136 Agreement Highways Verges | See Sheet 3
Highways Verges | Area 1 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 2 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 3 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 4 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 5 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 6 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 7 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 8 | Mow and strim around lampposts, street furniture etc | 7 monthly cuts | Monthly | Apr - Oct
Highways Verges | Area 9 | Mow and strim around lampposts, street furniture etc | 4 monthly cuts | 4 visits per year | Apr - Oct
Seating Areas /Bus Shelters/Misc | A-L listed below
A | Chater Street, High Street, Northampton Lane North, Overstone Road x 2 and West Street. | Maintenance visits to include litter picking and applying an approved herbicide, and where required, pruning and de-weeding. | 6 x Bench Seating Areas | Monthly | Apr - Oct | Contractor to supply black sacks for litter picking
B | Barlow Lane | Maintenance visits to include, pruning, de-weeding, litter picking, applying an approved herbicide and topping up bark mulch when required. | 2 x Gated Areas at Bottom | Monthly | Apr - Oct | Contractor to supply black sacks for litter picking
C | Stocks Hill | Maintenance visits to include, pruning, de-weeding, litter picking, applying an approved herbicide. | Border, around Bus Stop | Monthly | Apr - Oct | Contractor to supply black sacks for litter picking
D | Fuller Road / Northampton Lane North Junction | Maintenance visits to include, pruning, de-weeding, litter picking, applying an approved herbicide. Make sure noticeboard is accessible. | Notice Board Area | Monthly | Apr - Oct | Contractor to supply black sacks for litter picking
E | Cross Street | Maintenance visits to include, pruning, de-weeding, litter picking, applying an approved herbicide (grass verges included in cutting schedule in Area 3). | Borders at the top | Monthly | Apr - Oct | Contractor to supply black sacks for litter picking
F | Barlow Lane | Maintenance visits to include, pruning, de-weeding, litter picking, applying an approved herbicide, including trimming back all overhanging vegetation from car park area (but not from Cardigan Arms). | Car Park (large top car park) | Monthly | Apr - Oct | Contractor to supply black sacks for litter picking
G | Lunchfield | Maintenance visits to include, cutting back shrubs and clearing weeds at the back of the Scout Hut. | Lunchfield Triangle | Twice yearly | Mar/Oct
H | Parade Bank | Monthly maintenance to include pruning and weeding to the right of the book exchange to the corner of Parade Bank. | Book Exchange | Monthly | Apr - Oct
I | Overstone Road Bus Stop | Maintenance to include pruning and weeding – cut back and trim shrubs. | Bus Stop | Twice yearly | Mar/Oct
J | The Grove | Maintenance to trim Laurel bush from behind street sign so that height remains at 1m. | Corner of Church View | Twice yearly | Mar/Oct
K | Northampton Lane | Maintenance to include pruning and weeding – cut back and trim shrubs. | Bus Stops x 3 | Twice yearly | Mar/Oct
L | Crowfields | Strim around the noticeboards and dog bins at the bottom of Doves Lane and Ashley Lane entrance. |  | Monthly | Apr - Oct
Busbys Meadow NN3 7UF
POS | Busby’s Meadow | Mow approx. 1m wide strip around path (leave cuttings) and round rear of wildflower area house side including seat , bin and noticeboard strim | Grass nearest houses (Church View) | Monthly
POS | Busby’s Meadow | Full Mow (leave cuttings) | Grass nearest houses (Church View) | Late July
POS | Busby’s Meadow | Full Mow (leave cuttings) | Grass nearest houses (Church View) | Autumn
POS | Busby’s Meadow | Mow approx. 1m wide strip around path and a 1m wide strip from path leading to 1st bridge and 2nd bridge (leave cuttings) | Stream side | Fortnightly | Apr - Oct
POS | Busby’s Meadow | Full Mow (leave cuttings) | Stream side | Late July
POS | Busby’s Meadow | Full Mow (leave cuttings) | Stream side | Autumn
POS | Busby’s Meadow | Full Boundary Hedge Trim |  | Twice yearly | Mar/Oct
SUDS | Busby’s Meadow | Inspect drainage and water flow, check both bridges | Watercourse | Weekly
Cemetery NN3 7UF
Cemetery | The Grove | Mark out graves for burials (approx 12 per year)
Cemetery | The Grove | Put out bins for WNC collection |  | 3 weekly
Cemetery | The Grove | Mow and strim | Whole site | Weekly | Mar - Oct
Cemetery | The Grove | Herbicide application |  | Monthly | Mar - Oct
Cemetery | The Grove | Hedge Trim so all pathways are clear |  | Twice yearly and as required | Mar/Oct
Cemetery | The Grove | Leaf clearing |  | Fortnightly | Winter
Cemetery | The Grove | Re edge paths and top up pea shingle |  | Every 2 years | Winter
Cemetery | The Grove | All debris and litter to be removed during each visit |  | As required
Cemetery | The Grove | Repaint bench and gazebo |  | Every 2 years
Community Centre NN3 7AX
Community Centre | Sandy Hill | Site visit |  | Fortnightly | Apr - Oct
Community Centre | Sandy Hill | Site visit |  | Monthly | Nov - Mar
Community Centre | Sandy Hill | Mow and Trim all edges to paths, shrub areas and around trees | Grass Areas | Fortnightly | Mar - Oct
Community Centre | Sandy Hill | Regular herbicide applications | Shrub Areas and all hardstanding | Monthly
Community Centre | Sandy Hill | Full Prune | Shrub Areas | As required
Community Centre | Sandy Hill | Remove wind-blown litter |  | Each visit
Community Centre | Sandy Hill | Remove fallen leaves |  | Winter
Community Centre | Sandy Hill | Snow Clearing | As required, one off charge |  |  | Extra Charge
Community Centre | Sandy Hill | Supply and spread grit | As required, one off charge |  |  | Extra Charge
Crowfields Common (NN3 7TA Doves Lane entrance)
POS | Crowfields | Cut a 2m wide path | All fields. | Monthly | Apr - Aug
POS | Crowfields | Cutting back walkway hedges | All fields. | Annually
POS | Crowfields | Field 1 (Ridge & Furrow – Library) | Flail cut in July (Leave a 20m non-managed area from the badger set) | Jul | Jul
POS | Crowfields | Field 1 (Ridge & Furrow – Library) | Flail cut in September (Leave a 20m non-managed area from the badger set) | Sept | Sept
POS | Crowfields | Field 2 | Flail cut half in July, leaving other half to continue to grow until September | Jul | Jul
POS | Crowfields | Field 2 | Flail cut all of the field in September, but leave a 6m strip along the lower hedge | Sept | Sept
POS | Crowfields | Field 2 | Harrow in October | Oct | Oct
POS | Crowfields | Field 3 | Flail cut in July, except 6m strip along the bottom hedge | Jul | Jul
POS | Crowfields | Field 3 | Flail cut in September | Sept | Sept
POS | Crowfields | Field 3 | Harrow in October | Oct | Oct
POS | Crowfields | Field 4 (Wildflower Meadow) | Flail mow September | Sept | Sept
POS | Crowfields | Adjoining Field Walkways | To supply and spread Type 1 crushed stone to adjoining field walkways | Bi annually
Litter pick | Crowfields | Litter pick |  | Monthly |  | Contractor to supply black sacks for litter picking
Forester Road NN3 7SF
POS | Forester Road | Mow and strim | Play Areas | Fortnightly | Apr - Oct
POS | Forester Road | Mow and strim | Whole site | monthly | Apr - Oct
POS | Forester Road | Maintain | Planted Areas | Twice yearly | Mar/Oct
POS | Forester Road | Walkways | Repairing walkways with Breedon Gravel | Twice yearly | Mar/Oct
PLAY AREA | Forester Road | Weekly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Weekly
PLAY AREA | Forester Road | Quarterly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Quarterly
PLAY AREA | Forester Road | Weed killer safety surfaces |  | Quarterly
SUDS | Forester Road | Mow and strim | Attenuation Basins within site | Annually | Oct
SUDS | Forester Road | Inspect drainage and water flow | Attenuation Basins within site | Weekly
SUDS | Forester Road | Thin out excess growth to retain adequate flow in channel | Attenuation Basins within site | Annually | Oct
SUDS | Forester Road | Check attenuation basins at each monthly visit for blockages/litter removal and bank stability and clear debris as required | Attenuation Basins within site | Monthly as required
SUDS | Forester Road | Maintain bank side vegetation/weed cover | Attenuation Basins within site | Annually | Oct
Lunchfield Triangle NN3 7AB
POS | Lunchfield | Mow and strim | Lunchfield Triangle, Lunchfield Lane | Monthly | Apr - Oct
POS | Lunchfield | Trim back to current level- Cut back from around bin | Holly and Hawthorn Hedge | Every 2 years
Litter pick | Lunchfield | Litter pick | Lunchfield Lane | Fortnightly |  | Contractor to supply black sacks for litter picking
Morning Star Lane NN3 7BU
PLAY AREA | Morning Star Lane | Mow and strim | Whole site | Fortnightly | Apr - Oct
POS | Morning Star Lane | Hedge and Shrub Trim | Hedge and shrubs rear footpath and front of site | Twice yearly | Mar/Oct
PLAY AREA | Morning Star Lane | Weekly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Weekly
PLAY AREA | Morning Star Lane | Quarterly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Quarterly
SUDS | Morning Star Lane | Mow and strim | Attenuation Basin within site | Annually | Oct
SUDS | Morning Star Lane | Inspect drainage and water flow | Attenuation Basin within site | Weekly
SUDS | Morning Star Lane | Thin out excess growth to retain adequate flow in channel | Attenuation Basin within site | Annually
SUDS | Morning Star Lane | Check attenuation basins at each monthly visit for blockages/litter removal and bank stability and clear debris as required | Attenuation Basin within site | Monthly as required
SUDS | Morning Star Lane | Maintain bank side vegetation/weed cover. | Attenuation Basin within site | Annually | Oct
POS | Morning Star Lane | Check and empty bin | Play Areas | Weekly | Dog bin to be emptied by WNC
POS | Morning Star Lane | Mow and strim | Play Areas | Fortnightly | Apr - Oct
Moorbridge Road NN3 7AA | [5 empty] | Carey Fields
POS | Moorbridge Road | Mow and strim | Whole site | Monthly | Apr - Oct
POS | Moorbridge Road | Maintain | Wildlife Corridor | Twice yearly | Mar/Oct
POS | Moorbridge Road | Maintain | Planted areas | Twice yearly | Mar/Oct
POS | Moorbridge Road | Maintain Side up hedge | Planted hedge to Eastern Boundary | Twice yearly | Mar/Oct
POS | Moorbridge Road | Mow and strim | Play Areas | Fortnightly | Apr - Oct
POS | Moorbridge Road | Walkways | To supply and spread Type 1 crushed stone to field walkways x2 | Bi annually
PLAY AREA | Moorbridge Road | Weekly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Weekly
PLAY AREA | Moorbridge Road | Quarterly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins | Quarterly
PLAY AREA | Moorbridge Road | Weed killer safety surfaces |  | Quarterly
SUDS | Moorbridge Road | Mow | Attenuation Basins within site | Annually | Oct
SUDS | Moorbridge Road | Inspect drainage and water flow, fences and bridge | Attenuation Basins within site | Weekly
SUDS | Moorbridge Road | Thin out excess growth to retain adequate flow in channel | Attenuation Basins within site | Annually | Oct
Mulbridge Way NN3 7DZ | [5 empty] | Marsh Spinney Site
POS | Mulbridge Way | Mow and strim | Whole site | monthly | Apr - Oct
POS | Mulbridge Way | Hedge Trim | Boundary | Twice yearly | Mar/Oct
SUDS | Mulbridge Way | Mow and strim | Attenuation Basins within site | Annually | Oct
SUDS | Mulbridge Way | Inspect drainage and water flow | Attenuation Basins within site | Weekly
SUDS | Mulbridge Way | Thin out excess growth to retain adequate flow in channel | Attenuation Basins within site | Annually | Oct
SUDS | Mulbridge Way | Check attenuation basin at each monthly visit for blockages/litter removal and bank stability and clear debris as required | Attenuation Basins within site | Monthly as required
SUDS | Mulbridge Way | Maintain bank side vegetation/weed cover | Attenuation Basins within site | Annually | Oct
SUDS | Mulbridge Way | SUD's Inspection |  | Weekly
Parish
Weedkiller | Various | Chater Street, Stocks Hill to the Junction of Pound Lane, Church Hill, Church Street, The Grove to Farm Lane, High Street to Northampton Lane corner of Lunchfield, Overstone Road to the corner with Ashley Lane. Map A | Spray with glyphosate biased approved chemical | Monthly | Apr - Oct
Water | Various | Water hanging baskets and planters |  | Twice a week | Summer only
Install | Various | Install hanging baskets and sponsorship plaques |  | Annually | April/May
De-rig | Various | De-rig hanging baskets take back to Robs Nursery |  | Annually | Sept/Oct
Install | Various | Install Remembrance Poppies and Tommy's |  | Annually | Nov
De-rig | Various | De-rig Remembrance Poppies and Tommy's |  | Annually | Nov
Litter pick | Manor Road to Lunchfield Alleyway | Litter pick | Alleyway | Fortnightly |  | Contractor to supply black sacks for litter picking
Litter pick | Cross Street Alleyway | Litter pick | Alleyway | Fortnightly |  | Contractor to supply black sacks for litter picking
Litter pick | Barlow Lane Alleyway | Litter pick | Alleyway | Weekly |  | Contractor to supply black sacks for litter picking
Litter pick | Lunchfield & Fuller Road Alleyway | Litter pick | Alleyway | Fortnightly |  | Contractor to supply black sacks for litter picking
Paint | Stocks Hill Bus Shelter | Stain | Bus Shelters | Every 2 years
Paint | Overstone Road Bus Shelters | Stain | Bus Shelters | Every 2 years
Paint | The Grove Bus Shelters | Stain | Bus Shelters | Every 2 years
Paint | Doves Lane | Paint with marine varnish | Nature Sign double | Every 2 years
Paint | Ashley Lane | Paint with marine varnish | Nature Sign double | Every 2 years
Paint | Busby's Meadow | Paint with marine varnish | Nature Sign double | Every 2 years
Paint | Barlow Lane/Stocks Hill | Paint with marine varnish | Notice Boards | Every 2 years
Paint | Community Centre | Paint with marine varnish | Notice Boards | Every 2 years
Paint | Eynon Close/Boughton Road | Paint with marine varnish | Notice Boards | Every 2 years
Paint | Fuller Road/Northampton Lane North | Paint with marine varnish | Notice Boards | Every 2 years
Paint | Overstone Road/Ashley Lane | Paint with marine varnish | Notice Boards | Every 2 years
Paint | Public Gardens | Paint with marine varnish | Notice Boards | Every 2 years
Install | Outside Village Autos | Supply and install Christmas Tree with Lights |  | Annually | Dec
De-rig | Outside Village Autos | De-rig Christmas Tree with Lights |  | Annually | Jan
Extra Charge | Various | Runs to the local recycling centre to dispose of large items/additional rubbish | As required, one off charge |  |  | Extra Charge
Extra Charge | Various | Graffiti removal | As required, one off charge |  |  | Extra Charge
Extra Charge | Various | Supply and spread grit - Public Gardens | As required, one off charge |  |  | Extra Charge
Extra Charge | Various | Remove smashed bottles/broken branches | As required, one off charge |  |  | Extra Charge
Report | Various | Report any issues in village to Parish Administrator | Street lights not working/poor condition of post Pot holes, flooding/blocked drains, road markings in need of repainting Debris on road/footpaths – leaves, branches etc Poor condition of footpaths, loose kerb stones, Overhanging trees fouling power lines Resident trees/hedges overhanging footpaths Traffic/directional signs – cleanliness, condition of post Street name signs – in good condition/need of repair/securing | As required
Public Gardens NN3 7SP
POS | Public Gardens | Mow and strim |  | Fortnightly | Apr - Oct
POS | Public Gardens | Trim conifer hedge |  | Annually
POS | Public Gardens | Boundary hedge, laurel hedge around storage shed and hedges either side of vehicle entrance |  | Twice yearly | Mar/Oct
PLAY AREA | Public Gardens | Weekly Playground Inspections | Visual check all CCTV, Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Weekly
PLAY AREA | Public Gardens | Quarterly Playground Inspections | Manual check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Quarterly
PLAY AREA | Public Gardens | Weed killer safety surfaces |  | Quarterly
Litter pick | Public Gardens | Litter pick and clear stream, place full bin bags at the top for WNC collection every Friday morning | Stream | Weekly |  | Contractor to supply black sacks for litter picking
POS | Public Gardens | Empty bins |  | Twice a week
SUDS | Public Gardens | Weekly visual check of watercourse | Stream | Weekly
SUDS | Public Gardens | Stream clearance of slit and detritus around pipe | Stream | Monthly
POS | Public Gardens | Snow Clearing | As required, one off charge | As required |  | Extra Charge
POS | Public Gardens | Supply and spread grit | As required, one off charge | As required |  | Extra Charge
Rose Tree Close NN3 7SU
SUDS | Rose Tree Close | Inspect drainage and water flow | Attenuation Basins within site | Weekly
SUDS | Rose Tree Close | Cut shrubs & basin | Attenuation Basins within site | Annually | Oct
Sanders Drive NN3 7BY
POS | Sanders Drive | Mow and strim | Whole site | monthly | Apr - Oct
POS | Sanders Drive | Maintain | Planted Areas | Twice yearly | Mar/Oct
POS | Sanders Drive | Check and empty bin |  | Weekly
Sandy Hill NN3 7AX
POS | Sandy Hill | Mow and strim | Whole site | Monthly | Apr - Oct
POS | Sandy Hill | Maintain | Planted areas | Twice yearly | Mar/Oct
PLAY AREA | Sandy Hill | Mow and strim | Play Areas | Fortnightly | Apr - Oct
PLAY AREA | Reedings | Weekly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Weekly
PLAY AREA | Reedings | Quarterly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, Fences and Gates | Quarterly
PLAY AREA | Reedings | Weed killer safety surfaces |  | Quarterly
POS | Reedings | Check and empty bins | Play Area | Weekly |  | Contractor to supply black sacks for litter picking
SUDS | Sandy Hill | Mow and strim | Attenuation Basin within site | Annually | Oct
SUDS | Sandy Hill | Inspect drainage and water flow | Attenuation Basins within site | Weekly
SUDS | Sandy Hill | Thin out excess growth to retain adequate flow in channel | Attenuation Basins within site | Annually | Oct
Spinney Close NN3 7DH
POS | Spinney Close | Check and empty bins |  | Weekly |  | Contractor to supply black sacks for litter picking
PLAY AREA | Spinney Close | Mow and strim | Play Area | Fortnightly | Apr - Oct
PLAY AREA | Spinney Close | Weekly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, and Fences | Weekly
PLAY AREA | Spinney Close | Quarterly Playground Inspections | Check all Equipment, Signs, Surfaces, Benches, Bins, and Fences | Quarterly
PLAY AREA | Spinney Close | Weed killer safety surfaces |  | Quarterly

## Area's Sheet 3
Highway Grass Verges, to include:
Area 1
Pound Lane, Boughton Road (starting at the Moulton sign to the junction with the Pitsford Road, including triangle junctions to Carey Close and Arnsby Crescent), Carey Close (Kerbside verges only), Jeyes Close, Arnsby Crescent (Any untended areas as necessary), Pitsford Road (up to 30mph speed sign), Stewart Close, The Hollies, Morning Star Lane and Forester Road.
Area 2
Lunchfield Lane and Lunchfield Gardens verges.
Area 3
Cross Street, Parade Bank, The Grove (from the Moulton sign to junction with Alibone Close, in Chater Street). Mowing to be up to the wall on both sides of the road to include narrow verge into Church View alongside of Busby’s Meadow), Church View, Oakley Drive, Pytchley View, The Crescent. To include triangles at junctions with Pytchley View, Oakley Drive and The Crescent.
Area 4
Ashley Lane (any verges as necessary including junction with Kettering Road), Overstone Road (to the junction with the A43). The wide verge adjacent to Tarrant Way and junctions to Tarrant Way and Tarrant Close. The wide verges at the entrance to Park View including around the Total garage, Wantage Close, Tarrant Way, Tarrant Close, Top of Sandy Hill Road, Park View (all verges on both sides of the road to the end of the houses of the old A43 cul-de-sac).
Area 5
Northampton Lane North, Moorbridge Road , the corner verges at March Springs, Ryland Road, Greenwood Close, Harvey Lane, Fuller Road, Manor Road (including the two areas area in front of elderly people’s bungalows), Brunting Road and Whiting Court.
Area 6
Northampton Lane North (From the junction with Cross Street to the Moulton sign including triangles at junctions with Brunting Road, Fuller Road, Manning Road and Ryland Road.
Area 7
The Avenue (verges from the junction of the A43 until after the last house – No 5 Oakview).
Area 8
Grass verges either side of Barlow Lane, leading up to the top car park and the small area at the back of the Hall.
Area 9
Thorpeville Verges