# Schedule 1: Contract Data

## Part one – data provided by the Client

1 General

The conditions of contract are the core clauses and the clauses for the following main Options, the Option for resolving and avoiding disputes and secondary Options of the NEC4 Engineering and Construction Sub Contract June 2017 including January 2019 amendments Main Option - Option B: Priced contact with bill of quantities Option for resolving and avoiding disputes - Option W2 Secondary Options - Option X15 Subcontractors Design - Option X16: Retention - Option X20: Key Performance Indicators - Option Y(UK)2: Housing Grants, Construction and Regeneration Act 1996 in each case subject to and as amended and supplemented by the additional conditions of contract set out in Schedule 2

The works in the main contract are advanced civil engineering works in support of the Clients Repository Development Programme.- Minor Civil Works The Subcontract Works are Design, Supply and Install, test and commission the Lagoon D attenuation tank as per the Scope

The Contractor is Graham Construction Ltd Address for all Communications 5 Ballgowan Road, Hillsborough, Co. Down, Northern Ireland, BT26 6HX For site c/o Graham Construction, LLWR Site, Old Shore Road, Holmrook, CA19 1XP For Electronic Communications George.Smith@Graham.co.uk The Client in the main contract is Low Level Waste Repository Address for communications LLWR Site, Old Shore Road, Holmrook, CA19 1XP Address for electronic communications - Rhys.coyles@llwrsite.com

| The Project Manager in the main contract is |  |
| --- | --- |
| Name | Rhys Coyles |
| Address for communications | LLWR Site, Old Shore Road, Holmrook, CA19 1XP |
| Address for electronic communications | Rhys.coyles@llwrsite.com |
| The Subcontract Scope is (Enquiry Document Attenuation ) and further detailed in Schedule 3 |  |
| The Site Information is in: LLWR-RDP-T1.00-GEN-034 Site Information.pdf |  |
| The boundaries of the site are the Repository perimeter fence |  |
| The language of the contract is English |  |
| The law of the contract is the law of England and Wales |  |
| The period for reply is the period for reply of main contract identified within the main contract scope document reference LLWR-RDP-T1 plus 1 week or minimum of 2 weeks |  |
| The following matters will be included in the Early Warning Register - the matters identified in Schedule 5 |  |
| Early warning meetings are to be held at intervals no longer than weekly or as agreed between the parties |  |

| 2 The Sub-Contractor’s main responsibilities |  |  |  |
| --- | --- | --- | --- |
| If the Contractor has identified work which is set to meet a stated condition by a key date | The key dates and conditions to be met are |  |  |
|  |  | condition to be met | key date |
|  | (1) | To be input if appropriate to the package |  |
| 3 Time |  |  |  |
| The starting date is Commencement Date 01st June 2020 (for design) |  |  |  |
| The access dates are |  |  |  |
|  |  | part of the Site | date |
|  | (1) | The Site August 2020 (to be confirmed) |  |
|  | (2) |  |  |
|  | (3) |  |  |
| The Subcontractor submits revised programmes at intervals that align with the Client’s Reporting Calendar as detailed in the Schedule 5 |  |  |  |
| If the Contractor has decided the subcontract completion date for the whole of the subcontract works | The subcontract completion date for the whole of the subcontract works Nov 2020 (to be confirmed) |  |  |
| Taking over the works before the Subcontract Completion Date | The Contractor is not willing to take over the works before the Completion Date |  |  |
| If no programme is identified in part two of the Subcontract Data | The period after the SubContract Date within which the subcontractor is to submit a first programme for acceptance is 2 weeks |  |  |

| 4 Quality management |  |
| --- | --- |
|  | The period after the Subcontract Date within which the Subcontractor is to submit a quality policy statement and quality plan is 2 weeks |
|  | The period between Completion of the whole of the subcontract works and the defects date is 52 weeks |
|  | The defect correction period is 2 weeks |
| 5 Payment |  |
|  | The currency of the contract is GBP |
|  | The assessment interval is aligned with the Clients Reporting Calendar as detailed in the Scope as identified *********** |
|  | The interest rate is 2% per annum above the base lending rate of National Westminster Bank Plc |
|  | The payment period is 30 days |
| 6 Compensation events |  |
|  | The place where weather is recorded is St Bees Head |
|  | The weather measurements recorded for each calendar month are - the cumulative rainfall (mm) - the number of days with rainfall more then 5mm - the number of days with minimum air temperature less than 0 degrees Celsius - the number of days with snow lying at 07:00am hours GMT |
|  | The weather measurements are supplied by Met Office |
|  | The weather data are the records of past weather measurements for each calendar month which were recorded at St Bees Head and which are available from Met Office |
| If Option B or D is used If there are additional compensation events | The method of measurement is Method of Measurement for Highway Works contained in Section 1 of Volume 4 of the Manual of Contract Documents for Highway Works published as ISBN 0 11 552327 8 by The Stationery Office The are no additional compensation events |
| 8 Liabilities and insurance |  |
|  | The minimum amounts of cover for and the time until which the Subcontractor maintains insurance in respect of the following events and matters are as set out in the following table |

|  | INSURANCE TABLE |  |
| --- | --- | --- |
| Insurance against | Minimum amount of cover | Time until which Contractor maintains insurance (if later than otherwise stated in Clause Z83.2) |
| Loss of or damage to Plant and Materials and Equipment | The replacement cost |  |
| Loss of or damage to property (except Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor Providing the Service | £10,000,000 (ten million pounds) for any one event with cross liability so that the insurance applied to the Parties separately |  |
| Death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with the contract | The greater of the amount required by the applicable law and £10,000,000 (ten million pounds) for any one event |  |
| Fully comprehensive motor insurance | The amount required by law |  |
| Goods in transit insurance | The replacement cost |  |
| Professional indemnity insurance in respect of failure of the Contractor to use the skill and care normally used by professionals providing services | £5m in the annual aggregate | 12 years after Completion or 12 years after termination (if sooner) |

|  | similar to any services comprised in the works |
| --- | --- |
| Resolving and avoiding disputes |  |
|  | The adjudicator nominating body is the chair of the Technology and Construction Court Solicitors' Association |
|  | The tribunal is arbitration |
|  | The arbitration procedure is the London Court of International Arbitration (“LCIA”) arbitration rules current as at the date of the request for arbitration |
|  | The place where the arbitration is to be held is London |
|  | The person or organisation who will choose an arbitrator if the Parties cannot agree a choice is as stated in the arbitration procedure |
| X13: Performance Bond If Option X13 is used The amount of performance bond is Not Required X15: The Subcontractor’s design |  |
| If Option X15 is used | The period for retention following Completion of the whole of the works or earlier termination is twelve years The minimum amount of insurance cover for claims against the Subcontractor arising out of its failure to use the skill and care normally used by professionals designing works similar to the subcontractor works is, £5,000,000 in respect of each claim. |
| X16: Retention |  |
| If Option X16 is used | The retention free amount is nil |
|  | The retention percentage is 5% |
| Retention bond | The Subcontractor may not give the Client a retention bond |
| Y(UK)2 The Housing Grants, Construction and Regeneration Act 1996 |  |
| If option Y(UK) 2 is used and final date for payment is not fourteen days after the date on which payment becomes due | The period for payment is days after the date on which payment becomes due. |

Part two – data provided by the SubContractor

| 1 General |  |
| --- | --- |
| The SubContractor is Name ********************** Address for communications Address for electronic communications |  |
| The fee percentage is ******* % |  |
| The working areas are the site, site compounds, Designers offices and any other offsite fabrication or manufacturing yards |  |
| The key persons are |  |
| (1) | Name: |
|  | Job: |
|  | Responsibilities: Qualifications : |
|  | Experience: |
|  | The Following matters will be included in the Early Warning Register |

- The Subcontractor’s main responsibilities

If the Subcontractor is to provide Scope for its design

The Scope provided by the SubContractor for its design is in

Not Applicable

## Time

If a programme is to be identified in the Subcontract Data

If the Subcontractor is to decide the completion date for the whole of the subcontract works

The programme identified in the Contract Data is

The subcontract completion date for the whole of the work the subcontract works is

## 5 Payment

The bill of quantities is set out in Schedule 4

The tendered total of the Prices is *******************************

## Data for the Short Schedule of Cost Components

The people rates are

Category of person               unit                  rate

The published list of Equipment is the list of Equipment current at the Subcontract Date of the list published by the Civil Engineering Contractors Association

The percentage for adjustment for Equipment in the published list is

The rates for Defined Cost of manufacture and fabrication outside the Working Areas by the Contractor are

The rates for Defined Cost of design outside the Working Areas are

| category of person | rate |
| --- | --- |

The categories of design people whose traveling expenses to and from the Working Areas included are included in the Defined Cost are: