## Table (hidden)
Package | Site | Lift Site | No. Bags | Flying Start Date | Finish Date | Traffic Management Required
1 | Alport | Snake Summit | 3586 | 2018-10-15 | 2019-03-17 | TBC with Helicopter Company
2 | Derwent and Howden | Salter's Brook | 900 | 2018-10-04 | 2018-03-17 | No
3 | Noe Stool | Dale Head | 900 | 2018-08-13 | 2018-12-21 | No
4 | Peaknaze | Glossop Low | 3175 | 2018-10-04 | 2018-12-21 | No
5 | Stalybridge | Chew Track | 8500 | 2018-08-13 | 2019-03-17 | No
6 | Thurlstone | Snow Road | 51 | 2018-10-15 | 2019-02-15 | No
| Total |  | 17112
Summer start date
Autumn start date
Winter start date

## Matrix (hidden)
|  | Information |  | Evaluation Criteria
Package | Site | Lift Site | No. Bags | Cost Weighting % | Quality Citeria 1 Weighting % | Quality Citeria 2 Weighting % | Quality Citeria 3 Weighting %
1 | Alport | Snake Summit | 3586 | 50 | 20 | 15 | 5
2 | Derwent and Howden | Salter's Brook | 900 | 50 | 20 | 15 | 5
3 | Noe Stool | Dale Head | 900 | 50 | 20 | 15 | 5
4 | Peaknaze | Glossop Low | 3175 | 10 | 60 | 20 | 10
5 | Stalybridge | Chew Track | 8500 | 10 | 60 | 20 | 10
6 | Turlstone | Snow Road | 51 | 30 | 30 | 30 | 10
· Quality Criteria 1: XX% weighting. Capacity of the Tenderer to deliver the works in a time critical manner and provide a detailed Program of Works demonstrating how they are going to do so.
· Quality Criteria 2: XX% weighting. Method Statement documentation detailing how the objectives of the tender will be met
· Quality Criteria 3: XX% weighting. Experience in delivering upland conservation projects/similar projects

## Ovenden Summary
Site | Ovenden
Preliminary Costs | 0
Clean Up Costs | 0
Heather Brash Total | 0
Heather Bales Total | 0
Stone Dams Total | 0
Peat Dams and Reprofiling Total | 0
Fire Breaks Total | 0
Cutting Total | 0
Sphagnum Total | 0
Dwarf Shrub Seeding | 0
Grand Total | 0
Treatment Totals | Total | Unit
Heather Brash | 692 | Bags
Lime, Seed and Fertiliser | 10 | Hectares
Dwarf Shrub seeding only | 27 | Hectares
Gully Blocking - Heather Bale | 373 | Bales
Gully Blocking - Stone | 112 | Dams
Gully Blocking - Peat Dams | 99 | Dams
Hagg Reprofiling | 888 | Metres
Firebreak 1 – cut and plant sphagnum | 2 | Hectares
Firebreak 2 – bund, cut and plant sphagnum | 2 | Hectares
Heather cutting - selected blocks | Up to 5 | Hectares
Sphagnum Planting | 201 | Hectares

## Preliminary Costs
Preliminary Items - One off payment per site
Item | Total (excluding VAT)
Insurance of Works (£10,000,000 Aerial works, 5,000,000 all other)
Preparation of Pre-Tender Method Statements, Operational Risk Assessments, Safety Policy.
Preparation of Site Risk Assessments, COSHH Assessments.
Preparation of CDM Construction Phase Plan and carrying out all responsibilities as a duty holder under CDM 2015
Provision of GPS record of all completed works (to the specification as outlined in Section 1 Part B)
Any additional items required to meet contractual requirements
Grand Total | 0

## Clean Up
Site | Total Cost for removing and disposing of all waste materials from site
Ovenden

## Brash and LSF
|  | Cut and transport Heather Brash |  |  |  |  | Supply and spread Lime, seed and Fertiliser |  |  | Spreading Heather Brash |  |  | Grand Total
Site | No. Bags | Donor Site Location | Unit Cost Dumpy Bag Supply | Unit cost per bag cut and transport to spreading locations | Total Cost | Number of Days to cut and deliver all bags | Supply Lime and Fertiliser 10ha | Apply 10ha of lime, seed and fertiliser | Total Cost | Unit Cost per Bag | Total Cost | Number of days to spread all bags | Total | Total number of days
Ovenden | 692 | Ovenden |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | Additional Information – HEATHER BRASH | [7 empty] | Spreading
|  |  | Please specify method of transport to spreading locations | [7 empty] | Number of Bags spread per person per day | Bags
[11 empty] | Number of Spreaders available per day | Persons

## Heather Bales
|  | Supply and Deliver Heather Bales to lift site |  |  |  | Installing Heather Bales |  |  |  | Grand Total
Site | No. Bales | Donor Site Location | Unit cost per bale (cut and transported to dam location) | Total Cost | Number of Days to cut and deliver all bales | Provision of survey flags and marking out individual dam locations at the works site, prior to the installation | Unit Cost per Bale | Total Cost | Number of days to install all bales | Total | Total number of days
Ovenden | 373 | Ovenden |  | 0 |  |  |  | 0 |  | 0 | 0
|  | Additional Information – Heather Bales | [7 empty] | Additional Information - Heather Bales
|  | Please specify method of Delivery to dam locations | [7 empty] | Number of workers on Site each day
Number of Bales installed per person per day

## Stone Dams
|  | Supply, deliver and prepare Stone |  |  |  | Transporting Stone and Installing Dams |  |  |  | Grand Total
Site | No.Dams | Quarry Name | Unit cost per 750kg | Total Cost | Number of Days to deliver all stone | Provision of survey flags and marking out individual dam locations at the works site, prior to the installation | Unit Cost per Dam (incl. transportation and installation) | Total Cost | Number of days to install all dams | Total | Total number of days
Ovenden | 112 |  |  | 0 |  |  |  | 0 |  | 0 | 0
Additional Information –Transportation and Installation
Please specify method of transportation
Number of staff required on hill
Estimated Number of Dam Units completed each day

## Peat Dams and Reprofiling
|  |  | Tracking Machinery and Equipment to Work Sites |  |  | Peat Dams |  |  | Reprofiling |  |  | Grand Total
Site | No. Metres Reprofiling | No. Dams | Day Rate for Tracking Machinery and Equipment on and off work site | Total Cost | No. of days required to track machinery and equipment both on and off site | Unit Cost per Dam | Total Cost | Number of days to install all Dams | Unit Cost per Metre | Total Cost | Number of days to complete | Total | Total number of days
Ovenden | 888 | 99 |  | 0 | 2 |  | 0 |  |  | 0 |  | 0 | 2
|  |  | Make/model of equipment, powered machinery or fuel container | Description and details of equipment, powered machinery or fuel container
Estimate number of Dams created per day
Estimate number of metres of reprofiling per day
Number of machines on site per day

## Fire Breaks
|  | Bunding |  |  | Cutting |  |  | Sphagnum Planting |  |  | Grand Total
Site | No. Hectares | Day Rate for Bund Construction | Total Cost | Number of days machine work required | Unit Rate cutting per Ha | Total Cost | Number of days to complete | Unit Rate planting per Ha | Total Cost | Number of days to complete | Total | Total number of days
Fire break 1 | 2 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
Fire break 2 | 2 |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Make/model of equipment, powered machinery or fuel container |  | Description and details of equipment, powered machinery or fuel container
Estimate length of bunds created per day
Number of machines on site per day

## Cutting
|  |  | Cutting |  |  |  |  | Grand Total
Site | Material to cut | No. Hectares | Initial site visit with the Authority / Site Manager to discuss access and flailing areas/zones | Tracking of flailing Equipment to and from Work Site | Unit Rate cutting per Ha | Total Cost | Number of days to complete | Total | Total number of days
Ovenden | Heather | 5 |  |  |  | 0 | 0 | 0 | 0
|  |  | Make/model of equipment, powered machinery or fuel container |  | Description and details of equipment, powered machinery or fuel container
Estimate area cut per day per day
Number of machines on site per day

## Sphagnum Planting
|  | Sphagnum Planting |  |  |  |  | Grand Total
Site | No. Units - Plugs (1200 per ha) | No. Plugs planted per person per day | No. Staff on site per day | Unit Rate planting per Plug | Total Cost | Number of days to complete | Total | Total number of days
Ovenden | 240000 |  |  |  | 0 | 0 | 0 | 0

## Dwarf Shrub Seed Application
|  | Co-ordinate and Organise Delivery of Dwarf Shrub Seed | Application of Dwarf Shrub Seed |  |  | Grand Total
Site | No. Hectares | Total Cost | Unit Rate per Ha | Total Cost | Number of days to complete | Total | Total number of days
Ovenden | 27 |  |  | 0 | 0 | 0 | 0
Type of machinery and applicator to be used
Number of people required for operation
Estimate number of hectares complete per day