CONTENTS

TERMS AND CONDITIONS

Part 1 – DEFENCE CONDITIONS

- Defence Conditions (DEFCON)

Part 2 -   SPECIAL CONDITIONS

- Interpretation

- Precedence of Documents

- Contractual Matters

- Entire Agreement

- Assignment

- Contractor Warranties and Representations

- Contractor Undertakings

- Contractor’s Obligations

- Contract Period

- Price

- Payment

- Options

- Integrated Project Management Plan (IPMP)

- Risk

- Quality Assurance

- Quality – General Requirements

- Quality Management Plan

- Certificate of Conformity

- Quality Assurance Representative (QAR)

- Ships Safety and Environmental Protection

- NOT USED

- Continuous Improvement

- Authority’s Authorised Officer

- Government Furnished Equipment (GFE)

- Receipt of GFE

- Custody of GFE

- Government Furnished Information (GFI)

- Guarantee

- Sub-Contracts

- Matters to be Included in Sub-Contracts

- NOT USED

- Care and Protection of Police Patrol Craft (s)

- Continuing Obligations

- Debt Factoring

- Health and Safety

- Attendance by Makers’ Representatives and Certification Authorities

- Certification and Classification

- Changes in Certification and Classification

- Changes to the Contract

- Commonality of Equipment and Systems

- Replacement of Obsolescent Parts and Equipment

- Liquidated Damages

- Permissible Delays

- Termination for a Permissible Delay

- Take Over/Tow-Out Option

- Financial Consequences of Termination

- Major Incident Inquiries

- Jigs and Tools

- Inspection, Tests and Trials

- Acceptance

- Import and Export of Boats and/or Associated Equipment or Spares

- NOT USED

- Sustainable Procurement

- Compatibility with Authority Systems

- NOT USED

- PR and Publicity

- Exit

- Official and Official Sensitive Security Condition for UK contracts

- Background Information

- Technical Publications

- Gainshare

- Progress Meetings

- Earned Value Management

Schedules to Terms and Conditions

Schedule 1 – Schedule of Requirements

Schedule 2 – Statement of Technical Requirements (SoTR)

Schedule 3 – Definitions and Interpretations

Schedule 4 – Pricing and Rates

Schedule 5 – Addresses and Other Information (DEFFORM 111)

Schedule 6 – Integrated Project Management Plan (IPMP)

Schedule 7 – NOT USED

Schedule 8 – NOT USED

Schedule 9 – Corrective Action Plan

Schedule 10a – Certificate of Acceptance

Schedule 10b – Boats Sea Trial Form

Schedule 10c – Care and Custody Certificate

Schedule 11 – Contract Data Requirements List (DEFFORM 315)

Schedule 12 – NOT USED

Schedule 13 – Government Furnished Equipment (GFE)

Schedule 14 – NOT USED

Schedule 15 – Contract Change Proposal

Schedule 16 – NOT USED

Schedule 17 – Milestone Payment Plan

Schedule 18 – Bidders Commercially Sensitive Information (DEFFORM 539A)

Schedule 19 – Design Rights and Patents (DEFFORM 177)

Schedule 20 – Gainshare Agreement

Schedule 21 – Makers List

Schedule 22 – Sustainable Procurement Charter

Schedule 23 – NOT USED

Schedule 24 – Contractor Master Schedule

Schedule 24a – Project Schedule

Schedule 25 – NOT USED

Schedule 26 – Protection of Personal Data – DEFCON 532B

TERMS AND CONDITIONS

PART 1 – DEFENCE CONDITIONS

- Defence Conditions (DEFCON)

  - The following DEFCONs shall apply to the Contract:

| - No | - Edition | - Title |
| --- | --- | --- |
| - 5J | - (Edn. 18/11/16) | - Unique Identifiers |
| - 14 | - (Edn. 11/05) | - Inventions and Designs Crown Rights and Ownership of Patents and Registered Designs |
| - 16 | - (Edn. 10/04) | - Repair and Maintenance Information – See CDR No 001 attached at Schedule 11 (Contract Data Requirements List – DEFFORM 315) |
| - 19 | - (Edn. 01/76) | - Free User, Maintenance and Supply of Drawings |
| - 21 | - (Edn. 10/04) | - Retention of Records - See CDR No 001 attached at Schedule 11 (Contract Data Requirements List – DEFFORM 315) |
| - 23 | - (Edn. 08/09) | - Special Jigs, Tooling and Test Equipment |
| - 68 | - (Edn. 02/19) | Supply of Data for Hazardous Articles, Materials and Substances |
| - 76 | - (Edn. 12/06) | - Contractor's Personnel at Government Establishments |
| - 82 | - (Edn. 11/16) | - Special Procedures for Initial Spares |
| - 117 | - (Edn. 10/13) | - Supply of Documentation for NATO Codification and Defence Inventory Introduction |
| - 126 | - (Edn. 11/06) | - International Collaboration |
| - 127 | - (Edn.12/14) | - Price Fixing Condition for Contracts of Lesser Value (this shall apply to amendments to contract and Ad hoc Tasks valued at less than £250,000) |
| - 129 | - (Edn. 04/19) | - Packaging (For Articles other than munitions) |
| - 129J | - (Edn. 18/11/16) | - The Use Of The Electronic Business Delivery Form |
| - 501 | - (Edn. 11/17) | - Definitions and Interpretations |
| - 502 | - (Edn. 05/17) | - Specification Changes |
| - 503 | - (Edn. 12/14) | - Formal Amendments to Contract |
| - 507 | - (Edn. 10/18) | - Delivery |
| - 513 | - (Edn. 11/16) | - Value Added Tax |
| - 514 | - (Edn. 08/15) | - Material Breach |
| - 515 | - (Edn. 02/17) | - Bankruptcy and Insolvency |
| - 516 | - (Edn. 04/12) | - Equality |
| - 518 | - (Edn. 02/17) | - Transfer |
| - 520 | - (Edn. 05/18) | - Corrupt Gifts and Payments of Commission |
| - 522 | - (Edn. 11/17) | - Payment and Recovery of Sums Due |
| - 524 | - (Edn. 10/98) | - Rejection |
| - 525 | - (Edn. 10/98) | - Acceptance |
| - 526 | - (Edn. 08/02) | - Notices |
| - 527 | - (Edn. 09/97) | - Waiver |
| - 528 | - (Edn. 07/17) | - Overseas Expenditure, Import and Export Licences |
| - 529 | - (Edn. 09/97) | - Law (English) |
| - 530 | - (Edn. 12/14) | - Dispute Resolution (English Law) (Any dispute concerning a Police Patrol Craft’s compliance or non-compliance with the rules, regulations and requirements of the Classification Society or other Regulatory Authorities shall be referred to the appropriate Classification Society or Regulatory Authority for a decision which shall be final and binding upon the Parties. All other disputes shall be dealt with in accordance with DEFCON 530) |
| - 531 | - (Edn. 11/14) | - Disclosure of Information |
| - 532B | - (Edn. 05/18) | - Protection Of Personal Data |
| - 534 | - (Edn. 06/17) | - Subcontracting and Prompt Payment |
| - 537 | - (Edn. 06/02) | - Rights of Third Parties |
| - 538 | - (Edn. 06/02) | - Severability |
| - 539 | - (Edn. 08/13) | - Transparency (“Contractor Commercially Sensitive Information” shall mean the information listed in Schedule 18 (Commercial Sensitive Information)) |
| - 550 | - (Edn. 02/14) | - Child Labour and Employment Law |
| - 566 | - (Edn. 12/18) | - Change of Control of Contractor |
| - 601 | (Edn. 04/14) | - Redundant Materiel (shall apply in respect of DEFCON 611 (Edn. 02/16), Issued Property and to the extent that the redundant materiel derives from the property owned by the Authority and issued to the Contractor) |
| - 602A | (Edn. 12/17) | Deliverable Quality Plan |
| - 604 | - (Edn. 06/14) | - Progress Reports (for the purposes of the Contract, the frequency of reports shall be as detailed in the Annex B to the Integrated Project Management Plan (Schedule 6). |
| - 606 | (Edn. 06/14) | Change and Configuration Control Procedure |
| - 607 | (Edn. 05/08) | Radio Transmissions |
| - 608 | - (Edn. 10/14) | - Access and Facilities to be Provided by the Contractor (for the purposes of this Contract the Contractor shall ensure that any Offices, Lay Apart Stores or facilities provided by the Contractor to the Authority are fitted with security locks on all doors and any windows that can be opened. The Contractor shall ensure access to keys is limited to authorised personnel only, in agreement with the Authority). |
| - 609 | - (Edn. 08/18) | Contractor's Records |
| - 611 | - (Edn. 02/16) | - Issued Property |
| - 612 | - (Edn. 10/98) | - Loss of or Damage to the Articles |
| - 619A | - (Edn. 09/97) | - Customs Duty Drawback |
| - 621A | - (Edn. 06/97) | - Transport (if Authority is responsible for transport). |
| - 621B | - (Edn. 10/04) | - Transport (if the Contractor is responsible for transport). For the purposes of this Contract the Contractor shall comply with Department for Transport Code of Practice, Safety Loads on Vehicles and BS EN 12195 (Load restraining on vehicles – safety). |
| - 624 | (Edn. 11/13) | Use of Asbestos in Arms, Munitions or War Materials |
| - 627 | (Edn. 12/10) | Quality Assurance - Requirement for a Certificate of Conformity |
| - 632 | (Edn. 08/12) | Third Party Intellectual Property – Rights and Restrictions |
| - 637 | (Edn. 05/17) | Defect Investigation and Liability |
| - 642 | - (Edn. 06/14) | Progress Meetings |
| - 643 | - (Edn. 12/14) | - Price Fixing (Non-qualifying contracts) (this shall apply to amendments to contract and Ad hoc Tasks valued at more than £250,000). The period in Clause 4 of this DEFCON shall be 5 years. |
| - 644 | (Edn. 07/18) | Marking of Articles |
| - 646 | - (Edn. 10/98) | - Law and Jurisdiction (Foreign Suppliers) |
| - 647 | - (Edn. 04/19) | - Financial Management Information - Further to DEFCON 647 the frequency of reports shall be monthly. |
| - 649 | - (Edn. 12/16) | Vesting |
| - 656B | - (Edn. 08/16) | Termination for Convenience |
| - 658 | - (Edn. 10/17) | Cyber Further to DEFCON 658 the Cyber Risk Level of the Contract is LOW, as defined in Def Stan 05-138. |
| - 670 | - (Edn. 02/17) | - Tax Compliance |
| - 675 | - (Edn. 09/19) | - Advertising Subcontracts |
| - 678 | - (Edn. 09/19) | - SME Spend Data Collection |
| - 681 | - (Edn. 06/02) | - Decoupling Clause – Subcontracting with the Crown |
| - 691 | - (Edn. 03/15) | - Timber and Wood-Containing Products Supplied under the Contract |
| - 694 | - (Edn. 07/18) | - Accounting For Property of the Authority |
| - 703 | (Edn. 08/13) | - Intellectual Property Rights - Vesting in the Authority (This condition will only apply to tasks that are fully funded by the Authority). |

PART 2 – SPECIAL CONDITIONS

- Interpretation

  - In addition to the provisions of DEFCON 501 (Interpretation), the words and phrases set out in Schedule 3 (Definitions & Interpretations) shall have the meaning ascribed to them in those Schedules unless otherwise provided for in this Contract.

  - In this Contract, except where the context otherwise requires:

    - a reference in this Contract to any Clause, Paragraph, Schedule or Annex is, except where expressly stated to the contrary, a reference to such Clause, Paragraph, Schedule or Annex of this Contract;

    - any reference in this Contract to a range of Clauses, Paragraphs, Schedules or Annexes shall, except where expressly stated to the contrary, be inclusive of those Clauses, Paragraphs, Schedules or Annexes used to define the range;

    - any reference to this Contract or to any other document shall include any permitted variation, amendment or supplement to such document;

    - references to any documents being "in the agreed form" means such documents have been initialled by or on behalf of each of the parties for the purpose of identification;

    - reference to a person includes firms, partnerships and corporations and their successors and permitted assignees or transferees;

    - all covenants, agreements, undertakings, indemnities, representations and warranties by more than one person are entered into, given or made by such persons jointly and severally;

    - references to a public organisation (other than the Authority) shall be deemed to include a reference to any successor to such public organisation or any organisation or entity which has taken over either or both the functions and responsibilities of such public organisation. References to other persons (other than the Authority) shall include their successors and assignees;

    - reference to the phrase "agreed or determined" means agreed between the parties or determined pursuant to the resolution of any dispute under DEFCON 530 (Dispute Resolution (English Law));

    - any reference to any ISN website link is provided for Information purposes only and such link does not form part of the Contract.

  - The words and phrases “other”, “including” and “in particular” shall not limit the generality of any preceding words or be construed as being limited to the same class as any preceding words where a wider construction is possible.

  - Unless otherwise stated, the provisions of this Contract shall be read and construed as if separate and independent contracts had been entered into, in respect of each Police Patrol Craft and not as one contract for all Police Patrol Craft.

- Precedence of Documents

  - The documents constituting this Contract are intended to be consistent. In the event of any ambiguity, conflict or inconsistency between the Contract and any document referred to or cross-referenced in the Contract, or between documents referred to or cross-referenced in the Contract, the conflict shall be resolved according to the following descending order of priority:

    - Clauses 1 to 64 of this Contract and Schedule 3 (Definitions and Interpretations);

    - Schedule 2 (Statement of Technical Requirements) of this Contract;

    - Other Schedules;

    - any other document of this Contract;

    - any other document agreed between the Parties after the Commencement Date.

- Contractual Matters

  - All queries and correspondence relating to or affecting the Contract shall be addressed to the Authority’s Commercial Officer as specified in Box 1 to Schedule 5 (Appendix - Addresses and Other Information).

- Entire Agreement

  - This Contract constitutes the entire agreement between the Parties relating to the subject matter of this Contract. This Contract supersedes all prior negotiations, representations and undertakings, whether written or oral, except that this Clause shall not exclude liability in respect of any fraudulent misrepresentation.

- Assignment

  - Neither Party to the Contract shall give, bargain, sell, assign, or otherwise dispose of the Contract or any part thereof, or the benefit or advantage of the Contract or any part thereof, without the previous consent in writing of the other Party.

- Contractor Warranties and Representations

Contractor Warranties

  - The Contractor warrants and represents to the Authority that:

    - it is properly constituted and incorporated and has the corporate power to own its assets and to carry on its business as it is now being conducted;

    - it has the power to enter into and to exercise its rights and perform its obligations under this Contract;

    - all action necessary on the part of the Contractor to authorise the execution of and the performance of its obligations under this Contract has been taken or, in the case of any such document executed after the date of this Contract, shall be taken before such execution;

    - the obligations expressed to be assumed by the Contractor under this Contract are, or in the case of any such document executed after the date of this Contract shall be, legal, valid, binding and enforceable to the extent permitted by law and this Contract is or shall be in the proper form for enforcement in England;

    - the execution, delivery and performance by it of this Contract does not contravene any provision of:

      - any existing Legislation binding on the Contractor, including Legislation which has been enacted but is not yet in force;

      - the memorandum and articles of association of the Contractor;

      - any order or decree of any court or arbitrator which is binding on the Contractor;

      - any obligation which is binding upon the Contractor or upon any of its assets or revenues;

      - no claim is presently being assessed and no litigation, arbitration or administrative proceedings are presently in progress or, to the best of the knowledge of the Contractor (having made all due enquiry), pending or threatened against it or any of its assets which shall or might have a material adverse effect on the ability of the Contractor to perform its obligations under this Contract;

      - it is not the subject of any other obligation, compliance with which shall or is likely to have a material adverse effect on the ability of the Contractor to perform its obligations under this Contract;

      - no proceedings or other steps have been taken and not discharged (nor, to the best of the knowledge of the Contractor, having made all due enquiry, threatened) for its winding-up or dissolution or for the appointment of a receiver, administrative receiver, administrator, liquidator, trustee or similar officer in relation to any of its assets or revenues (or any equivalent procedure);

      - it shall not, and in entering into this Contract it has not, committed any Prohibited Act; and

      - there is not and nor has there been any infringement or alleged infringement of any third party's IPR in connection with this Contract (excluding any Government Furnished Information).

- Contractor Undertakings

  - The Contractor undertakes that for so long as this Contract remains in full force it shall:

    - provide notice of any Dispute Proceedings to the Authority that are likely to affect the Contractor’s ability to perform its obligations under the Contract or has the potential to cause reputational damage to the Authority, unless such notice is precluded by the rules of the court, arbitrator, administrator, adjudicator, mediator or any other relevant authority with jurisdiction over the Dispute Proceedings:

      - within twenty (20) Business Days of the Contractor becoming aware that Dispute Proceedings may be threatened or pending; and

      - immediately after the commencement of Dispute Proceedings;

      - not undertake the performance of its obligations under this Contract otherwise than:

        - at the Contractor’s Premises; and

        - through itself or a Sub-Contractor.

Status of Contractor Warranties and Undertakings

  - All warranties, representations, undertakings, indemnities and other obligations made, given or undertaken by the Contractor in this Contract are cumulative and none shall be given a limited construction by reference to any other.

- Contractor’s Obligations

  - The Contractor shall provide the Contractor Deliverables to the Authority, all in accordance with the Contract and Good Industry Practice and shall, inter alia, offer the Police Patrol Craft to the Authority fully in compliance with the Contract at the Contractor’s premises on the Required Delivery Date.

  - Without prejudice to the overriding obligation contained in Clause 9.1, the Contractor's responsibilities shall, unless provided otherwise in the terms of this Contract, include:

    - design, construction, launch, equipping, completing and delivering of the Police Patrol Craft to the Authority;

    - satisfactory completion of all Tests, Trials and Inspections required to prove the quality of the Contractor Deliverables in accordance with the Integrated Test and Evaluation Plan at Annex K of Schedule 6 (Integrated Project Management Plan);

    - providing support during the Authority’s Acceptance Trials up to Acceptance off Contract in accordance with the Contract;

    - the provision and proper fitting in place of all material, equipment, fittings and deliverables necessary for the completion of the Police Patrol Craft as required by the Contract unless otherwise specified;

    - the provision of all labour, plant, machinery, freight and port services necessary for the proper performance of the Contract;

    - the provision of all necessary services, facilities for and assistance to the Authority’s Representatives and the Authority’s Contractors in accordance with the Contract;

    - the provision of all necessary access, facilities and drawings for any classification, certification, surveys or trials to the Classification Society or Regulatory Authorities in accordance with the Contract;

    - examination, testing, and if necessary retesting of Lifting Equipment; ensuring that, at Acceptance Off Contract of each Police Patrol Craft, there remains at least 80% of the total period between tests or surveys being completed and the next test or survey falling due;

    - provision of all fuels, lubricating oils, greases and hydraulic fluids required for setting to work and trials of the Police Patrol Craft up to Acceptance Off Contract;

    - compliance with local Statutory Duties And Obligations up to Acceptance Off Contract and shall ensure that the Contractor Deliverables and any activities of the Contractor within the UK shall comply with UK Statutory Duties And Obligations;

    - supply of documentation and data for NATO Codification purposes in accordance with DEFCON 117 (Supply of Information for NATO Codification and Defence Inventory Introduction);

    - not, by any act or omission at any time, placing the Authority in breach of its obligations as an employer;

    - the Police Patrol Craft and its equipment being designed and built in metric units.

    - meeting all the requirements set out in Schedule 2 (Statement of Technical Requirements)

  - The Contractor shall not deviate from the Contract nor introduce any contrivance unusual in the kind of work covered by the Contract save as provided for in Clause 40 (Changes to the Contract)

  - Save in respect of the Contractor’s Sea Trials or as expressly agreed in writing by the Authority, all work involved in providing the Contractor Deliverables shall be carried out at the Contractor’s Premises.

  - The Contractor is responsible for producing a design of Police Patrol Craft that is safe to operate and fit for purpose by demonstrating to the Authority that the design developed by the Contractor meets the requirements of the Contract.

  - No advice, comment or information proffered, given or omitted by, or on behalf of, the Authority on or in relation to the Contractor's work in accordance with the Contract shall, in any way, extinguish, diminish or reduce the Contractor's obligations and responsibilities under the Contract to provide the Contractor Deliverables. Neither shall the activities of the Authority or its representatives including that of scrutiny of the design produced by the Contractor under the Contract derogate from the Contractor's obligations and responsibilities under the Contract.

  - The Contractor acknowledges that any risk assessment, questionnaire or risk register which has, or may be undertaken or maintained in connection with this Contract is done so in a management capacity only. Such risk assessment activity does not affect the legal relationship between the Parties or in any way limit or exclude the Contractor’s obligations under this Contract.

- Contract Period

  - This Contract and the rights and obligations of the Parties to this Contract shall take effect on the date of this Contract and, except as set out in Clause 34 (Continuing Obligations), shall terminate on the earlier of:

    - the date on which the Contractor has discharged all of its obligations in respect of the Contractor Deliverables; or

    - the Termination Date.

  - Each Year will run for the following Financial Years (FY):

    - Year 1 (FY 20/21) – Contract Commencement Date to 31 March 2021

    - Year 2 (FY 21/22) – 01 April 2021 to 31 March 2022

    - Year 3 (FY 22/23) – 01 April 2022 to 31 March 2023

    - Year 4 (FY 23/24) – 01 April 2023 to 31 March 2024

    - Year 5 (FY 24/25) – 01 April 2024 to 31 March 2025

    - Year 6 (FY 25/26) – 01 April 2025 to 31 March 2026

    - Option Year 7 (FY 26/27) – 01 April 2026 to 31 March 2027

- Price

  - The Contract contains a mix of Firm and Fixed prices as stated in Schedule 4 (Pricing and Rates). All prices quoted are exclusive of UK VAT in accordance with DEFCON 513 (Value Added Tax).

  - Prices recorded in Schedule 4 (Pricing and Rates) as FIRM are not subject to variation in any respect (including on account of fluctuations in wages, and/or cost of materials, interest rates or currency exchange rates)) save as provided for in Clause 40 (Changes to the Contract).

  - Prices recorded in Schedule 4 (Pricing and Rates) as FIXED are at Financial Year (FY) 21/22 price levels. The prices do not include provision beyond this date for increases or decreases in the market price of the Articles being purchased. For the purposes of agreeing Firm Prices for FY 24/25, 25/26 and 26/27 of the Contract the following price formula shall apply:

V = P (a+b(Oi/O0)) - P

Where:

V represents the variation of price

P represents the FIRM price for FY 21/22 as stated in Schedule 4

O represents the index K8ZU

O0 represents the monthly average of index K8ZU OUTPUT for the base period [date 12 months before contract start date] to [contract start date]

Oi represents the monthly average of index K8ZU OUTPUT across the financial year prior to the period for which the variation is being added

a represents the Non Variable Element (NVE) which shall be 10%

b represents the Variable Element which shall be 90%

a+b=1

  - For the purposes of this Contract a variation modifier can be derived by completing the operation Oi/OO. This variation modifier shall then be applied to each Fixed Price in Schedule 4 (Pricing and Rates) hereto to calculate prices for FY 24/25, 25/26 and 26/27 of the Contract.

  - The Index referred to in Clause 11.3 above shall be taken from the following Table K8ZU.

  - Indices published with a ‘B’ or ‘F’ marker, or a suppressed value, in the last 3 (three) years are not valid for Variation of Price clauses and shall not be used. Where the price index has an ‘F’ marker or suppression applied to it during the term of the Contract, the Authority and the Contractor shall agree an appropriate replacement index or indices. The replacement index or indices shall cover, to the maximum extent possible, the same economic activities as the original index or indices.

  - In the event that any material changes are made to the indices (e.g. a revised statistical base date) during the period of the contract and before final adjustment of the final contract price, then the re-basing methodology outlined by the Office for National Statistics (ONS, the series providers) to match the original index to the new series shall be applied.

  - In the event the agreed index or indices cease to be published (e.g. because of a change in the Standard Industrial Classification) the Authority and the Contractor shall agree an appropriate replacement index or indices, which shall cover to the maximum extent possible the same economic activities as the original index or indices. The methodology outlined by the Office for National Statistics used for rebasing indices shall then be applied.

  - Notwithstanding the above, any extant index / indices agreed in the Contract shall continue to be used as long as it is / they are available and subject to ONS revisions policy. Payments calculated using the extant index / indices during its / their currency shall not be amended retrospectively as a result of any change to the index or indices.

  - The Contractor shall notify the Authority of any significant changes in the purchasing / manufacturing plan on the basis of which these provisions were drawn up and agreed, or of any other factor having a material bearing on the operation of these provisions such as to cause a significant divergence from their intended purpose, in order that both parties may consider whether any change in this provision would be appropriate. In the event that the parties are unable to reach agreement the provisions of DEFCON 530 (Dispute Resolution) shall apply.

  - Prices shall be adjusted taking into account the effect of the above formula as soon as possible after publication of the relevant indices or at a later date if so agreed between the Authority and the Contractor. Where an index value is subsequently amended, the Authority and the Contractor shall agree a fair and reasonable adjustment to the price, as necessary.

- Payment

  - Payments shall be in Pounds Sterling.

  - The Contractor shall submit their claim for payment, in accordance with DEFCON 522 (Payment and Recovery of Sums Due).

Items 1 and 2 of Schedule 1 (Schedule of Requirements)

  - The Authority shall, subject to the following provisions of this Clause, make to the Contractor advances against the price(s) Items 1 and 2, Schedule 1 (Schedule of Requirements) to the Contract in accordance with the Stage Payment Scheme set out in Schedule 17 (Milestone Payment Plan) to the Contract.

  - The Contractor shall be entitled to interim payments, in accordance with Schedule 17 (Milestone Payment Plan), to be claimed in accordance with this Clause 12 for each stage under the Stage Payment Scheme, when:

12.4.1	the Contractor has completed all work comprised in the stage for which the interim payment is sought in accordance with the Contract; and

    - all previous stages have been completed; and

    - the Contractor shall have complied with all its contractual obligations which enable the Authority to monitor the Contractor’s contractual performance.

  - Notwithstanding Clause 12.4 above, the Authority shall not be obliged to make an interim payment to the Contractor if it has reasonable cause to believe that the Contractor will be unlikely to render complete performance of its obligations in respect of item 1 and 2 of Schedule 1 (Schedule of Requirements) to the Contract.

  - Where the Authority intends to rely on Clause 12.5 above as the basis for rejecting any claim for an interim payment which the Contractor may make, the Authority shall give to the Contractor notice in writing of its intention together with the Authority's reasons for the rejection.

  - The Authority shall without prejudice to any other right / remedy of either party be entitled to recover in full all interim payments made under the Contract where:

    - the Contract, or the part of the Contract under which Item 1 and 2 of Schedule 1 (Schedule of Requirements) are to be provided, is terminated otherwise than in accordance with DEFCON 656A (Termination for Convenience) , or expires by reason of passing of time; and/or

    - the Contractor has failed to complete performance of Item 1 and 2 of Schedule 1 (Schedule of Requirements) as specified in Schedule 2 (Statement of Technical Requirements).

  - In the event of repayment to the Authority under the provisions of Clause 12.7 above then all that which vested in the Authority under the provisions of DEFCON 649 (Vesting) and which related to Item 1 and 2 of Schedule 1 (Schedule of Requirements) to the Contract shall re-vest in and become the absolute property of the Contractor.

  - Payment of an interim payment by the Authority under this Clause 12 shall not, unless expressly stated to do so, constitute:

    - acceptance by the Authority of any contractual deliverable;

    - a representation by the Authority that the Contractor has complied with any Contractual obligations; or

    - a waiver of the Authority’s right to subsequently claim that the conditions for payment of that interim payment were not satisfied.

Items 3, 4 and 5 Item 6 of Schedule 1 (Schedule of Requirements)

  - The Contractor shall submit their claim for payment on completion of all work under this Statement of Technical Requirement Line Item, in accordance with DEFCON 522 (Payment and Recovery of Sums Due).

Item 6 of Schedule 1 (Schedule of Requirements)

  - The Contractor shall submit their claim for payment quarterly in arrears in accordance with DEFCON 522 (Payment and Recovery of Sums Due).

- Options

  - The Option prices detailed in Table 3 of Schedule 4 (Pricing and Rates) to this Contract are a mixture of Firm priced and Fixed price which is subject to adjustment in accordance with Clause 11 (Price).

  - In addition to the quantity detailed at Item 1 of Schedule 1 (Schedule of Requirements) to this Contract, the Contractor hereby grants to the Authority the following irrevocable option to purchase the quantities of Crafts in accordance with the terms and conditions set out in this Contract or any such subsequent contract or contracts where such options are taken up, it being agreed that that Authority has no obligation to exercise such options.

    - Option 1: Item 2 of Schedule 1 (Schedule of Requirements), a quantity of one  (1) Police Patrol Craft in addition to the fifteen (15) Police Patrol Craft already ordered under Item 1 of Schedule 1 (Schedule of Requirements) to this Contract and at the Fixed prices and in accordance with the delivery schedule set out at Table 3 of Schedule 4 (Pricing and Rates) to this Contract, provided that the Authority exercises each option by no later than 01 April 2024.

    - Option 2: Item 2 of Schedule 1 (Schedule of Requirements), a quantity of two (2) Police Patrol Craft in addition to the fifteen (15) Police Patrol Craft already ordered under Item 1 of Schedule 1 (Schedule of Requirements) to this Contract and at the Fixed prices and in accordance with the delivery schedule set out at Table 3 of Schedule 4 (Pricing and Rates) to this Contract, provided that the Authority exercises each option by no later than 01 April 2024.

    - Option 3: Item 2 of Schedule 1 (Schedule of Requirements), a quantity of two (2) Police Patrol Craft in addition to the fifteen (15) Police Patrol Craft already ordered under Item 1 of Schedule 1 (Schedule of Requirements) to this Contract and at the Fixed prices and in accordance with the delivery schedule set out at Table 3 of Schedule 4 (Pricing and Rates) to this Contract, provided that the Authority exercises each option by no later than 01 April 2024.

  - The Authority shall have the right to exercise this option by the specified dates or within such further period as corresponds to the aggregate of any such period(s):

    - of delay in the delivery programme whether constituting any breach of the Contract or resulting from any force majeure event within Clause 44 (Permissible Delays); or

    - for the duration of which the Authority is prevented from exercising any such option by reason of any other breach of the Contract by the Contractor.

  - The Authority shall not be obliged to exercise these options.

  - For the avoidance of doubt, where the Authority exercises an option, the prices as set out in the relevant section of Schedule 4 (Prices and Rates) shall apply.

- Integrated Project Management Plan (IPMP)

  - The Contractor shall demonstrate good project management practice in undertaking all activities under the Contract. The Authority and the Contractor shall adopt an open and honest approach at all times and ensure that potential risks to performance, cost and time are exposed at the earliest opportunity. The Contractor shall wherever practicable minimise the detrimental impact on the Authority so as to reduce costs and time and increase performance and shall identify any potential opportunities to the Authority.

  - The Integrated Project Management Plan (IPMP) (Schedule 6 to the Contract) shall define how the Contract activities shall be managed, outlining the processes, procedures and techniques to be used with details of how all activities, plans and programmes will be established, monitored, changed, controlled, integrated and communicated with the Authority.

  - The IPMP shall adopt a consistent and coherent approach to project management and establish procedures and reporting mechanisms. Implementation of the IPMP will provide the Authority with confidence in the Contractor’s ability to deliver to time, cost and performance in accordance with the Contract and provide early visibility of potential issues so that mitigating action can be taken.

  - No later than three (3) months from the date of this Contract, the Contractor shall update and finalise the draft Integrated Project Management Plan (IPMP) (Schedule 6 to the Contract) together with the associated Annexes and issue to the Authority to review. The updated IPMP shall address the scope of work as set out in the Contract.

  - The Authority will review the updated IPMP and associated Annexes and provide proposed amendments to the Contractor within twenty (20) Business Days of receipt. Any such proposals shall be subject to agreement of the Contractor who shall incorporate all reasonable proposals from the Authority in to the IPMP within twenty (20) Business Days of any discussion held between the parties as a result of the Authority’s comments. Within ten (10) Business Days thereafter the Contractor shall submit the IPMP and associated annexes at Revision 1 status to the Authority as Schedule 6 (Integrated Project Management Plan).

  - The IPMP shall cross reference to the Contract Clauses, the Statement of Technical Requirements (Schedule 2) and all associated Annexes within the IPMP as applicable.

  - The Contractor shall be responsible for the maintenance and updating of the IPMP throughout the life of the Contract.

  - The IPMP shall comprise of the following Annexes:

| IPMP Annex | Title |
| --- | --- |
| Introduction | Executive Summary |
| Annex A | Project Monitoring and Control Plan (Incl a Contract Set Up Plan) |
| Annex B | Stakeholder Management, Communication and Reporting Plan |
| Annex C | Earned Value Management Plan |
| Annex D | Risk Management Plan |
| Annex E | Quality Management Plan |
| Annex F | Safety and Environmental Management Plan |
| Annex G | Exit Strategy and Transition Plan |
| Annex H | Security Plan |
| Annex I | Test, Evaluation & Acceptance Plan |
| Annex J | Through Life Capability Maintainment Strategy |

- Risk

  - The Contractor shall provide and maintain a Risk Management Plan which shall as detailed at Annex D of Schedule 6 (Integrated Project Management Plan):

  - The risk management process shall be underpinned by the production and maintenance of a formal Joint Risk Register, incorporating both the Contractor’s and the Authority’s identified risks. The register shall be managed by the Contractor and presented to the Authority within three (3) months of the award of the Contract. Each risk in the register shall have a nominated risk owner who shall be responsible for the day-to-day management of the risk including the recording of mitigation actions, current risk parameters and status.

  - The Contractor acknowledges that any risk assessment including, without limitation, the identification of (or failure to identify) particular risks and their impact or risk reduction measures, contingency plans and remedial actions shall not in any way limit or exclude the Contractor's obligations under this Contract and shall be entirely without prejudice to the Authority's rights, privileges and powers under this Contract. Where the Contractor identifies and notifies risks during the risk assessment process such risks shall remain the risks of the Contractor and are not assumed by the Authority.

- Quality Assurance

  - The Contractor shall ensure that the quality of the Contractor Deliverables including those of Sub-Contractors conforms to the requirements of the Contract and the Specifications.

  - The Authority may reject any Contractor Deliverable that does not conform to the requirements of the Contract.

  - Non-Conformities shall be dealt with in accordance with Clause 40 (Changes to Contract).

  - The Contractor shall retain the quality control / inspection records for a period of ten (10) years after Acceptance Off Contract of each Police Patrol Craft, and shall make them accessible to the Authority on request.

- Quality - General Requirements

  - The Contractor shall be responsible for ensuring that the quality of the work performed, and of the articles and materials supplied or repaired by him and all his Sub-Contractors, conforms to the requirements of the Contract.

  - The Contractor shall maintain a quality management system and continually improve its effectiveness in accordance with the terms and conditions of this Contract, ISO 9001-2015, the AQAP 2100 series and Defence Standards, as detailed below:-

    - AQAP 2110 Edition D Ver 1 (NATO Quality Assurance Requirements for Design, Development & Production)

    - AQAP 2105 Edn 2 (NATO QA Requirements for Deliverable Quality Plans)

    - DEFSTAN 05-57 Issue 7 (Configuration Management of Defence Materiel)

    - DEFSTAN 05-61 Part 1 Issue 6 (Concessions)

    - DEFSTAN 05-61 Part 4 Issue 3 and Amendment 1 28/01/11 (Contractor Working Parties)

    - DEFSTAN 05-135 Issue 1 Avoidance of Counterfeit Material.

  - For the AQAP series, the following interpretations apply:

    - Where the Contract refers to the “Authority”, the AQAP series refers to the “Acquirer”

    - Where the Contract refers to the “Contractor”, the AQAP series refers to the “Supplier”

    - Where the Contract refers to the “Sub-Contractor”, the AQAP series refers to the “Sub-supplier”.

- Quality Management Plan

  - The Contractor shall implement and maintain for the duration of the Contract a Contract specific deliverable Quality Management Plan (QMP) (Annex E to Schedule 6 (Integrated Project Management Plan) compiled to meet the requirements of AQAP 2105.

  - The QMP shall address two complimentary roles;

    - Describe and document the ‘contract specific’ Quality Management System (QMS) requirements necessary to satisfy the contract requirements.

    - Describe and document the planning for product realisation in terms of the quality requirements of the product, including needed resources, required control activities (verification, validation, monitoring, inspection, testing and acceptance criteria).

  - Once the QMP has been agreed in accordance with Clause 14 (Integrated Project Management Plan), draft updates/amendments to the QMP shall be submitted to the Authority monthly except where the plan remains unchanged. All updates will be agreed with the Authority and issued within twenty (20) Business Days of submission to the Authority. The agreed Contract Quality Management Plan may be subject to QAR surveillance activity to ensure compliance with agreed contract requirements.

  - The Contractor shall throughout the duration of the Contract advise the Authority of any impact on product quality or on the process and controls detailed in the deliverable QMP resulting from revisions or changes to their QMS.

- Certificates of Conformity (CoC)

  - A Certificate of Conformity (CoC) meeting the requirements of DEFCON 627 (Quality Assurance - Requirement for a Certificate of Conformity), and in accordance with the Quality Management Plan detailed in Annex D to Schedule 6 (Integrated Project Management Plan), is to be provided on Acceptance Off Contract of each Police Patrol Craft.

- Quality Assurance Representative (QAR)

  - When called up in standards invoked by this Contract, Quality Assurance Representative (QAR) is to be read as Government Quality Assurance Representative (GQAR and/or Acquirer).

- Boat Safety and Environmental Protection

  - The Authority has dual responsibilities in relation to safety and environmental protection:

    - as the Safety Regulator (naval ships being excepted by IMO); and

    - as the owner of the Police Patrol Craft after Acceptance Off Contract.

  - The Contractor shall ensure that:

    - the Police Patrol Craft is safe to operate and maintain;

    - the requirements of Annex F of Schedule 6 (Integrated Project Management Plan) and Schedule 2 (Statement of Technical Requirements) are met;

    - in performing the Contract comply with all his Statutory Duties And Obligations relating to safety and environmental protection.

  - If, at any time after the Commencement Date, it becomes apparent to the Contractor that anything contained in Schedule 2 (Statement of Technical Requirements) renders the Police Patrol Craft non-compliant with, or the Contractor in breach of, any local or UK Statutory Duty or Obligation relating to safety the Contractor shall:

    - immediately draw that fact to the Authority's attention; and

    - vary Schedule 2 (Statement of Technical Requirements) (at the Contractor’s own expense) in a manner acceptable to the Authority so as not to render the Police Patrol Craft non-compliant with, or the Contractor in breach of, any local or UK Statutory Duty or Obligation relating to safety.

  - Any form of approval by the Authority of any plans, calculations or documents relating to craft safety and environmental protection submitted by the Contractor shall not be taken as transferring liability for craft safety and environmental protection to the Authority prior to Acceptance Off Contract.

- NOT USED

- Continuous Improvement

  - As part of the Contractor’s programme of continuous improvement the Contractor shall work with the Authority to identify process improvement which will result in increased craft availability and/or reduced costs. In recognition of the partnering principles, any benefits derived will be equally shared between the Parties.

- Authority’s Authorised Officer

  - Notwithstanding Clause 9 (Contractor’s Obligations), the Authority will appoint an Authority’s Authorised Officer as identified in Schedule 5 (Appendix – Addresses and Other Information) to:

    - inspect the work being done under the Contract and/or any part thereof, including materials and articles used or to be used therein;

    - provide the Contractor with information and advice as required;

    - monitor the progress of work on the Police Patrol Craft(s);

    - implement procedures for the authorisation of Extra and/or Emergent work;

    - co-ordinate all visits by Authority staff in connection with this Contract to the Contractor's premises;

    - arrange for the attendance of Authority inspection, tests and teams as required.

  - The Authority’s Authorised Officer will have the right to inspect all work being carried out under the Contract including at sub-contractors premises and to conduct product surveillance audits at any reasonable time. Any deficiencies or defects found during these inspections or audits shall be rectified by the Contractor at no additional cost to the Authority.

  - To enable the Authority’s Authorised Officer to carry out his duties, the Contractor shall:

    - permit full access at all times to the work in progress and to all drawings, models, samples and articles or things of any kind pertaining to the Contract; maintain full co-operation and provide all such drawings, information and assistance as may reasonably be required;

    - provide shore side office and equipment including but not limited to desk, chair, telephone, internet facilities; mains power, facsimile and access to a photocopier;

    - provide access to basic catering facilities (kitchen sink, running hot and cold water, water boiler, refrigerator and microwave);

    - submit all condition survey reports, dimension reports and readings from machinery in a timely manner;

  - The Authority’s Authorised Officer will have the right to:

    - reject any workmanship, article or material, which does not conform with the requirements of the Contract;

    - stop any test or trial or any other activity being carried out by the Contractor on the Police Patrol Craft(s) at any time if, in his opinion, the safety of the Police Patrol Craft(s), its equipment or personnel on board is compromised.

In respect of Clauses 24.4.1 and 24.4.2 above, the Contractor shall have a right of appeal to the Authority whose decision will be final and conclusive.

  - In the event of appeal by the Contractor against an Authority rejection of any	 workmanship, article or material;

    - notice of appeal shall be given to the Authority within seven (7) Business Days of receipt by the Contractor of notification of rejection;

    - workmanship shall not be made good nor the article or material removed until directed by the Authority.

  - Successful Appeal - Should an appeal by the Contractor prove successful then the Contractor will be entitled to request an extension of time, in accordance with Clause 44 (Permissible Delays) for a period which is equivalent time of the Authority’s action under clause 24.4.1 and/or 24.4.1 up to and including the date on which the appeal is determined. The Authority shall have the absolute right to determine whether or not to grant such an extension of time.

  - The Contractor shall make good or replace at his own expense and to the satisfaction of Authority’s Authorised Officer, any workmanship, article or material rejected by the Authority. The Contractor shall also, if so required by the Authority, mark any rejected article or material, in a manner acceptable to the Authority’s Authorised Officer.

  - The Contractor shall not use surplus or used stores without the Authority's prior written approval. Where the Contractor proposes to use surplus or used stores, they shall submit their detailed proposals, including the effects on agreed prices or programme, to the Authority’s Authorised Officer for consideration and, if appropriate, approval.

  - The Contractor shall be liable for all costs and expenses incurred in the provision and proper use of the accommodation and facilities provided in accordance with Clause 24.3 above.

  - The Authority shall indemnify the Contractor in respect of:

    - damage occurring at the Contractor’s Premises; and

    - any third party claims; and

    - Injury or death to the Contractor’s employees caused by the acts or omissions of the Authority’s Representatives.

  - The Contractor shall indemnify the Authority in respect of injury or death to Authority Representatives caused by the acts or omissions of the Contractor’s Representatives.

  - Clause 24.10 and Clause 24.11 do not apply to the extent that a Party is able to show that any such damage, injury or death was caused or contributed to by circumstances beyond the reasonable control of the Authority’s Representatives or Contractor’s Representatives as appropriate.

- Government Furnished Equipment

  - The Government Furnished Equipment listed in Schedule 13 shall be issued, free of charge to the Contractor for embarkation and embodiment or fitting to the Police Patrol Craft.

  - Embarkation, embodiment or fitting of the Government Furnished Equipment to the Police Patrol Craft shall be at the expense of the Contractor unless otherwise specified in writing by the Authority.

  - The Contractor shall provide:

    - storage space at his premises or their Sub-Contractor for the Government Furnished Equipment which shall be secure, of adequate volume and have a controlled environment suitable for the Government Furnished Equipment;

    - lifting equipment, racking and shelving;

    - goods inwards inspection, stores accounting to include receipt recording, notification of receipts to the Authority, storage recording, issue to the Police Patrol Craft and filing of supporting vouchers in a dedicated file for periodic inspection by the Authority, stowage and simple maintenance tasks.

  - The delivery dates of Government Furnished Equipment shall be agreed between the Authority and the Contractor and shall be recorded in Schedule 13 (Government Furnished Equipment) after the Commencement Date.

  - The Required Delivery Date of each Police Patrol Craft is based on the assumption that all items of Government Furnished Equipment shall be delivered on the dates stated in Schedule 13 (Government Furnished Equipment). In the event that the Required Delivery Date of each Police Patrol Craft is revised, the Parties may agree to amend the delivery dates in Schedule 13 (Government Furnished Equipment) to accord with the changed Required Delivery Date.

  - The Authority shall be liable for the costs of:

    - removing and/or replacing defective Government Furnished Equipment;

    - repairing or replacing any part of the Police Patrol Craft damaged by defective Government Furnished Equipment;

    - repeat trials occasioned solely by faulty design of, or defects in, Government Furnished Equipment;

    - any delay to the Required Delivery Date of the Police Patrol Craft caused by late delivery of the Government Furnished Equipment and where the Authority has agreed an extension of time in accordance with Clause 44 (Permissible Delays).

provided that such costs are not due to error, default, breach, omission or negligence on the part of the Contractor.

  - All Government Furnished Equipment shall remain the property of the Authority. It shall be used in the execution of the Contract and for no other purpose, without the prior approval in writing of the Authority.

  - Neither the Contractor, nor any Sub-Contractor, nor any other person, shall have a lien on Government Furnished Equipment, for any sum due to the Contractor, Sub-Contractor or other person, and the Contractor shall take all such steps as may be necessary to ensure that the title of the Authority, and the exclusion of any such lien, are brought to the notice of all Sub-Contractors and other persons dealing with any Government Furnished Equipment.

  - The equipment will be serviced by the Original Equipment Manufacturer(s) (OEM(s)) and delivered to the Contractors premises in accordance with the dates in Schedule 13 (Government Furnished Equipment);

  - The Contractor shall be responsible for the installation of the GFE in the Police Patrol Craft in accordance with Schedule 2 (Statement of Technical Requirements).

- Receipt of Government Furnished Equipment

  - Subject to Clauses 26.2 to 26.4 below, the Contractor shall promptly and no later than ten (10) Days of receipt of Government Furnished Equipment:

    - check that the Government Furnished Equipment corresponds with the Government Furnished Equipment specified in the Contract;

    - conduct a reasonable visual inspection; and

    - notify the Authority’s Authorised Officer of any defects, deficiencies or discrepancies discovered.

  - Where Government Furnished Equipment is packaged it shall not be unpacked earlier than is necessary. The period identified at Clause 26.1 above shall count from the date on which packages are opened.

  - The Authority shall within a reasonable time after receipt of any notice under Clause 26.1 replace, re-issue or arrange for the repair of the defective or deficient Government Furnished Equipment. If appropriate, it shall also issue written instructions for the return or disposal of the defective or deficient Government Furnished Equipment.

  - The proceeds of the sale of defective or deficient Government Furnished Equipment shall be credited to the Authority in accordance with arrangements made between the Contractor and the Authority. A list of the Government Furnished Equipment sold by the Contractor shall be sent to the Commercial Officer specified in the Schedule 5 (Appendix - Addresses and Other Information) together with a statement of the proceeds of sale.

  - In the event that the Authority fails to provide, replace, or arrange for the repair of the defective or deficient Government Furnished Equipment within a reasonable time of receipt of a notice in accordance with Clause 26.1, the Parties shall agree appropriate changes to the Contract in accordance with Clause 40 (Changes to the Contract) provided that the Contractor has taken all reasonable measures to mitigate the consequences of any such delay.

- Custody of Government Furnished Equipment

  - The Contractor shall be responsible for:

    - safe custody and return to the Authority of;

    - calibration and maintenance of;

    - loss or damage to;

the Government Furnished Equipment as set out in Schedule 13 (Government Furnished Equipment) from the expiry of the period specified in Clause 26.1 until the earlier of Acceptance Off Contract or re-delivery of the Government Furnished Equipment to the Authority in accordance with the Authority's instructions.

  - If requested, the Authority shall, within a reasonable time and where practicable before delivery of the Government Furnished Equipment, notify the Contractor of the value of the Government Furnished Equipment.

  - The Contractor shall not be liable to the Authority in respect of:

    - defects or deficiencies notified to the Authority in accordance with Clause 26.1 above or latent defects which the Contractor can show could not reasonably have been discovered by means of the activities described at Clause 26.1;

    - fair wear and tear of Government Furnished Equipment resulting from its normal and proper use in the execution of the Contract save where the deterioration is contributed to by any misuse, lack of care or maintenance by the Contractor;

  - At Acceptance Off Contract of each Police Patrol Craft the Contractor shall forward a list of Government Furnished Equipment still held by the Contractor to the Authority's Commercial Officer named in Schedule 5 (Appendix - Addressees and Other Information) and shall return or dispose of the Government Furnished Equipment in accordance with the Authority’s instructions.

- Government Furnished Information

General

  - All drawings, documents, design information and details of arrangements, models, mock-ups and samples provided by the Authority in connection with the Contract shall remain the property of the Authority.

  - Subject to Clause 28.1 the Contractor shall not in any way be relieved from any obligation under this Contract nor shall it be entitled to claim against the Authority on grounds that the Government Furnished Information is insufficient, and shall make its own enquiries as to the adequacy of that information.

  - In the event the Contractor discovers that the Government Furnished Information supplied by the Authority is inaccurate, the Contractor shall immediately notify the Authority of such inaccuracy and any impact on the Contract including any requirement for a change in the Contract under Clause 40 (Changes to the Contract) or extension of time in accordance with Clause 44 (Permissible Delays).

  - Nothing in this Clause 28 shall exclude any liability which the Authority or any of its agents or employees would otherwise have to the Contractor in respect of any statements made fraudulently or fraudulent omissions to make statements prior to the date of this Contract.

Drawings, documents and information

  - Where the Contract states that the Authority will supply any drawings, documents or information to the Contractor they will be provided free of charge.

  - On completion of the Contract, the Authority’s Authorised Officer will advise the Contractor of the method of disposal of all drawings, documents and other information supplied to him in accordance with Clause 28.

Review of Documents provided by the Contractor

  - During the course of the Contract where documents are delivered to the Authority for review, unless specified otherwise, the Contractor shall allow no less than ten (10) Business Days for the Authority to respond. The Authority’s comments on the documents will be supplied in writing. In cases where the Authority’s comments are extensive, a separate review meeting will be held with the Contractor to discuss the changes required to the document.

Supply of Support Documentation by the Contractor

  - The Contractor shall provide the Authority with technical handbooks, maintenance schedules, operating instructions, spare parts lists and/or any other documentation in accordance with Schedule 2 (Statement of Technical Requirements).

- Guarantee

  - The Contractor shall guarantee each Police Patrol Craft against Defects for a period of 2 years from acceptance off contract provided that such Defects are:

    - discovered within the Warranty Period for such Police Patrol Craft; and

    - notified to the Contractor as soon as reasonably possible after discovery describing the nature of the Defects and not later than thirty (30) Days after the expiry of the Warranty Period.

  - The Contractor shall not be liable for rectifying or paying the cost of rectifying any Defect arising from:

    - fair wear and tear; or

    - mis-management or neglect by any persons in control of the relevant Police Patrol Craft other than the Contractor, his servants, agents or Sub-Contractors.

  - The Contractor shall be responsible for all aspects of Warranty Guarantee management including but not limited to:

    - progressing the rectification of all Defects;

    - the management of Sub-Contract guarantees including the transfer of any rights in Sub-Contract guarantees to the Authority in accordance with Clause 29.12;

    - the production and distribution of Defect status reports; and

    - attendance at meetings with the Authority and/or Sub-Contractors to review Defects.

  - Save as provided for in Clause 46.2, the Contractor shall promptly make any necessary repairs or replacements to rectify any Defects or damage to any Police Patrol Craft caused as a direct consequence of such Defects. Such repairs and replacements shall be made at the Contractor’s cost and expense.

  - The Authority shall have the right to arrange for the rectification of any Defect, or damage to any Craft caused as a direct consequence of a Defect, to be undertaken at a location of the Authority’s choice and obtain any necessary replacement parts and materials where:

    - the Contractor cannot supply necessary replacement parts and materials without impairing or delaying the operation or working of the Police Patrol Craft; or

    - the Contractor is in default of Clause 29.4.

  - In the event that the Authority proposes to rectify Defects, the Authority shall notify the Contractor of the time and place the Defect rectification will take place. The Contractor shall be given a reasonable opportunity to inspect the nature and extent of the Defect and promptly advise the Authority whether or not they accept that the Defect is covered by the Warranty Guarantee but such advice to the Authority shall not be conclusive.

  - The Contractor shall pay the Authority the reasonable cost and expenses of rectifying a Defect in accordance with Clause 29.5 which shall be:

    - set off against the Final Milestone Payment (Retention 2); or

    - paid within (thirty) 30 Days of receipt of a written demand for payment from the Authority where:

      - the Final Instalment Payment (Retention 2) has already been paid by the Authority; or

      - the amount payable by the Contractor exceeds those sums which have been set off by the Authority in accordance with Clause 29.7.1.

  - At any time prior to rectification in accordance with Clause 29.5 the Contractor shall be entitled to request that the Authority return any parts replaced to the Contractor. The Authority shall make reasonable endeavours to comply with the Contractors request and any parts returned shall be at the Contractor’s cost.

  - In the event that any replaced parts returned to the Contractor in accordance with Clause 29.8 are the subject of a dispute,

  - the Contractor shall make available the replaced parts for inspection by the Authority.

  - The Contractor shall guarantee the repairs or replacements made in accordance with Clause 29.4 for a period which is the later of:

    - twelve (12) Months from the date of completion of the remedial work; or

    - the end of the Warranty Period, provided however in any event the Warranty Period including any extension under Clauses 29.10.1 and 29.11 shall not exceed thirty-six (36) Months after Acceptance Off Contract.

  - In relation to any Police Patrol Craft, the relevant Warranty Period shall be extended where the Police Patrol Craft has been lying idle for a continuous or cumulative period of thirty (30) Days as a result of any work undertaken in accordance with this Clause 29 up to a maximum of thirty-six (36) Months. The period of the extension shall be equivalent to the total time that the Police Patrol Craft has been lying idle.

  - The Contractor shall assign to the Authority all guarantees or warranties given by the Sub-Contractors or suppliers of any of the materials or equipment used in the construction of the Police Patrol Craft which exceed the relevant Warranty Period upon:

    - the date of expiry of the Warranty Period; and/or

    - the Authority exercising its rights in accordance with Clause 46 (Take Over / Tow-Out Option).

  - The Warranty Guarantee contained in this Clause 29 replaces and excludes any other liability, guarantee, warranty and/or condition imposed or implied by the law, customary, statutory or otherwise in relation to Defects.

- Sub-Contracts

  - No Sub-Contracting by the Contractor shall in any way extinguish, diminish or reduce the Contractor’s obligations under the Contract and the Contractor shall be fully responsible for acts, errors, defaults, breaches, omissions or negligence of any Sub-Contractor.

  - The Contractor shall perform its obligations under and observe all the terms of any Sub-Contracts.

  - Nothing in this Contract shall prohibit or prevent any Sub-Contractor employed by the Contractor from being employed by the Authority at any establishments of the Authority.

  - Where the Contractor enters into a Sub-Contract with a supplier or contractor for the purpose of performing the Contract, he shall cause a term to be included in such Sub-Contract which requires payment to be made by the Contractor to the supplier or contractor within a specified period not exceeding thirty (30) Days from receipt of a valid invoice and the requirements for a valid invoice shall be defined by the Sub-Contract.

  - The Contractor shall not place any Sub-Contract or order involving the design or development of Articles required under this Contract without the prior approval of the Authority.

  - The Contractor shall not enter into any commitment in relation to the design or development of equipment until such time as the Contractor has entered into an agreement with the Authority in the form set out at Schedule 19 (Design Rights and Patents (Sub-Contractors Agreement – DEFFORM 177). Wherever possible the request for approval should be accompanied by two copies of the agreement signed by the Sub-Contractor. If, in any case the Contractor is unable to comply with this Clause he shall report the matter to the Authority’s Commercial Officer and await further instructions before placing the Sub-Contractor or order.

  - The Contractor shall retain, for a period of at least ten (10) years after Acceptance Off Contract of the final Police Patrol Craft under the Contract or Termination Date, a copy of the Sub-Contracts (or the relevant parts thereof) sufficient to demonstrate the Authority’s rights with respect to Intellectual Property Rights and shall provide certified copies of such records to the Authority upon request.

  - The Authority shall have a right of direct access to any Sub Contractor for the purpose of monitoring the progress of work under the Contract, technical liaison and discussion with the Sub-Contractor provided that his presence at the site shall not hinder progress of the work. The Authority shall give prior notification to the Contractor of any proposed visits and the Contractor shall have a right to be present at any site visit by the Authority to a Sub Contractor. This right of direct access under this Clause shall also include the Authority's right to discuss, at any time, with Lloyd's Register or any relevant maritime and coastguard agency, or agency having similar jurisdiction, any aspects relating to the Contract.

Change of Sub-Contractors

  - The Contractor shall assign any guarantees or warranties provided by its Sub-Contractors to the Authority which exceed the Warranty Period.

- Matters To Be Included In Sub-Contracts

  - The Contractor shall ensure that all Sub-Contracts shall at all times include:

    - provisions such that the Sub-Contract shall not be rescinded, or varied in such a way as to alter or extinguish any rights granted to the Authority without the prior written consent of the Authority;

    - provisions that the Authority's rights referred to in this Clause 31, which are otherwise enforceable under the Contracts (Rights of Third Parties) Act 1999, are not rendered unenforceable; and

    - a requirement that either party to the Sub-Contract may release to the Authority any of those parts of the Sub-Contract as are necessary to be sufficient to demonstrate compliance with the provisions of this clause and that any such release shall not amount to a breach of any provision of confidentiality contained within the Sub-Contract.

    - provisions enabling the Contractor to terminate the Sub-Contract (on similar terms to those which apply to any termination by the Authority of this Contract under the Terms and Conditions of the Contract), and shall terminate such Sub-Contract where reasonably directed by the Authority to do so.

    - provisions enabling the Contractor to secure the dismissal of an employee of the Sub-Contractor, so as to enable implementation of any Authority requirement of the Contractor to secure such dismissal, due to a breach of DEFCON 520 (Corrupt Gifts and Payments of Omission) by that employee, include a provision enabling the Contractor to determine such Sub-Contracts in the event that the Authority exercises its rights under DEFCON 656B (Termination for Convenience) to terminate this Contract upon written notice;

    - include the power to determine the Sub-Contract on substantially the same terms as those which apply to any termination of this Contract pursuant to DEFCON 656B (Termination for Convenience), provided that references in the provisions DEFCON 656B (Termination for Convenience) to "Authority", "Contractor" and "Contract" shall be construed (as appropriate) as references to "Contractor, "Sub-Contractor" and "Sub-Contract" (respectively) for the purposes of the corresponding Sub-Contract provisions.

    - a requirement for any further Sub-Contracts of lower tiers to contain provisions capable of giving effect to all of the provisions of Clauses 30 (Sub-Contracts) and 31 (Matters to be Included in Sub-Contracts), to the extent reasonably required by the Authority.

  - When placing subcontracts, the Contractor is asked to give consideration, as far as possible, to placing work on a competitive basis with Subcontractors that are Supported Businesses. The Contractor can find details of Supported Businesses in the United Kingdom on the Supported Business Directory that is British Association for Supported Employment at Unit 4, 200 Bury Road, Tottington, Lancashire BL8 3DX (Telephone : 01204 880733) or http://business.base-uk.org/procurement.

- NOT USED

- Care and Protection of the Police Patrol Craft(s)

General

  - The Contractor shall be responsible for the care and protection, physical security, loss and damage of the Authority’s Police Patrol Craft, their equipment and other equipment and materials whilst in their custody from the point of acceptance from the Authority to the point of either:

    - delivery by the Contractor in accordance with DEFCON 621B (Transport (if the Contractor is responsible for Transport)): or

    - collection by the Authority from the Contractor’s premises in accordance with DEFCON 621A (Transport (if the Authority is responsible for Transport))

  - On acceptance from the Authority the Contractor shall complete Schedule 10c (Care and Custody Certificate) and an inventory of all loose items, engine serial number and hours before and after the repair work has been undertaken ensuring all loose items are held in accordance with Clause 25 (Government Furnished Equipment) and returned with the Police Patrol Craft.

Berthing/Slipping

  - The Police Patrol Craft(s), whilst in the care and protection of the Contractor, shall be docked and undocked and slipped and unslipped as required by the Contractor.  Any costs associated with this shall be bourne solely by the Contractor. At all other times the Contractor shall place the Police Patrol Craft(s) in a suitable berth approved by the Authority. Except as may otherwise be approved by the Authority, the Contractor shall ensure the Police Patrol Craft(s) is fully afloat at all states of the tide.

Stability

  - The Contractor shall be responsible for ensuring the Police Patrol Craft’s stability is, at all times, satisfactory whilst in their care and protection. The Authority will have the right to require the Contractor, at the Contractor’s expense, to check the stability of a Police Patrol Craft at any time.

Clean Boat and Protection of Equipment

  - The Contractor shall maintain high standards of cleanliness to decks, Police Patrol Craft compartments and passageways, Boat structure, dock bottom and steps (where applicable) and dock side.

  - The Contractor shall ensure there is no contamination of equipment or installation by any means including dirt, condensation, paint, shipyard arisings, corrosive products of grit blasting, lagging and kindred operations. Arisings shall be removed on a daily basis, whenever the nature of the work permits and debris shall not be allowed to accumulate. In places where equipment may be subject to heavy wear or knocks from passing traffic it must be boxed in. All deck coverings shall be protected from dirt and damage.

  - The Contractor shall be responsible for making good damage to paint-work and fittings arising from work in way.

  - The Contractor shall remain responsible for the condition and cleanliness until collection of the Police Patrol Craft by the Authority or delivery of the Police Patrol Craft by the Contractor.

  - The Contractor shall ensure compartments in which switchboards are located are kept clear of stores, tools and clothing.

  - The Contractor shall ensure all work which may have an adverse effect on electronic and/or environmentally sensitive equipment is completed before any such equipment is moved aboard and/or fitted.

Fire Precautions

  - The Contractor shall be responsible for fire fighting arrangements whilst a Police Patrol Craft is in their care and protection. The Contractor shall:

    - provide access and action by the local Fire Authority to meet applicable legislation;

    - provide fire watcher and fire-fighters at all times during working hours and up to one hour after any hot work is complete in accordance with hot work procedures and for security rounds at cessation of the working day;

    - ensure clearance of fire hazards;

    - ensure availability of alarms, extinguishers and appliances;

    - provide equipment and training and exercising of personnel.

  - Without prejudice to the Contractor's responsibility under Shipbuilding and Ship Repairing Regulations (1960), supplemented by the Health and Safety at Work Act and the Shipyard Auditable Health and Safety Policy Document and all applicable legislation, the Contractor shall as and when requested by the Authority:

    - allow access to the Contractor’s facilitates to enable the Authority to check that the efficacy of the Contractor's precautions at Clause 33.12 above is to the entire satisfaction of the Authority; and

    - provide evidence of their compliance with this 33.12.

- Continuing Obligations

  - Save as otherwise expressly provided in this Contract or as already taken into account in the calculation of any payment on termination pursuant to this Contract:

    - termination of this Contract shall be without prejudice to any accrued rights or obligations under this Contract prior to termination; and

    - termination of this Contract shall not affect the continuing rights and obligations of the Contractor and the Authority under:

      - Clauses 3 (Precedence of Documents), 9 (Contractor’s Obligations), DEFCON 527 (Waiver), DEFCON 529 (Law (English)), DEFCON 530 (Disputes), DEFCON 531 (Disclosure of Information), and DEFCON 538 (Severability); or:

      - any other Clause or any provision of this Contract which is expressed or implied to survive termination or which is required to give effect to such termination or the consequences of such termination.

- Debt Factoring

  - Subject to the Contractor obtaining the prior written consent of the Authority in accordance with DEFCON 518 (Transfer) the Contractor may assign to a third party (“the Assignee”) the right to receive payment of the Contract Price or any part thereof due to the Contractor under this Contract (including any interest incurred by the Authority under any Contract clause concerning the late payment of debts).

  - Any assignment of the right to receive payment of the Contract Price (or any part thereof) under DEFCON 518 (Transfer) shall be subject to:

    - reduction of any sums in respect of which the Authority exercises its right of recovery under DEFCON 522 (Payment and Recovery of Sums Due), or any narrative clause concerning recovery of sums due;

    - all related rights of the Authority under the Contract in relation to the recovery of sums due but unpaid; and

    - the Authority receiving notification under both Clause 35.3 and sub-Clause 35.4.2 below.

  - In the event that the Contractor obtains from the Authority the consent to assign the right to receive the Contract Price (or any part thereof) under Clause 35.1 above, the Contractor shall notify the Authority in writing of the assignment and the date upon which the assignment becomes effective.

  - The Contractor shall ensure that the Assignee:

    - is made aware of the Authority’s continuing rights under sub-Clauses 35.2.1 and 35.2.2 of this Clause 35; and

    - Notifies the Authority of the Assignee’s contact information and bank account details, to which the Authority shall make payment, subject to any reduction made by the Authority in accordance with sub-Clauses 35.2.1 and 35.2.2 above.

  - The provisions of the Contract, including any clauses concerning payment, shall continue to apply in all other respects after the assignment and shall not be amended without the prior approval of the Authority.

- Health and Safety

  - Notwithstanding and without prejudice to the provisions detailed elsewhere in the Contract, the Contractor shall be entirely responsible for the safety, whilst on his premises, of all personnel in connection with the Contract, whether or not in his employ.

  - Save as may otherwise be specifically defined in the Contract, the Contractor shall be in charge of, and entirely responsible for, the care, protection and security of the Police Patrol Craft(s) and all Authority property whilst in their possession.

  - Where the Authority engages an Independent Safety Advisor/Auditor/Assessor the Contractor shall provide access to records, including Sub-Contractor records to enable the Authority to carry out safety audits and other assessment activities. This shall include the provision of access to the Contractor and Sub-Contractors premises if required.

- Attendance by Makers' Representatives and Certification Authorities

  - The Contractor shall be responsible for co-ordinating and arranging all attendance to execute or oversee work in connection with delivery, installation on board, setting to work, acceptance, maintenance, trials and repair or examination of machinery, systems and equipment, under the Contract.

  - The Contractor shall make all arrangements for, and provide all necessary drawings, access and facilities for any work in connection with registration, classification, certification, surveys or trials.

  - The Contractor shall be responsible for co-ordinating and arranging attendance by all surveyors necessary for any certification required by the Contract.

  - The Contractor is encouraged to bring to the attention of the Authority any measures which might promote sustainable procurement from a social, economic and environmental point of view.

  - The Contractor shall take all reasonable steps to ensure that all activities under this Contract shall comply with certified environmental management standards based on ISO14001 or equivalent.

- Certification and Classification

  - The Police Patrol Craft shall be designed, constructed, surveyed, tested and delivered in compliance with the applicable laws, rules, regulations and requirements of the Classification Society, the Regulatory Authorities (including the Authority whose requirements are specified in this Contract):

    - in force as of the date of this Contract, or

    - if not in force as of the date of this Contract, which are ratified and promulgated on or before the date of this Contract and which will be compulsory for the Police Patrol Craft on or before the delivery of the Police Patrol Craft.

  - All such laws, rules, regulations and requirements of the Classification Society and the Regulatory Authorities shall be complied with without qualification.

  - Any subsequent Change in Certification and Classification shall be dealt with in accordance with Clause 39 (Changes in Certification and Classification).

  - The final decisions of the Classification Society or Regulatory Authorities shall be binding on the Parties as to the Police Patrol Craft’s compliance with their respective applicable laws, rules, regulations and requirements.

  - Subject to Clause 38.1 all costs, fees and charges in respect of compliance with the applicable laws, rules, regulations and requirements of the Classification Society or Regulatory Authorities referred to above (as well as the fees and costs payable to the Classification Society or Regulatory Authorities) shall be for the Contractor’s cost and expense.

- Changes in Certification and Classification

  - Subject to Condition 38 (Certification and Classification) above, the Clauses 39.2 to 39.7 below shall apply to any Change in Certification and Classification.

  - The Parties shall promptly notify the other Party of the change as soon as possible after becoming aware of the Change in Certification and Classification.

  - The Contractor shall at his own expense provide to the Authority a written statement detailing the consequences of implementing the Change in Certification and Classification, including but not limited to, any changes to:

    - Contract price;

    - Delivery Date;

    - Performance of the Police Patrol Craft;

    - Lifting weight.

  - If the Authority obtains an exemption from the Change in Certification and Classification he shall notify the Contractor of such and the Contractor shall take no further action in relation to the Change in Certification and Classification.

  - If the Authority has not sought or obtained an exemption from the Change in Certification and Classification the Contractor shall incorporate such Change in Certification and Classification into the construction of the Police Patrol Craft.

  - The Parties shall agree any adjustments to the Contract resulting from the incorporation into the construction of the Police Patrol Craft of any Change in Certification and Classification.

  - If the Parties fail to agree the adjustments, the Contractor shall proceed with required changes and the consequences of its implementation shall be decided in accordance with DEFCON 530 (Dispute Resolution).

- Changes to the Contract

Categorisation of Changes

  - Each proposal for a change to the Contract shall be categorised as follows:

    - Priority changes.

    - Routine changes.

  - The category shall be determined by the Authority’s Authorised Officer following the procedure set out at Clause 40.3 below.

Contract Change Proposal Procedure

  - The procedure set out in the following Table shall be followed by the Authority and the Contractor for all Changes to this Contract except as otherwise provided for under this Contract.

|  | Changes Initiated by the Authority | Changes Initiated by the Contractor |
| --- | --- | --- |
| Step 1 | A Change Number shall be allocated by the Authority’s Authorised Office using Contract Change Proposal Form (CCPF) 2. Change category assigned by the Authority’s Authorised Officer. Written request for a formal proposal shall be issued to the Contractor by the Authority. | The Contractor shall gain internal Contractor approval to submit a Contract Change Proposal. |
| Step 2 | The Contractor shall respond to the Authority within ten Business Days (five Business Days for priority changes) of receiving the written request advising the date by which the Contract Change Proposal Form (CCPF1) shall be submitted. | Initially an outline CCPF 1 shall be tabled by the Contractor with a Rough Order of Magnitude price to cover the change and advising the date by which the Contract Change Proposal Form (CCPF1) shall be submitted. The proposal shall be given a Change Proposal Number and registered on the Index of Contract Change Proposals (Form CCPF 2) by the Authority’s Authorised Officer who shall advise the Contractor whether to proceed with the following steps or that the change proposal is rejected. |
| Step 3 | Within fifteen Business Days (ten Business Days for priority changes) of receiving the written request the Contractor shall provide an outline CCPF 1 with an indication of the price to cover the change. The Authority’s Authorised Officer will advise the Contractor whether to proceed with the following steps or that the change proposal is rejected. | NOT USED |
| Step 4 | The Contractor shall determine, in conjunction with the Authority, whether sub-Contract competition is required |  |
| Step 5 | The Contractor shall provide formal completed CCPF1 including proposed Firm prices (including a price breakdown) in accordance with Schedule 1 (Schedule of Requirements) to this Contract. The CCPF 1 shall be submitted in accordance with Step 2. |  |
| Step 6 | If required, the Authority and the Contractor shall meet within five Business Days from receipt of CCPF1 to agree and approve the Change. The Authority’s Authorised Officer shall make the necessary arrangements to convene the meetings. |  |
| Step 7 | Subject to agreement of a Firm Price, any other changes to the Contract and approval of funding the Authority’s nominated Commercial Officer shall issue a serially numbered Contract Amendment in writing to the Contractor’s nominated Commercial Manager within ten Business Days of agreement of the change proposal. The provisions of DEFCON 503 (Dispute Resolution) shall apply. |  |
| Step 8 | The Contract Amendment shall be signed by the Contractor’s nominated Commercial Manager and such confirmation of acceptance returned to the Authority |  |

  - The Authority shall maintain configuration control of CCPF 1 forms and the CCPF 2 and shall issue copies to the Contractor’s nominated Project and Commercial Managers as requested.

  - Once the CCPF 1 has been agreed and authorised by the Authority the signed original CCPF 1 and all its attachments, including the Contractor’s quotation, shall be retained by the Authority’s nominated Commercial Officer who shall raise a Contract Amendment in accordance with Step 7 of the procedure set out at Clause 40.3 above indicating formal approval for the Contractor to implement the change. A copy of the CCPF1 shall be retained by the Contractor.

  - The Contractor’s cost for supporting in the Contract Change Proposal Procedures specified at Clause 40.5 above are included in the Contract Price detailed at Schedule 4 (Pricing and Rates).

Pricing Of Contract Change Proposals

  - Contract amendment(s) resulting from a CCPF 1 submission shall not be issued until Firm prices have been agreed by the Authority’s nominated Commercial Officer. Such prices shall be based upon the Contract Rates set out to Schedule 4 (Pricing and Rates) to this Contract.

  - In exceptional circumstances, where the Authority requires urgent action to be taken provisional prices for change may be set in accordance with DEFCON 643 (Price Fixing). Such provisional prices shall be based upon the Contract rates set out to Schedule 4 (Pricing and Rates) to this Contract.

  - Where the change has a sub-Contract element the Firm price proposed for that element on the CCPF 1 shall be equal to the sum of the quotation from the sub-Contractor plus the agreed Contractor’s rates detailed at Schedule 4 (Pricing and Rates) to this Contract.

General

  - The Authority shall not accept liability for any costs or charges incurred other than in accordance with this Contract including tasks properly raised and authorised in accordance with the procedures herein. This Contract may only be changed by the Contractor’s acceptance of a written amendment issued after a change has been proposed and evaluated by following the procedures of the Contract Change Proposal (CCP) Form, Schedule 15 to the Contract.

- Commonality of Equipment and Systems

  - The Contractor shall ensure that all Police Patrol Crafts ordered under this Contract are fitted with the same equipment and systems, unless such equipment and/or systems are no longer available. In the event that commonality of equipment and/or systems is not possible the Contractor shall immediately notify and seek approval from the Authority, providing details of the proposed replacement equipment and/or systems. Notwithstanding approval by the Authority, the Contractor shall ensure that any such replacement equipment and/or system is of the same (or better) quality and performance levels as required under this Contract.

- Replacement of Obsolescent Parts and Equipment

  - The Contractor shall be responsible for correctly specifying all material to be incorporated into the Police Patrol Craft, including the replacement of obsolescent parts and equipment and maintaining up-to-date records of equipment variants fitted in each Police Patrol Craft. The Contractor shall be required to provide assurance to the Authority that replacement parts and equipment where different from those originally fitted will not affect the Police Patrol Crafts fitness for purpose in its intended role. The Contractor shall also obtain certification from the relevant certification society for replacement parts or equipment where required.

- Liquidated Damages

  - It is recognised by the Parties that if the Contractor fails to deliver each Police Patrol Craft by the date(s) specified in the delivery schedule at Table 3 of Schedule 4 (Pricing and Rates), the Authority will suffer loss and damage.

  - Accordingly, for each Day’s delay (including bank holidays and weekends) the Contractor shall pay the Authority £1,000 per day per craft that delivery is delayed up to a maximum of £60,000 as Liquidated Damages. The Parties confirm that this sum represents a genuine pre-estimate of the Authority’s loss.

  - The provisions of this Clause are without prejudice to any other rights of the Authority under the Contract, including but not limited to those under DEFCON 514 (Material Breach), Clause 46 (Take Over/Tow Out Option) and Clause 47 (Financial Consequences of Termination). Accordingly, in the event that the Authority terminates the Contract, Liquidated Damages shall be payable under Clause 43.2 above until the date of such termination.

  - Unless expressly stated by the Authority in writing, the provisions of DEFCON 527 (Waiver) shall apply to the Authority’s right to recover Liquidated Damages under this Clause.

- Permissible Delays

  - The Contractor shall notify the Authority in writing within five (5) Business Days of the occurrence of a Force Majeure Event or Delay Event and may request in writing an extension to the Required Delivery Date in accordance with Clause 44.2 provided that:

    - any Delay Event:

      - was not caused by the error, neglect, act or omission of the Contractor or its Sub-Contractors; and

      - could not reasonably have been, foreseen by the Contractor at the date of the Contract; and

      - the Contractor shall have made all reasonable efforts to avoid and mitigate the effects such Force Majeure Event or Delay Event has on the delivery of the Police Patrol Craft.

  - A request for an extension of time to the Required Delivery Date shall be submitted by the Contractor to the Authority within ten (10) Business Days of the occurrence of the Force Majeure Event or Delay Event and shall include:

    - the cause and extent of the delay;

    - a statement on the effect the event has, or will have on the critical programme path of the Police Patrol Craft has or will be delayed;

    - those contractual obligations which have been affected by the delay;

    - proposals for mitigating the delay, including alternative arrangements.

  - A failure of the Contractor to notify the Authority in accordance with Clauses 44.1 and 44.2 shall prevent the Contractor from claiming an extension to the Required Delivery Date.

  - The Contractor shall:

    - advise the Authority immediately in writing that the Force Majeure Event or Delay Event has ended; and

    - as soon as reasonably practicable thereafter, and no later than fifteen (15) Business Days after the end of the Force Majeure Event or Delay Event, submit in writing details of the length of extension to the Required Delivery Date claimed including evidence that the critical path of the Police Patrol Craft has been delayed.

  - Any extension of time granted or rejected by the Authority pursuant to this Clause 44 shall be fair and reasonable. For the avoidance of doubt the Authority shall have a right to grant an extension to the Required Delivery Date irrespective of any claim by the Contractor.

  - For the avoidance of doubt, any act or omission of the Authority causing a Delay Event to a Police Patrol Craft shall not necessarily be a Delay Event in respect of any subsequent Police Patrol Crafts.

- Termination For A Permissible Delay

  - If a Permissible Delay is continuing, or its consequence remains such that the affected Party is unable to comply with its obligations under this Contract, for a period of more than one hundred and twenty (120) Business Days, then either Party may (subject to Clause 45.2 below) terminate this Contract or part thereof by serving upon the other Party a Termination Notice stating that:

    - It is terminating the Contract pursuant to Clause 45 and

    - The Contract shall terminate on the day falling fifteen (15) Business Days after the date of the Termination Notice.

  - If the Termination Notice has been served by the Contractor the Authority may elect to require the Contract or part thereof to continue by serving the Contractor with written notice of such and the Parties shall agree a fair and reasonable adjustment in accordance with Clause 40 (Changes to the Contract) - Changes Initiated by the Authority. The Contract or part thereof shall not terminate until the earlier of:

    - any applicable date for the termination or expiry of this Contract set out in Clause 10 (Contract Period); and

    - the expiry of any subsequent written notice (of at least thirty (30) Business Days) from the Authority to the Contractor that it wishes this Contract to terminate.

  - Subject to Clause 45.2 above the Contract shall terminate upon the expiry of fifteen (15) Business Days from the date of the Termination Notice.

- Take Over/Tow-Out Option

  - The Authority shall, within fifteen (15) Business Days after termination of this Contract in accordance with DEFCON 514 (Material Breach) or Clause 45 (Termination for a Permissible Delay), have the right to elect to take possession of the Police Patrol Craft, documentation and other deliverables in their current state and to:

    - complete such work as be necessary in order to remove the Police Patrol Craft, documentation and other deliverables from the Contractors Premises or the premises of a sub-contractor, using the premises, labour, plant, machinery and equipment of the Contractor or sub-contractor (at the Contractor’s risk); and

    - remove the Police Patrol Craft, documentation and other deliverables from the Contractors Premises or the premises of a sub-contractor in order to complete the Police Patrol Craft elsewhere in accordance with this Contract.

    - upon giving prior written notice of such to the Contractor.

  - In the event that the Contract is terminated in accordance with DEFCON 514 (Material Breach) all reasonable costs and expenses incurred by the Authority in exercising its rights in accordance with Clause 46.1 and completing the Police Patrol Craft elsewhere shall be deducted from any outstanding payments to be made to the Contractor if the same be sufficient and if the same is not sufficient shall be made good by the Contractor on demand.

  - This Clause shall not apply if the Contractor has commenced action under DEFCON 530 (Dispute Resolution) at any time prior to the Authority exercising its rights in accordance with Clause 46.1.

- Financial Consequences of Termination

Termination for Contractor Default

  - Where the Authority has terminated this Contract pursuant to DEFCON 514 (Material Breach) the Contractor shall, in respect of any Police Patrol Crafts that have not been Accepted Off Contract, but terminated by the Authority, promptly refund to the Authority the full amount of sums paid by the Authority to the Contractor under Clause 12 (Payment).

  - Where the Authority has exercised its right to Take Over/Tow-Out Option in accordance with Clause 46, the Authority shall not be entitled to a refund in accordance with Clause 47.1 and the financial consequences shall be dealt with in accordance with Clause 47.

  - Notwithstanding the refund of instalment payments in accordance with Schedule 17 (Milestone Payment Plan) , the Authority may elect to pay the Contractor for some or all of the Contractor Deliverables at prices to be agreed by the Parties.

  - Where the Authority is entitled to terminate this Contract pursuant to DEFCON 520 (Corrupt Gifts and Payments of Commission), the Authority shall, in addition to its rights set out in Clause 47.1 above (but without any double-counting) be entitled to:

    - recover from the Contractor the amount of any loss resulting from such termination;

    - where this Clause 47.4 applies but this Contract has not been terminated, to recover from the Contractor any other loss sustained as a result of such breach,

and any recovery action taken against any UK Government employee shall be without prejudice to any recovery action taken against the Contractor pursuant to this Clause.

Break

  - Where this Contract is terminated pursuant to DEFCON 656B (Termination for Convenience), then in addition to the provisions of DEFCON 656B, the provisions of Clause 47.5 below shall also apply.

    - The Authority shall not be liable under DEFCON 656B (Termination for Convenience) to pay any sum which;

    - would be claimable under any insurance held (or required to be held) by the Contractor, but for the fact that the Contractor has failed to make a claim on its insurance, or has failed to make a claim in accordance with the procedural requirements of the insurance policy, or has failed to take out or maintain any insurance that it is required to take out and/or maintain; or

    - When added to any sums already paid or due to the Contractor under this Contract, exceeds the total sum that would have been payable to the Contractor if this Contract had not been terminated pursuant to DEFCON 656B (Termination for Convenience).

Termination for a Permissible Delay

  - Where this Contract is terminated pursuant to Clause 45 (Termination for a Permissible Delay), the provisions of Clauses 47.76 to 47.99 below shall apply.

  - Subject to Clause 47.9 below, where the Contract has been determined in accordance with Clause 45 (Termination for a Permissible Delay) the Contractor shall promptly refund to the Authority the full amount of sums paid by the Authority to the Contractor under Clause 12 (Payment).

  - The Contractor shall only be entitled to be paid from the sums refunded to the Authority in accordance with Clause 47.7 for any aspect of the Contractor Deliverables that it has, as at the Termination Date, delivered to the Authority in accordance with the Contract (subject to any other provisions of this Contract affecting the level of such payment).

  - The Authority shall not be entitled to a refund under Clause 47.8 above where:

    - the permissible delay is caused entirely by an act or omission of the Authority; or

    - the Authority has exercised its right to Take Over/Tow-Out in accordance with Clause 46 above.

Miscellaneous Provisions

  - Each Party shall pay to the other any amounts payable pursuant to Clause 47 within twenty (20) Business Days of the Termination Date (or, if later, within twenty (20) Business Days of the amount being identified by both Parties as being payable, where it was not possible to determine on the Termination Date that such amount was payable).

  - Any payment made by the Authority to the Contractor or by the Contractor to the Authority, pursuant to this Clause 47 shall be in full satisfaction of the liability of the paying Party and shall be the sole remedy of the receiving Party in relation to this Clause 47.

- Major Incident Inquiries

  - If any Major Incident occurs the Contractor shall, as soon as possible and upon notice to the Authority, convene and conduct a formal enquiry under the chairmanship of a director of the Contractor to establish the causes of the incident and, where appropriate, recommend remedial action to prevent any recurrence of the Major Incident.

  - The requirement of Clause 48.1 shall be without prejudice to any inquiry by the relevant national health and safety regulatory body, as required by law, and in the event that any such Inquiry is convened the Contractor shall:

    - give notice of the inquiry to the Authority as soon as reasonably practicable;

    - to the extent lawful and practicable secure for the Authority the right to attend and to be represented at the inquiry;

  - The Authority shall have the right to appoint representatives to attend the Major Incident Inquiry in any of the following capacities:

    - as members of the Major Incident Inquiry board;

    - in an advisory capacity;

    - to question witnesses.

  - The presence of such representatives of the Authority shall be without prejudice to the Authority's right to accept or reject the findings and recommendations of the Major Incident Inquiry board.

  - A full report of the Major Incident Inquiry signed by all members of the board shall be forwarded to the Authority and shall include:

    - a summary of the proceedings;

    - evidence of any witnesses, together with copies of any sketches or diagrams which may have been produced;

    - details of any difference of opinion between the board members on any material point;

    - the conclusions and recommendations of the board.

  - Any Major Incident Inquiry shall not deliberate on adjustments to the Contract and shall be without prejudice to the rights and remedies of the Parties, under the Contract or otherwise, in respect of any loss or damage arising from any such incident.

  - Notwithstanding anything in this Clause 48, in certain circumstances the Authority may wish to conduct an inquiry itself; in which case the Authority shall have the right to require the Contractor, or any person in his employ, to attend the inquiry in any capacity.

  - If the Contractor proposes to call representatives of the Authority to the Major Incident Inquiry either to give evidence or for any other purpose, prior approval shall be sought from the Authority’s Authorised Representative.

- Jigs and Tools

  - The Contractor shall provide Jigs and Tools.

  - The Contractor shall advise the Authority in writing within three (3) Months of Contract award of any Special Jigs and Tools required for the purposes of this Contract.

  - Save as provided in Clause 49.8, the cost of all Jigs and Tools and Special Jigs and Tools including the cost of maintenance and calibration is included in the Contract Price. The Contractor shall not claim assistance from other UK Government funds towards the cost of any Special Jigs and Tools.

  - Special Jigs and Tools shall be the absolute property of the Authority.

  - Neither the Contractor, nor a Sub-Contractor, nor any other person shall have a lien on the Special Jigs and Tools for any sum due to the Contractor, Sub-Contractor or any other person. The Contractor shall take all reasonable steps necessary to ensure that the provisions of this clause are brought to the notice of all Sub-Contractors and other persons dealing with any Special Jigs and Tools.

  - Save as provided in this Clause 49, Special Jigs and Tools shall be treated as Government Furnished Equipment in accordance with Clause 25 (Government Furnished Equipment).

  - The Contractor shall be free to modify the Special Jigs and Tools as he may deem to be necessary in order to perform the Contract and the Authority's approval of such modifications shall not be required.

  - In the event that any Special Jigs and Tools are required by the Contractor for installation of Government Furnished Equipment, the Authority shall provide these to the Contractor free of charge. The Contractor shall be responsible for the cost of maintenance and calibration of Special Jigs and Tools provided under this Clause 49.8.

  - The Contractor shall not use the Special Jigs and Tools for any purposes other than those of the Authority without first obtaining the written approval of the Authority which may be conditional upon the Parties agreeing terms for commercial exploitation of the Special Jigs and Tools.

- Inspection, Tests and Trials

General

  - The Contractor shall undertake inspections, tests and trials in accordance with the requirements specified in Annex I of Schedule 6 (Integrated Project Management Plan). All inspection, tests, trials and rectification of defects arising must be completed prior to the Contractor offering up the Police Patrol Craft for Acceptance by the Authority.

  - The programme for undertaking such inspections, tests and trials shall be agreed between the Contractor and the Authority and the Contractor shall ensure that inspections, tests and trials are not fragmented.

  - The Contractor shall be solely responsible for conducting all inspections, tests and trials and for co-ordinating their requirements and those of his Sub-Contractors.

  - The Contractor shall confirm in writing to the Authority’s Authorised Officer five (5) Business Days before an inspection test or trial is to take place, or such other period if specified in the Contract, that:

    - the Police Patrol Craft or equipment or system will be ready; and

    - all pre-requisites for the trial will be met.

  - The Authority’s Authorised Officer will arrange for the attendance of the Authority’s inspection, test and trials team as required and will also advise the Contractor where he considers that all pre-requisites are not being met. In the event that written confirmation is not received by the Authority five (5) Business Days, or such other period as agreed between the Parties, prior to an inspection, test or trial taking place or where the Authority is not satisfied that all pre-requisites are being met, the Authority’s personnel will not attend the inspection, test or trial. In these circumstances the Contractor shall be liable for all costs.

  - The Authority will, at its discretion, have the right to:

    - postpone any or all inspections, tests or trials;

    - keep the Police Patrol Craft at sea for such periods as necessary;

    - require the Police Patrol Craft to proceed to sea for extra trials or for any other purpose not specified in the Contract;

    - and will reimburse the Contractor for any reasonable costs thereby incurred, except where the events in Clauses 50.6.1 to 50.6.3 above is due to error, breach, omission or negligence on part of the Contractor.

Additional Contractor Inspections, Tests and Trials

  - Any additional inspections, tests and trials which the Contractor wishes to carry out prior to the Contractor offering up the Police Patrol Craft for Acceptance by the Authority, shall be the responsibility and liability of the Contractor.

Inspection and Trials Teams

  - Where the Authority appoints personnel to attend inspections, tests and trials on behalf of the Authority, the presence of these personnel shall not in any way relieve the Contractor of his responsibilities under the Contract.

  - In the event that any inspection, test or trial or part thereof, undertaken by the Contractor has to be repeated for any reason, including but not limited to all pre-requisites or requirements not being met, and for which the Contractor is responsible, the Contractor shall re-programme or re-run the inspection, test or trial. In these circumstances the Contractor shall be liable for all costs, including reimbursement of the Authority’s reasonable costs.

  - Without prejudice to the Contractor's responsibilities, the Authority will, if so requested and subject to availability, provide staff to carry out under the Contractor's orders, and acting as unpaid servants of the Contractor, duties for which specialised knowledge is required. Nothing in this Clause 50 shall extinguish, diminish or reduce the Contractor's responsibilities for inspections, tests or trials in accordance with the Contract.

Sea Trials

  - Unless otherwise agreed between the Authority and the Contractor, the Contractor shall take command of the Police Patrol Craft(s) for sea trials. During all sea trials, whether Police Patrol Craft(s) are under the control of the Contractor or the Authority, the Contractor shall be fully responsible for the care and custody of the Police Patrol Craft(s). The Contractor shall liaise with the Authority’s Authorised Officer on matters of Police Patrol Craft(s) safety.

  - Arrangements for Contractor's and Sub-Contractors' representatives attending sea trials shall be agreed between the Contractor and the Authority’s Authorised Officer whose decision on numbers attending shall be final.

  - On satisfactory completion of sea trials, the Contractor shall complete Schedule 10a (Certificate of Acceptance) and Schedule 10b (Boats Sea Trial Form) to present to the Authority with all other deliverables required on Acceptance Off Contract.

- Acceptance

  - Acceptance of the Police Patrol Craft Off Contract shall be in accordance with the provisions set out in Annex I (Test, Evaluation & Acceptance Plan) of Schedule 6 (Integrated Project Management Plan).

  - Immediately prior to Acceptance Off Contract the Contractor shall complete and present to the Authority for review the Acceptance Form (Schedule 10a) together with all other deliverables required prior to acceptance in accordance with Schedule 2 (Statement of Technical Requirements). The Contractor shall record on Schedule 10a all outstanding items which shall be completed/rectified at the Contractors expense within five (5) Business Days of the Police Patrol Craft being presented for Acceptance Off Contract.

  - Subject to the Authority being satisfied that the Police Patrol Craft has met the condition for Acceptance Off Contract, the Authority will sign the Acceptance Form  (Schedule 10a). Should the Authority not be satisfied a Corrective Action Plan (Schedule 9) will be completed.

  - Following Acceptance Off Contract, the Authority reserves the right to retain the Police Patrol Craft at the Contractor’s Premises for a period of up to twenty (20) Business Days at the Contractor’s expense. Whilst the Police Patrol Craft is at the Contractor’s Premises following Acceptance Off Contract the Contractor shall be responsible for Care and Protection of the Police Patrol Craft in accordance with Clause 33 (Care and Protection of Boats).

- Import and Export of Boats and/or any Associated Equipment or Spares

  - In the event the Contractor, with the agreement of the Authority, takes the decision to transport a Boat, and/or any associated equipment or spares into or out of the UK the Contractor shall be responsible for all the relevant custom formalities. In these circumstances the Contractor shall be liable for all costs.

- NOT USED

- Sustainable Procurement

  - The Contractor shall take all reasonable steps to procure the observance of the economic, social and environmental legislation related to the subject matter or the execution of the Contract by any servants, employees or agents of the Contractor and any Sub-Contractors engaged in the performance of the Contract.

  - If the Contractor becomes aware of any potential or actual prosecution or proceedings, for criminal breaches of the economic, social and environmental legislation related to the subject matter or the execution of the Contract, against the Contractor, any servants, employees or agents of the Contractor and any Sub-Contractors engaged in performance of the Contract, the Contractor shall immediately notify the Authority at the address specified in the Contract.

  - Any convictions during the period of the Contract for criminal breaches of the economic, social and environmental legislation related to the subject matter or the execution of the Contract by the Contractor or any of the Contractor’s directors/partners or senior management who have powers of representation, decision or control, shall be regarded as a material breach of this Contract.

  - A sustainable procurement plan is not required for the purposes of this Contract.

- Compatibility With Authority Systems

  - The Contractor shall ensure that all documents required for this Contract including but not limited to plans, drawings, report, forms and logs are supplied in the English Language (UK) using both the Oxford English Dictionary and the principles of the Simplified Technical English (STE) Dictionary.

  - The Contractor shall ensure that all Notices and Deliverable Drawings and Documents are provided in, or shall be fully compatible with, the following applications:

    - MS Office 2010 applications (MS Word, MS Excel, MS PowerPoint, MS Outlook, MS Project)

    - Microsoft Office SharePoint portal Server 2007

    - Adobe Acrobat Reader vXI

    - Drawings (both formats to be provided for all drawings)

    - Autodesk AutoCAD Drawing (*dwg), DWF (available on AutoCAD v2004+);

    - PDF format that permits a word-based search function.

    - Active Risk Manager 5.1 by Strategic Thought Ltd, Release 5.1.1606 update 07 (or an alternative agreed with the Authority)

    - Telelogic DOORS® 9.5 (or an alternative agreed with the Authority)

  - In transferring information to the Authority, the Contractor shall:

    - ensure that all information is marked/classified in accordance with the Contract terms and conditions for data security and the security aspects letter.

    - ensure that all electronic information is free from viruses and malware.

    - ensure that e-mails do not exceed 8Mb in size (electronic files larger than 8Mb or MS Access files shall be sent to the Authority on CD or DVD).

    - not use memory sticks.

- NOT USED

- Public Relations and Publicity

  - The Contractor shall not by itself, its employees or agents, and shall procure that its Sub-Contractors shall not:

    - communicate with representatives of the press, television, radio or other communications media or members of the public on any matter concerning this Contract;

    - photograph or film in or upon any Authority Sites;

    - erect or exhibit on any part of the Authority Sites any signs or trade boards; or exhibit or attach to any part of the Authority Sites any notice or advertisement, unless the Authority has given its prior written consent or as otherwise required to comply with Legislation.

- Exit

  - On termination of the Contract and at any time and for whatever reason, the Authority shall not be liable for any additional costs, other than where the Authority is liable under the Contract, for the hand-over by the Contractor to any successor Contractor or to the Authority of all data as may exist in the Contractor’s possession at the time of termination of the Contract, and as relevant to the performance of the work by that successor Contractor or the Authority.

  - To provide for the possible hand-over to another Contractor on termination of the Contract, or transfer back of responsibility for the work to the Authority, throughout the duration of the Contract, the Contractor shall maintain records, including an IPR register, in a manner suitable to facilitate such a hand-over. The records shall be maintained by the Contractor in a manner that the Contractor would expect them to be maintained in were the Contractor to be a successor Contractor unfamiliar with the requirements. The Authority’s minimum requirement shall be, subject to the ownership of the hardware and Intellectual Property Rights/Free User Rights vesting with the Authority, the records required by the Authority from the Contractor shall include, but not be limited to the following:

    - a list of all Sub-Contractors and suppliers used by the Contractor in performance of the Contract including details of products and existing Contracts;

    - warranty, guarantee and certification documentation, including test certificates as appropriate;

    - a list of GFE holdings (including an inventory of the stores);

    - reports produced for the Authority during the Contract (including supporting information referenced therein);

    - a log of major technical and support decisions taken by the Contractor and the Authority during the Contract;

    - support manuals for the systems and equipment in service on expiry or termination of the Contract, that provide sufficient information for the successor Contractor and operator to safely and efficiently support and operate the equipment;

    - maintenance manuals, records and configuration status that provide sufficient information for the maintainer to safely and efficiently maintain the Police Patrol Craft(s); the maintenance manuals would include the parts breakdown of the equipment, etc.

  - In addition, the Contractor shall also return or destroy, with the Authority's permission, any documentation supplied by the Authority or generated by the Contractor on behalf of the Authority, including any information with a OFFICIAL- SENSITIVE classification in accordance with Clause 59 (OFFICIAL and OFFICIAL- SENSITIVE Security Condition for UK Contracts).

  - The requirement for hand-over records as detailed in Clause 58.2 above to be maintained by the Contractor shall be included in the Annex E (Exit Strategy Plan) to Schedule 6 (Integrated Project Management Plan).

- OFFICIAL and OFFICIAL- SENSITIVE Security Condition for UK Contracts

Definitions

  - The term "Authority" means a Ministry of Defence (MOD) official acting on behalf of the Secretary of State for Defence.

Security Grading

  - All aspects associated with this Contract are classified OFFICIAL. Some aspects are more sensitive and are classified as OFFICIAL-SENSITIVE. The Authority shall issue a Security Aspects Letter which shall define the OFFICIAL- SENSITIVE information that is furnished to the Contractor, or which is to be developed by it, under this Contract. The Contractor shall mark all OFFICIAL-SENSITIVE documents which it originates or copies during the Contract clearly with the OFFICIAL-SENSITIVE classification. However, the Contractor is not required to mark information/material related to the contract which is only OFFICIAL.

Official Secrets Acts

  - The Contractor's attention is drawn to the provisions of the Official Secrets Acts 1911-1989 in general, and to the provisions of Section 2 of the Official Secrets Act 1911 (as amended by the Act of 1989) in particular. The Contractor shall take all reasonable steps to make sure that all individuals employed on any work in connection with the Contract (including sub-contractors) have notice that these statutory provisions, or any others provided by the Authority, apply to them and shall continue so to apply after the completion or earlier termination of the Contract.

Protection of OFFICIAL and OFFICIAL- SENSITIVE Information

  - The Contractor shall protect OFFICIAL and OFFICIAL-SENSITIVE information provided to it or generated by it in accordance with the requirements detailed in this Security Condition and any other conditions that may be specified by the Authority. The Contractor shall take all reasonable steps to prevent the loss or compromise of the information or from deliberate or opportunist attack.

  - The contractor shall apply Industry Security Notice (ISN) 2017/01 requirements to every industry owned IT and communication system used to store, process or generate MOD information including those systems containing OFFICIAL and/or OFFICIAL-SENSITIVE information. ISN 2017/01 details Defence Assurance and Risk Tool (DART) registration, IT security accreditation processes, risk assessment and risk management requirements. The ISN is available at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/594320/DART_ISN_-_V2_3.pdf

  - OFFICIAL and OFFICIAL-SENSITIVE information shall be protected in a manner to avoid unauthorised access. The Contractor shall take all reasonable steps to prevent the loss, compromise or inappropriate access of the information or from deliberate or opportunist attack.

  - All OFFICIAL and OFFICIAL-SENSITIVE material including documents, media and other material shall be physically secured to prevent unauthorised access. When not in use OFFICIAL and OFFICIAL- SENSITIVE documents/material shall be handled with care. As a minimum, when not in use, OFFICIAL-SENSITIVE material shall be stored under lock and key and in a lockable room, cabinets, drawers or safe and the keys/combinations are themselves to be subject to a level of physical security and control.

  - Disclosure of OFFICIAL and OFFICIAL-SENSITIVE information shall be strictly in accordance with the "need to know" principle. Except with the written consent of the Authority, the Contractor shall not disclose any of the classified aspects of the Contract detailed in the Security Aspects Letter other than to a person directly employed by the Contractor or sub-Contractor, or Service Provider.

  - Any samples, patterns, specifications, plans, drawings or any other documents issued by or on behalf of the Authority for the purposes of the Contract remain the property of the Authority and shall be returned on completion of the Contract or, if directed by the Authority, destroyed in accordance with Clause 59.32.

Access

  - Access to OFFICIAL and OFFICIAL-SENSITIVE information shall be confined to those individuals who have a “need-to-know”, have been made aware of the requirement to protect the information and whose access is essential for the purpose of his or her duties.

  - The Contractor shall ensure that all individuals having access to OFFICIAL-SENSITIVE information have undergone basic recruitment checks. Contractors shall apply the requirements of HMG Baseline Personnel Security Standard (BPSS) for all individuals having access to OFFICIAL-SENSITIVE information. Further details and the full requirements of the BPSS can be found at the Gov.UK website at:

https://www.gov.uk/government/publications/government-baseline-personnel-security-standard.

Hard Copy Distribution

  - OFFICIAL and OFFICIAL-SENSITIVE documents shall be distributed, both within and outside company premises in such a way as to make sure that no unauthorised person has access. It may be sent by ordinary post or Commercial Couriers in a single envelope. The words OFFICIAL or OFFICIAL-SENSITIVE shall not appear on the envelope. The envelope should bear a stamp or details that clearly indicates the full address of the office from which it was sent.

  - Advice on the distribution of OFFICIAL-SENSITIVE documents abroad or any other general advice including the distribution of OFFICIAL-SENSITIVE hardware shall be sought from the Authority.

Electronic Communication, Telephony and Facsimile Services

  - OFFICIAL information may be emailed unencrypted over the internet. OFFICIAL-SENSITIVE information shall normally only be transmitted over the internet encrypted using either a CESG Commercial Product Assurance (CPA) cryptographic product or a MOD approved cryptographic technique such as Transmission Layer Security (TLS). In the case of TLS both the sender and recipient organisations must have TLS enabled. Details of the required TLS implementation are available at:

https://www.ncsc.gov.uk/guidance/tls-external-facing-services

Details of the CPA scheme are available at:

https://www.ncsc.gov.uk/scheme/commercial-product-assurance-cpa

Exceptionally, in urgent cases, OFFICIAL-SENSITIVE information may be emailed unencrypted over the internet where there is a strong business need to do so and only with the prior approval of the Authority.

  - OFFICIAL-SENSITIVE information shall only be sent when it is known that the recipient has been made aware of and can comply with the requirements of these Security Conditions and subject to any explicit limitations that the authority shall require. Such limitations, including any regarding publication, further circulation or other handling instructions shall be clearly identified in the email sent with the material.

  - OFFICIAL information may be discussed on fixed and mobile telephones with persons located both within the UK and overseas. OFFICIAL-SENSITIVE information may be discussed on fixed and mobile types of telephone within the UK, but not within earshot of unauthorised persons.

  - OFFICIAL information may be faxed to recipients located both within the UK and overseas, however OFFICIAL-SENSITIVE information may be faxed only to UK recipients.

Use of Information Systems

  - The detailed functions that must be provided by an IT system to satisfy the minimum requirements cannot all be described here; it is for the implementers to identify possible means of attack and ensure proportionate security mitigations are applied to prevent a successful attack.

  - The contractor shall ensure 10 Steps to Cyber Security is applied in a proportionate manner for each IT and communications system storing, processing or generating MOD UK OFFICIAL or OFFICIAL-SENSITIVE information. 10 Steps to Cyber Security is available at:

https://www.ncsc.gov.uk/guidance/10-steps-cyber-security

The contractor shall ensure competent personnel apply 10 Steps to Cyber Security.

  - As a general rule, any communication path between an unauthorised user and the data can be used to carry out an attack on the system or be used to compromise or ex-filtrate data.

  - Within the framework of the 10 Steps to Cyber Security, the following describes the minimum security requirements for processing and accessing OFFICIAL-SENSITIVE information on IT systems.

    - Access Physical access to all hardware elements of the IT system is to be strictly controlled. The principle of “least privilege” will be applied to System Administrators. Users of the IT System -Administrators should not conduct ‘standard’ User functions using their privileged accounts.

    - Identification and Authentication (ID&A). All systems shall have the following functionality:

      - Up-to-date lists of authorised users.

      - Positive identification of all users at the start of each processing    session.

    - Passwords. Passwords are part of most ID&A, Security Measures. Passwords shall be ‘strong’ using an appropriate method to achieve this, for example including numeric and “special” characters (if permitted by the system) as well as alphabetic characters.

    - Internal Access Control. All systems shall have internal Access Controls to prevent unauthorised users from accessing or modifying the data.

    - Data Transmission. Unless the Authority authorises otherwise, OFFICIAL- SENSITIVE information shall be transmitted or accessed electronically (e.g. point to point computer links) via a public network like the Internet, using a CPA product or equivalent as described in Clause 59.13 above,

    - Security Accounting and Audit. Security relevant events fall into two categories, namely legitimate events and violations.

      - The following events shall always be recorded:

        - All log on attempts whether successful or failed,

        - Log off (including time out where applicable),

        - The creation, deletion or alteration of access rights and privileges,

        - The creation, deletion or alteration of passwords,

      - For each of the events listed above, the following information is to be recorded:

        - Type of event,

        - User ID,

        - Date & Time,

        - Device ID, The accounting records shall have a facility to provide the System Manager with a hard copy of all or selected activity. There shall also be a facility for the records to be printed in an easily readable form. All security records are to be inaccessible to users without a need to know. If the operating system is unable to provide this then the equipment shall be protected by physical means when not in use i.e. locked away or the hard drive removed and locked away.

    - Integrity & Availability. The following supporting measures shall be implemented:

      - Provide general protection against normally foreseeable accidents/mishaps and known recurrent problems (e.g. viruses and power supply variations),

      - Defined Business Contingency Plan,

      - Data backup with local storage,

      - Anti-Virus Software (Implementation, with updates, of an acceptable industry standard Anti-virus software),

      - Operating systems, applications and firmware should be supported,

      - Patching of Operating Systems and Applications used shall be in line with the manufacturers recommended schedule. If patches cannot be applied an understanding of the resulting risk will be documented,

    - Logon Banners Wherever possible, a “Logon Banner” shall be provided to summarise the requirements for access to a system which may be needed to institute legal action in case of any breach occurring. A suggested format for the text (depending on national legal requirements) could be:

“Unauthorised access to this computer system may constitute a criminal offence”

    - Unattended Terminals. Users are to be automatically logged off the system if their terminals have been inactive for some predetermined period of time, or systems must activate a password protected screen saver after 15 minutes of inactivity, to prevent an attacker making use of an unattended terminal.

    - Internet Connections. Computer systems shall not be connected direct to the Internet or ‘untrusted’ systems unless protected by a firewall (a software based personal firewall is the minimum but risk assessment and management must be used to identify whether this is sufficient).

    - Disposal Before IT storage media (e.g. disks) are disposed of, an erasure product shall be used to overwrite the data. This is a more thorough process than deletion of files, which does not remove the data.

Laptops

  - Laptops holding any MOD supplied or contractor generated OFFICIAL-SENSITIVE information are to be encrypted using a CPA product or equivalent as described in paragraph 14 above.

  - Unencrypted laptops not on a secure site are to be recalled and only used or stored in an appropriately secure location until further notice or until approved full encryption is installed. Where the encryption policy cannot be met, a Risk Balance Case that fully explains why the policy cannot be complied with and the mitigation plan, which should explain any limitations on the use of the system, is to be submitted to the Authority for consideration. Unencrypted laptops and drives containing personal data are not to be taken outside of secure sites. For the avoidance of doubt the term “drives” includes all removable, recordable media (e.g. memory sticks, compact flash, recordable optical media e.g. CDs and DVDs), floppy discs and external hard drives.

  - Any token, touch memory device or password(s) associated with the encryption package is to be kept separate from the machine whenever the machine is not in use, left unattended or in transit.

  - Portable CIS devices are not to be left unattended in any public location. They are not to be left unattended in any motor vehicles either in view or in the boot or luggage compartment at any time. When the vehicle is being driven the CIS is to be secured out of sight in the glove compartment, boot or luggage compartment as appropriate to deter opportunist theft.

Loss and Incident Reporting

  - The contractor shall immediately report any loss or otherwise compromise of any OFFICIAL or OFFICIAL-SENSITIVE information to the Authority.

  - Accordingly, in accordance with Industry Security Notice 2014/02 as may be subsequently updated at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/293480/ISN 2014_02_Incident_Reporting.pdf

any security incident involving any MOD owned, processed, or Contractor generated OFFICIAL or OFFICIAL-SENSITIVE information defined in the contract Security Aspects Letter shall be immediately reported to the MOD Defence Industry Warning, Advice and Reporting Point (WARP), within the Joint Security Co-ordination Centre (JSyCC). This will assist the JSyCC in formulating a formal information security reporting process and the management of any associated risks, impact analysis and upward reporting to the MOD’s Chief Information Officer (CIO) and, as appropriate, the company concerned. The MOD WARP will also advise the contractor what further action is required to be undertaken.

JSyCC WARP Contact Details

Email: For those with access to the RLI: CIO-DSAS-JSyCCOperations

Email: For those without access to the RLI: CIO-DSAS-JSyCCOperations@mod.gov.uk

Telephone: Working Hours: 0306 770 2187

Out of Hours/Duty Officer Phone: 07768 558863

Fax: 01480 446328

Mail: Joint Security Co-ordination Centre (JSyCC), X007 Bazalgette Pavilion, RAF Wyton,

Huntingdon, Cambs, PE28 2EA.

Sub-Contracts

  - The Contractor may Sub-contract any elements of this Contract to Sub-contractors within the United Kingdom notifying the Authority. When sub-contracting to a Sub-contractor located in the UK the Contractor shall ensure that these Security Conditions shall be incorporated within the Sub-contract document. The prior approval of the Authority shall be obtained should the Contractor wish to Sub-contract any OFFICIALSENSITIVE elements of the Contract to a Sub-contractor located in another country. The first page of Appendix 5 (MOD Form 1686 (F1686)) of the Security Policy Framework Contractual Process chapter is to be used for seeking such approval. The MOD Form 1686 can be found at Appendix 5 at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/367494/Contractual_Process_-_Appendix_5_form.doc.

If the Sub-contract is approved, the Authority shall provide the Contractor with the security conditions that shall be incorporated within the Sub-contract document. Chapter 2: Contract Security – Annex N

Publicity Material

  - Contractors wishing to release any publicity material or display hardware that arises from this contract shall seek the prior approval of the Authority. Publicity material includes open publication in the contractor’s publicity literature or website or through the media; displays at exhibitions in any country; lectures or symposia; scientific or technical papers, or any other occasion where members of the general public may have access to the information even if organised or sponsored by the MOD, Services or any other government department.

Private Venture

  - Any defence related Private Venture derived from the activities of this Contract are to be formally assessed by the Authority for determination of its appropriate classification. Contractors are to submit a definitive product specification for PV Security Grading in accordance with the requirement detailed at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/414857/20150310_PV_Ex_Guidance_Document.pdf

Promotions and Potential Export Sales

  - Contractors wishing to promote, demonstrate, sell or export any material that may lead to the release of information or equipment classified OFFICIAL-SENSITIVE (including classified tactics, training or doctrine related to an OFFICIAL-SENSITIVE equipment) are to obtain the prior approval of the Authority utilising the MOD Form 680 process, as identified at:

https://www.gov.uk/mod-f680-applications.

Destruction

  - As soon as no longer required, OFFICIAL and OFFICIAL-SENSITIVE information/material shall be destroyed in such a way as to make reconstitution unlikely, for example, by burning, shredding or tearing into small pieces. Advice shall be sought from the Authority when information/material cannot be destroyed or, unless already authorised by the Authority, when its retention is considered by the Contractor to be necessary or desirable. Unwanted OFFICIAL-SENSITIVE information/material which cannot be destroyed in such a way shall be returned to the Authority.

Interpretation/Guidance

  - Advice regarding the interpretation of the above requirements should be sought from the Authority.

  - Further requirements, advice and guidance for the protection of MOD information at the level of OFFICIAL-SENSITIVE may be found in Industry Security Notices at:

https://www.gov.uk/government/publications/industry-security-notices-isns.

Audit

  - Where considered necessary by the Authority, the Contractor shall provide evidence of compliance with this Security Condition and/or permit the inspection of the Contractors processes and facilities by representatives of the Authority to ensure compliance with these requirements

- Background Information

  - For the purposes of this clause, “background information” refers to any information not generated under the Contract.

  - Where the Contractor intends to utilise a pre-existing design(s) in their performance of the Contract, and where this design and its associated information are owned entirely or in part by the Contractor, the Contractor shall furnish the Authority with such detailed information as is necessary to clearly identify the Contractor-owned elements of any final design developed under the Contract.

  - As soon as he becomes aware, the Contractor shall notify the Authority of any third party information which exists in any pre-existing design(s) utilised in the performance of the Contract or which is otherwise relevant to the Contract.

  - The Contractor hereby grants the Authority a non-exclusive, worldwide and irrevocable licence to use or have used (including copy, modify or disclose) in confidence any Contractor or third party owned Background Information included within or embedded in any design under the following circumstances:

  - Where use is necessary for any purposes within any United Kingdom government department, the United Kingdom Police and civil defence agencies; and

  - Where the Authority is required to disclose to or authorise use by a service provider under a tender, agreement or contract, solely for the purposes of provision of a service to Authority. These services shall be limited to managing, monitoring, evaluating, assessing or auditing the work under the Contract, provided that the service provider is identified for this purpose at the time of Contract placement or is later agreed with the Contractor. Agreement shall not be unreasonably withheld unless there is a demonstrable conflict of interest identified by the Contractor.

  - The rights under Clause 60.4 above shall be granted at no additional cost to the Authority.

- Technical Publications

  - The Contractor shall ensure that the Authority has the right to copy, amend, extend or have copied, amended or extended any technical publication called for under the Contract or any part thereof including any such part when incorporated in any amended or extended version of such technical publication, and to circulate, use or have used said technical publication including any amended or extended version and any copies thereof for any United Kingdom Government purpose but not for the purpose of manufacturing equipment to which the technical publication relates.

- Gainshare

  - Both Parties acknowledge that there is an agreed baseline for the Firm prices agreed under this Contract, as set out in the Statement of Requirements at Schedule 1 to this Contract, and that changes to that baseline which lead to cost reductions shall represent a Gainshare proposal.

  - The Agreement at Schedule 20 to this Contract details the possible, but not exclusive, areas for which the Authority and the Contractor shall work together to realise potential opportunities for increased efficiency and savings under the Contract.

  - All savings achieved, as a result of the Agreement at Schedule 20 to this Contract, shall be shared on an agreed basis between both parties, subject to the following:

    - any non-recurring costs incurred during investigation and subsequent implementation of any agreed Gainshare arrangement shall be offset against the agreed savings prior to the sharing of savings apportionment; and

    - Any non-recurring costs incurred during investigating a proposed Gainshare, which has been approved by the Authority but at a later date it is agreed not to pursue for a reason listed in the Framework Agreement, shall be allowed as a genuine charge to the Contract.  No profit shall be permitted to be claimed when recovering non-recurring costs under the Gainshare proposal.

  - Any successful Gainshare Opportunities shall be implemented by formal amendment to the Contract following agreement by the Authority and the Contractor.

  - The Contractor shall, where appropriate, flow down the principles of Gainshare in his Contracts with sub-Contractors and suppliers used in the performance of this Contract.

- Progress Meetings

  - Progress Meetings shall be held at monthly intervals unless otherwise agreed by the Authority.  The Contractor may be required to attend ad hoc Progress Meetings as necessary.

  - Meetings with the Authority shall alternate between the Contractor's and the Authority’s premises and shall be chaired by the Contractor (or the Authority) at the discretion of CSS Boats Team.  The Contractor shall provide all administrative and secretarial functions for the meetings including but not limited to:

    - Sending out a calling notice one month before the planned meeting;

    - Sending an Agenda (Agenda to be agreed at the first meeting) one week prior to the meeting;

    - Sending the meeting minutes within two weeks after the meeting.

  - Gain Share Opportunities (in accordance with Clause 62 (Gainshare)) shall be discussed at each Progress Meeting and if accepted by the Authority shall be implemented in accordance with Clause 40 (Changes to the Contract).

- Earned Value Management

Organisation

  - The work undertaken by the Contractor shall be subdivided into portions that are agreeable with the Authority. These subdivisions may be characterised as a Contractor Work Breakdown Structure (CWBS) and shall be defined in a Contractor Work Breakdown Structure Dictionary.

Planning, Scheduling and Budgeting

  - The Contractor is required to produce a schedule at a summary level of detail that reflects the scope of work and time frame required to complete delivery to the Authority. A single page plan that represents the highest level of summary shall be made available to the Authority.

Accounting Considerations

  - The Contractor shall ensure that actual costs are accurately and separately recorded against relevant elements of the CWBS.

Analysis and Reporting

  - The Contractor shall provide a monthly report of spending against plan that compares actual expenditures by CWBS element to the planned values.

  - The Contractor shall provide an in year spending forecast and shall indicate to the Authority within five (5) Business Days if at any time the Contractor expects that the funds required to complete the contract will exceed the agreed contract value. Additionally, if the funds required within any fiscal year are expected to exceed the amount authorised by the Authority, the Contractor shall notify the Authority within no more than five (5) Business Days.

Revisions and Data Management

  - The Contractor shall manage change in a manner that ensures only Authority approved changes are incorporated.