# Annex A

| Title of project: | Marine monitoring procedural guideline: Unmanned Aerial Vehicles for marine monitoring |
| --- | --- |
| Date and time for return of tenders: | Wednesday 5th December 2018 |
| Contract Reference No: | C18-0208-1284 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO SOPHIE RUSH, HAYLEY HINCHEN OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Sophie Rush Marine Monitoring and Evidence Team Joint Nature Conservation Committee Email: sophie.rush@jncc.gov.uk Tel: +44 (0)1733 866 913 Hayley Hinchen Marine Monitoring and Evidence Team Joint Nature Conservation Committee Email: hayley.hinchen@jncc.gov.uk Tel: +44 (0)1733 866 815 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance and Planning Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | As soon as possible upon awarding contract. |
| Proposed end-date: | 15th March 2019 |

## Marine monitoring procedural guideline: Unmanned Aerial Vehicles for marine monitoring

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	5

5.	Project Objectives: Detailed tasks	6

6.	Outputs	14

7.	Dissemination	15

8.	Timescale	16

9.	Health and safety	16

10.	Product specification	16

11.	Project management	17

12.	Instructions for tender submission	17

13.	Evaluation Criteria	19

14.	Payment	20

15.	Additional Contractor requirements	20

16.	References	20

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which we deem relevant to these functions.

Background to JNCC can be found on the JNCC website: http://jncc.defra.gov.uk/page-1729

## Project Aims

This project aims to develop procedural guidance for best practice on the use of Unmanned Aerial Vehicles (UAVs) to monitor marine benthic and pelagic habitats. It will build upon existing guidance as well as deliver unique additional perspectives to better advise and support the marine monitoring scientist who wishes to use UAVs to meet their monitoring objectives.

## Project Background

  - UK Marine Biodiversity Monitoring R&D Programme (UK MBMP)

There are multiple policy and legislative drivers for marine biodiversity monitoring within the UK, including the EU Marine Strategy Framework Directive (2008), the EU Habitats Directive (1992), the EU Birds Directive (1979 amended 2009), the UK Marine and Coastal Access Act 2009, the Marine (Scotland) Act 2010 and the Marine Act (Northern Ireland) 2013. All of these drivers have individual requirements for assessment and reporting which cover varying geographical scales and different aspects of biodiversity (Hinchen, 2014).

Therefore, improved evidence on the state of marine biodiversity, and focussed research into whether and how the biodiversity elements are changing in response to both natural and human induced pressures, is vital. However, to be efficient and effective and to avoid duplication and overlap, it is necessary to set up biodiversity monitoring schemes that are general in nature, rather than specific schemes for each driver.

To answer this need, the UK Marine Biodiversity Monitoring Programme (hereafter referred to as ‘the UK MBMP’) was established to provide a coordinated and integrated approach to monitoring UK marine biodiversity, both in protected sites and the wider environment. JNCC is leading on a number of the elements of this Programme, including developing guidelines on monitoring best practice for seabed habitats and communities through the UK MBMP Habitats Monitoring project. The project builds on the widely-used Marine Monitoring Handbook (Davies et al., 2001), as well as current monitoring method guidance such as that collated in the Marine Monitoring Method Finder.

  - Marine monitoring method updates for UK MBMP

The process of updating procedural guidelines for marine biodiversity monitoring is an ongoing one in the UK that has spanned nearly two decades:

- Following on from the publication of the 29 procedural guidelines in the original Marine Monitoring Handbook (Davies et al., 2001) , three new procedural guidelines were added to it in 2005.

- The JNCC developed an additional eight common standards monitoring guidance documents  in 2004.

- The Mapping European Seabed Habitats (MESH) project developed fifteen recommended operating guidelines to support a wide range of marine survey work in 2007 (Coggan et al., 2007). After significant improvements to some of the methods and technologies used in these guidelines, three of them were updated in 2012 and 2013.

- The UK Technical Advisory Group (UKTAG)  developed many monitoring standards and assessment methods in 2014 to meet the requirements of the Water Framework Directive (2000), sixteen of which were marine habitat and community specific.

- Since then numerous other guidelines have been produced across many organisations (e.g. NMBAQC, PREMIAM) all of which reflect the nature of continuous improvement to monitoring standards, advice and guidance in the UK.

The JNCC have identified the need to update a number of procedural guidelines from the Marine Monitoring Handbook (Davies et al., 2001). There is also a need to create new procedural guidelines for emerging work areas and technologies as a result of changes to marine monitoring drivers since 2001, specifically the EU Marine Strategy Framework Directive (2008), the UK Marine and Coastal Access Act 2009, the Marine (Scotland) Act 2010 and the Marine Act (Northern Ireland) 2013, as well as findings from the OSPAR intermediate assessment (2017) .

3.3. Procedural guidelines for monitoring marine benthic and pelagic habitats with Unmanned Aerial Vehicles

It is the purpose of this contract to create a new Procedural Guideline (PG) for the monitoring of marine benthic and pelagic habitats using Unmanned Aerial Vehicles (UAVs), also commonly known as ‘Drones’. UAVs are emerging as a viable alternative to other conventional marine platforms for providing high-resolution remote-sensing data at a reduced cost and with increased operational flexibility (Klemas, 2015). Broadly, the two main types of UAVs are the ‘aeroplane’ fixed-winged and the rotary wing ‘helicopter’ configurations. With pre-programmed flight planning and GPS guidance, UAVs can obtain very high spatial resolution imagery of landscape features concurrent with field observations without the constraint of fixed satellite observation periods (Lechner et al., 2012). These novel devices can cover areas several kilometres wide due to their long-range communication and thus enable the possibility of monitoring areas that are difficult to survey, which is a common situation in the marine environment (Trasvina-Moreno et al., 2017). Furthermore, with the advancement in the development of miniaturised sensors, new sensors have been specifically designed for UAVs to allow hyperspectral imagery, LIDAR, synthetic aperture radar and thermal imaging. As a result, UAVs are becoming increasingly used in many marine environmental studies. For example, Rajan et al. (2014) combined UAVs with measurements from Autonomous Underwater Vehicles (AUVs) to study Portuguese coastal waters and Oliveira et al. (2013) similarly combined UAVs and AUVs to test new techniques for tracking marine animals.

The wide range of capabilities that UAVs offer creates enormous potential for the monitoring of marine benthic and pelagic habitats. As they can be equipped with a variety of sampling devices and tools they can collect multiple types of data simultaneously. They can also operate in areas where it is difficult to collect data using traditional methods, such as cliffs. This PG must explore these advantages, as well as report the limitations that UAVs have, such as the difficulties in cost optimisation, technical issues, maintenance and legality issues. By also focusing on the range of capabilities that UAVs have and the different situations in which they are useful, the PG will capture the broad range of UAV types as well as their differing functions and capabilities. It will also build upon operational knowledge and experience gained from using UAVs over recent years. Overall, the aim of the PG is to consolidate existing knowledge of UAV application as well as to deliver unique additional perspectives to better advise and support the marine monitoring scientist who wishes to use UAVs to monitor marine benthic and pelagic habitats.

## Project Objectives

The successful contractor is required to deliver on all of the following objectives:

| Objective | Objective overview | Objective output(s) |
| --- | --- | --- |
| 1 | Review literature from relevant studies, guidelines and standards that use Unmanned Aerial Vehicles (UAVs) to monitor marine benthic and pelagic habitats. | - Documentation of literature reviewed in a spreadsheet, to include information on key criteria in the data fields provided by JNCC proforma spreadsheet (see 5.1., Task 1.1, 1.2); - Compile case study examples in separate word document (Task 1.2). |
| 2 | Collate evidence from the literature review (Objective 1) to summarise UAVs capabilities, range of uses, limitations and costs into a method summary. | Summary information on UAVs using tables provided in JNCC proforma spreadsheet (see 5.2., Tasks 2.1, 2.2). |
| 3 | Compile evidence from literature review (Objective 1) and method summary (Objective 2) to write up procedural guideline for the use of UAVs to monitor marine benthic and pelagic habitats. | Complete all sections of the JNCC procedural guideline template, completing a draft of the procedural guideline ready for external review. |
| 4 | Organise and send draft guidance to internal and external reviewers and to use the feedback to finalise the procedural guideline. | - Send documentation to list of internal and external reviewers in JNCC proforma spreadsheet (see 5.4, Task 4.1); - Collated comments from internal and external reviews in JNCC proforma spreadsheet (see Task 4.1); - Final edits culminating in the draft final procedural guideline submitted to JNCC (Task 4.2). |
| 5 | To finalise the procedural guideline. | - Final version of procedural guideline (Tasks 5.1, 5.2). |

## Project Objectives: Detailed tasks

The specific tasks required to fulfil each objective are outlined below. The tender submissions must provide a description of how the tasks will be delivered and propose any additional aspects which may be necessary to meet the objectives. Sufficient time and resources (including financial) should be allowed for requesting and collating relevant information from suitable organisations; tenderers should specify which information they intend to consider and where they intend to source such information from.

Here are a few definitions to clear up misunderstanding of monitoring method terminology used by JNCC:

| Project steering group (PSG) | A group comprised of JNCC and external colleagues responsible for managing the contract and reviewing its products. The contract will be managed by a project technical lead with oversight provided by a project manager. Other members of the project steering group will act solely as reviewers. |
| --- | --- |
| Sample type | The nature of the sample collected by the sample collection device, e.g. video imagery, stills imagery, physical grab sample, water sample. |
| Sampling approaches | The different approaches to using UAVs, whether it is using larger or smaller UAVs or equipping them with specialist sampling equipment (e.g. sensors, videos, cameras, LIDAR, Radar, thermal imagery). |
| Sampling design | The ‘flight plan’ for the UAV. Examples may be to follow height/depth contours, conduct circular searches of an area, to ‘zig-zag’ search an area or to survey discrete areas with high intensity before moving off in search of other areas. |
| JNCC proforma spreadsheet | A spreadsheet with prepared tables and fields to be used by the contractor to demonstrate completion of tasks and objectives in this project. |
| JNCC procedural guideline template | A standardised word document template for JNCC procedural guidelines on best practice approaches to using monitoring methods. |

### Objective 1

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 1 | Review literature from relevant studies, guidelines and standards that use Unmanned Aerial Vehicles (UAVs) to monitor marine benthic and pelagic habitats. | - Documentation of literature reviewed in a spreadsheet, to include information on key criteria in the data fields provided by JNCC proforma spreadsheet (Task 1.1, 1.2); - Compile case study examples in separate word document (Task 1.2). |

Task 1.1: Review relevant literature on the use of UAVs to monitor marine benthic and pelagic habitats.

- Review studies, research, guidelines or standards that focus on the use of UAVs as sampling platforms to monitor marine benthic and pelagic habitats. The contractor will have consulted a broad range of literature from different sources in order to achieve this task, all of which should be provided to JNCC as part of this contract, for future reference.

- A list of potential relevant reading has been supplied in Appendix A. This list acts only as a suggestion and it is expected that wider research is conducted as part of the literature review process.

- In every item of literature reviewed, the contractor should note the capabilities and practicalities of using UAVs, paying particular interest to the following criteria:

  - Full reference of item of literature (must include author/s, year of publication, title, publishing body/organisation at very least);

  - Sample type (e.g. stills imagery, video imagery, LiDAR, infrared imagery);

  - Scale of operation/range of sample footprint (e.g. 100-10 m2);

  - Horizontal resolution (e.g. 2 x 2 m, 0.01 x 0.01 m);

  - Uses of method (e.g. habitat mapping, biodiversity monitoring);

  - Applicable habitats (e.g. Moderate energy intertidal rock, A1.2; see Appendix B for potentially relevant list of habitats);

  - Sampling costs (£ per survey day);

  - Advantages of UAV application in survey;

  - Limitations of UAV application in survey;

  - Logistical concerns when using UAVs (e.g. equipment and personnel required, planning, health and safety concerns);

  - Operational information, i.e. key information for using UAVs in survey;

  - Sample processing and data analysis information;

  - Relevant quality assurance measures for use of method;

  - Databases/Data Archive Centres (DAC) into which the samples/data feed or could feed into;

  - If literature is sourced from outside the UK, identify where and provide a few details so that comparisons can be made;

  - Compile case study information (see Task 1.2 for details).

- The evidence acquired from the literature review must be tabulated into the JNCC proforma spreadsheet, using the above criteria as spreadsheet fields (under the Objective 1 tab). If new, useful criteria were identified and used by the contractor then these should be added to the fields in the spreadsheet too.

- JNCC have a preference for information from primary, peer-reviewed literature that covers species and habitats found in the UK. However, we acknowledge that information may be sparse and in such cases the use of grey literature (e.g. County Nature Conservation Body publications) or habitat proxies and examples from other temperate seas may need to be used. In such cases, this information must be clearly referenced to indicate it has come from outside the UK.

Task 1.2: Identify examples of different applications of UAVs in real world situations to serve as a ‘case study’ examples for those applications.

- While reviewing the literature in Task 1.1, the contractor must also identify examples or studies that could act as ‘case studies’ for different applications of UAVs. These must be noted in the JNCC proforma spreadsheet. The contractor should make a note of all potential case studies in the appropriate field of the ‘Objective 1’ tab in the JNCC proforma spreadsheet, in order to convey the range of situations in which UAVs could be used in marine monitoring.

- The contractor must then select the most appropriate examples of case studies to provide suitable examples of UAV applications in this guidance, as well as any additional, useful applications encountered in the literature review, and write short summaries of them. They should take the form of a short abstract (< 500 words) with supporting references to the peer-reviewed literature or agency report from where it came. Figures and tables may be used to better convey the case study if the contractor sees fit to do so. The summaries and accompanying tables and figure should be presented to the PSG separately in a word document (PSG will decide which case studies will be selected for the final procedural guideline).

### Objective 2

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 2 | Use evidence from the literature review (Objective 1) to summarise UAVs capabilities, range of uses, limitations and costs. | Summary information on UAVs using tables provided in JNCC proforma spreadsheet (Task 2.1, 2.2). |

Task 2.1: Extract and organise evidence acquired from literature review to summarise UAV method.

- The evidence gathered in the literature review must be summarised for use of UAVs.

- The contractor should collate the evidence from within each field of the literature review and summarise it within the prepared table in the JNCC proforma spreadsheet (under the ‘Objective 2’ tab). As this summary uses many of the same fields as used in the literature review the information should be directly transferable.

- When tabulating the summary, the contractor should aim to present the range of different values that exist for each attribute e.g. scale of operation. If possible, they should identify the most common value within the range, which may be taken as the ‘most desired’ or ‘most commonly used’ approach within that field. This information will help identify which approaches may be recommended for use in monitoring programmes, if they are practical and cost-efficient to do so.

Task 2.2: Estimate costs and required resources when using UAVs.

- The contractor must estimate the costs required to carry out a day’s survey using UAVs. If a range of options exist (i.e. application of fixed-wing or rotary UAVs) these options must be presented separately. The contractor must also attempt to list the resources that would be required for each different application of UAVs (i.e. application of fixed-wing or rotary UAVs, use of bespoke sensors or cameras if additional costs are associated). The aim of this task is to provide monitoring scientists with an overview of these important factors as they may determine whether to use an UAV or which type of UAV should be used in a monitoring survey.

- The contractor should fill in the correct tab of the JNCC proforma spreadsheet for this task (‘Objective 2 costs’). This table is to serve as a guide for the contractor and may be modified to better suit the task if the contractor sees fit. Currently there are fields for:

  - Equipment needed;

  - Personnel needed;

  - Planning required;

  - Health and safety requirements and training;

  - Sample collection costs;

  - Sample processing costs;

  - Data analysis costs;

  - Database export costs.

- Where information is difficult to source for this task the contractor may use their best judgement to provide a range in their estimates. If in doubt they should seek approval from the contract manager. The contractor may also present different costs for different scenarios in which the costs may vary, such as whether the work is contracted out or conducted in-house, or carried out in different habitats or seasons. Equally, the costs will vary depending on what type of UAV is used and what sensors/sampling apparatus it is equipped with. Again, the information presented here is to provide the monitoring scientists with a guide where currently none exists.

- The final unit cost per day from this task must be added to the summary table generated in Task 2.1.

### Objective 3

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 3 | Compile evidence from literature review (Objective 1) and method summary (Objective 2) to write up a procedural guideline for the use of UAVs to monitor marine benthic and pelagic habitats. | Complete all sections of the JNCC procedural guideline template, completing a draft of the procedural guideline ready for internal and external review (Tasks 3.1, 3.2 and 3.3). |

Task 3.1: Populate the JNCC procedural guideline template with evidence from Objective 1 and summary from Objective 2.

- The JNCC PG template attempts to standardise all new procedural guidelines so that they share common features and are, therefore, more uniform in approach. This is a similar approach to that taken in the Marine Monitoring Handbook (Davies et al., 2001). However, unlike the ‘Handbook’, the template serves as a guide and need not be rigid when its format may be inappropriate to the subject matter.

- The contractor must attempt to fill out the JNCC procedural guideline template as best they can. When filling out each section in the template the contractor should attempt to be as succinct and as prescriptive as possible. The broad sections within the template include:

  - Title, authors and contact details;

  - Method overview;

  - Logistical information;

  - Operational guidelines;

  - Interpretation guidelines;

  - Quality assurance measures;

  - Data products;

  - References;

  - Appendices (including summary of costs and time), ‘top tips’ and case studies.

- The contractor may choose how to populate each section with the evidence from Objective 1 and the summary from Objective 2. For example, they may choose to modify the table in the ‘Method overview’ section to suit the different types of UAV or different sampling systems they may be equipped with. Indeed, it is likely that many sections in the JNCC procedural guideline template may need to be modified to reflect the different types of UAV and the equipment they can carry. It is the nature of ‘good guidance’ to offer up a range of possibilities to the worker, to equip them to make the decision themselves.

- However, JNCC are also keen that the contractor uses the summary from Objective 2, specifically the ‘most common values’ from each field to attempt to recommend the overall approach that represents best practice in terms of which UAV approaches should be used to monitor marine benthic and pelagic habitats. The contractor will have to weigh up the advantages, limitations, costs and benefits of using different UAVs (and their configurations) in order to do so. It is desirable that the contractor recommends approaches for different budgets and situations (habitats, seasons, communities) or even a single approach over the rest for use in marine benthic and pelagic habitats. This will depend on the strength of the evidence gathered in Objective 1, the clarity of the summaries in Objective 2 and the experience of the contractor in this field. Seek clarity from the contract manager if unsure.

- Any sampling recommendations made must represent ‘best-practice’ in the field and include approaches that are robust, efficient and practical, cost-effective and repeatable. Furthermore, they must be safe to the monitoring scientist who will use them.

- The contractor is encouraged to create useful tables and figures to illustrate the range of applications of UAVs. These will be in addition to those already in the JNCC procedural guideline template. They may focus on the most useful pieces of information (perhaps from fields in the JNCC proforma spreadsheet) regarding the application of UAVs.

- It is intended that the volume of information presented in this procedural guideline should be only what is useful and necessary to the user of the guideline. Additional information, to supplement the methods presented or to provide additional context may be supplied in an appendix. For more information, see Task 3.2 below.

Task 3.2: Record additional information to support the procedural guideline in the appendix.

- Supporting information that is not directly useful to the user of the procedural guidance or a recommendation or unused but interesting table or figure should be presented in the appendix. The purpose of placing it here is so that the main body of the procedural guideline may be free from too much discussion and potential confusion for users.

- The information in the appendix/appendices is still important to users of the procedural guidelines as it can provide context and background to the methods as well as their costs. The successful contractor must, therefore, organise the information into a format that is easy to understand and present it clearly. All contractors must propose an approach to structuring the appendix/appendices in their tender submission.

Task 3.3: Record case studies and ‘top tips’ to support the application of method/s in appropriate section of the standard template.

- The contractor must add the case study examples from Objective 1 (Task 1.2) to the section towards the end of the JNCC procedural guideline template.

- If the contractor has personal experiences of using UAVs that may assist other users, these may be recorded within a ‘top tips’ section towards the end of the standard template. Equally so, if they come across ‘top tips’ within the literature review these may also be recorded in this section.

### Objective 4

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 4 | Organise and send draft guidance to internal and external reviewers and use the feedback to finalise the procedural guideline. | - Send documentation to list of internal and external reviewers in JNCC proforma spreadsheet (Task 4.1); - Collated comments from internal and external reviews in JNCC proforma spreadsheet see (Task 4.1); - Final edits culminating in the final draft of the procedural guideline submitted to JNCC (Task 4.2). |

Task 4.1: Conduct internal and external peer-review of draft guidance using pre-selected reviewers.

- The contractor is responsible for organising and carrying out an internal and external peer-review of the draft procedural guideline by the reviewers approved by JNCC. This includes contact with the reviewers, sending the documentation out and collecting the comments back in. This will take time. The contractor will need to account for this in their tender submission.

- JNCC intends to run a three-tiered review process, if time allows. The first review will be completed by JNCC staff. The second review will be conducted by a Project Steering Group pre-selected by JNCC. The third review will be completed by pre-selected external reviewers. The details and timetable of the review process will be discussed with the successful contractor at the appropriate time.

- Upon completion of the review, the contractor must collate each reviewer’s comments and proposed edits into the correct tab of the JNCC proforma spreadsheet (‘Objective 4 comments’).

- The contractor must address all comments as best they can and make the necessary amendments to the procedural guideline. The JNCC proforma spreadsheet tab ‘Objective 4 comments’ has a field for ‘action’ in which these amendments must be recorded.

- All comments which the contractor is unsure what to do must be submitted to the Contract Manager. The challenging comments and proposed edits in this list may be submitted to the PSG to decide what action to take.

Task 4.2: Make necessary amendments to the draft final guidance, proposed by the reviewers and accepted by the PSG.

- Once the PSG have agreed an action for the challenging comments and once the amendments already made by the contractor have been accepted, the contractor will be tasked with making the necessary amendments to the procedural guidance. The expectation is that this will be the draft of the final version of the procedural guideline.

### Objective 5

| 5 | To finalise the procedural guideline. | - Final version of procedural guideline (Tasks 5.1, 5.2). |
| --- | --- | --- |

Task 5.1: Conduct the final review of the procedural guideline.

- JNCC will conduct a review of the draft final procedural guideline. Again, the contractor must allow time for this to happen, although, owing to the tight turn around for this project (see time estimates in section 8), this review will be conducted over a shorter time frame than the first review.

- Again, the contractor must collate each reviewer’s comments and proposed edits into the correct tab of the JNCC proforma spreadsheet (‘Objective 4 comments’) and aim to address those they are confident with. As before, any comments which the contractor is unsure what to do with must be submitted to the Contract Manager. The challenging comments and proposed edits in this list may be submitted to the PSG to decide what action to take.

Task 5.2: Make final edits to the guidance to produce the final version of the procedural guideline.

- Once the PSG have agreed actions for outstanding challenging comments and once the amendments already made by the contractor have been accepted, the contractor will make the necessary amendments to the procedural guidance. The expectation is that this will be the final version of the procedural guideline.

- However, if JNCC decide this final version is not at the desired standard, the contractor will be required to make the necessary amendments until this standard is reached.

## Outputs

The following outputs are expected from this contract:

| Objective | Output |
| --- | --- |
| 1 | A. Completion of ‘Objective 1’ tab in JNCC proforma spreadsheet: - Documentation of literature review exploring the use of UAVs to monitor sublittoral habitats in the UK. - All spreadsheet fields populated as far as possible. B. Case studies summarised in word document. |
| 2 | Completion of ‘Objective 2’ and ‘Objective 2 costs’ tabs in JNCC proforma spreadsheet: - Summary table created for use of UAVs (table modification if different approaches are explored). |
| 3 | Completion of all sections of the JNCC procedural guideline template; - The draft guideline should be fully referenced; - The draft guideline should be around 8 pages or less in length, excluding any appendices, annexes, case studies or ‘top tips’; - The draft guideline should be written in a style that is accessible to a non-specialist audience; - The draft guideline must be ready for full external review. |
| 4 | - Send documentation to list of reviewers in JNCC proforma spreadsheet. - Collate comments and proposed edits from the external and internal reviewers in the JNCC proforma spreadsheet. - Completion of all edits to the draft guideline culminating in the production of the draft final procedural guideline. |
| 5 | - Collated comments and proposed edits from the second internal review in the JNCC proforma spreadsheet. - Completion of all edits to the draft guideline culminating in the production of the final procedural guideline. |

The contractor will be required to provide the relevant draft outputs for each objective for prior approval and quality checking by the PSG to ensure the documents are in line with expectations. The PSG may comment and propose edits to the draft outputs which must be incorporated into those relevant draft output documents.

## Dissemination

The report produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. It may also be made available under Open Government License The findings from this contract will also be made available to JNCC, the UK Conservation Agencies (Natural England, Natural Resources Wales, Scottish Natural Heritage, Department of Agriculture, Environment and Rural Affairs, Northern Ireland), Defra, the UK Healthy and Biologically Diverse Seas Evidence Group (HBDSEG), the Devolved Administrations, OSPAR Contracting Parties and EU Member States, as required, to feed into relevant projects at the national and international level.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | As soon as possible after award of contract (suggested Early-December 2018) |
| Objective 1: literature review complete and appropriate section of JNCC proforma spreadsheet submitted. Case studies complete. | Mid-January 2019 |
| Objective 2: method summary and cost estimates complete and appropriate section of JNCC proforma spreadsheet submitted. | Late January 2019 |
| Objective 3: write up draft procedural guideline using JNCC procedural guideline template. | Mid-February 2019 |
| Objective 4: Internal and external review finished and amended draft procedural guideline submitted with all comments and proposed edits from reviewers. | Late-February/Early March 2019 |
| Objective 5: internal review finished and draft procedural guideline amended, with comments and proposed edits from reviewers submitted | Second week of March 2019 |
| Objective 5: Final procedural guideline submitted | 15 March 2019 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The draft and final guidance must use the pre-constructed JNCC Procedural Guidance Template. This Template will be provided to the successful contractor at the initial start-up meeting. We shall also provide previous Marine Monitoring Platform Guidelines for reference. The draft and final guidance should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

The successful contractor must ensure this project is in compliance with the new JNCC Evidence Quality Assurance Policy. Tenderers are asked to note the Evidence Quality Assurance Policy document and Guidance Notes that accompany the Invitation to Tender.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Sophie Rush

Applied Marine Ecologist

Marine Monitoring and Evidence Team

Joint Nature Conservation Committee

Monkstone House

City Road

Peterborough

PE1 1JY

Email: sophie.rush@jncc.gov.uk

Tel: +44 (0)1733 866 913

Hayley Hinchen

Marine Habitats Monitoring Manager

Marine Monitoring and Evidence Team

Joint Nature Conservation Committee

Monkstone House

City Road

Peterborough

PE1 1JY

Email:  hayley.hinchen@jncc.gov.uk

Tel: +44 (0)1733 866 815

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 13);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft structure of how the appendices will likely be structured;

Details of Quality Control procedures to be followed (this should be in accordance with the new JNCC Evidence Quality Assurance Policy; tenderers are asked to note the Evidence Quality Assurance Policy document and Guidance Notes that accompany the Invitation to Tender);

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough during November/December 2018.

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 13.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs and understanding / experience of UAVs and marine habitat monitoring) | 10 |  |
|  | Soundness and logicality of methods | 7 |  |
|  | Realism and measurability of milestones | 6 |  |
|  | Identification and proposed solutions to potential problems/risks | 6 |  |
|  | Serious weaknesses which threaten success | 6 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (25 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 9 |  |
|  | Risks if important team members drop out | 7 |  |
|  | Adequacy of subcontractors (if any) | 9 |  |
|  | Sub Totals | 25 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 6 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 7 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

COGGAN, R., POPULUS, J., WHITE J., SHEEHAN, K., FITZPATRICK, F.& PIEL, S. 2007. Review of Standards and Protocols for Seabed Habitat Mapping. Mapping European Seabed Habitats (MESH), Peterborough, Available from: http://www.emodnet-seabedhabitats.eu/default.aspx?page=1442 (Accessed 24 October 2018).

DAVIES, J., BAXTER, J., BRADLEY, M., CONNOR, D., KHAN, J., MURRAY, E., SANDERSON, W., TURNBULL, C. & VINCENT, M., 2001. Marine Monitoring Handbook. Joint Nature Conservation Committee, Peterborough, Available from: http://jncc.defra.gov.uk/MarineMonitoringHandbook  (Accessed 24 October 2018).

HINCHEN, H., 2014. Review of marine biodiversity assessment obligations in the UK. Part I: A summary of the marine biodiversity assessment obligations stipulated within national and international legislative and policy instruments, JNCC Report 497, Available from: http://jncc.defra.gov.uk/page-6673 (Accessed 24 October 2018).

KLEMAS, V.V., 2015. Coastal and environmental remote sensing from unmanned aerial vehicles: An overview. Journal of

Coastal Research, 31(5), 1260–1267. Coconut Creek (Florida), ISSN 0749-0208, Available from: http://www.jcronline.org/doi/pdf/10.2112/JCOASTRES-D-15-00005.1 (Accessed 26 October 2018).

LECHNER, A.M., FLETCHER, A., JOHANSEN, K., & ERSKINE, P., 2012. Characterizing upland swamps using object-based classification

methods and hyper-spatial resolution imagery derived from an unmanned aerial vehicle. Proceedings of the XXII ISPRS Congress Annuals of the Photogrammetry, Remote Sensing and Spatial Information Sciences, Volume I–4 (Melbourne, Australia, ISPRS), pp. 101–106.

OLIVEIRA, M., RAJAN, K., SOUSA, J., & NIILER, E., 2013 Fish-tracking robots take to the seas and skies of Portugal. Monterey Bay Aquarium Research Institute News Release, 13 July 2013, pp. 1–3.

RAJAN, K., SOUSA, J., & NIILER, E., 2014. Eyes in the sky—And the sea. Discover, April 2014, p. 20.

ROBSON, L., 2014. Monitoring, assessment and reporting of UK benthic habitats: A rationalised list, JNCC Report 499, Available from: http://jncc.defra.gov.uk/page-6671 (Accessed 24 October 2018).

Appendix A –  Potential Relevant Literature List

Table 1 - Sourced from the Marine Monitoring Method Finder

| Title of guidance | Source | Year published | Weblink |
| --- | --- | --- | --- |
| Clean Seas Environment Monitoring Programme (CSEMP) Green Book | CSEMP | 2012 | https://www.cefas.co.uk/publications/greenbook/greenbookv15.pdf |
| JAMP Guidelines on Quality Assurance for Biological Monitoring in the OSPAR Area (Agreement 2002-15) | JAMP | 2015 | https://www.ospar.org/work-areas/cross-cutting-issues/cemp |
| Biological monitoring of marine Special Areas of Conservation: a review of methods for detecting change | JNCC | 1998 | http://jncc.defra.gov.uk/page-3817 |
| PG 6.2 Relocation of intertidal and subtidal sites | JNCC | 2001 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |
| Common Standards Monitoring Guidance for Generic Introduction for marine features | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| MESH Survey Scoping tool | MESH | 2008 | http://www.emodnet-seabedhabitats.eu/default.aspx?page=1931 |
| Designs for marine remote sampling: a review and discussion of sampling methods, layout, and scaling issues | UWA | 2004 | http://www.ozcoasts.gov.au/geom_geol/case_studies/pdf/CRC_CB3_mile2.1-1.pdf |
| A review of sublittoral monitoring methods in temperate waters: a focus on scale | UU | 2009 | http://www.ingentaconnect.com/content/sut/unwt/2009/00000028/00000003/art00004 |
| Monitoring guidance for marine benthic habitats | JNCC | 2017 | http://jncc.defra.gov.uk/page-7336 |
| Habitat mapping method suitability tool | DEFRA | 2015 | http://randd.defra.gov.uk/Default.aspx?Module=More&ProjectID=19533 |
| Common Standards Monitoring Guidance for Littoral sediment flats (mud/sand flats) | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| Common Standards Monitoring Guidance for Estuaries | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| Common Standards Monitoring Guidance for Inlets and Bays | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| Common Standards Monitoring Guidance for Sea Caves | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| Development of WFD intertidal seagrass classification tool | UKTAG | 2010 | http://www.wfduk.org/resources%20/transitional-and-coastal-waters-intertidal-seagrass |
| Common Standards Monitoring Guidance for Lagoons | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| Common Standards Monitoring Guidance for Saltmarsh | JNCC | 2005 | http://jncc.defra.gov.uk/page-2204 |
| Development of WFD rocky shore macroalgae tools | UKTAG | 2014 | http://www.wfduk.org/resources%20/coastal-waters-rocky-shore-macroalgae |
| Development of WFD opportunistic macroalgae tools | UKTAG | 2014 | http://www.wfduk.org/resources%20/transitional-and-coastal-waters-opportunistic-macroalgae |
| The role of seabed mapping techniques in environmental monitoring and management | CEFAS | 2006 | https://www.cefas.co.uk/publications/techrep/techrep127.pdf |
| Common Standards Monitoring Guidance for Littoral rock and inshore sublittoral rock (Reefs) | JNCC | 2004 | http://jncc.defra.gov.uk/page-2236 |
| PG 6.1 Positioning by differential GPS in near-shore tidal waters | JNCC | 2001 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |
| PG 1.1 Intertidal resource mapping using aerial photographs | JNCC | 2001 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |
| Review of standards and protocols for seabed habitat mapping | MESH | 2007 | http://www.emodnet-seabedhabitats.eu/default.aspx?page=1442 |
| Aerial photography | MESH | 2007 | http://www.emodnet-seabedhabitats.eu/ROGs |
| Airbourne digital imagery | MESH | 2007 | http://www.emodnet-seabedhabitats.eu/ROGs |
| High resolution satellite imagery | MESH | 2007 | http://www.emodnet-seabedhabitats.eu/ROGs |
| LiDAR | MESH Atlantic | 2012 | http://www.emodnet-seabedhabitats.eu/ROGs |
| WFD assessment method for angiosperms (Saltmarsh tool) | UKTAG | 2014 | http://www.wfduk.org/resources/transitional-and-coastal-waters-saltmarsh |
| WFD assessment method for intertidal seagrass | UKTAG | 2014 | http://www.wfduk.org/resources%20/transitional-and-coastal-waters-intertidal-seagrass |
| WFD assessment method for phytoplankton in coastal waters | UKTAG | 2014 | http://www.wfduk.org/resources%20/coastal-waters-phytoplankton |
| PG 1.6 Monitoring Biotope Richness using Remote Video | JNCC | 2005 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |
| WFD assessment method for opportunistic macroalgae (greens) | UKTAG | 2014 | http://www.wfduk.org/resources%20/transitional-and-coastal-waters-opportunistic-macroalgae |
| WFD assessment of fucoid extent in transitional waters | UKTAG | 2014 | http://www.wfduk.org/resources%20/transitional-waters-macroalgae-fucoid-extent |
| WFD assessment method for rocky shore macroalgae | UKTAG | 2014 | http://www.wfduk.org/resources%20/coastal-waters-rocky-shore-macroalgae |
| Epibiota remote monitoring from digital imagery - operational guidelines | NMBAQC | 2015 | http://www.nmbaqcs.org/scheme-components/epibiota/reports/ |
| Epibiota remote monitoring from digital imagery - interpretation guidelines | NMBAQC | 2016 | http://www.nmbaqcs.org/scheme-components/epibiota/reports/ |
| PG 3.11 Littoral monitoring using fixed quadrat photography | JNCC | 2001 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |
| PG 3.12 Quantitative surveillance of sublittoral rock biotopes and species using photographs | JNCC | 2001 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |
| PG 3.5 Identifying biotopes using video recordings | JNCC | 2001 | http://jncc.defra.gov.uk/MarineMonitoringHandbook |

Appendix B – Monitoring Habitats

Table 2. List of potentially relevant marine benthic habitats to be monitored in the UK. All habitats are considered to be ‘monitoring habitats’ unless marked by an asterisk (*), in which case they are from the ‘rationalised list of marine habitats’ (Robson et al., 2014). The general working environment and biotopes included in the habitat are included to provide extra information on the habitat.

| Working environment | Habitat | Biotopes included |
| --- | --- | --- |
| Coastal | Annual vegetation of drift lines (Cakiletea maritimae class) | A2.511, A2.515 |
| Coastal | Coastal saltmarsh | A2.5 |
| Intertidal | Intertidal coarse sediment | A2.1 |
| Intertidal | Intertidal mixed sediments | A2.4 |
| Intertidal | Littoral Mud and Sand | A2.2, A2.3 |
| Intertidal | Ephemeral intertidal seaweeds | A2.82 |
| Intertidal | High energy intertidal rock | A1.11, A1.12 |
| Intertidal | Intertidal boulder communities | A1.2142, A3.2112 |
| Intertidal | Intertidal rockpools | A1.41, A1.42 |
| Intertidal | Intertidal soft rock communities | A1.126, A1.127, A1.2143, A1.223, A1.441, B3.114, B3.115 |
| Intertidal | Littoral cave and overhang fauna * | A1.44 |
| Intertidal | Low energy intertidal rock | A1.31 |
| Intertidal | Moderate energy intertidal rock | A1.2 [excluding A1.2142 and A1.223] |
| Intertidal | Sabellaria alveolata reefs | A4.22, A5.611 |
| Both Intertidal and Subtidal | Fouling communities | A3.72, A4.72 |
| Both Intertidal and Subtidal | Angiosperm communities in reduced salinity | A5.541 |
| Both Intertidal and Subtidal | Estuaries * |  |
| Both Intertidal and Subtidal | Seagrass beds / zostera beds | A2.61, A5.53 |
| Both Intertidal and Subtidal | Estuarine rocky habitats | A1.32, A1.45, A3.321, A3.322, A3.323, A3.361 |
| Both Intertidal and Subtidal | Blue mussel beds | A2.212, A2.721, A3.361, A5.625 |
| Both Intertidal and Subtidal | Ostrea edulis beds | A5.435 |
| Subtidal | File/flame shell beds (Limaria hians) | A5.434 |
| Subtidal | Kelp and seaweed communities on sublittoral sediment | A5.52 (excluding A5.526 and A5.528) |
| Subtidal | Maerl or coarse shell gravel with burrowing sea cucumbers (Neopentadactyla mixta) | A5.144 |
| Subtidal | Shallow sublittoral coarse sediment | A5.12, A5.13, A5.14 |
| Subtidal | Shallow sublittoral mixed sediments | A5.42, A5.43, A5.44 (excluding A5.434 and A5.435) |
| Subtidal | Shallow sublittoral mud | A5.32, A5.33, A5.34, A5.35, A5.36 |
| Subtidal | Shallow sublittoral sand | A5.22, A5.23, A5.24, A5.25, A5.26 |
| Subtidal | Shallow tideswept coarse sands with burrowing bivalves | A5.133 |
| Subtidal | Shelf sublittoral coarse sediment | A5.15 |
| Subtidal | Shelf sublittoral mixed sediments | A5.45 |
| Subtidal | Shelf sublittoral mud | A5.37 |
| Subtidal | Shelf sublittoral sand | A5.27 |
| Subtidal | Coral gardens | A6.1, A6.2, A6.3, A6.4, A6.5, A6.7, A6.8, A6.9 |
| Subtidal | Fragile sponge and anthozoan communities on subtidal rocky habitats including northern seafan and sponge communities | A4.12, A4.131, A4.133, A4.211 |
| Subtidal | High energy circalittoral rock | A4.11, most A4.13 biotopes |
| Subtidal | High energy infralittoral rock | A3.11 [excluding kelp bed biotopes], A3.12 [excluding A3.126] |
| Subtidal | Kelp beds | A3.113, A3.115, A3.2122, A3.2141-2144 |
| Subtidal | Low energy circalittoral rock | A4.3 |
| Subtidal | Low energy infralittoral rock | A3.31 |
| Subtidal | Moderate energy circalittoral rock | A4.2 [excluding A4.22] |
| Subtidal | Moderate energy infralittoral rock | A3.21 (excluding A3.2112), A3.22 [excluding kelp and seaweed biotopes] |
| Subtidal | Musculus discors beds | A4.242 |
| Subtidal | Subtidal soft rock communities | A3.2113, A3.217, A4.23, A4.231 |
| Subtidal | Surge gully and cave fauna * | A3.71, A4.71 |
| Subtidal | Tide-swept algal communities | A1.15, A3.126 , A3.213, A3.22 |
| Subtidal | Horse mussel beds | A5.621, A5.622, A5.623, A5.624 |
| Subtidal | Maerl beds | A5.51 |
| Subtidal | Sabellaria spinulosa reefs | A2.71, A5.612 |
| Subtidal | Serpula vermicularis reefs | A5.613 |

Marine Monitoring Method Finder. URL: http://jncc.defra.gov.uk/default.aspx?page=7171.

Marine Monitoring Handbook. URL: http://jncc.defra.gov.uk/page-2430.

Common Standards Monitoring. URL: http://jncc.defra.gov.uk/page-2236.

Mapping European Seabed Habitats. URL: http://jncc.defra.gov.uk/page-1542.

United Kingdom Technical Advisory Group. URL: http://www.wfduk.org/.

NE Atlantic Marine Biological Analytical Quality Control Scheme. URL: http://www.nmbaqcs.org/.

Pollution Response in Emergencies: Marine Impact Assessment and Monitoring. URL: https://www.cefas.co.uk/premiam/.

OSPAR Intermediate Assessment 2017. URL:  https://oap.ospar.org/en/ospar-assessments/intermediate-assessment-2017//.

Open Government License ((http://www.nationalarchives.gov.uk/doc/open-government-licence/version/3/).

Marine Monitoring Platform Guidelines (http://jncc.defra.gov.uk/page-7610)

Marine Monitoring Method Finder (http://jncc.defra.gov.uk/page-7171)