|  |  |  |  | SW1A 2BQ |  |
| --- | --- | --- | --- | --- | --- |
|  | Jigsaw Research W1T 3LA |  |  |  |  |
|  |  |  |  | Tel |  |
|  |  |  |  | Fax |  |
|  |  |  |  | www.hmrc.gov.uk |  |
|  | Date | 27th July 2016 |  |  |  |
|  | Our Ref |  |  | DX: |  |
| ________ | Your Ref |  |  |  |  |
|  |  | Commercial - In Confidence |  |  |  |

Dear

# Service Order: Exploring Business reporting errors and how these can be addressed within software design for the MTD Transformation Team.

Assignment under the Market Research Framework MR130001

I refer to the Market Research MR130001 Framework Agreement contract. This letter is to formally issue an assignment under this framework titled Exploring Business reporting errors and how these can be addressed within software design. This project is a second phase of work from the original research specification of ‘Exploring Business customers’ and Agents engagement with Making Tax Digital’, as outlined in the brief.

The assignment is detailed in the following documents:

- HMRC’s specification of requirements of 5th July 2016 for this assignment.

- Your revised proposal of 26th July 2016.

#### A revised sample design was agreed on the 26th July 2016 and is detailed at slide 16 of the revised proposal.

- The Market Research MR130001 Framework Contract (which comprises HMRC’s specification and ITT, your final proposal, plus the terms and conditions of the contract). Unless specifically amended by the assignment specification or proposal, in all other regards the terms and conditions of the framework agreement apply. For the purpose of this assignment the ‘notice period’ shall be 2 weeks’.

The formal start date of this assignment is the date of this letter. The assignment is estimated to be completed by late October/early November 2016.

The total cost of the assignment is fixed at £49,750 (excluding VAT which will be charged at the appropriate rate. The invoice schedule is as follows:

| Invoice Schedule |  |  |  |
| --- | --- | --- | --- |
| Approximate Date | % a | Amount to be invoiced | Milestones a |
| 27/07/16 | 30% | £14,925 + VAT | Following initiation meeting. |
| 29/08/16 | 30% | £14,925 + VAT | Completion of Phase 1: Toplines to HMRC |
| 28/10/16 | 40% | £19,900 + VAT | On satisfactory completion of project. |
| Total | 100% | £49,750 + VAT |  |
| Notes a According to those agreed under the Framework Agreement. |  |  |  |

To note the final invoice is subject to the satisfactory (to the Department) completion of all aspects of the work. The Department’s nominated officer for the project is Jane Breeze.

Could you please ensure that the following PO Number is quoted on all invoices for this project:

Could you please e-mail to confirm agreement with the terms of this assignment under the Market Research MR130001 Framework Agreement?

Yours faithfully,

NB ‘Personal’, ‘Confidential’ and ‘Commercial’ sensitive information has been redacted according to the provisions in the FOI Act (sections 40, 41 & 42).