## Sheet1
CLARIFICATION LOG
Tender: | Structural Groundworks and site modifications
Tender Reference: | BUS003_0081_1.6
Published Date: | 2024-10-22
Version number: | 0.2
Number | Clarification | Response | Reply date
1 | The documents downloaded indicate Concrete piling, is this correct, or are you looking for a Steel sheet piling alternative | Having consulted with our structural engineers, a sheet piled alternative should not be pursued. It is best to keep with the ODEX piles due to the ground conditions. It is extremely important that the piling contractor reviews the ground investigation report from Karn Geo and proposes and designs an appropriate piling system to suit the ground conditions and to support the new slab. The NBS (Specification) and Designers Risk Assessment should also be thoroughly reviewed. It is anticipated that there will be a significant amount of obstructions within the ground owing to the historical use and changes to the building which should be considered. | 2024-10-29
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie.george@linkedsolutionsmarine.com