## 4. Schedule of Works
SPECIFICATION DOCUMENT
Osney Lock House
SCHEDULE OF WORKS
Ref. | Description | £ | p
4 | SCHEDULE OF WORKS
4.1 | EXTERNAL FABRIC WORKS
4.1.1 | The contractor is to allow to remove and dispose the timber blanking plates that have been installed externally over the below ground floor vents at low level. This is to the following 3 No. locations. Allow to make good surfaces: - Below the Kitchen window (right hand side elevation). - Below the Living Room window (rear elevation). - Below the Living Room window (left hand side elevation).
4.1.2 | The contractor is to allow to carefully supply and install new mastic sealant around the existing vertical uPVC pipe, where it protrudes the roof of the utility boxing surround. This is located to the right hand elevation. Allow to install new mastic (clear in colour) to prevent any water ingress occurring below. Then the contractor is to then supply and install a new suitable pipe collar / surround around the vertical pipe and leave secure and watertight. Colour: Black.
4.2 | INTERNAL FABRIC WORKS
4.2.1 | Floors
4.2.1.1 | The contractor is to allow to retain the existing carpet floor finishes within the Living Room, Dining Room, Bedroom 2 and Bedroom 3 of the property. Include to repair, stretch and fix any areas of loose carpet to ensure a suitable finish. Include to deep clean all surfaces. Where required install new gripper rods etc., to ensure a secure finish.
4.2.1.2 | The contractor is to carefully remove all of the existing vinyl floor covering from the Ground Floor Toilet and Rear Lobby area, including all residue adhesive, trims and associated surfaces etc. and dispose. Prepare surfaces and leave ready for new covering.
4.2.1.3 | Following the safe and correct removal of the vinyl floor covering in the Ground Floor Toilet and Rear Lobby area (see item above), the contractor is to sweep, clear and clean the floor in readiness for the new floor covering to be installed. Then allow to supply and install new Polyflor Expona Commercial flooring throughout. All joints to be welded. Where required allow for a latex levelling screed to be applied to the concrete floor throughout. All works to be in accordance with manufacturer's recommendations and guidelines. Range: Polyflor Expona Commercial vinyl flooring. Style: To be confirmed by the Environment Agency.
4.2.1.4 | Following the replacement of the vinyl flooring in the Ground Floor Toilet and Rear Lobby area (see item above), the contractor is to supply and install new mastic sealant to the perimeter edges, where the floor abuts the walls, skirting and sanitaryware. All works to be in accordance with manufacturer's recommendations and guidelines. Colour of sealant: White.
4.2.1.5 | The contractor is to carefully remove and dispose of the existing nosing to the small step detail between the Rear Lobby and Kitchen floors and make good all affected surfaces. Then allow to supply and install a new aluminium nosing to this step detail. All works to be in accordance with manufacturer's recommendations and guidelines. Colour: Silver.
4.2.1.6 | The contractor is to carefully remove all of the existing vinyl floor covering from the Kitchen including all residue adhesive, trims, any backing boarding and associated surfaces etc. and dispose. Prepare surfaces and leave ready for new covering.
4.2.1.7 | Following the safe and correct removal of the vinyl floor covering in the Kitchen (see item above), the contractor is to sweep, clear and clean the floor in readiness for the new floor covering to be installed. Supply and install new 6mm WBP backing board throughout the floor area to provide a level surface for the new covering. Then allow to supply and install new Polyflor Expona Commercial flooring throughout. All joints to be welded. Where required allow for any latex levelling screed to be applied. Ensure a smooth and level finish is provided throughout. All works to be in accordance with manufacturer's recommendations and guidelines. Range: Polyflor Expona Commercial vinyl flooring. Style: To be confirmed by the Environment Agency.
4.2.1.8 | Following the replacement of the vinyl flooring in the Kitchen (see item above), the contractor is to supply and install new mastic sealant to the perimeter edges, where the floor abuts the walls, skirting and kitchen units. All works to be in accordance with manufacturer's recommendations and guidelines. Colour of sealant: White.
4.2.1.9 | The contractor is to carefully remove all of the existing vinyl floor covering from the Bathroom including all residue adhesive, trims and associated surfaces etc. and dispose. Prepare surfaces and leave ready for new covering.
4.2.1.10 | Following the safe and correct removal of the vinyl floor covering in the Bathroom (see item above), the contractor is to sweep, clear and clean the floor in readiness for the new floor covering to be installed. Supply and install new 6mm WBP backing board throughout the floor area to provide a level surface for the new covering. Then allow to supply and install new Polyflor Expona Commercial flooring throughout. All joints to be welded. Where required allow for any latex levelling screed to be applied. Ensure a smooth and level finish is provided throughout. All works to be in accordance with manufacturer's recommendations and guidelines. Range: Polyflor Expona Commercial "Smoked Beam" (code: 4033).
4.2.1.11 | Following the replacement of the vinyl flooring in the Bathroom (see item above), the contractor is to supply and install new mastic sealant to the perimeter edges, where the floor abuts the walls, bath panel, boxing and sanitaryware. Including around the toilet. All works to be in accordance with manufacturer's recommendations and guidelines. Colour of sealant: White.
4.2.1.12 | Following the replacement of the vinyl flooring in the Bathroom (see items above), the contractor is to remove the existing threshold bar with the junction of the Bathroom and the Hallway. Then allow to supply and install aluminium threshold bar to the Bathroom door threshold. Colour: Silver.
4.2.1.13 | The contractor is to carefully remove and dispose all of the existing carpet floor covering provided within the ground floor Hallway, Staircase and First Floor Landing, including all remaining adhesive, gripper rods etc. Prepare surfaces and leave ready for new covering. Allow to refix any loose floorboards, sweep, clear and clean the floor and leave in readiness for the new carpet floor covering. Then the contractor is to allow to supply and install new carpet and suitable grade underlay throughout the ground floor Hallway, Staircase and First Floor Landing. All new flooring (carpet and underlay) to be laid in accordance with manufacturer’s instructions, including all new underlay, fixings, gripper rods etc. For initial pricing purposes, allow for Cormar Carpet, Easy Clean, "Primo Plus" range. However the final range, colour and style to be confirmed by Environment Agency.
4.2.1.14 | The contractor is to carefully remove and dispose all of the existing carpet floor covering provided within Bedroom 1 (apart from the retained section required for the eaves storage cupboard - see item 4.2.1.13 below), including all remaining adhesive, gripper rods etc. Prepare surfaces and leave ready for new covering. Allow to refix any loose floorboards, sweep, clear and clean the floor and leave in readiness for the new carpet floor covering. Then the contractor is to allow to supply and install new carpet and suitable grade underlay throughout Bedroom 1. All new flooring (carpet and underlay) to be laid in accordance with manufacturer’s instructions, including all new underlay, fixings, gripper rods etc. For initial pricing purposes, allow for Cormar Carpet, Easy Clean, "Primo Plus" range. However the final range, colour and style to be confirmed by Environment Agency.
4.2.1.15 | The contractor is to note that following the required removal of the existing carpet within Bedroom 1 (see item 4.2.1.12 above), the contractor is to reuse part of the carpet (suitable condition) and allow to cut to size and install the required amount of carpet within the eaves storage area within Bedroom 1. Allow to securely fit throughout the cupboard.
4.2.2 | Walls
4.2.2.1 | The contractor is to carefully remove and dispose of the numerous recessed wall fixings to the section of wall below the window in the Rear Lobby area (between the Ground Floor Toilet and the Kitchen). Allow to fill and make good all surfaces and leave level and smooth with surrounding surfaces. Prepare surfaces and leave ready for decoration.
4.2.2.2 | The contractor is to carefully remove and dispose of all the existing and remaining plaster / adhesive to the wall above the Living Room fireplace / opening. Include for making good the section of wall, applying base coat and finishing with British Gypsum 3mm Thistle Multi-Finish top coat plaster. Include for making good the detailing between the existing boarding at lower level (surrounding the fire opening) and the new section of plastered wall above. Prepare surfaces and leave ready for decoration.
4.2.2.3 | The contractor is to carefully remove and dispose of the 4 No. recessed wall fixings to the right hand side of the door, in the Dining Room. Allow to fill and make good all surfaces and leave level and smooth with surrounding surfaces. Prepare surfaces and leave ready for decoration.
4.2.2.4 | The contractor is to carefully remove and dispose of the 4 No. recessed wall fixings at high level, to the right hand side of the door, in the Dining Room. Allow to fill and make good all surfaces and leave level and smooth with surrounding surfaces. Prepare surfaces and leave ready for decoration.
4.2.2.5 | The contractor is to carefully remove and dispose of the 4 No. recessed wall fixings to at high level, between the windows in the Dining Room. Allow to fill and make good all surfaces and leave level and smooth with surrounding surfaces. Prepare surfaces and leave ready for decoration.
4.2.2.6 | The contractor is to carefully fill and make good the hole in the Bathroom wall, between the high level extract and the isolator switch. Make good surfaces, leave smooth and ready for decoration.
4.2.2.7 | The contractor is to supply and install a new timber skirting to the section of wall forming the staircase (opposite the Dining Room door). The new skirting is to match the size, style and profile of the existing skirting within the Hallway. Ensure new skirting is well secured and fixed throughout and then leave ready for decoration.
4.2.2.8 | The contractor is to refix the loose cable back to the wall in the Hallway, using suitable cable fixing clips with screws (Tillex similar approved). This is to the right hand side of the main front entrance door. Ensure cable is tightly positioned and secure.
4.2.2.9 | The contractor is to carefully remove and dispose the existing redundant (cut off) / loose cable and fixing clips from the wall around the Bathroom door, including the data point (located at low level). Make good all affected surfaces, leave smooth and ready for decoration.
4.2.2.10 | The contractor is to supply, form and install new timber boxing section in the Bathroom (to cover the exposed pipework), between the bath and the vanity unit. The new boxing is to match the size, style and profile of the existing skirting and bath panel. Ensure new boxing is well secured and fixed throughout and then leave ready for decoration.
4.2.2.11 | The contractor is to supply and install new sections of plastic edge trim around the window in the Bathroom. The new trim is to be installed to the tiled section of window cill, as well as to the left hand right hand tiled reveals. The new plastic trim is to match the size, style and profile of the existing trim within the window reveal. Colour: White.
4.2.2.12 | The contractor is to refix the loose cable back to the wall in Bedroom 1, using suitable cable fixing clips with screws (Tillex similar approved). This is to the left hand side of the chimney. Ensure cable is tightly positioned and secure.
4.2.2.13 | The contractor is to carefully remove and dispose of the existing ventilation grille from the chimney opening in Bedroom 1. Allow to clear out opening where required. Then supply and install new Map Vent plastic adjustable vent (or similar approved). Fix flush to surrounding wall surfaces. Install as per manufacturer's guidelines. Size: to match existing / opening in wall.
4.2.2.14 | The contractor carefully remove and dispose of the remaining timber structure that forms the wardrobe in Bedroom 1. This includes the timber frame, supports, high level panel, soffit, fixings, clothes rail etc. Allow to make good all affected wall, floor, skirting and ceiling surfaces.
4.2.2.15 | The contractor is to carefully remove and dispose of the 2 No. recessed wall fixings to the right hand side of the door of Bedroom 2. Allow to fill and make good all surfaces and leave level and smooth with surrounding surfaces. Prepare surfaces and leave ready for decoration.
4.2.2.16 | The contractor is to allow a Provisional Amount of 10 sqm (over and above the areas stated within the rest of this schedule of works), to allow to hack off any damp or blown areas of plaster to the walls and allow for the Contract Administrator to inspect the areas prior to undertaking any plastering / plaster repairs. Include for making good walls, applying base coat and finishing with British Gypsum 3mm Thistle Multi-Finish top coat plaster. Include for removing areas of lining paper to areas where wallpaper has been applied. Exact locations are to be confirmed by the Ridge & Partners LLP and the Environment Agency.
4.2.3 | Windows & Doors
4.2.3.1 | The contractor is to retain the existing window blinds within the Kitchen. Allow to ease and adjust (if required) and clean all surfaces / fixings / slats etc., using a non abrasive solution.
4.2.3.2 | The contractor is to retain all of the curtain rail poles, support brackets and stop ends throughout the property (living room, dining room and bedrooms). Clean all surfaces using a non abrasive solution.
4.2.3.3 | The contractor is to remove and dispose of the existing window blind and associated track in the Bathroom. Allow to make good all surfaces. Then allow to supply and install a new roller blind to fit the window opening. Include for all associated fixings, brackets and operational winder / chain. Colour: Grey.
4.2.3.4 | The contractor is to allow a Provisional Sum of £500.00 to overhaul the windows, including allowing to repair (or replace, if beyond repair) the catches, restrictors, handles, locks etc. Ensure all windows are left in a suitable working condition.
4.2.3.5 | The contractor is to overhaul and refix and secure the loose door handle to the door of the Ground Floor Toilet.
4.2.3.6 | The contractor is to remove the existing lock and associated fixings (located at high level to the Hallway side) to the Dining Room door. Allow to make good all affected surfaces to he door and the frame / architrave.
4.2.3.7 | The contractor is to note that the existing internal doors are to remain. As a result, allow a Provisional Sum of £500.00 to overhaul, repair, ease and adjust the retained timber doors and associated ironmongery, including door handles and rim locks etc. Ensure they are left in a suitable working condition, handles are secure and are able to open and close correctly within their frames.
4.2.4 | Bathroom
4.2.4.1 | The contractor is to note that the existing sanitaryware is to remain (toilet, wash hand basin, bath and shower). Allow to check all existing pipework and connections etc., to ensure no leaks are present and the installations are working correctly. Following this, allow to thoroughly deep clean the retained sanitaryware and associated pipework, using a non abrasive solution.
4.2.4.2 | The contractor is to rake out all existing mastic sealant from around the joint of the retained wash hand basin and surrounding vanity unit. Then allow to supply and install new mastic. Make good affected surfaces. Colour: Clear. Install as per manufacturer's guidelines.
4.2.4.3 | The contractor is to supply and install new chrome plated shower door knob (where missing) to both sides of the existing glazed shower door. Ensure installations are securely installed as per manufacturer's guidelines.
4.2.4.4 | The contractor is to supply and install a new chrome drain outlet retainer, plug and chain for the bath.
4.2.4.5 | The contractor is to supply and install a new chrome drain outlet retainer, plug and chain for the wash hand basin.
4.2.4.6 | The contractor is to supply and install a new chrome overflow outlet for the wash hand basin.
4.2.4.7 | The contractor is to remove and dispose of the existing 1 No. toilet seat, including all associated fixings etc. Supply and install new duraplast soft-close toilet seat and lid. Include for all associated fixings. Size to correctly match that of the toilet. Colour: To match colour of toilet. Install as per manufacturer's guidelines and recommendations.
4.2.4.8 | The contractor is to carefully remove and dispose of the existing plastic seal / edge trim detail to the bottom of the glazed shower door. Allow to clean all surfaces and then instal new clear trim (full width). Ensure the trim and the door are watertight.
4.2.5 | Ground Floor Toilet
4.2.5.1 | The contractor is to note that the existing sanitaryware forming the ground floor toilet (wash hand basin and toilet) is to remain. Allow to check all existing pipework and connections etc., to ensure no leaks are present and the installations are working correctly. Following this, allow to thoroughly deep clean the retained sanitaryware and associated pipework, using a non abrasive solution.
4.2.5.2 | The contractor is to supply and install a new chrome handle to the toilet cistern (from www.screwfix.com or similar approved. Ensure all mechanisms forming the flush of the toilet and cistern are left in suitable working condition. Allow to install as per manufacturer's guidelines.
4.2.5.3 | The contractor is to supply and install a new chrome drain outlet retainer, plug and chain for the wash hand basin.
4.2.6 | Kitchen Units & Surfaces Etc.
4.2.6.1 | The contractor is to allow to clean down and remove all grease and staining to all retained kitchen wall tiling, base units, cupboards and worksurfaces etc., using a non abrasive solution.
4.2.6.2 | The contractor is to allow to liaise with the Environment Agency's Term Electrical contractor within regards to any kitchen works.
4.2.6.3 | The contractor is to include for resealing all the joint between the worksurface upstand and the retained wall tiling and the joint around the sink with silicone. Colour: Clear.
4.2.6.4 | The contractor is to supply and install a new kitchen unit to the enclose the existing wall mounted boiler and associated pipework. Allow for all fixings and supports etc. Include for unit door and ironmongery. This is to fit between the existing and retained wall tiling and the ceiling. New unit to match existing kitchen units in terms of style, profile, colour etc.
4.2.6.5 | The contractor is to supply and install a new metal angle trim to the corner of the worksurface opposite the 2 No. window cills. Allow to securely fix. Colour: Black.
4.2.6.6 | The contractor is to carefully remove and dispose the existing tap provided to the kitchen sink. Then allow to supply and install a new Bristan Monza Monobloc Sink Mixer in Chrome kitchen tap and sink outlet (or similar approved). Allow to install and fix in accordance with manufacturer's recommendations and guidance.
4.2.7 | Ceilings - Generally
4.2.7.1 | The contractor is to allow to liaise with the separate Environment Agency's Term Electrical Contractor, in relation to the existing electrical installations, prior to undertaking any works to the ceilings (removal , repairs, replastering etc.).
4.2.7.2 | The contractor is to allow a Provisional Amount of 5 sqm (over and above the areas stated within the rest of this schedule of works), to allow to hack off any damp or blown areas of plaster to the ceilings and allow for the Contract Administrator to inspect the areas prior to undertaking any plastering / plaster repairs. Include for making good walls, applying base coat and finishing with British Gypsum 3mm Thistle Multi-Finish top coat plaster. Include for removing areas of lining paper to areas where wallpaper has been applied. Exact locations are to be confirmed by the Ridge & Partners LLP and the Environment Agency.
4.2.8 | Ceilings - Bedroom 1
4.2.8.1 | The contractor is to note that the following works specified to the skeeling areas within Bedroom 1 are to provide an increase in thermal insulation to the skeeling section of the ceiling in this room. The proposed works, as detailed below allow for additional insulated plasterboard to be installed to the existing plasterboard skeeling surface.
4.2.8.2 | The contractor is to rub down, prepare and leave ready the existing skeeling within Bedroom 1 (see location in Appendix B: First Floor Skeeling Drawing), in order to receive proposed works.
4.2.8.3 | The contractor is to supply and install new British Gypsum Gyproc ThermaLine Plus (40mm) insulated backed plasterboard (or similar approved) to the affected skeeling area in Bedroom 1. New plasterboard to be correctly fitted to the existing / retained plasterboard surfaces. Allow to securely fix, seal, tape and joint. Allow to make good all surrounding surfaces where disturbed. Leave ready for plaster top coat finish. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations.
4.2.8.4 | Following the installation of the new insulated backed plasterboard to the skeeling section of the ceiling within Bedroom 1 (see item 4.2.8.3 above), the contractor is to plaster all of the new skeeling surface with British Gypsum 3mm Thistle Multi-Finish top coat. Include to make good all areas around the edges of the ceiling and where the main ceiling abuts the new skeeling, as well as any other surfaces etc. Ensure all works to be in accordance with manufacturer's instructions and recommendations. Leave ready for decoration.
4.2.9 | Ceilings - Bedroom 2
4.2.9.1 | The contractor is to note that the following works specified to the skeeling areas within Bedroom 2 are to provide an increase in thermal insulation to the skeeling section of the ceiling in this room. The proposed works, as detailed below allow for additional insulated plasterboard to be installed to the existing plasterboard skeeling surface.
4.2.9.2 | The contractor is to rub down, prepare and leave ready the existing skeeling within Bedroom 2 (see location in Appendix B: First Floor Skeeling Drawing), in order to receive proposed works.
4.2.9.3 | The contractor is to supply and install new British Gypsum Gyproc ThermaLine Plus (40mm) insulated backed plasterboard (or similar approved) to the affected skeeling area in Bedroom 2. New plasterboard to be correctly fitted to the existing / retained plasterboard surfaces. Allow to securely fix, seal, tape and joint. Allow to make good all surrounding surfaces where disturbed. Leave ready for plaster top coat finish. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations.
4.2.9.4 | Following the installation of the new insulated backed plasterboard to the skeeling section of the ceiling within Bedroom 2 (see item 4.2.9.3 above), the contractor is to plaster all of the new skeeling surface with British Gypsum 3mm Thistle Multi-Finish top coat. Include to make good all areas around the edges of the ceiling and where the main ceiling abuts the new skeeling, as well as any other surfaces etc. Ensure all works to be in accordance with manufacturer's instructions and recommendations. Leave ready for decoration.
4.2.10 | Ceilings - Bedroom 3
4.2.10.1 | The contractor is to note that the following works specified to the skeeling areas within Bedroom 3 are to provide an increase in thermal insulation to the skeeling section of the ceiling in this room. The proposed works, as detailed below allow for additional insulated plasterboard to be installed to the existing plasterboard skeeling surface.
4.2.10.2 | The contractor is to rub down, prepare and leave ready the existing skeeling within Bedroom 3 (see location in Appendix B: First Floor Skeeling Drawing), in order to receive proposed works.
4.2.10.3 | The contractor is to supply and install new British Gypsum Gyproc ThermaLine Plus (40mm) insulated backed plasterboard (or similar approved) to the affected skeeling area in Bedroom 3. New plasterboard to be correctly fitted to the existing / retained plasterboard surfaces. Allow to securely fix, seal, tape and joint. Allow to make good all surrounding surfaces where disturbed. Leave ready for plaster top coat finish. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations.
4.2.10.4 | Following the installation of the new insulated backed plasterboard to the skeeling section of the ceiling within Bedroom 3 (see item 4.2.10.3 above), the contractor is to plaster all of the new skeeling surface with British Gypsum 3mm Thistle Multi-Finish top coat. Include to make good all areas around the edges of the ceiling and where the main ceiling abuts the new skeeling, as well as any other surfaces etc. Ensure all works to be in accordance with manufacturer's instructions and recommendations. Leave ready for decoration.
4.2.11 | Ceilings - Stairwell
4.2.11.1 | The contractor is to note that the following works specified to the skeeling areas within the Stairwell are to provide an increase in thermal insulation to the skeeling section of the ceiling in this area. The proposed works, as detailed below allow for additional insulated plasterboard to be installed to the existing plasterboard skeeling surface.
4.2.11.2 | The contractor is to rub down, prepare and leave ready the existing skeeling within the Stairwell area (see location in Appendix B: Ground & First Floor Skeeling Drawings), in order to receive proposed works.
4.2.11.3 | The contractor is to supply and install new British Gypsum Gyproc ThermaLine Plus (40mm) insulated backed plasterboard (or similar approved) to the affected skeeling area in the Stairwell. New plasterboard to be correctly fitted to the existing / retained plasterboard surfaces. Allow to securely fix, seal, tape and joint. Allow to make good all surrounding surfaces where disturbed. Include to install and correctly detail in adjacent to the existing purlin. Leave ready for plaster top coat finish. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations.
4.2.11.4 | The contractor is to supply and install new British Gypsum Gyproc ThermaLine Plus (27mm) or British Gypsum Gyproc ThermaLine Basic (22mm) insulated backed plasterboard (or similar approved) - size / thickness dependent on space available in the opening. This is to be installed to the left, right, bottom and top reveals around the existing Velux window. New plasterboard to be correctly fitted to the existing / retained plasterboard surfaces. Allow to securely fix, seal, tape and joint. Allow to make good all surrounding surfaces where disturbed. Include to install and correctly detail the reveals corners. Ensure the existing Velux window can correctly open, close and lock. Leave ready for plaster top coat finish. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations.
4.2.11.5 | Following the installation of the new insulated backed plasterboard to the skeeling section of the ceiling within the Stairwell (see items 4.2.11.3 and 4.2.11.4 above), the contractor is to plaster all of the new skeeling surface with British Gypsum 3mm Thistle Multi-Finish top coat. Include to make good all areas around the edges of the ceiling and the purlin and where the main ceiling abuts the new skeeling, as well as any other surfaces etc. Ensure all works to be in accordance with manufacturer's instructions and recommendations. Leave ready for decoration.
4.2.12 | Velux Stairwell Window
4.2.12.1 | The contractor is to ease, adjust, overall and clean the 1 No. Velux window and associated frame, located within the stairwell area. Retain access pole.
4.2.13 | Bedroom 1 - Eaves Storage Cupboard
4.2.13.1 | The contractor is to note that the following works specified within the Eaves Storage Cupboard of Bedroom 1 are to provide an increase in thermal insulation. The proposed works, as detailed below allow for additional insulated plasterboard to be installed to the existing brickwork walls and the back of the existing timber door.
4.2.13.2 | The contractor is to rub down and prepare surfaces. Then is to supply and install new British Gypsum Gyproc ThermaLine Plus (40mm) insulated backed plasterboard (or similar approved) to the brickwork walls (2 no. walls in total) within in the Eaves Storage Cupboard. New plasterboard to be correctly fitted to the existing / retained brickwork surfaces. Allow to securely fix, seal, tape and joint. Allow to make good all surrounding surfaces where disturbed. Include to install and correctly detail around the door opening and the junctions of the blockwork wall, floor and sloping ceiling. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations. The walls (full height and full width) are as follows:
a). The right hand side brickwork wall.
b). The brickwork wall forming the back of the existing bedroom wall (wall with the door).
4.2.13.3 | The contractor is to supply and install new British Gypsum Gyproc ThermaLine Plus (27mm) or British Gypsum Gyproc ThermaLine Basic (22mm) insulated backed plasterboard (or similar approved) - to the back of the cupboard door (cupboard side). The size / thickness of insulated board used is dependent on the space available to ensure the cupboard door can suitably open and close correctly. Allow to securely fix. Include to install and correctly detail at the edges. Install new insulated plasterboard in accordance with manufacturer's instructions and recommendations.
4.2.14 | Roof Void
4.2.14.1 | The contractor is to note that access to the roof void is via the ceiling loft hatch in the first floor landing.
4.2.14.2 | The contractor is to allow a Provisional Sum of £750.00 for the supply and installation of a new access platform in the loft space to provide safe and suitable access to the existing water tank (for maintenance purposes. Include to provide suitable loft legs in order for the access platform to be positioned above the existing insulation levels. Allow for all suitable boarding, supports, fixings etc. Prior to the installation the contractor is to review and confirm proposals with Ridge and the Environment Agency for approval.
4.2.15 | Decoration
4.2.15.1 | Prior to decorating, the contractor is to allow to protect surfaces, floor finishes and all fixtures and fittings, allow to take down light fittings, switches & the like prior to decorating.
4.2.15.2 | The contractor is to inspect all of the areas of lining paper to the walls and ceiling (where provided). Ensure all the paper is suitably secured to surrounding surfaces. Include for any repairs where required. Leave ready for decoration.
4.2.15.3 | The contractor is to allow to suitably prepare all previously decorated wall and ceiling surfaces with sugar soap solution, rinsed with clean water and allow to dry. Fully rub down all surfaces to remove any loose coverings and repair. Include for fill all areas of cracking etc. Allow to prepare and leave ready for redecoration.
4.2.15.4 | The contractor is to allow to prepare and decorate all internal walls, and boxing (excluding the Kitchen and Bathroom) within the property. Allow to prepare walls in line with the paint manufacturers guidelines and apply two coats of Dulux Trade Vinyl Matt including all necessary base coats. Include for all undercoat and preparation works as required and recommended by the manufacturer. Colour to be confirmed by the Environment Agency.
4.2.15.5 | In the Bathroom, the contractor is to allow to prepare and decorate the Bathroom walls, boxing, bath panel, skirting and ceiling. Allow to prepare walls in line with the paint manufacturers guidelines and apply two coats of Dulux Trade Mouldshield Fungicidal Eggshell, Bathroom paint including all necessary base coats. Include for all undercoat and preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.6 | In the Kitchen, the contractor is to allow to prepare and decorate the Kitchen walls, boxing and ceiling. Allow to prepare walls in line with the paint manufacturers guidelines and apply two coats of Dulux Trade Mouldshield Fungicidal Eggshell Kitchen paint, including all necessary base coats. Include for all undercoat and preparation works as required and recommended by the manufacturer. Colour: Walls - Magnolia. Ceiling: White.
4.2.15.7 | The contractor is to allow to prepare and decorate all internal ceilings (excluding Kitchen and Bathroom). Allow to prepare the ceilings in line with the paint manufacturers guidelines and apply two coats of Dulux Trade Vinyl Matt including all necessary base coats. Include for all undercoat and preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.8 | The contractor is to allow to prepare and decorate new and existing joinery (skirtings, door joinery, window cills / boards, staircase, banisters, spindles, handrails, stairwell purlin etc.) with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.9 | The contractor is to allow to prepare and decorate the existing varnished picture rails and skirtings in the Living Room with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.10 | The contractor is to allow to prepare and decorate the existing varnished picture rails and skirtings in the Dining Room with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.11 | The contractor is to allow to prepare and decorate the existing varnished fire hearth trim / surround in the Dining Room with two coats of Sadolin timber varnish (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: to match existing.
4.2.15.12 | The contractor is to allow to prepare and decorate all retained timber doors, frames and linings (excluding the Living Room and Kitchen doors) with two coats of Dulux paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.13 | The contractor is to allow to prepare and decorate the retained Kitchen and Living Room varnished timber doors, frames and linings with two coats of Sadolin timber varnish (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: to match existing.
4.2.15.14 | The contractor is to allow to prepare and decorate the existing 6 No. varnished timber threshold bars within the door openings, with two coats of Sadolin timber varnish (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: to match existing.
4.2.15.15 | The contractor is to allow to prepare and decorate the retained eaves loft access door, frame and threshold (located within Bedroom 1), both sides, with two coats of Dulux paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.16 | The contractor is to allow to decorate all previously decorated and retained pipework, including any visible pipework within the Bathroom etc., where visible to the ground and first floors. Include for all preparation works as required and recommended by the manufacturer. Allow for two coats of final paint: White.
4.2.15.17 | The contractor is to allow to prepare and redecorate all of the previously decorated radiators and associated pipework within the property with two coats of Dulux radiator paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.18 | The contractor is to allow to prepare and decorate the existing timber loft access hatch and surround with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.19 | The contractor is to allow to prepare and decorate the existing timber Velux window frame and surround with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.20 | The contractor is to allow to prepare and decorate all of the shelving and cupboard doors within Bedroom 2. Include to decorate the 2 no. double cupboard doors (both sides) and frames, walls within the exposed shelving area, exposed shelving (including the underside), plus the walls and shelving within the lower cupboard area and the walls and ceiling in the larger cupboard (containing the water cylinder) with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: similar to existing (Mushroom or similar approved).
4.2.15.21 | The contractor is to note that the shelving in the water cylinder cupboard in Bedroom 2 are not to be decorated.
4.2.15.22 | The contractor is to allow to prepare and decorate all of the wardrobe within Bedroom 3. Include to decorate the doors (both sides), frame, walls, skirting, shelving etc. with two coats of Dulux Satin paint (or similar approved). Include for all preparation works as required and recommended by the manufacturer. Colour: White.
4.2.15.23 | Where any affected surfaces have been altered or stripped out in accordance with the electrical works (liaise with the Environment Agency's Term Contractor), allow to make good all surfaces and to leave the area in a fully completed condition, including any decoration to match.
4.2.16 | Mechanical & Electrical Works
4.2.16.1 | The contractor is to note that the all the mechanical and electrical works within the property are scheduled to be undertaken prior to these works, by the Environment Agency's Term Electrical Contractor's proposed works. The contractor is to allow to liaise with the separate Mechanical and Electrical Contractor (if required to ensure all works are completed). The proposed works include:
- New mechanical ventilation extract in the Ground Floor Toilet.
- Overhaul the existing extract unit above Kitchen cooker space.
- New mechanical ventilation extract in the Kitchen.
- Inspect / overhaul shower installation within the Bathroom.
- Relocate the existing pull cord light switch in the Bathroom.
- Installation of LED bulbs to rooms where required.
- Refix loose utility boxing within the external enclosure.
4.3 | CLEANING & COMPLETION
4.3.1 | The contractor is to leave the property clear, debris free and tidy on completion of the works, to the satisfaction of Ridge & Partners LLP, including the removal of all debris, materials plant and equipment etc., ready for inspection and handover.
4.3.2 | The contractor is to clean all surfaces forming the fireplace, hearth, tiling, surround and grate etc. in the Dining Room, using a non abrasive solution.
4.3.3 | The contractor is to clean all surfaces forming the fireplace, hearth and log burner etc. in the Living Room, using a non abrasive solution.
4.3.4 | The contractor is to clean all the window and door glazing and frames internally and externally throughout the property, using a non abrasive solution.
4.3.5 | Allow for providing all necessary installation certification and warranties for all materials and installations included within the works. All certification and testing must be undertaken by a nationally qualified specialist.
4.3.6 | The contractor is to provide and ensure Health and Safety File and Building Manual for the works has been issued for comment 1 week prior to completion. The Health and Safety File is to include all O&M information for the works. Where required, allow to liaise with the Environment Agency's chosen electrical Term Contractor, to ensure all the correct information is provided.
4.3.7 | Upon completion of the works, the contractor is to ensure that a full and completed electronic copy of the Health and Safety file and all associated information for the works undertaken are provided to Ridge & Partners LLP and the Environment Agency one week after Practical Completion.
4.3.8 | The contractor is to ensure that upon completion of the works, all the insurance backed guarantees covering the external works, including the installation and workmanship etc., are to be handed to Ridge & Partners LLP and included within the O&M Manuals for the works.
SECTION 4 - COSTED TOTAL (Excl VAT) £