## Incentive Schedule
Project KPIs | Measure | Basis of Metric | Basis of Calibration | Frequency | Weight | Total
Project cost | Actual Project Cost versus Project Cost at Outline Business Case or Final Business Case | For Delivery Phases 1a and 1b the Project Cost will be the Form 300 Assured Estimate of project cost within the Outline Business Case submission to DfT. For Delivery Phases 2-5 the Project Cost will be the Form 300 Assured Estimate of project cost within the Final Business Case submission to DFT. Actual Project Cost will be measured from the forecast project cost required under CS3-03.7 | Actual Project Cost 90% or less of Project Cost at Final Business Case = 200. Actual Cost equal to Project Cost at Final Business Case = 100. Actual Project Cost 105% or more of Project Cost at Final Business Case = 0 | Phase | 35%
Project Schedule | Road Open to Traffic Date versus Planned Road Open to Traffic Date | For all Delivery Phases the baseline will be the Road Open to Traffic Date stated within the Outline Business Case submission to DfT. Planned Road Open to Traffic Date measured from the Integrated Project Programme required under CS3-03.4 | 12 weeks float or greater against baseline = 200. 4 weeks float or less against baseline = 100. Any negative float = 0 | Phase | 30%
LTC BSC | BSC score for CSF3, CSF7, CSF8, CSF9, CSF10, CSF12 and CSF15 strategic themes | Refer to BSC Schedule tab | Metric Achieved = 100. 110% or greater of Metric Achieved = 200. 90% or less of Metric Achieved = 0. Metric to be defined during Phase M by Highways England and to be agreed with the Consultant | Phase | 10%
Consultant Cost | Actual cost of the services versus Baseline Price Estimate | Baseline will be the total Baseline Price Estimate including the profit for all Phases as stated within the Pricing Documents in the Consultant's tender submission. Baseline Price Estimate indexed in accordance with Z51. Actual cost measured from the interim payment certificates plus forecast of cost to completion for the Consultant with forecast amounts derived from Task Orders issued and forecast of Time Charge to Completion and Baseline Price Estimate where Task Orders have not yet been issued. | Actual cost 90% or less of Baseline = 200. Actual cost equal to Baseline = 100. Actual cost 110% or more of Baseline = 0 | Completion | 25% | 100%
Phase KPIs - Phase M |  |  |  | By (working days): | Weight
Task Orders | Target Cost quotations for Phase 1 accepted for all Service Lines | All quotations required under the applicable Key Date | Absolute | 60 | 30%
Service Plan | Service Plan accepted for all Service Lines | The Service Plan which comprises of the Services Contract Management Plan, the Annual Audit Plan and the Quality Plan required under the applicable Key Date. | Absolute | 60 | 30%
Mobilisation Plan | Successful delivery of the Mobilisation Plan | All activities identified within the Mobilisation Plan are completed by the end of the Mobilisation Phase. | Absolute | 60 | 25%
Integrated Client Team | Collaborated with the ICT to create our set of behavioural development plans and our maturity benchmarking map | All behavioural development plans and maturity benchmarking map have been created with applicable input from the the Consultant by the end of the Mobilisation Phase. | Absolute | 60 | 15% | 100%
Phase KPIs - Phase 1a and 1b |  |  |  | Frequency | Weight
Phase 1 Cost .v. Target | Actual cost of the services for Phase 1 versus Task Order value | Baseline will be the Task Order value. Actual cost measured from the interim payment certificates plus forecast of cost to completion for the Phase for the Consultant | Actual cost of the services 90% or less of Baseline = 200. Actual cost of the services equal to Baseline = 100. Actual cost of the services 110% or more of Baseline = 0 | 1/4ly | 20%
Quality of Deliverables | Performance under CPF as per S544 versus Quality Management Points as per S542 | High performance as the positive axis as determined by the quarterly CPF score, quality as the negative axis as determined by the number of quality management points as determined by the provisions of S542 and as per the Consultant's quality management system | Nil Quality Management Points and CPF score of 10 = 200. Nil Quality Management Points and CPF score of 6 = 100. 25 Quality Management Points and CPF score of less than 6 = 0 | 1/4ly | 10%
Partnership Review | 360 Degree behaviours and values survey as required by PS8-03.12 | Satisfaction levels as measured by 360 degree survey of Project Contractors and Integrated Client Team | To be developed in Mobilisation Phase, assymetrical to drive positive behaviours and values. | 1/4ly | 10%
Contract Administration | All Project Managers and Service Managers do not default on contractual Periods for Reply. | The baseline will be the Periods for Reply in the Technical Partner Contract, the Integration Partner contract, the Project Contracts and the Ancillary Contracts. Actual periods of reply will be those captured in CEMAR. | Absolute | 1/4y | 15%
Predictability of Costs | All contracts provide monthly, quarterly and annual forecasts and actuals within the defined predictability limits. | For all contracts the monthly, quarterly and annual forecasts an actuals have to achieve a predictability measure of +/- 5%. | Actual predictability is +/- 2% or less = 200 Actual predictability is +/- 5% = 100 Actual predictability is +/-8% or greater = 0 | 1/4yr | 15%
Dispute Avoidance | Early identifiication and mitigation of disputes on all contracts. | The Consultant supports Highways England to identify and mitigate potential disputes on the Technical Partner Contract, the Integration Partner Contract, the Project Contracts and the Ancillary Contracts. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Delivery of Efficiencies | Delivery of identified efficiencies and identification of new effiiencies | Support Highways England to deliver identified efficiencies and collaborate with ICT to identify further efficiencies to enable Highways England to exceed targets. | To be developed in Mobilisation Phase. | 1/4yr | 10%
MWC mobilisation | Successful completion of Project Contractor mobilisation and Phase 1 as per S205.1 | Baseline will be the Integrated Project Programme | Absolute | Phase end | 10% | 100%
Phase KPIs - Phase 2 |  |  |  | Frequency | Weight
Phase 2 Cost .v. Target | Actual cost of the services for Phase 2 versus Task Order value | Baseline will be the Task Order value. Actual cost measured from the interim payment certificates plus forecast of cost to completion for the phase for the Consultant | Actual cost of the services 90% or less of Baseline = 200. Actual cost of the services equal to Baseline = 100. Actual cost of the services 110% or more of Baseline = 0 | 1/4ly | 20%
Quality of Deliverables | Performance under CPF as per S544 versus Quality Management Points as per S542 | High performance as the positive axis as determined by the quarterly CPF score, quality as the negative axis as determined by the number of quality management points as determined by the provisions of S542 and as per the Consultant's quality management system | Nil Quality Management Points and CPF score of 10 = 200. Nil Quality Management Points and CPF score of 6 = 100. 25 Quality Management Points and CPF score of less than 6 = 0 | 1/4ly | 10%
Partnership Review | 360 Degree behaviours and values survey as required by PS8-03.12 | Satisfaction levels as measured by 360 degree survey of Project Contractors and Integrated Client Team | To be developed in Mobilisation Phase, assymetrical to drive positive behaviours and values. | 1/4ly | 10%
Contract Administration | All Project Managers and Service Managers do not default on contractual Periods for Reply. | The baseline will be the Periods for Reply in the Technical Partner Contract, the Integration Partner contract, the Project Contracts and the Ancillary Contracts. Actual periods of reply will be those captured in CEMAR. | Absolute | 1/4yr | 15%
Predictability of Costs | All contracts provide monthly, quarterly and annual forecasts and actuals within the defined predictability limits. | For all contracts the monthly, quarterly and annual forecasts an actuals have to achieve a predictability measure of +/- 5%. | Actual predictability is +/- 2% or less = 200 Actual predictability is +/- 5% = 100 Actual predictability is +/-8% or greater = 0 | 1/4yr | 15%
Dispute Avoidance | Early identifiication and mitigation of disputes on all contracts. | The Consultant supports Highways England to identify and mitigate potential disputes on the Technical Partner Contract, the Integration Partner Contract, the Project Contracts and the Ancillary Contracts. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Delivery of Efficiencies | Delivery of identified efficiencies and identification of new effiiencies | Support Highways England to deliver identified efficiencies and collaborate with ICT to identify further efficiencies to enable Highways England to exceed targets. | To be developed in Mobilisation Phase. | 1/4yr | 10%
De-risking Project | Increased headroom within Project Contractors target budgets and creation of float within Project Contractors' Accepted Programme | Baseline will be the Target Budget at award for each Project Contract and the Road Open For Traffic Date within the Accepted Programme for each Project Contract. Headroom measured by the Forecast of Defined Cost for each Project Contract and the Forecast date for Road Open for Traffic in each Project Contract | Absolute | Phase end | 10% | 100%
Phase KPIs - Phase 3 |  |  |  | Frequency | Weight
Phase 3 Cost .v. Target | Actual cost of the services for Phase 3 versus Task Order value | Baseline will be the Task Order value. Actual cost measured from the interim payment certificates plus forecast of cost to completion for the phase for the Consultant | Actual cost of the services 90% or less of Baseline = 200. Actual cost of the services equal to Baseline = 100. Actual cost of the services 110% or more of Baseline = 0 | 1/4ly | 20%
Quality of Deliverables | Performance under CPF as per S544 versus Quality Management Points as per S542 | High performance as the positive axis as determined by the quarterly CPF score, quality as the negative axis as determined by the number of quality management points as determined by the provisions of S542 and as per the Consultant's quality management system | Nil Quality Management Points and CPF score of 10 = 200. Nil Quality Management Points and CPF score of 6 = 100. 25 Quality Management Points and CPF score of less than 6 = 0 | 1/4ly | 10%
Partnership Review | 360 Degree behaviours and values survey as required by PS8-03.12 | Satisfaction levels as measured by 360 degree survey of Project Contractors and Integrated Client Team. | To be developed in Mobilisation Phase, assymetrical to drive positive behaviours and values. | 1/4ly | 10%
Contract Administration | All Project Managers and Service Managers do not default on contractual Periods for Reply. | The baseline will be the Periods for Reply in the Technical Partner Contract, the Integration Partner contract, the Project Contracts and the Ancillary Contracts. Actual periods of reply will be those captured in CEMAR. | Absolute | 1/4yr | 15%
Predictability of Costs | All contracts provide monthly, quarterly and annual forecasts and actuals within the defined predictability limits. | For all contracts the monthly, quarterly and annual forecasts an actuals have to achieve a predictability measure of +/- 5%. | Actual predictability is +/- 2% or less = 200 Actual predictability is +/- 5% = 100 Actual predictability is +/-8% or greater = 0 | 1/4yr | 15%
Dispute Avoidance | Early identifiication and mitigation of disputes on all contracts. | The Consultant supports Highways England to identify and mitigate potential disputes on the Technical Partner Contract, the Integration Partner Contract, the Project Contracts and the Ancillary Contracts. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Delivery of Efficiencies | Delivery of identified efficiencies and identification of new effiiencies | Support Highways England to deliver identified efficiencies and collaborate with ICT to identify further efficiencies to enable Highways England to exceed targets. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Interface Management | Measured by number of Early Warning Notices issued via CEMAR for resolution of interface matters | Measured against number of unresolved EWN's relating to interface matters at each monthly reporting period cut off date | To be developed in Mobilisation Phase assymetrical to drive high performance | 1/4ly | 10% | 100%
Phase KPIs - Phase 4 |  |  |  | Frequency | Weight
Phase 4 Cost .v. Target | Actual cost of the services for Phase 4 versus Task Order value | Baseline will be the Task Order value. Actual cost measured from the interim payment certificates plus forecast of cost to completion for the phase for the Consultant | Actual cost of the services 90% or less of Baseline = 200. Actual cost of the services equal to Baseline = 100. Actual cost of the services 110% or more of Baseline = 0 | 1/4ly | 20%
Quality of Deliverables | Performance under CPF as per S544 versus Quality Management Points as per S542 | High performance as the positive axis as determined by the quarterly CPF score, quality as the negative axis as determined by the number of quality management points as determined by the provisions of S542 and as per the Consultant's quality management system | Nil Quality Management Points and CPF score of 10 = 200. Nil Quality Management Points and CPF score of 6 = 100. 25 Quality Management Points and CPF score of less than 6 = 0 | 1/4ly | 10%
Partnership Review | 360 Degree behaviours and values survey as required by PS8-03.12 | Satisfaction levels as measured by 360 degree survey of Project Contractors and Integrated Client Team | To be developed in Mobilisation Phase, assymetrical to drive positive behaviours and values. | 1/4ly | 10%
Contract Administration | All Project Managers and Service Managers do not default on contractual Periods for Reply. | The baseline will be the Periods for Reply in the Technical Partner Contract, the Integration Partner contract, the Project Contracts and the Ancillary Contracts. Actual periods of reply will be those captured in CEMAR. | Absolute | 1/4yr | 15%
Predictability of Costs | All contracts provide monthly, quarterly and annual forecasts and actuals within the defined predictability limits. | For all contracts the monthly, quarterly and annual forecasts an actuals have to achieve a predictability measure of +/- 5%. | Actual predictability is +/- 2% or less = 200 Actual predictability is +/- 5% = 100 Actual predictability is +/-8% or greater = 0 | 1/4yr | 15%
Dispute Avoidance | Early identifiication and mitigation of disputes on all contracts. | The Consultant supports Highways England to identify and mitigate potential disputes on the Technical Partner Contract, the Integration Partner Contract, the Project Contracts and the Ancillary Contracts. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Delivery of Efficiencies | Delivery of identified efficiencies and identification of new effiiencies | Support Highways England to deliver identified efficiencies and collaborate with ICT to identify further efficiencies to enable Highways England to exceed targets. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Interface Management | Measured by number of Early Warning Notices issued via CEMAR for resolution of interface matters | Measured against number of unresolved EWN's relating to interface matters at each monthly reporting period cut off date | To be developed in Mobilisation Phase assymetrical to drive high performance | 1/4yr | 10% | 100%
Phase KPIs - Phase 5 |  |  |  | Frequency | Weight
Phase 5 Cost .v. Target | Actual cost of the services for Phase 5 versus Task Order value | Baseline will be the Task Order value. Actual cost measured from the interim payment certificates plus forecast of cost to completion for the phase for the Consultant | Actual cost of the services 90% or less of Baseline = 200. Actual cost of the services equal to Baseline = 100. Actual cost of the services 110% or more of Baseline = 0 | 1/4ly | 20%
Quality of Deliverables | Performance under CPF as per S544 versus Quality Management Points as per S542 | High performance as the positive axis as determined by the quarterly CPF score, quality as the negative axis as determined by the number of quality management points as determined by the provisions of S542 and as per the Consultant's quality management system | Nil Quality Management Points and CPF score of 10 = 200. Nil Quality Management Points and CPF score of 6 = 100. 25 Quality Management Points and CPF score of less than 6 = 0 | 1/4ly | 10%
Partnership Review | 360 Degree behaviours and values survey as required by PS8-03.12 | Satisfaction levels as measured by 360 degree survey of Project Contractors and Integrated Client Team | To be developed in Mobilisation Phase, assymetrical to drive positive behaviours and values. | 1/4ly | 10%
Contract Administration | All Project Managers and Service Managers do not default on contractual Periods for Reply. | The baseline will be the Periods for Reply in the Technical Partner Contract, the Integration Partner contract, the Project Contracts and the Ancillary Contracts. Actual periods of reply will be those captured in CEMAR. | Absolute | 1/4yr | 15%
Predictability of Costs | All contracts provide monthly, quarterly and annual forecasts and actuals within the defined predictability limits. | For all contracts the monthly, quarterly and annual forecasts an actuals have to achieve a predictability measure of +/- 5%. | Actual predictability is +/- 2% or less = 200, Atual predictability is +/- 5% = 100 Actual predictability is +/-8% or greater = 0 | 1/4yr | 15%
Dispute Avoidance | Early identifiication and mitigation of disputes on all contracts. | The Consultant supports Highways England to identify and mitigate potential disputes on the Technical Partner Contract, the Integration Partner Contract, the Project Contracts and the Ancillary Contracts. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Delivery of Efficiencies | Delivery of identified efficiencies and identification of new effiiencies | Support Highways England to deliver identified efficiencies and collaborate with ICT to identify further efficiencies to enable Highways England to exceed targets. | To be developed in Mobilisation Phase. | 1/4yr | 10%
Final Accounts Close Out | All final accounts to be agreed with contractors and consultants. | Measured against the number and value of final accounts closed out within the required timescales. | To be developed in Mobilisation Phase | Phase End | 10% | 100%

## BSC Schedule
Strategic Themes |  | Critical Success factors |  | Performance Management Measure (PIs) | Commitments in Contract Volume 2 Scope | HE 2017/8 Performance Statements | CPF cross reference
Safety |  | Improve HSSW for our workforce and customers | CSF 1 | AIM: Raise the bar on HSSW standards and ensure home safe and well 1. Zero deaths during construction (working towards zero KSI by 2041) - Reduce non-fatal injuries by 45% of industry best practice. - Reduce health impact incidents by 45% of industry best practice. 2. Lost time due to injury and RIDDOR metrics 3. Reporting on near misses and learning from them 4. Zero AFR 5. Report on Absence due to illness, target is no more than 4 days per year. 6. Contractors to be ISO 18001 compliant or ISO 45001 compliant or transitioning to, from ISO 18001 by Mar 21. 7. Prioritise workforce wellbeing and health with a clear plan of programmed support and facilities Additional requirements: Damage to TPI equipment, (target is zero annually) Digital Application (how to change to be more automated) Innovation (technology to reduce people, maximise off site manufacture) | S1100 HSSW | Home safe and well strategy | 1.1a 1.1c 1.1d 1.1e 1.2a
|  | Improve HSSW standards | CSF 2 | AIM: Safe standards for road users. Ensuring design and tecnology encompasses safety as part of 0 KSI by 2041 with a demonstrable % reduction in interventions 1. Zero deaths (working towards zero KSI by 2041) during road works 2. Demonstrate safe road work practices to minimise road user injuries during during road works 3. Allow flexibility for enabling technology on the SRN | S1100 HSSW S300 Design S200 Minimum operating requirements and PRAMS | Making the network safer | 1.1b
Customers | ST3 | Minimise impacts for customers during construction and operation. | CSF 5 | AIM: Putting customers first 1. Measurement of customer satisfaction / complaints, feedback, impact during construction 2. Development of a customer focus plan during construction 3. Achieve 98.5% network availability on SRN during construction at online locations 4. Compliance with the Code of construction practice 5. Clear up rates on the SRN | S251 Customer Focus S865 Communications S866 Public consultation | Supporting the smooth flow of traffic | 2.1a 2.1b 3.2a 4.1a
|  | Optimise Customer & Stakeholder Management | CSF 6 | AIM: Optimising stakeholder and customer relationships 1. Improve the accuracy of roadwork scheduling (target is 100% accurate 7 days in advance). 2. Development and implementation of a Customer Relationship Management system 3. Providing community liaison officers during construction 4. Work with stakeholders to understand their needs and requirements | S251 Customer Focus S865 Communications S866 Public consultation | Improving User Satisfaction | 2.1h 2.2a 3.1a
Delivery | ST 6 | Collaborative innovation culture to enable delivery | CSF 11 | AIM: Develop collaborative relationships on the project 1. Compliance with ISO 44001 accreditation - Relationship Management Plans and supply frameworks 2. Development and maintain Joint Operations Forums with all contracts 3. Record lean management and innovation opportunities across contracts | S850 meetings S600 Management systems | Strong relationships | 4.4b
|  | On budget delivery of the LTC (roads and tunnels) within affordability envelope. | CSF 12 | AIM: Deliver value for money 1. Monthly programme and cost reporting 2. Risk management reporting, assured Risk register and its use, Drawdown of risk fund against planned risk spend. | Sxx Risk Management S500 Programme | Achieving real efficiency | 6.1a
|  | LTC on schedule OTT and project-wide delivery to milestones | CSF 13 | AIM Deliver on time 1. Maintain programme and project control through the PCF framework 2. Monthly monitoring and reporting on programme and cost scheduling to ensure progress with spend matching forecast (EV SPI) 3. Contractors plan demonstrates LEAN application to drive efficiencies. | S255 project controls S500 management or works | On time delivery | 6.1a
|  | Sustainable, high quality whole-life solutions | CSF 14 | Aim: Deliver sustainable whole life solutions 1. LTC designed in accordance with the current draft standard ‘GD300 Expressways’. 2. Designed & construct for life with minimum maintenance (Tideway constructed for 120 year life), 3. Whole life cost provisions and options including Life cycle costing and incentives | S300 - Design | Keeping the network in a good condition | 6.1a
|  | Quality management embedded | CSF 15 | AIM : Deliver high quality product 1. Compliance with ISO 9001 and continued accreditation. 2. Right First time Every time, but Cost of Poor Quality (Where a non-conformance occurs, there is to be no impact on cost and schedule to the project. Measured by cost, value, time lost, impact on wider project?) 3. Demonstrate Continual Improvement and a QMS culture. 4. Set criteria for and track membership of relevant professional institutions. 5. Share learning across the supply chain. | S600 Quality S400 completion | Achieving good quality | 6.3a
Environment | ST 2 | Manage and reduce environmental impacts | CSF 3 | AIM: Protect and enhance the environment 1. Compliance to ISO 14001 2. Report and monitor environmental performance through construction period 3. 100 % compliance with REAC - register of environmental actions and commitments from the DCO 4. Compliance with the Code of Construction Practice 5. Achieve excellent in CEEQUAL standard 6.. Compliance to PAS 2080 - Carbon management framework 7. Production of a carbon reduction plan and reduce emissions against the LTC baseline 8. Development and compliance with waste management plans. 9. Achieve zero waste to landfill for non contaminated material 10. Monitor air and noise levels during contstruction Air and noise pollution targets (maximum) 11. Management of water environment Notable areas of development Plant fleet to include maximum numbers of low emissions vehicles (electric, hybrid, bio-fuel etc) Comply with Article 6 of the Procurement and Policy Note 7/14 on energy efficiency. Whole life costs and sustainable products (% of prime running temporary generation at Stage 111B classification) | S207 - Environment requirements of contract Volume 2 scope S209 - Sustainability requirements of contract volume 2 scope Code of Constrution Practice REAC - environmental commitments register | Delivering better environmental outcomes | 5.1a 5.1c
|  | Protect / improve biodiversity | CSF 4 | AIM: Support Highways England in the ambition to improve biodiversity on the network 1. Work collaboratively with Highways England maximise biodiversity along the route including improved road side verges (enhanced grass area or wild meadows) 2. work with local stakeholders on environmental management programmes 3. Measurement of DEFRA biodiversity net gain | S254 Legacy outcomes | Delivering better environmental outcomes | 5.1b
People & Communities | ST 4 | Create jobs / apprentices / skills in local supply chain and ensure culture of inclusions developed on the contracts. | CSF 7 | AIM: Supporting the local communities in Skills, Employment and Education 1. Development of Skills and employment plan in line with Skills Employment and Education strategy 2. Programme of apprenticeships, graduates, training, school engagement - See attached metric breakdown 3. Record all new employment opportunities 4. Actively implement fair and inclusive recruitment practices 5. Development of a Social inclusion Plan with EDI metrics | S253 people Strategy | Being a good neighbour | 4.3a 4.4a
|  | Understand and support community priorities | CSF 8 | AIM: Supporting community initiatives and groups 1.Set and track social value gained (quarterly report) 2. Deliver access to NMU routes with local population requirements. 3. Work with local community groups through volunteering programme | S253 people Strategy S254 Legacy Strategy | Helping NMU of the network
Economic | ST 5 | Increased opportunities for local businesses through a circular economy. | CSF 9 | AIM: Help improve opportunities for local business development 1. Optimise contract spend in the local authority areas 2. undertake programme of engagement with local business through local labour forums, meet the buyer events and sustainability supply chain school initiatives NOTE: Be realistic if EDI targets are set (85-90% white UK (5% white other; Asians 5% of population). | S1200 Subcontracting S865 stakeholde engagement S253 People Strategy (linked to SEE) | Encouraging economic growth
|  | Supply Chain size and scale to support the project | CSF 10 | AIM: Encourage the local supply chain to be involved 1. record % of spend with local business 2. Track and monitor supply chain support platforms 3. Early access and advertising on job opportunities in local area 4. Develop and implement fair payment processes , report monthly. | S1200 Subcontracting S253 people strategy | Encouraging economic growth
Benefits and Outcomes Wheel