## Sheet1
Main Construction | Original Notes | Additional Notes
Dismantling | Dismantle existing WC block, kitchen and storage area at front of building, ensuring loft storage is supported and does not collapse. Capping off water and removal of existing sanitary ware. Safe clear back of electrics. Cleaning up floor surface. Disposal of all unneeded materials. (Kitchen sink & kitchen side units to be retained). | Contractor to set out plan to secure loft support, both front and rear Contractor to set out plan to maintain asbestos roof. PC will provide CDM certification PC will advise on Building Regs needs Remove fan unit/chimney within rear loft and remove current wall ensuring loft space remains in place.
Flooring Insulation |  | Install flooring insulation throughout, specific specification to be agreed with PC Incorporate 6 equidistant electrical outlets blocks within floor; specific plan to be agreed with PC
New WC Block | Rebuild new WC block with new stud partitioning. This to include 1x disabled accessible WC with Doc M pack and baby changing facility, plus 2x small single WCs - as per plans. Estimates for Structure, Sanitary ware, plumbing & electrics to be itemised. | PC will provide electrical plan and plumbing plan Hot water to be provided with individual wall heaters (3 WCs).
New office and kitchen | Rebuild office to front of building with door access from entrance hall. Restructuring kitchen within main hall as per plans. Estimates for Structure, plumbing & electrics to be itemised | Kitchen will be full spec (hob/oven, dishwasher, fridge, etc.) PC will provide electrical plan Hot water to be provided with individual wall heater Install water softener to feed system throughout
Rear door porch |  | Outer mini-porch/frame required to provide sufficient width for disabled access
Front Loft space |  | Will not be used for storage; retain current access into main room. Insulation to full spec.
Rear Loft space |  | Will not be used for storage; retain current access into rear room. Insulation to full spec. Widen doorway from main room for disabled access Repair/rebuild wall to provide flat surface side to side Build partitioned storage space in back room with access from main hall and rear room.
Heating
Electric radiators |  | To be retained - 8 units
Security
Alarm |  | Internal alarm on each door, movement alarms in each room/area. External movement triggered floodlights on approaches to building and to rear and side.